## README
Work Breakdown Structure — HWSD Municipal Water Capital Improvement Program
Portfolio review export. Source of truth is 03_excel_model/HWSD_Project_Controls_Model.xlsx, tab 02_WBS.
Portfolio disclaimer | All program, project, cost, schedule, and organizational data in this workbook is synthetic and created for portfolio demonstration purposes. Harborview Water & Sewer Department (HWSD) is a fictional utility.
WBS structure — 4 levels
Level 1 — Program | The single HWSD Municipal Water Capital Improvement Program. Not broken out as its own row in the WBS sheet; it is the implicit root of every WBS_Code (all codes begin with '1.').
Level 2 — Project | One of the 12 numbered projects (P01–P12). Fixed scope and a fixed BAC, each with one accountable Project Manager. Represented by the Project_ID / Project_Name columns.
Level 3 — Control Account / Lifecycle Phase | The level at which cost and schedule performance is actually measured and owned. Each project has 6 control accounts, one per lifecycle phase. Eleven projects use the standard phase names (Planning, Design, Procurement, Construction, Testing & Commissioning, Closeout); P12 uses differently-worded phases suited to standing small-capital/emergency work, but every phase still maps to one of the same 6 categories via the Standard_Lifecycle_Phase column. In Phase 4 (Earned Value Management), each control account will receive its own allocated slice of the project's BAC, plus PV/EV/AC, and the project-level BAC will roll up from its 6 control accounts.
Level 4 — Work Package | A further breakdown of a control account into a discrete, describable piece of deliverable scope (e.g., 'Chemical Feed System Installation'). Work packages are sized proportionally to the complexity of the phase and project — simple phases like Planning or Closeout carry 1–2 work packages, while Construction and (for P03 specifically) Testing & Commissioning carry more. Schedule activities, built in the next phase of this project, will each attach to exactly one Level-4 work package.
What's NOT in this WBS yet | Dollar amounts (BAC/PV/EV/AC) are not yet allocated to control accounts — that happens in the Earned Value Management phase. Schedule activities, durations, and dates are not yet attached to work packages — that happens in the Baseline Schedule phase.
Column reference
WBS_Code | Hierarchical code, e.g. 1.03.4.2 = Program.Project 03.Control Account 4.Work Package 2.
WBS_Level | 3 = Control Account, 4 = Work Package.
Project_ID / Project_Name | Identifies the project (P01–P12); constant across every file in this repository.
Control_Account_ID / Control_Account_Name | Identifies the lifecycle-phase control account within the project.
Work_Package_ID / Work_Package_Name | Identifies the work package within the control account. Blank on Level-3 (control account) rows.
Standard_Lifecycle_Phase | Maps every control account — including P12's differently-worded phases — back to one of the program's 6 standard lifecycle categories, for consistent Power BI rollups across all 12 projects.
Responsible_Role | The role type accountable for that control account / work package.
Description | Plain-English description of the scope covered.

## WBS
Finalized Work Breakdown Structure
Synthetic data, created for portfolio demonstration purposes only. Source of truth: HWSD_Project_Controls_Model.xlsx (02_WBS).
WBS_Code | WBS_Level | Project_ID | Project_Name | Control_Account_ID | Control_Account_Name | Work_Package_ID | Work_Package_Name | Standard_Lifecycle_Phase | Responsible_Role | Description
1.01.1 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Downtown 12-inch Water Main Replacement: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.01.1.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning | P01-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Downtown 12-inch Water Main Replacement.
1.01.1.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning | P01-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Downtown 12-inch Water Main Replacement.
1.01.2 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Downtown 12-inch Water Main Replacement: develop and finalize engineering design to support procurement and construction.
1.01.2.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design | P01-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Downtown 12-inch Water Main Replacement.
1.01.2.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design | P01-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Downtown 12-inch Water Main Replacement.
1.01.3 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Downtown 12-inch Water Main Replacement: solicit, award, and execute construction and/or equipment contracts.
1.01.3.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement | P01-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Downtown 12-inch Water Main Replacement.
1.01.3.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement | P01-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Downtown 12-inch Water Main Replacement.
1.01.4 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Downtown 12-inch Water Main Replacement: execute physical construction, installation, or implementation work.
1.01.4.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP041 | Pipe Installation & Jointing | Construction | Construction Manager / Contractor | Excavate, lay, and joint new 12-inch ductile iron water main along the downtown corridor route.
1.01.4.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP042 | Valve & Hydrant Tie-Ins | Construction | Construction Manager / Contractor | Install new isolation valves and fire hydrant connections and tie into the existing distribution system.
1.01.4.3 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP043 | Pavement & Surface Restoration | Construction | Construction Manager / Contractor | Backfill, compact, and restore pavement, sidewalks, and surface features disturbed by construction.
1.01.5 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Downtown 12-inch Water Main Replacement: test, start up, and verify system performance prior to acceptance.
1.01.5.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA05 | Testing & Commissioning | P01-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Downtown 12-inch Water Main Replacement.
1.01.6 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Downtown 12-inch Water Main Replacement: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.01.6.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout | P01-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Downtown 12-inch Water Main Replacement.
1.01.6.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout | P01-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Downtown 12-inch Water Main Replacement.
1.02.1 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Northside Pump Station Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.02.1.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning | P02-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Northside Pump Station Rehabilitation.
1.02.1.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning | P02-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Northside Pump Station Rehabilitation.
1.02.2 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Northside Pump Station Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.02.2.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design | P02-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Northside Pump Station Rehabilitation.
1.02.2.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design | P02-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Northside Pump Station Rehabilitation.
1.02.3 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Northside Pump Station Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.02.3.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement | P02-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Northside Pump Station Rehabilitation.
1.02.3.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement | P02-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Northside Pump Station Rehabilitation.
1.02.4 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Northside Pump Station Rehabilitation: execute physical construction, installation, or implementation work.
1.02.4.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP041 | Pump & Motor Replacement | Construction | Construction Manager / Contractor | Remove existing pumps and motors and install new high-efficiency units per design.
1.02.4.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP042 | Electrical Switchgear Upgrade | Construction | Construction Manager / Contractor | Replace station switchgear, VFDs, and associated electrical distribution equipment.
1.02.4.3 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP043 | Wetwell Structural Rehabilitation | Construction | Construction Manager / Contractor | Repair and recoat wetwell concrete structure and associated access hardware.
1.02.5 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Northside Pump Station Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.02.5.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA05 | Testing & Commissioning | P02-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Northside Pump Station Rehabilitation.
1.02.6 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Northside Pump Station Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.02.6.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout | P02-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Northside Pump Station Rehabilitation.
1.02.6.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout | P02-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Northside Pump Station Rehabilitation.
1.03.1 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Central Water Treatment Plant Process Upgrade: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.03.1.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning | P03-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Central Water Treatment Plant Process Upgrade.
1.03.1.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning | P03-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Central Water Treatment Plant Process Upgrade.
1.03.2 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Central Water Treatment Plant Process Upgrade: develop and finalize engineering design to support procurement and construction.
1.03.2.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design | P03-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Central Water Treatment Plant Process Upgrade.
1.03.2.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design | P03-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Central Water Treatment Plant Process Upgrade.
1.03.3 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Central Water Treatment Plant Process Upgrade: solicit, award, and execute construction and/or equipment contracts.
1.03.3.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement | P03-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Central Water Treatment Plant Process Upgrade.
1.03.3.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement | P03-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Central Water Treatment Plant Process Upgrade.
1.03.4 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Central Water Treatment Plant Process Upgrade: execute physical construction, installation, or implementation work.
1.03.4.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP041 | Process Mechanical Installation | Construction | Construction Manager / Contractor | Install new process mechanical equipment (clarifiers, filters, pumps) per the treatment process design.
1.03.4.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP042 | Electrical & Instrumentation Installation | Construction | Construction Manager / Contractor | Install new electrical distribution, control panels, and process instrumentation.
1.03.4.3 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP043 | Chemical Feed System Installation | Construction | Construction Manager / Contractor | Install new chemical storage, feed pumps, and containment for treatment process chemicals.
1.03.5 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Central Water Treatment Plant Process Upgrade: test, start up, and verify system performance prior to acceptance.
1.03.5.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP051 | Process Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform sequential process startup and functional testing of new mechanical and electrical systems.
1.03.5.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP052 | Performance / Acceptance Testing | Testing & Commissioning | Commissioning Lead | Conduct performance testing against design criteria and regulatory treatment standards.
1.03.5.3 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP053 | Regulatory Sign-off & SCADA Integration Checkout | Testing & Commissioning | Commissioning Lead | Coordinate state regulatory sign-off and verify full SCADA integration prior to substantial completion.
1.03.6 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Central Water Treatment Plant Process Upgrade: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.03.6.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout | P03-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Central Water Treatment Plant Process Upgrade.
1.03.6.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout | P03-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Central Water Treatment Plant Process Upgrade.
1.04.1 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Hilltop Storage Tank Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.04.1.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning | P04-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Hilltop Storage Tank Rehabilitation.
1.04.1.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning | P04-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Hilltop Storage Tank Rehabilitation.
1.04.2 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Hilltop Storage Tank Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.04.2.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design | P04-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Hilltop Storage Tank Rehabilitation.
1.04.2.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design | P04-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Hilltop Storage Tank Rehabilitation.
1.04.3 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Hilltop Storage Tank Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.04.3.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement | P04-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Hilltop Storage Tank Rehabilitation.
1.04.3.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement | P04-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Hilltop Storage Tank Rehabilitation.
1.04.4 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Hilltop Storage Tank Rehabilitation: execute physical construction, installation, or implementation work.
1.04.4.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP041 | Tank Interior/Exterior Coating | Construction | Construction Manager / Contractor | Prepare surfaces and apply new interior and exterior protective coating systems to the storage tank.
1.04.4.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP042 | Structural Steel Repairs | Construction | Construction Manager / Contractor | Repair or replace corroded structural steel members identified during inspection.
1.04.4.3 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP043 | Cathodic Protection System Installation | Construction | Construction Manager / Contractor | Install a new impressed-current cathodic protection system to mitigate future corrosion.
1.04.5 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Hilltop Storage Tank Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.04.5.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA05 | Testing & Commissioning | P04-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Hilltop Storage Tank Rehabilitation.
1.04.6 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Hilltop Storage Tank Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.04.6.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout | P04-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Hilltop Storage Tank Rehabilitation.
1.04.6.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout | P04-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Hilltop Storage Tank Rehabilitation.
1.05.1 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Lead Service Line Replacement - Phase 1: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.05.1.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning | P05-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Lead Service Line Replacement - Phase 1.
1.05.1.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning | P05-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Lead Service Line Replacement - Phase 1.
1.05.2 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Lead Service Line Replacement - Phase 1: develop and finalize engineering design to support procurement and construction.
1.05.2.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design | P05-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Lead Service Line Replacement - Phase 1.
1.05.2.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design | P05-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Lead Service Line Replacement - Phase 1.
1.05.3 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Lead Service Line Replacement - Phase 1: solicit, award, and execute construction and/or equipment contracts.
1.05.3.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement | P05-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Lead Service Line Replacement - Phase 1.
1.05.3.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement | P05-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Lead Service Line Replacement - Phase 1.
1.05.4 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Lead Service Line Replacement - Phase 1: execute physical construction, installation, or implementation work.
1.05.4.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP041 | Service Line Excavation & Replacement | Construction | Construction Manager / Contractor | Excavate and replace individual lead service lines with new copper or approved alternative piping.
1.05.4.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP042 | Property Restoration | Construction | Construction Manager / Contractor | Restore landscaping, driveways, and other surface features disturbed at each service address.
1.05.4.3 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP043 | Water Quality Sampling & Verification | Construction | Construction Manager / Contractor | Collect and analyze post-replacement water samples to verify compliance with lead action levels.
1.05.5 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Lead Service Line Replacement - Phase 1: test, start up, and verify system performance prior to acceptance.
1.05.5.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA05 | Testing & Commissioning | P05-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Lead Service Line Replacement - Phase 1.
1.05.6 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Lead Service Line Replacement - Phase 1: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.05.6.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout | P05-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Lead Service Line Replacement - Phase 1.
1.05.6.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout | P05-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Lead Service Line Replacement - Phase 1.
1.06.1 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for AMI / Smart Meter Modernization: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.06.1.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning | P06-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for AMI / Smart Meter Modernization.
1.06.1.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning | P06-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for AMI / Smart Meter Modernization.
1.06.2 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for AMI / Smart Meter Modernization: develop and finalize engineering design to support procurement and construction.
1.06.2.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design | P06-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for AMI / Smart Meter Modernization.
1.06.2.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design | P06-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for AMI / Smart Meter Modernization.
1.06.3 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for AMI / Smart Meter Modernization: solicit, award, and execute construction and/or equipment contracts.
1.06.3.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement | P06-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for AMI / Smart Meter Modernization.
1.06.3.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement | P06-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for AMI / Smart Meter Modernization.
1.06.4 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for AMI / Smart Meter Modernization: execute physical construction, installation, or implementation work.
1.06.4.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP041 | Meter Deployment & Installation | Construction | Construction Manager / Contractor | Remove existing meters and install new AMI-compatible meters at customer premises.
1.06.4.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP042 | Head-End System Integration | Construction | Construction Manager / Contractor | Install and configure the head-end data collection system and network gateways.
1.06.4.3 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP043 | Customer Data Migration & Validation | Construction | Construction Manager / Contractor | Migrate existing customer account and consumption data into the new metering platform and validate accuracy.
1.06.5 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for AMI / Smart Meter Modernization: test, start up, and verify system performance prior to acceptance.
1.06.5.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA05 | Testing & Commissioning | P06-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for AMI / Smart Meter Modernization.
1.06.6 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for AMI / Smart Meter Modernization: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.06.6.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout | P06-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for AMI / Smart Meter Modernization.
1.06.6.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout | P06-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for AMI / Smart Meter Modernization.
1.07.1 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for East Zone Pressure Management Improvements: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.07.1.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning | P07-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for East Zone Pressure Management Improvements.
1.07.1.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning | P07-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for East Zone Pressure Management Improvements.
1.07.2 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for East Zone Pressure Management Improvements: develop and finalize engineering design to support procurement and construction.
1.07.2.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design | P07-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for East Zone Pressure Management Improvements.
1.07.2.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design | P07-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for East Zone Pressure Management Improvements.
1.07.3 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for East Zone Pressure Management Improvements: solicit, award, and execute construction and/or equipment contracts.
1.07.3.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement | P07-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for East Zone Pressure Management Improvements.
1.07.3.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement | P07-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for East Zone Pressure Management Improvements.
1.07.4 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for East Zone Pressure Management Improvements: execute physical construction, installation, or implementation work.
1.07.4.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP041 | PRV Station Installation | Construction | Construction Manager / Contractor | Construct new pressure-reducing valve vaults and install PRV equipment at designated zone boundaries.
1.07.4.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP042 | Zone Isolation Valve Installation | Construction | Construction Manager / Contractor | Install new isolation valves to establish discrete pressure zone boundaries.
1.07.4.3 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP043 | Pressure Monitoring Instrumentation | Construction | Construction Manager / Contractor | Install remote pressure monitoring sensors and telemetry at key system locations.
1.07.5 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for East Zone Pressure Management Improvements: test, start up, and verify system performance prior to acceptance.
1.07.5.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA05 | Testing & Commissioning | P07-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for East Zone Pressure Management Improvements.
1.07.6 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for East Zone Pressure Management Improvements: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.07.6.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout | P07-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for East Zone Pressure Management Improvements.
1.07.6.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout | P07-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for East Zone Pressure Management Improvements.
1.08.1 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Emergency Generator & Electrical Resiliency: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.08.1.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning | P08-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Emergency Generator & Electrical Resiliency.
1.08.1.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning | P08-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Emergency Generator & Electrical Resiliency.
1.08.2 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Emergency Generator & Electrical Resiliency: develop and finalize engineering design to support procurement and construction.
1.08.2.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design | P08-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Emergency Generator & Electrical Resiliency.
1.08.2.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design | P08-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Emergency Generator & Electrical Resiliency.
1.08.3 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Emergency Generator & Electrical Resiliency: solicit, award, and execute construction and/or equipment contracts.
1.08.3.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement | P08-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Emergency Generator & Electrical Resiliency.
1.08.3.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement | P08-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Emergency Generator & Electrical Resiliency.
1.08.4 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Emergency Generator & Electrical Resiliency: execute physical construction, installation, or implementation work.
1.08.4.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP041 | Generator Installation | Construction | Construction Manager / Contractor | Install new standby generator units and associated foundations/enclosures at each site.
1.08.4.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP042 | Automatic Transfer Switch Installation | Construction | Construction Manager / Contractor | Install automatic transfer switches and integrate with existing electrical distribution.
1.08.4.3 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP043 | Fuel Storage System Installation | Construction | Construction Manager / Contractor | Install fuel storage tanks and supply piping per code requirements.
1.08.5 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Emergency Generator & Electrical Resiliency: test, start up, and verify system performance prior to acceptance.
1.08.5.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA05 | Testing & Commissioning | P08-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Emergency Generator & Electrical Resiliency.
1.08.6 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Emergency Generator & Electrical Resiliency: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.08.6.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout | P08-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Emergency Generator & Electrical Resiliency.
1.08.6.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout | P08-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Emergency Generator & Electrical Resiliency.
1.09.1 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for River Crossing Main Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.09.1.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning | P09-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for River Crossing Main Rehabilitation.
1.09.1.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning | P09-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for River Crossing Main Rehabilitation.
1.09.2 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for River Crossing Main Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.09.2.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design | P09-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for River Crossing Main Rehabilitation.
1.09.2.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design | P09-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for River Crossing Main Rehabilitation.
1.09.3 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for River Crossing Main Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.09.3.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement | P09-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for River Crossing Main Rehabilitation.
1.09.3.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement | P09-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for River Crossing Main Rehabilitation.
1.09.4 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for River Crossing Main Rehabilitation: execute physical construction, installation, or implementation work.
1.09.4.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP041 | Directional Drilling / Crossing Installation | Construction | Construction Manager / Contractor | Perform horizontal directional drilling to install new main beneath the river crossing.
1.09.4.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP042 | Pipe Fusion & Pressure Testing | Construction | Construction Manager / Contractor | Fuse HDPE pipe segments and perform hydrostatic pressure testing of the completed crossing.
1.09.4.3 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP043 | Riverbank Restoration | Construction | Construction Manager / Contractor | Restore riverbank grading, erosion control, and vegetation at entry/exit pit locations.
1.09.5 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for River Crossing Main Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.09.5.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA05 | Testing & Commissioning | P09-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for River Crossing Main Rehabilitation.
1.09.6 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for River Crossing Main Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.09.6.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout | P09-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for River Crossing Main Rehabilitation.
1.09.6.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout | P09-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for River Crossing Main Rehabilitation.
1.10.1 | 3 | P10 | SCADA Controls Modernization | P10-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for SCADA Controls Modernization: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.10.1.1 | 4 | P10 | SCADA Controls Modernization | P10-CA01 | Planning | P10-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for SCADA Controls Modernization.
1.10.1.2 | 4 | P10 | SCADA Controls Modernization | P10-CA01 | Planning | P10-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for SCADA Controls Modernization.
1.10.2 | 3 | P10 | SCADA Controls Modernization | P10-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for SCADA Controls Modernization: develop and finalize engineering design to support procurement and construction.
1.10.2.1 | 4 | P10 | SCADA Controls Modernization | P10-CA02 | Design | P10-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for SCADA Controls Modernization.
1.10.2.2 | 4 | P10 | SCADA Controls Modernization | P10-CA02 | Design | P10-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for SCADA Controls Modernization.
1.10.3 | 3 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for SCADA Controls Modernization: solicit, award, and execute construction and/or equipment contracts.
1.10.3.1 | 4 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement | P10-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for SCADA Controls Modernization.
1.10.3.2 | 4 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement | P10-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for SCADA Controls Modernization.
1.10.4 | 3 | P10 | SCADA Controls Modernization | P10-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for SCADA Controls Modernization: execute physical construction, installation, or implementation work.
1.10.4.1 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP041 | PLC Programming & Configuration | Construction | Construction Manager / Contractor | Develop and configure PLC logic for affected pump stations and treatment facilities.
1.10.4.2 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP042 | HMI Development | Construction | Construction Manager / Contractor | Develop human-machine interface screens and alarm configurations for operator use.
1.10.4.3 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP043 | Network & Communications Infrastructure | Construction | Construction Manager / Contractor | Install and configure the SCADA communications network linking field sites to the control center.
1.10.5 | 3 | P10 | SCADA Controls Modernization | P10-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for SCADA Controls Modernization: test, start up, and verify system performance prior to acceptance.
1.10.5.1 | 4 | P10 | SCADA Controls Modernization | P10-CA05 | Testing & Commissioning | P10-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for SCADA Controls Modernization.
1.10.6 | 3 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for SCADA Controls Modernization: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.10.6.1 | 4 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout | P10-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for SCADA Controls Modernization.
1.10.6.2 | 4 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout | P10-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for SCADA Controls Modernization.
1.11.1 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Valve Replacement & Isolation Program: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.11.1.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning | P11-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Valve Replacement & Isolation Program.
1.11.1.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning | P11-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Valve Replacement & Isolation Program.
1.11.2 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Valve Replacement & Isolation Program: develop and finalize engineering design to support procurement and construction.
1.11.2.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design | P11-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Valve Replacement & Isolation Program.
1.11.2.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design | P11-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Valve Replacement & Isolation Program.
1.11.3 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Valve Replacement & Isolation Program: solicit, award, and execute construction and/or equipment contracts.
1.11.3.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement | P11-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Valve Replacement & Isolation Program.
1.11.3.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement | P11-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Valve Replacement & Isolation Program.
1.11.4 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Valve Replacement & Isolation Program: execute physical construction, installation, or implementation work.
1.11.4.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP041 | Isolation Valve Installation | Construction | Construction Manager / Contractor | Install new isolation valves at designated locations across the distribution system.
1.11.4.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP042 | Distribution System Mapping Update | Construction | Construction Manager / Contractor | Update GIS and system mapping records to reflect newly installed valve locations and status.
1.11.4.3 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP043 | Site Restoration | Construction | Construction Manager / Contractor | Restore pavement and surface conditions at each valve installation location.
1.11.5 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Valve Replacement & Isolation Program: test, start up, and verify system performance prior to acceptance.
1.11.5.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA05 | Testing & Commissioning | P11-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Valve Replacement & Isolation Program.
1.11.6 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Valve Replacement & Isolation Program: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.11.6.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout | P11-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Valve Replacement & Isolation Program.
1.11.6.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout | P11-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Valve Replacement & Isolation Program.
1.12.1 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA01 | Planning & Prioritization |  |  | Planning | Program Controls Office | Planning & Prioritization phase for Programwide Small Capital & Emergency Response Improvements: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.12.1.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA01 | Planning & Prioritization | P12-WP011 | Work Order Intake & Prioritization | Planning | Program Controls Office | Intake, screen, and prioritize candidate small-capital and emergency work orders across the program.
1.12.2 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA02 | Design / Scope Development |  |  | Design | Program Controls Office | Design / Scope Development phase for Programwide Small Capital & Emergency Response Improvements: develop and finalize engineering design to support procurement and construction.
1.12.2.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA02 | Design / Scope Development | P12-WP021 | Field Scoping & Estimate | Design | Program Controls Office | Develop field scope and cost estimate for prioritized work orders.
1.12.3 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Programwide Small Capital & Emergency Response Improvements: solicit, award, and execute construction and/or equipment contracts.
1.12.3.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA03 | Procurement | P12-WP031 | Contractor / Materials Procurement | Procurement | Procurement & Contracts Lead | Procure contractor task-order support and/or materials for prioritized work orders.
1.12.4 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution |  |  | Construction | Field Operations / Contractor | Execution phase for Programwide Small Capital & Emergency Response Improvements: perform planned small-capital repairs and prioritized emergency-response work.
1.12.4.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution | P12-WP041 | Small Capital Repair Execution | Construction | Field Operations / Contractor | Execute planned, prioritized small-capital repair work orders across the distribution system.
1.12.4.2 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution | P12-WP042 | Emergency Response Work Execution | Construction | Field Operations / Contractor | Execute unplanned emergency repair work orders as they are identified and prioritized.
1.12.5 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA05 | Verification / Acceptance |  |  | Testing & Commissioning | Program Controls Office | Verification / Acceptance phase for Programwide Small Capital & Emergency Response Improvements: confirm completed work meets specification before closing the work order.
1.12.5.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA05 | Verification / Acceptance | P12-WP051 | Work Order Acceptance & Sign-off | Testing & Commissioning | Program Controls Office | Confirm completed work orders meet specification and obtain sign-off.
1.12.6 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA06 | Closeout |  |  | Closeout | Program Controls Office | Closeout phase for Programwide Small Capital & Emergency Response Improvements: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.12.6.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA06 | Closeout | P12-WP061 | Documentation & Work Order Closeout | Closeout | Program Controls Office | Finalize work order documentation and close out completed small-capital/emergency work orders.