## Field_Dictionary
HWSD Project Controls Model — Data Dictionary
Defines every field before it is populated. Expanded in each build phase as new sheets are added.
01_PROJECTS — Project Master List (built in Phase 1)
Field | Definition | Example
project_id | Unique project identifier, constant across every file in this repository | P03
project_name | Short, plain-English project title | Central WTP Process Upgrade
category | Infrastructure category used for grouping and dashboard filtering | Treatment
project_manager | Name of the project manager accountable for this project | Sarah Whitfield
bac | Budget at Completion — total authorized baseline budget for the project (USD) | 22000000
pct_of_program_budget | Project BAC as a share of the $96.0M program BAC | 22.9%
planned_start | Baseline planned start date (month-level precision at this phase) | Jan-2025
planned_finish | Baseline planned finish date (month-level precision at this phase) | Sep-2027
planned_duration_months | planned_finish minus planned_start, in months | 33
status_as_of_status_date | High-level phase status as of the fixed reporting date (Mar 31, 2026) | In Construction
Fields defined in the guide, populated starting Phase 4 (Earned Value Management)
Field | Definition | Example
pv | Planned Value — budgeted cost of work scheduled through the status date | 7700000
ev | Earned Value — budgeted cost of work actually performed through the status date | 6600000
ac | Actual Cost — actual cumulative cost incurred through the status date | 7100000
cpi | Cost Performance Index = EV / AC. Above 1.0 is favorable, below 1.0 is unfavorable. | 0.93
spi | Schedule Performance Index = EV / PV. Above 1.0 is favorable, below 1.0 is unfavorable. | 0.86
eac | Estimate at Completion = BAC / CPI (simplified method, assumes current efficiency continues) | 23655914
etc | Estimate to Complete = EAC − AC | 16555914
vac | Variance at Completion = BAC − EAC | -1655914
Fields defined in the guide, populated starting Phase 5 (Risk Register)
Field | Definition | Example
risk_id | Unique risk identifier | R-014
risk_score | Inherent risk score = probability_score (1-5) × impact_score (1-5) | 16
Fields defined in the guide, populated starting Phase 6 (Change Control)
Field | Definition | Example
change_cost | Approved or proposed budget impact of a change order (USD) | 600000