## 00_README
HWSD_Project_Controls_Model.xlsx
Source-of-truth project-controls workbook for the HWSD Municipal Water Capital Improvement Program (simulated).
Project BAC total (P01-P12): $88,500,000 ¦ Program contingency reserve: $7,500,000
Total program authorization: $96,000,000 ¦ 12 projects ¦ 36-month program (Jan 2025 - Dec 2027)
Status date (all PV/EV/AC/schedule status is measured as of this date): March 31, 2026 (Month 15 of 36)
IMPORTANT: For all Earned Value Management calculations (Phase 4), 'program BAC' means the
$88,500,000 project BAC total, NOT the $96,000,000 total authorization. The $7,500,000
contingency reserve is unallocated and only enters the model through an approved change
(07_CHANGES tab), at which point it is drawn down and the receiving project's BAC increases.
Build status: Phase 1 complete (01_PROJECTS). All other tabs are structural shells only —
column headers are final, but data has not yet been entered. Each phase of the build populates
the next tab(s). See the repository README for the full phase sequence.
Conventions used throughout this workbook:
- Blue font = hardcoded input. Black font = formula. Do not hand-edit formula cells.
- All dollar figures are in whole USD.
- project_id is the join key across every sheet in this workbook and every CSV in /02_data.
- This workbook is the controlled source of truth. Power BI and Python read from exports
of this workbook or from /02_data/processed — they do not maintain independent copies of
baseline data.
All program, project, cost, schedule, risk, and vendor data in this workbook is synthetic
and created for portfolio demonstration purposes only.
BASELINE CONTROL — SYNTHETIC RECOVERY APPROVED
03_SCHEDULE: 428 activity/milestone rows; 03_SCHEDULE_RELATIONSHIPS: 498 dependency records.
Schedule CPM complete: 428 activities and milestones; 498 dependency records; all twelve approved project finishes unchanged.
Five user-approved synthetic NTP release holds were inserted and retained in the relationship CSV.
Critical / near-critical criteria: 0bd / 1–5bd total float under per-project finish anchors. See CPM_SUMMARY and CPM_METHOD.
P08-MOUTAGE is independently fixed on 2026-05-22; its zero float is constraint-driven and not evidence of the governing construction path.
Project BAC $88.5M, reserve $7.5M, authorized total $96M unchanged.
Phase 3G: approved synthetic cost ownership and PV proxy rules implemented. See COST_* sheets.
04_MONTHLY_COSTS now contains 432 project-month baseline PV rows, actuals/commitments left blank.
All project PV totals $88.5M through December 2027; $7.5M contingency excluded.
Monthly PV is budgeted scheduled work; not contractor invoicing, cash expenditure or earned progress.
Phase 4B: synthetic progress, cost and commitment records through March 31 2026.
EV is separate from PV; synthetic evidence is not contractor documentation.
05_EVM and EVM_* sheets contain scenario snapshot; approved schedule and COST_* baseline unchanged.
Commitments are excluded from AC and EV; frozen snapshot rerun needed on changes.

## 01_PROJECTS
Project Master List
One row per project. project_id is the join key used across every other sheet and CSV in this repository.
project_id | project_name | category | project_manager | bac | pct_of_project_bac_total | planned_start | planned_finish | planned_duration_months | status_as_of_status_date
P01 | Downtown 12-inch Water Main Replacement | Distribution | Maria Chen | 7400000 | 8.362% | 2025-01-02 | 2025-12-29 | 11.9 | Substantially Complete
P02 | Northside Pump Station Rehabilitation | Pumping | David Okafor | 8800000 | 9.944% | 2025-02-03 | 2026-02-25 | 12.7 | In Construction
P03 | Central Water Treatment Plant Process Upgrade | Treatment | Sarah Whitfield | 20300000 | 22.94% | 2025-01-02 | 2027-01-27 | 24.8 | In Construction
P04 | Hilltop Storage Tank Rehabilitation | Storage | James Patel | 5500000 | 6.215% | 2025-06-02 | 2026-04-24 | 10.7 | In Construction
P05 | Lead Service Line Replacement - Phase 1 | Distribution / Public Health | Maria Chen | 11100000 | 12.54% | 2025-03-03 | 2026-05-15 | 14.4 | In Construction
P06 | AMI / Smart Meter Modernization | Metering / Digital | Angela Torres | 6900000 | 7.797% | 2025-08-01 | 2026-12-24 | 16.8 | In Construction
P07 | East Zone Pressure Management Improvements | Distribution | Robert Kim | 4100000 | 4.633% | 2025-10-01 | 2026-09-01 | 11 | In Construction
P08 | Emergency Generator & Electrical Resiliency | Resiliency | Robert Kim | 4600000 | 5.198% | 2025-12-01 | 2027-01-08 | 13.2 | Design / Early Construction
P09 | River Crossing Main Rehabilitation | Distribution | David Okafor | 7800000 | 8.814% | 2026-02-02 | 2027-03-03 | 12.9 | Mobilization / Early Construction
P10 | SCADA Controls Modernization | Digital / Controls | Angela Torres | 3700000 | 4.181% | 2026-04-01 | 2027-08-06 | 16.2 | Planning / Not Started
P11 | Valve Replacement & Isolation Program | Distribution | James Patel | 3200000 | 3.616% | 2025-04-01 | 2026-03-09 | 11.2 | In Construction
P12 | Programwide Small Capital & Emergency Response Improvements | Small Capital & Emergency Response | Program Controls Office | 5100000 | 5.763% | 2025-01-02 | 2027-06-23 | 29.6 | Ongoing / As-Needed
| PROJECT BAC TOTAL (P01-P12) |  |  | 88500000
| Program Contingency Reserve (not a project; held at program level) |  |  | 7500000
| TOTAL PROGRAM AUTHORIZATION |  |  | 96000000
QA checks: | OK - Project BAC total = $88.5M
OK - Total program authorization = $96.0M
Note: | P12 (Programwide Small Capital & Emergency Response Improvements) is real, planned, scoped standing capital work with its own BAC, included in the $88.5M project total above. It is NOT the program contingency reserve. Truly unplanned/unscoped changes draw from the $7.5M program contingency reserve via an approved change request (07_CHANGES), not from P12.

## 02_WBS
Work Breakdown Structure
Level 3 = Control Account (receives its own allocated BAC/PV/EV/AC in Phase 4; project BAC rolls up from its control accounts). Level 4 = Work Package (schedule activities in Phase 2 will attach here). Standard_Lifecycle_Phase maps every control account - including P12's differently-worded phases - back to one of six portfolio-wide categories for Power BI rollups.
WBS_Code | WBS_Level | Project_ID | Project_Name | Control_Account_ID | Control_Account_Name | Work_Package_ID | Work_Package_Name | Standard_Lifecycle_Phase | Responsible_Role | Description
1.01.1 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Downtown 12-inch Water Main Replacement: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.01.1.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning | P01-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Downtown 12-inch Water Main Replacement.
1.01.1.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning | P01-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Downtown 12-inch Water Main Replacement.
1.01.2 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Downtown 12-inch Water Main Replacement: develop and finalize engineering design to support procurement and construction.
1.01.2.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design | P01-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Downtown 12-inch Water Main Replacement.
1.01.2.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design | P01-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Downtown 12-inch Water Main Replacement.
1.01.3 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Downtown 12-inch Water Main Replacement: solicit, award, and execute construction and/or equipment contracts.
1.01.3.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement | P01-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Downtown 12-inch Water Main Replacement.
1.01.3.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement | P01-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Downtown 12-inch Water Main Replacement.
1.01.4 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Downtown 12-inch Water Main Replacement: execute physical construction, installation, or implementation work.
1.01.4.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP041 | Pipe Installation & Jointing | Construction | Construction Manager / Contractor | Excavate, lay, and joint new 12-inch ductile iron water main along the downtown corridor route.
1.01.4.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP042 | Valve & Hydrant Tie-Ins | Construction | Construction Manager / Contractor | Install new isolation valves and fire hydrant connections and tie into the existing distribution system.
1.01.4.3 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP043 | Pavement & Surface Restoration | Construction | Construction Manager / Contractor | Backfill, compact, and restore pavement, sidewalks, and surface features disturbed by construction.
1.01.5 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Downtown 12-inch Water Main Replacement: test, start up, and verify system performance prior to acceptance.
1.01.5.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA05 | Testing & Commissioning | P01-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Downtown 12-inch Water Main Replacement.
1.01.6 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Downtown 12-inch Water Main Replacement: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.01.6.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout | P01-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Downtown 12-inch Water Main Replacement.
1.01.6.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout | P01-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Downtown 12-inch Water Main Replacement.
1.02.1 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Northside Pump Station Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.02.1.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning | P02-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Northside Pump Station Rehabilitation.
1.02.1.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning | P02-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Northside Pump Station Rehabilitation.
1.02.2 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Northside Pump Station Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.02.2.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design | P02-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Northside Pump Station Rehabilitation.
1.02.2.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design | P02-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Northside Pump Station Rehabilitation.
1.02.3 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Northside Pump Station Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.02.3.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement | P02-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Northside Pump Station Rehabilitation.
1.02.3.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement | P02-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Northside Pump Station Rehabilitation.
1.02.4 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Northside Pump Station Rehabilitation: execute physical construction, installation, or implementation work.
1.02.4.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP041 | Pump & Motor Replacement | Construction | Construction Manager / Contractor | Remove existing pumps and motors and install new high-efficiency units per design.
1.02.4.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP042 | Electrical Switchgear Upgrade | Construction | Construction Manager / Contractor | Replace station switchgear, VFDs, and associated electrical distribution equipment.
1.02.4.3 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP043 | Wetwell Structural Rehabilitation | Construction | Construction Manager / Contractor | Repair and recoat wetwell concrete structure and associated access hardware.
1.02.5 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Northside Pump Station Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.02.5.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA05 | Testing & Commissioning | P02-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Northside Pump Station Rehabilitation.
1.02.6 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Northside Pump Station Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.02.6.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout | P02-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Northside Pump Station Rehabilitation.
1.02.6.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout | P02-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Northside Pump Station Rehabilitation.
1.03.1 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Central Water Treatment Plant Process Upgrade: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.03.1.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning | P03-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Central Water Treatment Plant Process Upgrade.
1.03.1.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning | P03-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Central Water Treatment Plant Process Upgrade.
1.03.2 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Central Water Treatment Plant Process Upgrade: develop and finalize engineering design to support procurement and construction.
1.03.2.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design | P03-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Central Water Treatment Plant Process Upgrade.
1.03.2.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design | P03-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Central Water Treatment Plant Process Upgrade.
1.03.3 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Central Water Treatment Plant Process Upgrade: solicit, award, and execute construction and/or equipment contracts.
1.03.3.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement | P03-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Central Water Treatment Plant Process Upgrade.
1.03.3.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement | P03-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Central Water Treatment Plant Process Upgrade.
1.03.4 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Central Water Treatment Plant Process Upgrade: execute physical construction, installation, or implementation work.
1.03.4.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP041 | Process Mechanical Installation | Construction | Construction Manager / Contractor | Install new process mechanical equipment (clarifiers, filters, pumps) per the treatment process design.
1.03.4.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP042 | Electrical & Instrumentation Installation | Construction | Construction Manager / Contractor | Install new electrical distribution, control panels, and process instrumentation.
1.03.4.3 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP043 | Chemical Feed System Installation | Construction | Construction Manager / Contractor | Install new chemical storage, feed pumps, and containment for treatment process chemicals.
1.03.5 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Central Water Treatment Plant Process Upgrade: test, start up, and verify system performance prior to acceptance.
1.03.5.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP051 | Process Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform sequential process startup and functional testing of new mechanical and electrical systems.
1.03.5.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP052 | Performance / Acceptance Testing | Testing & Commissioning | Commissioning Lead | Conduct performance testing against design criteria and regulatory treatment standards.
1.03.5.3 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP053 | Regulatory Sign-off & SCADA Integration Checkout | Testing & Commissioning | Commissioning Lead | Coordinate state regulatory sign-off and verify full SCADA integration prior to substantial completion.
1.03.6 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Central Water Treatment Plant Process Upgrade: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.03.6.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout | P03-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Central Water Treatment Plant Process Upgrade.
1.03.6.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout | P03-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Central Water Treatment Plant Process Upgrade.
1.04.1 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Hilltop Storage Tank Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.04.1.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning | P04-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Hilltop Storage Tank Rehabilitation.
1.04.1.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning | P04-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Hilltop Storage Tank Rehabilitation.
1.04.2 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Hilltop Storage Tank Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.04.2.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design | P04-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Hilltop Storage Tank Rehabilitation.
1.04.2.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design | P04-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Hilltop Storage Tank Rehabilitation.
1.04.3 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Hilltop Storage Tank Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.04.3.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement | P04-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Hilltop Storage Tank Rehabilitation.
1.04.3.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement | P04-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Hilltop Storage Tank Rehabilitation.
1.04.4 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Hilltop Storage Tank Rehabilitation: execute physical construction, installation, or implementation work.
1.04.4.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP041 | Tank Interior/Exterior Coating | Construction | Construction Manager / Contractor | Prepare surfaces and apply new interior and exterior protective coating systems to the storage tank.
1.04.4.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP042 | Structural Steel Repairs | Construction | Construction Manager / Contractor | Repair or replace corroded structural steel members identified during inspection.
1.04.4.3 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP043 | Cathodic Protection System Installation | Construction | Construction Manager / Contractor | Install a new impressed-current cathodic protection system to mitigate future corrosion.
1.04.5 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Hilltop Storage Tank Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.04.5.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA05 | Testing & Commissioning | P04-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Hilltop Storage Tank Rehabilitation.
1.04.6 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Hilltop Storage Tank Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.04.6.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout | P04-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Hilltop Storage Tank Rehabilitation.
1.04.6.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout | P04-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Hilltop Storage Tank Rehabilitation.
1.05.1 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Lead Service Line Replacement - Phase 1: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.05.1.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning | P05-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Lead Service Line Replacement - Phase 1.
1.05.1.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning | P05-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Lead Service Line Replacement - Phase 1.
1.05.2 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Lead Service Line Replacement - Phase 1: develop and finalize engineering design to support procurement and construction.
1.05.2.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design | P05-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Lead Service Line Replacement - Phase 1.
1.05.2.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design | P05-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Lead Service Line Replacement - Phase 1.
1.05.3 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Lead Service Line Replacement - Phase 1: solicit, award, and execute construction and/or equipment contracts.
1.05.3.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement | P05-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Lead Service Line Replacement - Phase 1.
1.05.3.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement | P05-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Lead Service Line Replacement - Phase 1.
1.05.4 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Lead Service Line Replacement - Phase 1: execute physical construction, installation, or implementation work.
1.05.4.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP041 | Service Line Excavation & Replacement | Construction | Construction Manager / Contractor | Excavate and replace individual lead service lines with new copper or approved alternative piping.
1.05.4.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP042 | Property Restoration | Construction | Construction Manager / Contractor | Restore landscaping, driveways, and other surface features disturbed at each service address.
1.05.4.3 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP043 | Water Quality Sampling & Verification | Construction | Construction Manager / Contractor | Collect and analyze post-replacement water samples to verify compliance with lead action levels.
1.05.5 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Lead Service Line Replacement - Phase 1: test, start up, and verify system performance prior to acceptance.
1.05.5.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA05 | Testing & Commissioning | P05-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Lead Service Line Replacement - Phase 1.
1.05.6 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Lead Service Line Replacement - Phase 1: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.05.6.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout | P05-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Lead Service Line Replacement - Phase 1.
1.05.6.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout | P05-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Lead Service Line Replacement - Phase 1.
1.06.1 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for AMI / Smart Meter Modernization: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.06.1.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning | P06-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for AMI / Smart Meter Modernization.
1.06.1.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning | P06-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for AMI / Smart Meter Modernization.
1.06.2 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for AMI / Smart Meter Modernization: develop and finalize engineering design to support procurement and construction.
1.06.2.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design | P06-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for AMI / Smart Meter Modernization.
1.06.2.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design | P06-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for AMI / Smart Meter Modernization.
1.06.3 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for AMI / Smart Meter Modernization: solicit, award, and execute construction and/or equipment contracts.
1.06.3.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement | P06-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for AMI / Smart Meter Modernization.
1.06.3.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement | P06-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for AMI / Smart Meter Modernization.
1.06.4 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for AMI / Smart Meter Modernization: execute physical construction, installation, or implementation work.
1.06.4.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP041 | Meter Deployment & Installation | Construction | Construction Manager / Contractor | Remove existing meters and install new AMI-compatible meters at customer premises.
1.06.4.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP042 | Head-End System Integration | Construction | Construction Manager / Contractor | Install and configure the head-end data collection system and network gateways.
1.06.4.3 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP043 | Customer Data Migration & Validation | Construction | Construction Manager / Contractor | Migrate existing customer account and consumption data into the new metering platform and validate accuracy.
1.06.5 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for AMI / Smart Meter Modernization: test, start up, and verify system performance prior to acceptance.
1.06.5.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA05 | Testing & Commissioning | P06-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for AMI / Smart Meter Modernization.
1.06.6 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for AMI / Smart Meter Modernization: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.06.6.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout | P06-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for AMI / Smart Meter Modernization.
1.06.6.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout | P06-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for AMI / Smart Meter Modernization.
1.07.1 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for East Zone Pressure Management Improvements: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.07.1.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning | P07-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for East Zone Pressure Management Improvements.
1.07.1.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning | P07-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for East Zone Pressure Management Improvements.
1.07.2 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for East Zone Pressure Management Improvements: develop and finalize engineering design to support procurement and construction.
1.07.2.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design | P07-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for East Zone Pressure Management Improvements.
1.07.2.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design | P07-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for East Zone Pressure Management Improvements.
1.07.3 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for East Zone Pressure Management Improvements: solicit, award, and execute construction and/or equipment contracts.
1.07.3.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement | P07-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for East Zone Pressure Management Improvements.
1.07.3.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement | P07-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for East Zone Pressure Management Improvements.
1.07.4 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for East Zone Pressure Management Improvements: execute physical construction, installation, or implementation work.
1.07.4.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP041 | PRV Station Installation | Construction | Construction Manager / Contractor | Construct new pressure-reducing valve vaults and install PRV equipment at designated zone boundaries.
1.07.4.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP042 | Zone Isolation Valve Installation | Construction | Construction Manager / Contractor | Install new isolation valves to establish discrete pressure zone boundaries.
1.07.4.3 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP043 | Pressure Monitoring Instrumentation | Construction | Construction Manager / Contractor | Install remote pressure monitoring sensors and telemetry at key system locations.
1.07.5 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for East Zone Pressure Management Improvements: test, start up, and verify system performance prior to acceptance.
1.07.5.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA05 | Testing & Commissioning | P07-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for East Zone Pressure Management Improvements.
1.07.6 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for East Zone Pressure Management Improvements: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.07.6.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout | P07-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for East Zone Pressure Management Improvements.
1.07.6.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout | P07-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for East Zone Pressure Management Improvements.
1.08.1 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Emergency Generator & Electrical Resiliency: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.08.1.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning | P08-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Emergency Generator & Electrical Resiliency.
1.08.1.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning | P08-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Emergency Generator & Electrical Resiliency.
1.08.2 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Emergency Generator & Electrical Resiliency: develop and finalize engineering design to support procurement and construction.
1.08.2.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design | P08-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Emergency Generator & Electrical Resiliency.
1.08.2.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design | P08-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Emergency Generator & Electrical Resiliency.
1.08.3 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Emergency Generator & Electrical Resiliency: solicit, award, and execute construction and/or equipment contracts.
1.08.3.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement | P08-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Emergency Generator & Electrical Resiliency.
1.08.3.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement | P08-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Emergency Generator & Electrical Resiliency.
1.08.4 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Emergency Generator & Electrical Resiliency: execute physical construction, installation, or implementation work.
1.08.4.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP041 | Generator Installation | Construction | Construction Manager / Contractor | Install new standby generator units and associated foundations/enclosures at each site.
1.08.4.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP042 | Automatic Transfer Switch Installation | Construction | Construction Manager / Contractor | Install automatic transfer switches and integrate with existing electrical distribution.
1.08.4.3 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP043 | Fuel Storage System Installation | Construction | Construction Manager / Contractor | Install fuel storage tanks and supply piping per code requirements.
1.08.5 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Emergency Generator & Electrical Resiliency: test, start up, and verify system performance prior to acceptance.
1.08.5.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA05 | Testing & Commissioning | P08-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Emergency Generator & Electrical Resiliency.
1.08.6 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Emergency Generator & Electrical Resiliency: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.08.6.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout | P08-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Emergency Generator & Electrical Resiliency.
1.08.6.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout | P08-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Emergency Generator & Electrical Resiliency.
1.09.1 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for River Crossing Main Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.09.1.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning | P09-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for River Crossing Main Rehabilitation.
1.09.1.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning | P09-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for River Crossing Main Rehabilitation.
1.09.2 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for River Crossing Main Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.09.2.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design | P09-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for River Crossing Main Rehabilitation.
1.09.2.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design | P09-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for River Crossing Main Rehabilitation.
1.09.3 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for River Crossing Main Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.09.3.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement | P09-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for River Crossing Main Rehabilitation.
1.09.3.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement | P09-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for River Crossing Main Rehabilitation.
1.09.4 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for River Crossing Main Rehabilitation: execute physical construction, installation, or implementation work.
1.09.4.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP041 | Directional Drilling / Crossing Installation | Construction | Construction Manager / Contractor | Perform horizontal directional drilling to install new main beneath the river crossing.
1.09.4.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP042 | Pipe Fusion & Pressure Testing | Construction | Construction Manager / Contractor | Fuse HDPE pipe segments and perform hydrostatic pressure testing of the completed crossing.
1.09.4.3 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP043 | Riverbank Restoration | Construction | Construction Manager / Contractor | Restore riverbank grading, erosion control, and vegetation at entry/exit pit locations.
1.09.5 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for River Crossing Main Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.09.5.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA05 | Testing & Commissioning | P09-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for River Crossing Main Rehabilitation.
1.09.6 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for River Crossing Main Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.09.6.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout | P09-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for River Crossing Main Rehabilitation.
1.09.6.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout | P09-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for River Crossing Main Rehabilitation.
1.10.1 | 3 | P10 | SCADA Controls Modernization | P10-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for SCADA Controls Modernization: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.10.1.1 | 4 | P10 | SCADA Controls Modernization | P10-CA01 | Planning | P10-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for SCADA Controls Modernization.
1.10.1.2 | 4 | P10 | SCADA Controls Modernization | P10-CA01 | Planning | P10-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for SCADA Controls Modernization.
1.10.2 | 3 | P10 | SCADA Controls Modernization | P10-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for SCADA Controls Modernization: develop and finalize engineering design to support procurement and construction.
1.10.2.1 | 4 | P10 | SCADA Controls Modernization | P10-CA02 | Design | P10-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for SCADA Controls Modernization.
1.10.2.2 | 4 | P10 | SCADA Controls Modernization | P10-CA02 | Design | P10-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for SCADA Controls Modernization.
1.10.3 | 3 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for SCADA Controls Modernization: solicit, award, and execute construction and/or equipment contracts.
1.10.3.1 | 4 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement | P10-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for SCADA Controls Modernization.
1.10.3.2 | 4 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement | P10-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for SCADA Controls Modernization.
1.10.4 | 3 | P10 | SCADA Controls Modernization | P10-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for SCADA Controls Modernization: execute physical construction, installation, or implementation work.
1.10.4.1 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP041 | PLC Programming & Configuration | Construction | Construction Manager / Contractor | Develop and configure PLC logic for affected pump stations and treatment facilities.
1.10.4.2 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP042 | HMI Development | Construction | Construction Manager / Contractor | Develop human-machine interface screens and alarm configurations for operator use.
1.10.4.3 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP043 | Network & Communications Infrastructure | Construction | Construction Manager / Contractor | Install and configure the SCADA communications network linking field sites to the control center.
1.10.5 | 3 | P10 | SCADA Controls Modernization | P10-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for SCADA Controls Modernization: test, start up, and verify system performance prior to acceptance.
1.10.5.1 | 4 | P10 | SCADA Controls Modernization | P10-CA05 | Testing & Commissioning | P10-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for SCADA Controls Modernization.
1.10.6 | 3 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for SCADA Controls Modernization: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.10.6.1 | 4 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout | P10-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for SCADA Controls Modernization.
1.10.6.2 | 4 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout | P10-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for SCADA Controls Modernization.
1.11.1 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Valve Replacement & Isolation Program: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.11.1.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning | P11-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Valve Replacement & Isolation Program.
1.11.1.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning | P11-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Valve Replacement & Isolation Program.
1.11.2 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Valve Replacement & Isolation Program: develop and finalize engineering design to support procurement and construction.
1.11.2.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design | P11-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Valve Replacement & Isolation Program.
1.11.2.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design | P11-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Valve Replacement & Isolation Program.
1.11.3 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Valve Replacement & Isolation Program: solicit, award, and execute construction and/or equipment contracts.
1.11.3.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement | P11-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Valve Replacement & Isolation Program.
1.11.3.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement | P11-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Valve Replacement & Isolation Program.
1.11.4 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Valve Replacement & Isolation Program: execute physical construction, installation, or implementation work.
1.11.4.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP041 | Isolation Valve Installation | Construction | Construction Manager / Contractor | Install new isolation valves at designated locations across the distribution system.
1.11.4.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP042 | Distribution System Mapping Update | Construction | Construction Manager / Contractor | Update GIS and system mapping records to reflect newly installed valve locations and status.
1.11.4.3 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP043 | Site Restoration | Construction | Construction Manager / Contractor | Restore pavement and surface conditions at each valve installation location.
1.11.5 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Valve Replacement & Isolation Program: test, start up, and verify system performance prior to acceptance.
1.11.5.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA05 | Testing & Commissioning | P11-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Valve Replacement & Isolation Program.
1.11.6 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Valve Replacement & Isolation Program: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.11.6.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout | P11-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Valve Replacement & Isolation Program.
1.11.6.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout | P11-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Valve Replacement & Isolation Program.
1.12.1 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA01 | Planning & Prioritization |  |  | Planning | Program Controls Office | Planning & Prioritization phase for Programwide Small Capital & Emergency Response Improvements: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.12.1.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA01 | Planning & Prioritization | P12-WP011 | Work Order Intake & Prioritization | Planning | Program Controls Office | Intake, screen, and prioritize candidate small-capital and emergency work orders across the program.
1.12.2 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA02 | Design / Scope Development |  |  | Design | Program Controls Office | Design / Scope Development phase for Programwide Small Capital & Emergency Response Improvements: develop and finalize engineering design to support procurement and construction.
1.12.2.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA02 | Design / Scope Development | P12-WP021 | Field Scoping & Estimate | Design | Program Controls Office | Develop field scope and cost estimate for prioritized work orders.
1.12.3 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Programwide Small Capital & Emergency Response Improvements: solicit, award, and execute construction and/or equipment contracts.
1.12.3.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA03 | Procurement | P12-WP031 | Contractor / Materials Procurement | Procurement | Procurement & Contracts Lead | Procure contractor task-order support and/or materials for prioritized work orders.
1.12.4 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution |  |  | Construction | Field Operations / Contractor | Execution phase for Programwide Small Capital & Emergency Response Improvements: perform planned small-capital repairs and prioritized emergency-response work.
1.12.4.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution | P12-WP041 | Small Capital Repair Execution | Construction | Field Operations / Contractor | Execute planned, prioritized small-capital repair work orders across the distribution system.
1.12.4.2 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution | P12-WP042 | Emergency Response Work Execution | Construction | Field Operations / Contractor | Execute unplanned emergency repair work orders as they are identified and prioritized.
1.12.5 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA05 | Verification / Acceptance |  |  | Testing & Commissioning | Program Controls Office | Verification / Acceptance phase for Programwide Small Capital & Emergency Response Improvements: confirm completed work meets specification before closing the work order.
1.12.5.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA05 | Verification / Acceptance | P12-WP051 | Work Order Acceptance & Sign-off | Testing & Commissioning | Program Controls Office | Confirm completed work orders meet specification and obtain sign-off.
1.12.6 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA06 | Closeout |  |  | Closeout | Program Controls Office | Closeout phase for Programwide Small Capital & Emergency Response Improvements: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.12.6.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA06 | Closeout | P12-WP061 | Documentation & Work Order Closeout | Closeout | Program Controls Office | Finalize work order documentation and close out completed small-capital/emergency work orders.

## 03_SCHEDULE
Schedule
Approved HWSD synthetic recovery baseline — CPM calculated with per-project finish anchors, cross-project interfaces, 5 approved release holds and a source-explicit fixed-date P08 outage milestone.
activity_id | project_id | activity_name | wbs_code | baseline_start | baseline_finish | forecast_start | forecast_finish | actual_start | actual_finish | duration_days | predecessor | percent_complete | is_milestone | critical_flag | control_account_id | work_package_id | activity_type | assumption_basis | recovery_status | early_start | early_finish | late_start | late_finish | total_float_days
P01-A1 | P01 | Conduct Needs Assessment | 1.01.1.1 | 2025-01-02 | 2025-01-15 |  |  |  |  | 10 |  |  | FALSE | TRUE | P01-CA01 | P01-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-01-02 | 2025-01-15 | 2025-01-02 | 2025-01-15 | 0
P01-A6 | P01 | Contractor Mobilization | 1.01.3.2 | 2025-05-15 | 2025-06-04 |  |  |  |  | 15 | P01-M2 |  | FALSE | FALSE | P01-CA03 | P01-WP032 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-15 | 2025-06-04 | 2025-07-08 | 2025-07-28 | 38
P01-A7a | P01 | Pipe / Valve / Hydrant Submittal Review | 1.01.3.1 | 2025-05-15 | 2025-06-04 |  |  |  |  | 15 | P01-M2 |  | FALSE | TRUE | P01-CA03 | P01-WP031 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-15 | 2025-06-04 | 2025-05-15 | 2025-06-04 | 0
P01-A2 | P01 | Finalize Project Definition & Scope | 1.01.1.2 | 2025-01-16 | 2025-01-22 |  |  |  |  | 5 | P01-A1 |  | FALSE | TRUE | P01-CA01 | P01-WP012 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-01-16 | 2025-01-22 | 2025-01-16 | 2025-01-22 | 0
P01-A3 | P01 | Develop Preliminary Design | 1.01.2.1 | 2025-01-23 | 2025-02-19 |  |  |  |  | 20 | P01-A2 |  | FALSE | TRUE | P01-CA02 | P01-WP021 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-01-23 | 2025-02-19 | 2025-01-23 | 2025-02-19 | 0
P01-A7b | P01 | Pipe Fabrication | 1.01.4.1 | 2025-06-05 | 2025-07-16 |  |  |  |  | 30 | P01-A7a |  | FALSE | TRUE | P01-CA04 | P01-WP041 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-05 | 2025-07-16 | 2025-06-05 | 2025-07-16 | 0
P01-A4u | P01 | Utility Coordination & Locate Requests | 1.01.4.1 | 2025-02-20 | 2025-03-05 |  |  |  |  | 10 | P01-A3 |  | FALSE | FALSE | P01-CA04 | P01-WP041 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 10 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-20 | 2025-03-05 | 2025-07-15 | 2025-07-28 | 103
P01-A4 | P01 | Complete Final Design | 1.01.2.2 | 2025-03-06 | 2025-04-09 |  |  |  |  | 25 | P01-A3 |  | FALSE | TRUE | P01-CA02 | P01-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-03-06 | 2025-04-09 | 2025-03-06 | 2025-04-09 | 0
P01-A7c | P01 | Delivery & Receiving Inspection | 1.01.4.1 | 2025-07-17 | 2025-07-28 |  |  |  |  | 8 | P01-A7b |  | FALSE | TRUE | P01-CA04 | P01-WP041 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-17 | 2025-07-28 | 2025-07-17 | 2025-07-28 | 0
P01-A8 | P01 | Install & Joint Water Main Pipe | 1.01.4.1 | 2025-07-29 | 2025-09-29 |  |  |  |  | 45 | P01-A6, P01-A7c, P01-A4u |  | FALSE | TRUE | P01-CA04 | P01-WP041 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-29 | 2025-09-29 | 2025-07-29 | 2025-09-29 | 0
P01-A5 | P01 | Prepare & Advertise Bid Package | 1.01.3.1 | 2025-03-27 | 2025-04-16 |  |  |  |  | 15 | P01-A4 |  | FALSE | TRUE | P01-CA03 | P01-WP031 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-03-27 | 2025-04-16 | 2025-03-27 | 2025-04-16 | 0
P01-A9 | P01 | Install Valves & Hydrant Tie-Ins | 1.01.4.2 | 2025-08-19 | 2025-09-08 |  |  |  |  | 15 | P01-A8 |  | FALSE | FALSE | P01-CA04 | P01-WP042 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-19 | 2025-09-08 | 2025-09-16 | 2025-10-06 | 20
P01-A4b | P01 | Regulatory Plan Review & Approval | 1.01.2.2 | 2025-04-10 | 2025-04-30 |  |  |  |  | 15 | P01-A4 |  | FALSE | FALSE | P01-CA02 | P01-WP022 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 15 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-10 | 2025-04-30 | 2025-04-24 | 2025-05-14 | 10
P01-M1 | P01 | Design Complete | 1.01.2.2 | 2025-04-09 | 2025-04-09 |  |  |  |  | 0 | P01-A4 |  | TRUE | FALSE | P01-CA02 | P01-WP022 | Milestone | Approved standard milestone; exact milestone date reconstructed from final network | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-09 | 2025-04-09 | 2025-12-29 | 2025-12-29 | 188
P01-A9b | P01 | Shutdown Planning & Operations Coordination | 1.01.4.2 | 2025-08-26 | 2025-09-08 |  |  |  |  | 10 | P01-A8 |  | FALSE | FALSE | P01-CA04 | P01-WP042 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 10 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-26 | 2025-09-08 | 2025-09-23 | 2025-10-06 | 20
P01-A5b | P01 | Bid Evaluation, Selection & Award Recommendation | 1.01.3.1 | 2025-04-17 | 2025-04-30 |  |  |  |  | 10 | P01-A5 |  | FALSE | TRUE | P01-CA03 | P01-WP031 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-17 | 2025-04-30 | 2025-04-17 | 2025-04-30 | 0
P01-M2 | P01 | Contract Award / NTP | 1.01.3.2 | 2025-05-14 | 2025-05-14 |  |  |  |  | 0 | P01-A5b, P01-A4b |  | TRUE | TRUE | P01-CA03 | P01-WP032 | Milestone | Approved standard milestone; exact milestone date reconstructed from final network | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 0
P01-A11 | P01 | Pressure Testing & Disinfection | 1.01.5.1 | 2025-10-07 | 2025-10-13 |  |  |  |  | 5 | P01-A8, P01-A9, P01-A9b |  | FALSE | TRUE | P01-CA05 | P01-WP051 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-07 | 2025-10-13 | 2025-10-07 | 2025-10-13 | 0
P01-A12 | P01 | Bacteriological Sampling & Regulatory Clearance | 1.01.2.2 | 2025-10-14 | 2025-10-20 |  |  |  |  | 5 | P01-A11 |  | FALSE | TRUE | P01-CA02 | P01-WP022 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-14 | 2025-10-20 | 2025-10-14 | 2025-10-20 | 0
P01-A10 | P01 | Pavement & Surface Restoration | 1.01.4.3 | 2025-10-21 | 2025-11-10 |  |  |  |  | 15 | P01-A12 |  | FALSE | TRUE | P01-CA04 | P01-WP043 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-21 | 2025-11-10 | 2025-10-21 | 2025-11-10 | 0
P01-A13 | P01 | Documentation & Turnover | 1.01.6.1 | 2025-11-25 | 2025-12-08 |  |  |  |  | 10 | P01-M3 |  | FALSE | TRUE | P01-CA06 | P01-WP061 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered ¦ PROPOSED AFTER SUBSTANTIAL COMPLETION: final turnover -> financial closeout -> final completion (not original-source recovered) | 2025-11-25 | 2025-12-08 | 2025-11-25 | 2025-12-08 | 0
P01-A14 | P01 | Financial Closeout | 1.01.6.2 | 2025-12-09 | 2025-12-29 |  |  |  |  | 15 | P01-A13, P01-A15 |  | FALSE | TRUE | P01-CA06 | P01-WP062 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered ¦ PROPOSED AFTER SUBSTANTIAL COMPLETION: final turnover -> financial closeout -> final completion (not original-source recovered) | 2025-12-09 | 2025-12-29 | 2025-12-09 | 2025-12-29 | 0
P01-A15 | P01 | Final Inspection & Punch List | 1.01.4.1 | 2025-11-11 | 2025-11-24 |  |  |  |  | 10 | P01-A10 |  | FALSE | TRUE | P01-CA04 | P01-WP041 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 10 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-11 | 2025-11-24 | 2025-11-11 | 2025-11-24 | 0
P01-M3 | P01 | Substantial Completion | 1.01.5.1 | 2025-11-24 | 2025-11-24 |  |  |  |  | 0 | P01-A15 |  | TRUE | TRUE | P01-CA05 | P01-WP051 | Milestone | Approved standard milestone; exact milestone date reconstructed from final network | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 0
P01-M4 | P01 | Final Completion | 1.01.4.1 | 2025-12-29 | 2025-12-29 |  |  |  |  | 0 | P01-A14 |  | TRUE | TRUE | P01-CA04 | P01-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit validated finish date ¦ Scenario dates calculated from reconstructed logic, not source recovered ¦ PROPOSED AFTER SUBSTANTIAL COMPLETION: final turnover -> financial closeout -> final completion (not original-source recovered) | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 0
P02-A1 | P02 | Conduct Needs Assessment | 1.02.1.1 | 2025-02-03 | 2025-02-14 |  |  |  |  | 10 |  |  | FALSE | TRUE | P02-CA01 | P02-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-03 | 2025-02-14 | 2025-02-03 | 2025-02-14 | 0
P02-A11a | P02 | Switchgear/VFD Submittal & Shop Drawing Review | 1.02.4.2 | 2025-06-02 | 2025-06-27 |  |  |  |  | 20 | P02-M2 |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | Synthetic reconstruction from approved audit standard | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-02 | 2025-06-27 | 2025-06-23 | 2025-07-18 | 15
P02-A6 | P02 | Contractor Mobilization | 1.02.3.2 | 2025-06-02 | 2025-06-13 |  |  |  |  | 10 | P02-M2 |  | FALSE | FALSE | P02-CA03 | P02-WP032 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-02 | 2025-06-13 | 2025-10-09 | 2025-10-22 | 93
P02-A6b | P02 | Bypass Planning & Operations Coordination | 1.02.4.1 | 2025-02-03 | 2025-02-21 |  |  |  |  | 15 |  |  | FALSE | FALSE | P02-CA04 | P02-WP041 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 15 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-03 | 2025-02-21 | 2025-10-02 | 2025-10-22 | 173
P02-A6c | P02 | Electric Utility Coordination | 1.02.4.2 | 2025-02-03 | 2025-02-21 |  |  |  |  | 15 |  |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 15 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-03 | 2025-02-21 | 2025-11-13 | 2025-12-03 | 203
P02-A7a | P02 | Pump/Motor Submittal & Shop Drawing Review | 1.02.4.1 | 2025-06-02 | 2025-06-27 |  |  |  |  | 20 | P02-M2 |  | FALSE | TRUE | P02-CA04 | P02-WP041 | Task | Synthetic reconstruction from approved audit standard | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-02 | 2025-06-27 | 2025-06-02 | 2025-06-27 | 0
P02-A2 | P02 | Finalize Project Definition & Scope | 1.02.1.2 | 2025-02-17 | 2025-02-21 |  |  |  |  | 5 | P02-A1 |  | FALSE | TRUE | P02-CA01 | P02-WP012 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-21 | 0
P02-A3 | P02 | Develop Preliminary Design | 1.02.2.1 | 2025-02-24 | 2025-03-21 |  |  |  |  | 20 | P02-A2 |  | FALSE | TRUE | P02-CA02 | P02-WP021 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-24 | 2025-03-21 | 2025-02-24 | 2025-03-21 | 0
P02-A8 | P02 | Install Temporary Bypass Pumping | 1.02.4.1 | 2025-06-16 | 2025-06-27 |  |  |  |  | 10 | P02-A6, P02-A6b |  | FALSE | FALSE | P02-CA04 | P02-WP041 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-16 | 2025-06-27 | 2025-10-23 | 2025-11-05 | 93
P02-A11b | P02 | Switchgear/VFD Fabrication | 1.02.4.2 | 2025-06-30 | 2025-10-17 |  |  |  |  | 80 | P02-A11a |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | Approved equipment-realistic scenario | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-30 | 2025-10-17 | 2025-07-21 | 2025-11-07 | 15
P02-A7b | P02 | Pump/Motor Fabrication | 1.02.4.1 | 2025-06-30 | 2025-10-31 |  |  |  |  | 90 | P02-A7a |  | FALSE | TRUE | P02-CA04 | P02-WP041 | Task | Approved equipment-realistic scenario | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-30 | 2025-10-31 | 2025-06-30 | 2025-10-31 | 0
P02-A9 | P02 | Demolition & Removal | 1.02.4.1 | 2025-06-30 | 2025-07-18 |  |  |  |  | 15 | P02-A8 |  | FALSE | FALSE | P02-CA04 | P02-WP041 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-30 | 2025-07-18 | 2025-11-06 | 2025-11-26 | 93
P02-M3 | P02 | Bypass Operational | 1.02.4.1 | 2025-06-27 | 2025-06-27 |  |  |  |  | 0 | P02-A8 |  | TRUE | FALSE | P02-CA04 | P02-WP041 | Milestone | Approved P02 milestone | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-27 | 2025-06-27 | 2026-02-25 | 2026-02-25 | 173
P02-A4 | P02 | Complete Final Design | 1.02.2.2 | 2025-03-24 | 2025-04-25 |  |  |  |  | 25 | P02-A3 |  | FALSE | TRUE | P02-CA02 | P02-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-03-24 | 2025-04-25 | 2025-03-24 | 2025-04-25 | 0
P02-A13 | P02 | Wetwell Structural Rehabilitation | 1.02.4.3 | 2025-07-21 | 2025-08-15 |  |  |  |  | 20 | P02-A9 |  | FALSE | FALSE | P02-CA04 | P02-WP043 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-21 | 2025-08-15 | 2025-12-04 | 2025-12-31 | 98
P02-A5 | P02 | Prepare & Advertise Bid Package | 1.02.3.1 | 2025-04-14 | 2025-05-02 |  |  |  |  | 15 | P02-A4 |  | FALSE | TRUE | P02-CA03 | P02-WP031 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-14 | 2025-05-02 | 2025-04-14 | 2025-05-02 | 0
P02-A4b | P02 | Regulatory Plan Review & Approval | 1.02.2.2 | 2025-04-28 | 2025-05-23 |  |  |  |  | 20 | P02-A4 |  | FALSE | FALSE | P02-CA02 | P02-WP022 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 20 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-28 | 2025-05-23 | 2025-05-05 | 2025-05-30 | 5
P02-M1 | P02 | Design Complete | 1.02.2.2 | 2025-04-25 | 2025-04-25 |  |  |  |  | 0 | P02-A4 |  | TRUE | FALSE | P02-CA02 | P02-WP022 | Milestone | Approved P02 milestone | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-25 | 2025-04-25 | 2026-02-25 | 2026-02-25 | 218
P02-A5b | P02 | Bid Evaluation, Selection & Award Recommendation | 1.02.3.1 | 2025-05-05 | 2025-05-16 |  |  |  |  | 10 | P02-A5 |  | FALSE | TRUE | P02-CA03 | P02-WP031 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-05 | 2025-05-16 | 2025-05-05 | 2025-05-16 | 0
P02-M2 | P02 | Contract Award / NTP | 1.02.3.2 | 2025-05-30 | 2025-05-30 |  |  |  |  | 0 | P02-A5b, P02-A4b |  | TRUE | TRUE | P02-CA03 | P02-WP032 | Milestone | Approved P02 milestone | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 0
P02-A11c | P02 | FAT — Switchgear/VFDs | 1.02.4.2 | 2025-10-20 | 2025-10-31 |  |  |  |  | 10 | P02-A11b |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-20 | 2025-10-31 | 2025-11-10 | 2025-11-21 | 15
P02-A11d | P02 | Delivery & Receiving — Switchgear/VFDs | 1.02.4.2 | 2025-11-03 | 2025-11-12 |  |  |  |  | 8 | P02-A11c |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-03 | 2025-11-12 | 2025-11-24 | 2025-12-03 | 15
P02-A7c | P02 | FAT — Pumps & Motors | 1.02.4.1 | 2025-11-03 | 2025-11-14 |  |  |  |  | 10 | P02-A7b |  | FALSE | TRUE | P02-CA04 | P02-WP041 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-03 | 2025-11-14 | 2025-11-03 | 2025-11-14 | 0
P02-A12 | P02 | Install Switchgear / VFDs | 1.02.4.2 | 2025-11-13 | 2025-12-10 |  |  |  |  | 20 | P02-A9, P02-A11d, P02-A6c |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-13 | 2025-12-10 | 2025-12-04 | 2025-12-31 | 15
P02-A7d | P02 | Delivery & Receiving — Pumps & Motors | 1.02.4.1 | 2025-11-17 | 2025-11-26 |  |  |  |  | 8 | P02-A7c |  | FALSE | TRUE | P02-CA04 | P02-WP041 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-17 | 2025-11-26 | 2025-11-17 | 2025-11-26 | 0
P02-A10 | P02 | Install New Pumps & Motors | 1.02.4.1 | 2025-11-27 | 2025-12-31 |  |  |  |  | 25 | P02-A9, P02-A7d |  | FALSE | TRUE | P02-CA04 | P02-WP041 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-27 | 2025-12-31 | 2025-11-27 | 2025-12-31 | 0
P02-A14 | P02 | Startup & Functional Testing | 1.02.5.1 | 2026-01-01 | 2026-01-14 |  |  |  |  | 10 | P02-A10, P02-A12, P02-A13 |  | FALSE | TRUE | P02-CA05 | P02-WP051 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-01 | 2026-01-14 | 2026-01-01 | 2026-01-14 | 0
P02-A15 | P02 | Bypass Deactivation / Cutover | 1.02.5.1 | 2026-01-15 | 2026-01-21 |  |  |  |  | 5 | P02-A14 |  | FALSE | TRUE | P02-CA05 | P02-WP051 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-15 | 2026-01-21 | 2026-01-15 | 2026-01-21 | 0
P02-A15b | P02 | Final Inspection & Punch List | 1.02.4.1 | 2026-01-22 | 2026-02-04 |  |  |  |  | 10 | P02-A15 |  | FALSE | FALSE | P02-CA04 | P02-WP041 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-22 | 2026-02-04 | 2026-02-12 | 2026-02-25 | 15
P02-A16 | P02 | Documentation & Turnover | 1.02.6.1 | 2026-01-22 | 2026-02-04 |  |  |  |  | 10 | P02-A15 |  | FALSE | TRUE | P02-CA06 | P02-WP061 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-22 | 2026-02-04 | 2026-01-22 | 2026-02-04 | 0
P02-A17 | P02 | Financial Closeout | 1.02.6.2 | 2026-02-05 | 2026-02-25 |  |  |  |  | 15 | P02-A16, P02-A15b |  | FALSE | TRUE | P02-CA06 | P02-WP062 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-05 | 2026-02-25 | 2026-02-05 | 2026-02-25 | 0
P02-M4 | P02 | Substantial Completion | 1.02.5.1 | 2026-02-04 | 2026-02-04 |  |  |  |  | 0 | P02-A15b |  | TRUE | FALSE | P02-CA05 | P02-WP051 | Milestone | Approved P02 milestone; renamed in recovered export to avoid collision with existing final milestone ID | ID normalized to documented original P02 M4 Substantial Completion; provisional milestone date remains unverified ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-04 | 2026-02-04 | 2026-02-25 | 2026-02-25 | 15
P02-M5 | P02 | Final Completion | 1.02.4.1 | 2026-02-25 | 2026-02-25 |  |  |  |  | 0 | P02-A17 |  | TRUE | TRUE | P02-CA04 | P02-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit validated finish date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 0
P03-A1 | P03 | Conduct Needs Assessment | 1.03.1.1 | 2025-01-02 | 2025-01-22 |  |  |  |  | 15 |  |  | FALSE | TRUE | P03-CA01 | P03-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-01-02 | 2025-01-22 | 2025-01-02 | 2025-01-22 | 0
P03-A2 | P03 | Finalize Project Definition & Scope | 1.03.1.2 | 2025-01-23 | 2025-02-05 |  |  |  |  | 10 | P03-A1 |  | FALSE | TRUE | P03-CA01 | P03-WP012 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-01-23 | 2025-02-05 | 2025-01-23 | 2025-02-05 | 0
P03-A2b | P03 | Regulatory Pre-Design Coordination | 1.03.2.2 | 2025-02-06 | 2025-02-19 |  |  |  |  | 10 | P03-A2 |  | FALSE | TRUE | P03-CA02 | P03-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-06 | 2025-02-19 | 2025-02-06 | 2025-02-19 | 0
P03-A3 | P03 | Preliminary Design (30%) | 1.03.2.1 | 2025-02-20 | 2025-04-16 |  |  |  |  | 40 | P03-A2b |  | FALSE | TRUE | P03-CA02 | P03-WP021 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-20 | 2025-04-16 | 2025-02-20 | 2025-04-16 | 0
P03-A4 | P03 | Design Review Gate 1 (30% review & comment resolution) | 1.03.2.1 | 2025-04-17 | 2025-05-07 |  |  |  |  | 15 | P03-A3 |  | FALSE | TRUE | P03-CA02 | P03-WP021 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-17 | 2025-05-07 | 2025-04-17 | 2025-05-07 | 0
P03-A5 | P03 | 60%/90% Design Development | 1.03.2.2 | 2025-05-08 | 2025-06-18 |  |  |  |  | 30 | P03-A4 |  | FALSE | TRUE | P03-CA02 | P03-WP022 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-08 | 2025-06-18 | 2025-05-08 | 2025-06-18 | 0
P03-A6 | P03 | Design Review Gate 2 (90% review & comment resolution) | 1.03.2.2 | 2025-06-19 | 2025-07-09 |  |  |  |  | 15 | P03-A5 |  | FALSE | TRUE | P03-CA02 | P03-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-19 | 2025-07-09 | 2025-06-19 | 2025-07-09 | 0
P03-A7 | P03 | Final Design (100%) | 1.03.2.2 | 2025-06-26 | 2025-07-23 |  |  |  |  | 20 | P03-A6 |  | FALSE | TRUE | P03-CA02 | P03-WP022 | Task | Synthetic, industry-informed | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-26 | 2025-07-23 | 2025-06-26 | 2025-07-23 | 0
P03-I-P03-01 | P03 | Controls / I/O Design Freeze | 1.03.4.2 | 2025-07-23 | 2025-07-23 |  |  |  |  | 0 | P03-M1 |  | TRUE | FALSE | P03-CA04 | P03-WP042 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-23 | 2025-07-23 | 2027-01-27 | 2027-01-27 | 395
P03-M1 | P03 | Design Complete | 1.03.4.1 | 2025-07-23 | 2025-07-23 |  |  |  |  | 0 | P03-A7 |  | TRUE | FALSE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-23 | 2025-07-23 | 2027-01-27 | 2027-01-27 | 395
P03-A8 | P03 | Prepare & Advertise Bid Package | 1.03.3.1 | 2025-07-10 | 2025-08-06 |  |  |  |  | 20 | P03-A7 |  | FALSE | TRUE | P03-CA03 | P03-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-10 | 2025-08-06 | 2025-07-10 | 2025-08-06 | 0
P03-A7b | P03 | Regulatory Plan Review & Approval | 1.03.2.2 | 2025-07-24 | 2025-09-03 |  |  |  |  | 30 | P03-A7 |  | FALSE | FALSE | P03-CA02 | P03-WP022 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-24 | 2025-09-03 | 2025-08-07 | 2025-09-17 | 10
P03-A9 | P03 | Bid Evaluation, Selection & Award Recommendation | 1.03.3.1 | 2025-08-07 | 2025-08-27 |  |  |  |  | 15 | P03-A8 |  | FALSE | TRUE | P03-CA03 | P03-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-07 | 2025-08-27 | 2025-08-07 | 2025-08-27 | 0
P03-A9b | P03 | Governing Body Award Approval | 1.03.3.2 | 2025-08-28 | 2025-09-17 |  |  |  |  | 15 | P03-A9 |  | FALSE | TRUE | P03-CA03 | P03-WP032 | Task | Approved P03 v2 explicit replacement for +15bd lag | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-28 | 2025-09-17 | 2025-08-28 | 2025-09-17 | 0
P03-M2 | P03 | Contract Award / NTP | 1.03.4.1 | 2025-09-17 | 2025-09-17 |  |  |  |  | 0 | P03-A9b, P03-A7b |  | TRUE | TRUE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 0
P03-A10 | P03 | Contractor Mobilization | 1.03.3.2 | 2025-09-18 | 2025-10-15 |  |  |  |  | 20 | P03-M2 |  | FALSE | FALSE | P03-CA03 | P03-WP032 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-18 | 2025-10-15 | 2026-12-31 | 2027-01-27 | 335
P03-A11 | P03 | Process Equipment Submittal & Shop Drawing Review | 1.03.4.1 | 2025-09-18 | 2025-10-15 |  |  |  |  | 20 | P03-M2 |  | FALSE | TRUE | P03-CA04 | P03-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-18 | 2025-10-15 | 2025-09-18 | 2025-10-15 | 0
P03-A16 | P03 | Electrical/I&C Submittal & Shop Drawing Review | 1.03.4.2 | 2025-09-18 | 2025-10-15 |  |  |  |  | 20 | P03-M2 |  | FALSE | FALSE | P03-CA04 | P03-WP042 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-18 | 2025-10-15 | 2025-11-24 | 2025-12-19 | 47
P03-A21 | P03 | Chemical Feed Equipment Submittal & Review | 1.03.4.3 | 2025-09-18 | 2025-10-08 |  |  |  |  | 15 | P03-M2 |  | FALSE | FALSE | P03-CA04 | P03-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-18 | 2025-10-08 | 2026-03-23 | 2026-04-10 | 132
P03-A22 | P03 | Chemical Feed Equipment Fabrication | 1.03.4.3 | 2025-10-09 | 2025-12-17 |  |  |  |  | 50 | P03-A21 |  | FALSE | FALSE | P03-CA04 | P03-WP043 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-09 | 2025-12-17 | 2026-04-13 | 2026-06-19 | 132
P03-I-P03-02 | P03 | Approved Point List Available | 1.03.4.1 | 2025-10-15 | 2025-10-15 |  |  |  |  | 0 | P03-A16 |  | TRUE | FALSE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-15 | 2025-10-15 | 2026-11-17 | 2026-11-17 | 284
P03-A12 | P03 | Process Equipment Fabrication | 1.03.4.1 | 2025-10-16 | 2026-03-04 |  |  |  |  | 100 | P03-A11 |  | FALSE | TRUE | P03-CA04 | P03-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-16 | 2026-03-04 | 2025-10-16 | 2026-03-04 | 0
P03-A17 | P03 | Electrical Switchgear & Instrumentation Fabrication | 1.03.4.2 | 2025-10-16 | 2026-02-04 |  |  |  |  | 80 | P03-A16 |  | FALSE | FALSE | P03-CA04 | P03-WP042 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-16 | 2026-02-04 | 2025-12-22 | 2026-04-10 | 47
P03-A23 | P03 | Delivery & Receiving Inspection — Chemical Feed | 1.03.4.3 | 2025-12-18 | 2025-12-29 |  |  |  |  | 8 | P03-A22 |  | FALSE | FALSE | P03-CA04 | P03-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-18 | 2025-12-29 | 2026-06-22 | 2026-07-01 | 132
P03-A18 | P03 | FAT — Electrical/I&C | 1.03.4.2 | 2026-02-05 | 2026-02-18 |  |  |  |  | 10 | P03-A17 |  | FALSE | FALSE | P03-CA04 | P03-WP042 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-05 | 2026-02-18 | 2026-04-13 | 2026-04-24 | 47
P03-A19 | P03 | Delivery & Receiving Inspection — Electrical/I&C | 1.03.4.2 | 2026-02-19 | 2026-03-02 |  |  |  |  | 8 | P03-A18 |  | FALSE | FALSE | P03-CA04 | P03-WP042 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-19 | 2026-03-02 | 2026-04-27 | 2026-05-06 | 47
P03-A13 | P03 | FAT — Process Equipment | 1.03.4.1 | 2026-03-05 | 2026-03-25 |  |  |  |  | 15 | P03-A12 |  | FALSE | TRUE | P03-CA04 | P03-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-03-05 | 2026-03-25 | 2026-03-05 | 2026-03-25 | 0
P03-A14 | P03 | Delivery & Receiving Inspection — Process Equipment | 1.03.4.1 | 2026-03-26 | 2026-04-08 |  |  |  |  | 10 | P03-A13 |  | FALSE | TRUE | P03-CA04 | P03-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-03-26 | 2026-04-08 | 2026-03-26 | 2026-04-08 | 0
P03-M5 | P03 | Major Process Equipment Delivered | 1.03.4.1 | 2026-04-08 | 2026-04-08 |  |  |  |  | 0 | P03-A14 |  | TRUE | FALSE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-08 | 2026-04-08 | 2027-01-27 | 2027-01-27 | 210
P03-A15 | P03 | Process Mechanical Installation | 1.03.4.1 | 2026-04-09 | 2026-07-01 |  |  |  |  | 60 | P03-A14 |  | FALSE | TRUE | P03-CA04 | P03-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-09 | 2026-07-01 | 2026-04-09 | 2026-07-01 | 0
P03-A20 | P03 | Electrical & Instrumentation Installation | 1.03.4.2 | 2026-05-07 | 2026-07-08 |  |  |  |  | 45 | P03-A15, P03-A19 |  | FALSE | TRUE | P03-CA04 | P03-WP042 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-07 | 2026-07-08 | 2026-05-07 | 2026-07-08 | 0
P03-A24 | P03 | Chemical Feed System Installation | 1.03.4.3 | 2026-05-21 | 2026-06-24 |  |  |  |  | 25 | P03-A15, P03-A23 |  | FALSE | FALSE | P03-CA04 | P03-WP043 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-21 | 2026-06-24 | 2026-07-02 | 2026-08-05 | 30
P03-A25 | P03 | Electrical & Controls Integration | 1.03.4.2 | 2026-07-09 | 2026-08-05 |  |  |  |  | 20 | P03-A15, P03-A20 |  | FALSE | TRUE | P03-CA04 | P03-WP042 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-09 | 2026-08-05 | 2026-07-09 | 2026-08-05 | 0
P03-A26 | P03 | Pre-Startup Inspection & Punch List | 1.03.5.1 | 2026-08-06 | 2026-08-26 |  |  |  |  | 15 | P03-A15, P03-A25, P03-A24 |  | FALSE | TRUE | P03-CA05 | P03-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-06 | 2026-08-26 | 2026-08-06 | 2026-08-26 | 0
P03-I-P03-03 | P03 | Controls Installation Ready for Integration | 1.03.4.2 | 2026-08-26 | 2026-08-26 |  |  |  |  | 0 | P03-M6 |  | TRUE | FALSE | P03-CA04 | P03-WP042 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-08-26 | 2027-01-27 | 2027-01-27 | 110
P03-M6 | P03 | Installation Complete / Ready for Startup | 1.03.5.1 | 2026-08-26 | 2026-08-26 |  |  |  |  | 0 | P03-A26 |  | TRUE | FALSE | P03-CA05 | P03-WP051 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-08-26 | 2027-01-27 | 2027-01-27 | 110
P03-A27 | P03 | Process Startup & Functional Testing | 1.03.5.1 | 2026-08-27 | 2026-10-07 |  |  |  |  | 30 | P03-A26 |  | FALSE | TRUE | P03-CA05 | P03-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-27 | 2026-10-07 | 2026-08-27 | 2026-10-07 | 0
P03-A29 | P03 | SCADA Integration Checkout | 1.03.4.1 | 2026-09-10 | 2026-09-30 |  |  |  |  | 15 | P03-A27 |  | FALSE | FALSE | P03-CA04 | P03-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-09-10 | 2026-09-30 | 2026-10-15 | 2026-11-04 | 25
P03-M7 | P03 | Process Startup Complete | 1.03.5.1 | 2026-10-07 | 2026-10-07 |  |  |  |  | 0 | P03-A27 |  | TRUE | FALSE | P03-CA05 | P03-WP051 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-07 | 2026-10-07 | 2027-01-27 | 2027-01-27 | 80
P03-A28 | P03 | Performance / Acceptance Testing | 1.03.5.1 | 2026-10-08 | 2026-11-04 |  |  |  |  | 20 | P03-A27 |  | FALSE | TRUE | P03-CA05 | P03-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-08 | 2026-11-04 | 2026-10-08 | 2026-11-04 | 0
P03-M8 | P03 | Performance Testing Complete | 1.03.5.1 | 2026-11-04 | 2026-11-04 |  |  |  |  | 0 | P03-A28 |  | TRUE | FALSE | P03-CA05 | P03-WP051 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-04 | 2026-11-04 | 2027-01-27 | 2027-01-27 | 60
P03-A30 | P03 | Regulatory Acceptance / Final Inspection | 1.03.2.2 | 2026-11-05 | 2026-12-02 |  |  |  |  | 20 | P03-A28, P03-A29 |  | FALSE | TRUE | P03-CA02 | P03-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-05 | 2026-12-02 | 2026-11-05 | 2026-12-02 | 0
P03-M3 | P03 | Substantial Completion | 1.03.4.1 | 2026-12-02 | 2026-12-02 |  |  |  |  | 0 | P03-A30 |  | TRUE | FALSE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-02 | 2026-12-02 | 2027-01-27 | 2027-01-27 | 40
P03-M9 | P03 | Regulatory Acceptance | 1.03.2.2 | 2026-12-02 | 2026-12-02 |  |  |  |  | 0 | P03-A30 |  | TRUE | FALSE | P03-CA02 | P03-WP022 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-02 | 2026-12-02 | 2027-01-27 | 2027-01-27 | 40
P03-A31 | P03 | Final Inspection & Punch List (closeout) | 1.03.6.1 | 2026-12-03 | 2026-12-23 |  |  |  |  | 15 | P03-A30 |  | FALSE | FALSE | P03-CA06 | P03-WP061 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-03 | 2026-12-23 | 2027-01-07 | 2027-01-27 | 25
P03-A32 | P03 | Documentation & Turnover | 1.03.6.1 | 2026-12-03 | 2026-12-30 |  |  |  |  | 20 | P03-A30 |  | FALSE | TRUE | P03-CA06 | P03-WP061 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-03 | 2026-12-30 | 2026-12-03 | 2026-12-30 | 0
P03-A33 | P03 | Financial Closeout | 1.03.6.2 | 2026-12-31 | 2027-01-27 |  |  |  |  | 20 | P03-A32, P03-A31 |  | FALSE | TRUE | P03-CA06 | P03-WP062 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-31 | 2027-01-27 | 2026-12-31 | 2027-01-27 | 0
P03-M4 | P03 | Final Completion | 1.03.4.1 | 2027-01-27 | 2027-01-27 |  |  |  |  | 0 | P03-A33 |  | TRUE | TRUE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-01-27 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 0
P04-A1 | P04 | Conduct Needs Assessment | 1.04.1.1 | 2025-06-02 | 2025-06-13 |  |  |  |  | 10 |  |  | FALSE | TRUE | P04-CA01 | P04-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-02 | 2025-06-13 | 2025-06-02 | 2025-06-13 | 0
P04-A2 | P04 | Finalize Project Definition & Scope | 1.04.1.2 | 2025-06-16 | 2025-06-20 |  |  |  |  | 5 | P04-A1 |  | FALSE | TRUE | P04-CA01 | P04-WP012 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-16 | 2025-06-20 | 2025-06-16 | 2025-06-20 | 0
P04-A3 | P04 | Preliminary Design (30%) | 1.04.2.1 | 2025-06-23 | 2025-07-18 |  |  |  |  | 20 | P04-A2 |  | FALSE | TRUE | P04-CA02 | P04-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-23 | 2025-07-18 | 2025-06-23 | 2025-07-18 | 0
P04-A4 | P04 | Final Design (100%) | 1.04.2.2 | 2025-08-04 | 2025-09-05 |  |  |  |  | 25 | P04-A3 |  | FALSE | TRUE | P04-CA02 | P04-WP022 | Task | Synthetic, industry-informed; +10bd review lag in logic | Source-derived / reconstructed network | 2025-08-04 | 2025-09-05 | 2025-08-04 | 2025-09-05 | 0
P04-A5 | P04 | Prepare & Advertise Bid Package | 1.04.3.1 | 2025-08-18 | 2025-09-05 |  |  |  |  | 15 | P04-A4 |  | FALSE | TRUE | P04-CA03 | P04-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-08-18 | 2025-09-05 | 2025-08-18 | 2025-09-05 | 0
P04-M1 | P04 | Design Complete | 1.04.4.1 | 2025-09-05 | 2025-09-05 |  |  |  |  | 0 | P04-A4 |  | TRUE | FALSE | P04-CA04 | P04-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-09-05 | 2025-09-05 | 2026-04-24 | 2026-04-24 | 165
P04-A4b | P04 | Regulatory Plan Review & Approval | 1.04.2.2 | 2025-09-08 | 2025-09-26 |  |  |  |  | 15 | P04-A4 |  | FALSE | FALSE | P04-CA02 | P04-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2025-09-08 | 2025-09-26 | 2025-10-06 | 2025-10-24 | 20
P04-A5b | P04 | Bid Evaluation, Selection & Award Recommendation | 1.04.3.1 | 2025-09-08 | 2025-09-19 |  |  |  |  | 10 | P04-A5 |  | FALSE | TRUE | P04-CA03 | P04-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-09-08 | 2025-09-19 | 2025-09-08 | 2025-09-19 | 0
P04-A5c | P04 | Governing Body Award Approval | 1.04.3.2 | 2025-09-22 | 2025-10-03 |  |  |  |  | 10 | P04-A5b |  | FALSE | TRUE | P04-CA03 | P04-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | 0
P04-M2 | P04 | Contract Award / NTP | 1.04.4.1 | 2025-10-24 | 2025-10-24 |  |  |  |  | 0 | P04-A5c, P04-A4b |  | TRUE | TRUE | P04-CA04 | P04-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 0
P04-A6 | P04 | Contractor Mobilization | 1.04.3.2 | 2025-10-27 | 2025-11-07 |  |  |  |  | 10 | P04-M2 |  | FALSE | FALSE | P04-CA03 | P04-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-27 | 2025-11-07 | 2025-11-03 | 2025-11-14 | 5
P04-A7 | P04 | Tank Shutdown & Dewatering Planning | 1.04.4.1 | 2025-10-27 | 2025-11-14 |  |  |  |  | 15 | P04-M2 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-27 | 2025-11-14 | 2025-10-27 | 2025-11-14 | 0
P04-A8 | P04 | Take Tank Offline & Dewater | 1.04.4.1 | 2025-11-17 | 2025-11-21 |  |  |  |  | 5 | P04-A6, P04-A7 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2025-11-17 | 2025-11-21 | 2025-11-17 | 2025-11-21 | 0
P04-A9 | P04 | Interior/Exterior Surface Preparation (abrasive blasting) | 1.04.4.1 | 2025-11-24 | 2025-12-12 |  |  |  |  | 15 | P04-A8 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2025-11-24 | 2025-12-12 | 2025-11-24 | 2025-12-12 | 0
P04-A10 | P04 | Structural Steel Repairs | 1.04.4.2 | 2025-12-15 | 2025-12-26 |  |  |  |  | 10 | P04-A9 |  | FALSE | TRUE | P04-CA04 | P04-WP042 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-15 | 2025-12-26 | 2025-12-15 | 2025-12-26 | 0
P04-A11 | P04 | Cathodic Protection System Installation | 1.04.4.3 | 2025-12-29 | 2026-01-16 |  |  |  |  | 15 | P04-A10 |  | FALSE | TRUE | P04-CA04 | P04-WP043 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-29 | 2026-01-16 | 2025-12-29 | 2026-01-16 | 0
P04-A12 | P04 | Interior/Exterior Coating Application | 1.04.4.1 | 2026-01-19 | 2026-02-13 |  |  |  |  | 20 | P04-A11 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network | 2026-01-19 | 2026-02-13 | 2026-01-19 | 2026-02-13 | 0
P04-A13 | P04 | Coating Cure Time | 1.04.4.1 | 2026-02-16 | 2026-02-27 |  |  |  |  | 10 | P04-A12 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-02-16 | 2026-02-27 | 2026-02-16 | 2026-02-27 | 0
P04-A14 | P04 | Refill & Disinfection | 1.04.4.1 | 2026-03-02 | 2026-03-06 |  |  |  |  | 5 | P04-A13 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-02 | 2026-03-06 | 2026-03-02 | 2026-03-06 | 0
P04-A15 | P04 | Bacteriological Sampling & Regulatory Clearance | 1.04.2.2 | 2026-03-09 | 2026-03-13 |  |  |  |  | 5 | P04-A14 |  | FALSE | TRUE | P04-CA02 | P04-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 0
P04-M5 | P04 | Major Process Equipment Delivered | 1.04.4.1 | 2026-03-13 | 2026-03-13 |  |  |  |  | 0 | P04-A15 |  | TRUE | FALSE | P04-CA04 | P04-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-03-13 | 2026-03-13 | 2026-04-24 | 2026-04-24 | 30
P04-A16 | P04 | Final Inspection & Punch List | 1.04.4.1 | 2026-03-16 | 2026-03-27 |  |  |  |  | 10 | P04-A15 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-16 | 2026-03-27 | 2026-03-16 | 2026-03-27 | 0
P04-M3 | P04 | Substantial Completion | 1.04.4.1 | 2026-03-27 | 2026-03-27 |  |  |  |  | 0 | P04-A16 |  | TRUE | FALSE | P04-CA04 | P04-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-03-27 | 2026-03-27 | 2026-04-24 | 2026-04-24 | 20
P04-A17 | P04 | Documentation & Turnover | 1.04.6.1 | 2026-03-30 | 2026-04-10 |  |  |  |  | 10 | P04-A16 |  | FALSE | TRUE | P04-CA06 | P04-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-30 | 2026-04-10 | 2026-03-30 | 2026-04-10 | 0
P04-A18 | P04 | Financial Closeout | 1.04.6.2 | 2026-04-06 | 2026-04-24 |  |  |  |  | 15 | P04-A17, P04-A16 |  | FALSE | TRUE | P04-CA06 | P04-WP062 | Task | Project-type realism | Recovered from approved P04 M3/M4 dates + SS+5 closeout overlap | 2026-04-06 | 2026-04-24 | 2026-04-06 | 2026-04-24 | 0
P04-M4 | P04 | Final Completion | 1.04.4.1 | 2026-04-24 | 2026-04-24 |  |  |  |  | 0 | P04-A18 |  | TRUE | TRUE | P04-CA04 | P04-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 0
P05-A1 | P05 | Lead Service Line Inventory Review & Prioritization | 1.05.1.1 | 2025-03-03 | 2025-03-21 |  |  |  |  | 15 |  |  | FALSE | TRUE | P05-CA01 | P05-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-03-03 | 2025-03-21 | 2025-03-03 | 2025-03-21 | 0
P05-A2 | P05 | Project Definition & Zone/Batch Plan Development | 1.05.1.2 | 2025-03-24 | 2025-04-04 |  |  |  |  | 10 | P05-A1 |  | FALSE | TRUE | P05-CA01 | P05-WP012 | Task | Project-type realism | Source-derived / reconstructed network | 2025-03-24 | 2025-04-04 | 2025-03-24 | 2025-04-04 | 0
P05-A3 | P05 | Preliminary Design — Typical Replacement Details & Specs (30%) | 1.05.2.1 | 2025-04-07 | 2025-04-25 |  |  |  |  | 15 | P05-A2 |  | FALSE | TRUE | P05-CA02 | P05-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2025-04-07 | 2025-04-25 | 2025-04-07 | 2025-04-25 | 0
P05-A4 | P05 | Final Design — Standard Specs & Bid Documents (100%) | 1.05.2.2 | 2025-05-05 | 2025-05-23 |  |  |  |  | 15 | P05-A3 |  | FALSE | TRUE | P05-CA02 | P05-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network | 2025-05-05 | 2025-05-23 | 2025-05-05 | 2025-05-23 | 0
P05-A5 | P05 | Bid Advertisement | 1.05.3.1 | 2025-05-19 | 2025-06-06 |  |  |  |  | 15 | P05-A4 |  | FALSE | TRUE | P05-CA03 | P05-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-05-19 | 2025-06-06 | 2025-05-19 | 2025-06-06 | 0
P05-M1 | P05 | Design Complete | 1.05.4.1 | 2025-05-23 | 2025-05-23 |  |  |  |  | 0 | P05-A4 |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-05-23 | 2025-05-23 | 2026-05-15 | 2026-05-15 | 255
P05-A4b | P05 | Regulatory Plan Review & Approval | 1.05.2.2 | 2025-05-26 | 2025-06-13 |  |  |  |  | 15 | P05-A4 |  | FALSE | FALSE | P05-CA02 | P05-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2025-05-26 | 2025-06-13 | 2025-06-23 | 2025-07-11 | 20
P05-A5b | P05 | Evaluation & Award Recommendation | 1.05.3.1 | 2025-06-09 | 2025-06-20 |  |  |  |  | 10 | P05-A5 |  | FALSE | TRUE | P05-CA03 | P05-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-09 | 2025-06-20 | 2025-06-09 | 2025-06-20 | 0
P05-A5c | P05 | Governing Body Approval | 1.05.3.2 | 2025-06-23 | 2025-07-04 |  |  |  |  | 10 | P05-A5b |  | FALSE | TRUE | P05-CA03 | P05-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-23 | 2025-07-04 | 2025-06-23 | 2025-07-04 | 0
P05-M2 | P05 | Contract Award / NTP | 1.05.4.1 | 2025-07-11 | 2025-07-11 |  |  |  |  | 0 | P05-A5c, P05-A4b |  | TRUE | TRUE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | 0
P05-A10 | P05 | Street Opening / Right-of-Way Permitting (program-wide) | 1.05.2.2 | 2025-07-14 | 2025-08-01 |  |  |  |  | 15 | P05-M2 |  | FALSE | FALSE | P05-CA02 | P05-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2025-07-14 | 2025-08-01 | 2025-08-04 | 2025-08-22 | 15
P05-A11 | P05 | Material Procurement — Copper Tubing & Fittings | 1.05.3.2 | 2025-07-14 | 2025-08-22 |  |  |  |  | 30 | P05-M2 |  | FALSE | TRUE | P05-CA03 | P05-WP032 | Task | Synthetic, industry-informed | Semantic WBS mapping corrected: bulk material procurement belongs in Procurement, not Construction | 2025-07-14 | 2025-08-22 | 2025-07-14 | 2025-08-22 | 0
P05-A6 | P05 | Contractor Mobilization (multi-crew) | 1.05.3.2 | 2025-07-14 | 2025-08-01 |  |  |  |  | 15 | P05-M2 |  | FALSE | FALSE | P05-CA03 | P05-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-07-14 | 2025-08-01 | 2025-08-04 | 2025-08-22 | 15
P05-A7 | P05 | Customer/Property Outreach Campaign (program-wide) | 1.05.4.1 | 2025-07-14 | 2025-09-05 |  |  |  |  | 40 | P05-M2 |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network | 2025-07-14 | 2025-09-05 | 2025-07-14 | 2025-09-05 | 0
P05-A9 | P05 | Access/Consent Coordination & Scheduling | 1.05.4.1 | 2025-07-28 | 2025-08-22 |  |  |  |  | 20 | P05-A7 |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-07-28 | 2025-08-22 | 2025-07-28 | 2025-08-22 | 0
P05-A8 | P05 | Property Eligibility & Service Line Material Verification | 1.05.1.1 | 2025-08-04 | 2025-09-12 |  |  |  |  | 30 | P05-A7 |  | FALSE | FALSE | P05-CA01 | P05-WP011 | Task | Project-type realism | Semantic WBS mapping corrected: eligibility/material verification is pre-field inventory/assessment work | 2025-08-04 | 2025-09-12 | 2026-04-06 | 2026-05-15 | 175
P05-A12a | P05 | Zone A Field Replacement | 1.05.4.1 | 2025-08-25 | 2025-11-07 |  |  |  |  | 55 | P05-A6, P05-A9, P05-A10, P05-A11 |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Synthetic, industry-informed | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-08-25 | 2025-11-07 | 2025-08-25 | 2025-11-07 | 0
P05-AFIRST | P05 | Complete First Service Line Replacement | 1.05.4.1 | 2025-08-25 | 2025-08-26 |  |  |  |  | 2 | P05-A12a |  | FALSE | FALSE | P05-CA04 | P05-WP041 | Task | Approved P05 v2 explicit completed-scope activity | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-08-25 | 2025-08-26 | 2026-05-14 | 2026-05-15 | 188
P05-MFIRST | P05 | MFIRST | 1.05.4.1 | 2025-08-26 | 2025-08-26 |  |  |  |  | 0 | P05-AFIRST |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-08-26 | 2025-08-26 | 2026-05-15 | 2026-05-15 | 188
P05-A12b | P05 | Zone A Property Restoration | 1.05.4.2 | 2025-09-15 | 2025-11-28 |  |  |  |  | 55 | P05-A12a |  | FALSE | FALSE | P05-CA04 | P05-WP042 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-09-15 | 2025-11-28 | 2025-12-08 | 2026-02-20 | 60
P05-A13a | P05 | Zone B Field Replacement | 1.05.4.1 | 2025-09-22 | 2025-12-05 |  |  |  |  | 55 | P05-A12a |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Synthetic, industry-informed | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-09-22 | 2025-12-05 | 2025-09-22 | 2025-12-05 | 0
P05-A13b | P05 | Zone B Property Restoration | 1.05.4.2 | 2025-10-13 | 2025-12-26 |  |  |  |  | 55 | P05-A13a |  | FALSE | FALSE | P05-CA04 | P05-WP042 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-10-13 | 2025-12-26 | 2025-12-08 | 2026-02-20 | 40
P05-A14a | P05 | Zone C Field Replacement | 1.05.4.1 | 2025-10-20 | 2026-01-02 |  |  |  |  | 55 | P05-A13a |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Synthetic, industry-informed | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-10-20 | 2026-01-02 | 2025-10-20 | 2026-01-02 | 0
P05-M25 | P05 | M25 | 1.05.4.1 | 2025-11-07 | 2025-11-07 |  |  |  |  | 0 | P05-A12a |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-11-07 | 2025-11-07 | 2026-05-15 | 2026-05-15 | 135
P05-A14b | P05 | Zone C Property Restoration | 1.05.4.2 | 2025-11-10 | 2026-01-23 |  |  |  |  | 55 | P05-A14a |  | FALSE | FALSE | P05-CA04 | P05-WP042 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-11-10 | 2026-01-23 | 2025-12-08 | 2026-02-20 | 20
P05-A15a | P05 | Zone D Field Replacement | 1.05.4.1 | 2025-11-17 | 2026-01-30 |  |  |  |  | 55 | P05-A14a |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Synthetic, industry-informed | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-11-17 | 2026-01-30 | 2025-11-17 | 2026-01-30 | 0
P05-A12c | P05 | Zone A Water Quality Sampling & Customer Notification | 1.05.5.1 | 2025-12-01 | 2025-12-19 |  |  |  |  | 15 | P05-A12b |  | FALSE | FALSE | P05-CA05 | P05-WP051 | Task | Project-type realism; remapped to Testing & Commissioning | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-12-01 | 2025-12-19 | 2026-02-23 | 2026-03-13 | 60
P05-M50 | P05 | M50 | 1.05.4.1 | 2025-12-05 | 2025-12-05 |  |  |  |  | 0 | P05-A13a |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-12-05 | 2025-12-05 | 2026-05-15 | 2026-05-15 | 115
P05-A15b | P05 | Zone D Property Restoration | 1.05.4.2 | 2025-12-08 | 2026-02-20 |  |  |  |  | 55 | P05-A15a |  | FALSE | TRUE | P05-CA04 | P05-WP042 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-12-08 | 2026-02-20 | 2025-12-08 | 2026-02-20 | 0
P05-A13c | P05 | Zone B Water Quality Sampling & Customer Notification | 1.05.5.1 | 2025-12-29 | 2026-01-16 |  |  |  |  | 15 | P05-A13b |  | FALSE | FALSE | P05-CA05 | P05-WP051 | Task | Project-type realism; remapped to Testing & Commissioning | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-12-29 | 2026-01-16 | 2026-02-23 | 2026-03-13 | 40
P05-M75 | P05 | M75 | 1.05.4.1 | 2026-01-02 | 2026-01-02 |  |  |  |  | 0 | P05-A14a |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-01-02 | 2026-01-02 | 2026-05-15 | 2026-05-15 | 95
P05-A14c | P05 | Zone C Water Quality Sampling & Customer Notification | 1.05.5.1 | 2026-01-26 | 2026-02-13 |  |  |  |  | 15 | P05-A14b |  | FALSE | FALSE | P05-CA05 | P05-WP051 | Task | Project-type realism; remapped to Testing & Commissioning | Recovered by reconciliation to approved P05 milestone dates and published durations | 2026-01-26 | 2026-02-13 | 2026-02-23 | 2026-03-13 | 20
P05-MTARGET | P05 | MTARGET | 1.05.4.1 | 2026-01-30 | 2026-01-30 |  |  |  |  | 0 | P05-A15a |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-01-30 | 2026-01-30 | 2026-05-15 | 2026-05-15 | 75
P05-A15c | P05 | Zone D Water Quality Sampling & Customer Notification | 1.05.5.1 | 2026-02-23 | 2026-03-13 |  |  |  |  | 15 | P05-A15b |  | FALSE | TRUE | P05-CA05 | P05-WP051 | Task | Project-type realism; remapped to Testing & Commissioning | Recovered by reconciliation to approved P05 milestone dates and published durations | 2026-02-23 | 2026-03-13 | 2026-02-23 | 2026-03-13 | 0
P05-A16 | P05 | Final Program Inspection & Punch List | 1.05.4.1 | 2026-03-16 | 2026-04-03 |  |  |  |  | 15 | P05-A12c, P05-A13c, P05-A14c, P05-A15c |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | 0
P05-M3 | P05 | Substantial Completion | 1.05.4.1 | 2026-04-03 | 2026-04-03 |  |  |  |  | 0 | P05-A16 |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 30
P05-A17 | P05 | GIS & Service Line Inventory Records Update / Documentation & Turnover | 1.05.6.1 | 2026-04-06 | 2026-05-01 |  |  |  |  | 20 | P05-A16 |  | FALSE | TRUE | P05-CA06 | P05-WP061 | Task | Project-type realism | Semantic WBS mapping corrected: documentation/GIS turnover belongs in Closeout | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | 0
P05-A18 | P05 | Financial Closeout | 1.05.6.2 | 2026-04-20 | 2026-05-15 |  |  |  |  | 20 | P05-A17 |  | FALSE | TRUE | P05-CA06 | P05-WP062 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2026-04-20 | 2026-05-15 | 2026-04-20 | 2026-05-15 | 0
P05-M4 | P05 | Final Completion | 1.05.4.1 | 2026-05-15 | 2026-05-15 |  |  |  |  | 0 | P05-A18 |  | TRUE | TRUE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 0
P06-A1 | P06 | Needs Assessment | 1.06.1.1 | 2025-08-01 | 2025-08-21 |  |  |  |  | 15 |  |  | FALSE | TRUE | P06-CA01 | P06-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-01 | 2025-08-21 | 2025-08-01 | 2025-08-21 | 0
P06-A2 | P06 | Project Definition | 1.06.1.2 | 2025-08-22 | 2025-09-04 |  |  |  |  | 10 | P06-A1 |  | FALSE | TRUE | P06-CA01 | P06-WP012 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-22 | 2025-09-04 | 2025-08-22 | 2025-09-04 | 0
P06-A3 | P06 | Preliminary Design | 1.06.2.1 | 2025-09-05 | 2025-10-02 |  |  |  |  | 20 | P06-A2 |  | FALSE | TRUE | P06-CA02 | P06-WP021 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-05 | 2025-10-02 | 2025-09-05 | 2025-10-02 | 0
P06-A4 | P06 | Final Design | 1.06.2.2 | 2025-10-10 | 2025-11-06 |  |  |  |  | 20 | P06-A3 |  | FALSE | TRUE | P06-CA02 | P06-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-10 | 2025-11-06 | 2025-10-10 | 2025-11-06 | 0
P06-A5 | P06 | Bid Advertisement | 1.06.3.1 | 2025-10-24 | 2025-11-13 |  |  |  |  | 15 | P06-A4 |  | FALSE | TRUE | P06-CA03 | P06-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-24 | 2025-11-13 | 2025-10-24 | 2025-11-13 | 0
P06-M1 | P06 | Design Complete | 1.06.4.1 | 2025-11-06 | 2025-11-06 |  |  |  |  | 0 | P06-A4 |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-06 | 2025-11-06 | 2026-12-24 | 2026-12-24 | 295
P06-A4b | P06 | Regulatory Plan Review & Approval | 1.06.2.2 | 2025-11-07 | 2025-11-20 |  |  |  |  | 10 | P06-A4 |  | FALSE | FALSE | P06-CA02 | P06-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-07 | 2025-11-20 | 2025-11-28 | 2025-12-11 | 15
P06-A5b | P06 | Evaluation & Award | 1.06.3.1 | 2025-11-14 | 2025-11-27 |  |  |  |  | 10 | P06-A5 |  | FALSE | TRUE | P06-CA03 | P06-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-14 | 2025-11-27 | 2025-11-14 | 2025-11-27 | 0
P06-A5c | P06 | Governing Body Approval | 1.06.3.2 | 2025-11-28 | 2025-12-11 |  |  |  |  | 10 | P06-A5b |  | FALSE | TRUE | P06-CA03 | P06-WP032 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-28 | 2025-12-11 | 2025-11-28 | 2025-12-11 | 0
P06-M2 | P06 | Contract Award / NTP | 1.06.4.1 | 2025-12-11 | 2025-12-11 |  |  |  |  | 0 | P06-A5c, P06-A4b |  | TRUE | TRUE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 0
P06-A10 | P06 | Meter/Endpoint Inventory & Route Planning | 1.06.1.1 | 2025-12-12 | 2026-01-08 |  |  |  |  | 20 | P06-M2 |  | FALSE | FALSE | P06-CA01 | P06-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2026-01-08 | 2026-11-27 | 2026-12-24 | 250
P06-A11 | P06 | Meter/Endpoint Submittal Review | 1.06.3.1 | 2025-12-12 | 2026-01-01 |  |  |  |  | 15 | P06-M2 |  | FALSE | TRUE | P06-CA03 | P06-WP031 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2026-01-01 | 2025-12-12 | 2026-01-01 | 0
P06-A15 | P06 | Pilot Deployment Planning & Customer Selection | 1.06.4.1 | 2025-12-12 | 2025-12-25 |  |  |  |  | 10 | P06-M2 |  | FALSE | FALSE | P06-CA04 | P06-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2025-12-25 | 2026-04-03 | 2026-04-16 | 80
P06-A6 | P06 | Contractor Mobilization | 1.06.3.2 | 2025-12-12 | 2025-12-25 |  |  |  |  | 10 | P06-M2 |  | FALSE | FALSE | P06-CA03 | P06-WP032 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2025-12-25 | 2026-04-03 | 2026-04-16 | 80
P06-A7 | P06 | Communications/Network Design | 1.06.2.2 | 2025-12-12 | 2026-01-08 |  |  |  |  | 20 | P06-M2 |  | FALSE | FALSE | P06-CA02 | P06-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2026-01-08 | 2026-01-09 | 2026-02-05 | 20
P06-A8 | P06 | Cybersecurity & IT Coordination | 1.06.2.2 | 2025-12-12 | 2026-01-01 |  |  |  |  | 15 | P06-M2 |  | FALSE | FALSE | P06-CA02 | P06-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2026-01-01 | 2026-02-27 | 2026-03-19 | 55
P06-A12 | P06 | Meter/Endpoint Fabrication | 1.06.3.2 | 2026-01-02 | 2026-03-26 |  |  |  |  | 60 | P06-A11 |  | FALSE | TRUE | P06-CA03 | P06-WP032 | Task | Synthetic, industry-informed | Semantic WBS mapping corrected: meter/endpoint fabrication is procurement ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-02 | 2026-03-26 | 2026-01-02 | 2026-03-26 | 0
P06-A9 | P06 | Head-End / Meter Data Management System Configuration | 1.06.4.2 | 2026-01-09 | 2026-02-19 |  |  |  |  | 30 | P06-A7 |  | FALSE | FALSE | P06-CA04 | P06-WP042 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-09 | 2026-02-19 | 2026-02-06 | 2026-03-19 | 20
P06-A14 | P06 | System Integration — head-end / MDM / billing | 1.06.4.2 | 2026-02-20 | 2026-03-19 |  |  |  |  | 20 | P06-A9, P06-A8 |  | FALSE | FALSE | P06-CA04 | P06-WP042 | Task | Project-type realism | Semantic WBS mapping corrected: head-end/MDM/billing integration maps to Head-End System Integration ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-20 | 2026-03-19 | 2026-03-20 | 2026-04-16 | 20
P06-A13 | P06 | Meter/Endpoint Delivery | 1.06.3.2 | 2026-03-27 | 2026-04-09 |  |  |  |  | 10 | P06-A12 |  | FALSE | TRUE | P06-CA03 | P06-WP032 | Task | Synthetic, industry-informed | Semantic WBS mapping corrected: meter/endpoint delivery is procurement ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-03-27 | 2026-04-09 | 2026-03-27 | 2026-04-09 | 0
P06-APILOTSTAGE | P06 | Pilot Equipment Staging & Configuration | 1.06.4.1 | 2026-04-10 | 2026-04-16 |  |  |  |  | 5 | P06-A13 |  | FALSE | TRUE | P06-CA04 | P06-WP041 | Task | Approved P06 v2 added prerequisite | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-10 | 2026-04-16 | 2026-04-10 | 2026-04-16 | 0
P06-A16 | P06 | Pilot Deployment | 1.06.4.1 | 2026-04-17 | 2026-05-07 |  |  |  |  | 15 | P06-A14, P06-A15, P06-APILOTSTAGE, P06-A8, P06-A6, P06-MPILOTREADY |  | FALSE | TRUE | P06-CA04 | P06-WP041 | Task | Synthetic, industry-informed | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-17 | 2026-05-07 | 2026-04-17 | 2026-05-07 | 0
P06-AFIRSTPILOT | P06 | Install First Pilot Endpoints | 1.06.4.1 | 2026-04-17 | 2026-04-20 |  |  |  |  | 2 | P06-A16 |  | FALSE | FALSE | P06-CA04 | P06-WP041 | Task | Approved P06 v2 explicit completed-scope activity | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-17 | 2026-04-20 | 2026-12-23 | 2026-12-24 | 178
P06-MFIRSTPILOT | P06 | First Pilot Endpoints Live | 1.06.5.1 | 2026-04-20 | 2026-04-20 |  |  |  |  | 0 | P06-AFIRSTPILOT |  | TRUE | FALSE | P06-CA05 | P06-WP051 | Milestone | Approved P06 v2 completed-scope milestone | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-20 | 2026-04-20 | 2026-12-24 | 2026-12-24 | 178
P06-MSYSINT | P06 | MSYSINT | 1.06.4.2 | 2026-03-19 | 2026-03-19 |  |  |  |  | 0 | P06-A14 |  | TRUE | FALSE | P06-CA04 | P06-WP042 | Milestone | Approved milestone / interface milestone | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-03-19 | 2026-03-19 | 2026-04-16 | 2026-04-16 | 20
P06-A17 | P06 | Pilot Validation | 1.06.5.1 | 2026-05-08 | 2026-05-28 |  |  |  |  | 15 | P06-A16 |  | FALSE | TRUE | P06-CA05 | P06-WP051 | Task | Project-type realism | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-08 | 2026-05-28 | 2026-05-08 | 2026-05-28 | 0
P06-A18a | P06 | Field Deployment Wave 1 | 1.06.4.1 | 2026-05-29 | 2026-07-16 |  |  |  |  | 35 | P06-A17 |  | FALSE | FALSE | P06-CA04 | P06-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-29 | 2026-07-16 | 2026-07-31 | 2026-09-17 | 45
P06-MPILOTREADY | P06 | Pilot Ready | 1.06.5.1 | 2026-04-16 | 2026-04-16 |  |  |  |  | 0 | P06-MSYSINT, P06-A15, P06-APILOTSTAGE, P06-A8, P06-A6 |  | TRUE | TRUE | P06-CA05 | P06-WP051 | Milestone | Approved P06 v2 corrected pre-deployment gate | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 0
P06-A19a | P06 | Field Deployment Wave 2 | 1.06.4.1 | 2026-06-19 | 2026-08-06 |  |  |  |  | 35 | P06-A17 |  | FALSE | FALSE | P06-CA04 | P06-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-06-19 | 2026-08-06 | 2026-07-31 | 2026-09-17 | 30
P06-MPILOTDONE | P06 | MPILOTDONE | 1.06.4.1 | 2026-05-28 | 2026-05-28 |  |  |  |  | 0 | P06-A17 |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-28 | 2026-05-28 | 2026-12-24 | 2026-12-24 | 150
P06-A20a | P06 | Field Deployment Wave 3 | 1.06.4.1 | 2026-07-10 | 2026-08-27 |  |  |  |  | 35 | P06-A17 |  | FALSE | FALSE | P06-CA04 | P06-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-10 | 2026-08-27 | 2026-07-31 | 2026-09-17 | 15
P06-A18b | P06 | Wave 1 Data Migration / Account Reconciliation | 1.06.4.3 | 2026-07-17 | 2026-07-30 |  |  |  |  | 10 | P06-A18a |  | FALSE | FALSE | P06-CA04 | P06-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-17 | 2026-07-30 | 2026-09-18 | 2026-10-01 | 45
P06-A21a | P06 | Field Deployment Wave 4 | 1.06.4.1 | 2026-07-31 | 2026-09-17 |  |  |  |  | 35 | P06-A17 |  | FALSE | TRUE | P06-CA04 | P06-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-31 | 2026-09-17 | 2026-07-31 | 2026-09-17 | 0
P06-A19b | P06 | Wave 2 Data Migration / Account Reconciliation | 1.06.4.3 | 2026-08-07 | 2026-08-20 |  |  |  |  | 10 | P06-A19a |  | FALSE | FALSE | P06-CA04 | P06-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-07 | 2026-08-20 | 2026-09-18 | 2026-10-01 | 30
P06-M25 | P06 | M25 | 1.06.4.1 | 2026-07-16 | 2026-07-16 |  |  |  |  | 0 | P06-A18a |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-16 | 2026-07-16 | 2026-12-24 | 2026-12-24 | 115
P06-A20b | P06 | Wave 3 Data Migration / Account Reconciliation | 1.06.4.3 | 2026-08-28 | 2026-09-10 |  |  |  |  | 10 | P06-A20a |  | FALSE | FALSE | P06-CA04 | P06-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-28 | 2026-09-10 | 2026-09-18 | 2026-10-01 | 15
P06-M50 | P06 | M50 | 1.06.4.1 | 2026-08-06 | 2026-08-06 |  |  |  |  | 0 | P06-A19a |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-06 | 2026-08-06 | 2026-12-24 | 2026-12-24 | 100
P06-A21b | P06 | Wave 4 Data Migration / Account Reconciliation | 1.06.4.3 | 2026-09-18 | 2026-10-01 |  |  |  |  | 10 | P06-A21a |  | FALSE | TRUE | P06-CA04 | P06-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-09-18 | 2026-10-01 | 2026-09-18 | 2026-10-01 | 0
P06-M75 | P06 | M75 | 1.06.4.1 | 2026-08-27 | 2026-08-27 |  |  |  |  | 0 | P06-A20a |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-27 | 2026-08-27 | 2026-12-24 | 2026-12-24 | 85
P06-A22 | P06 | Exception Handling & Remediation | 1.06.4.1 | 2026-10-02 | 2026-10-22 |  |  |  |  | 15 | P06-A18b, P06-A19b, P06-A20b, P06-A21b |  | FALSE | TRUE | P06-CA04 | P06-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-02 | 2026-10-22 | 2026-10-02 | 2026-10-22 | 0
P06-MFULL | P06 | MFULL | 1.06.4.1 | 2026-09-17 | 2026-09-17 |  |  |  |  | 0 | P06-A21a |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-09-17 | 2026-09-17 | 2026-12-24 | 2026-12-24 | 70
P06-A23 | P06 | Final Deployment Verification | 1.06.5.1 | 2026-10-23 | 2026-11-05 |  |  |  |  | 10 | P06-A22 |  | FALSE | TRUE | P06-CA05 | P06-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | 0
P06-A24 | P06 | Operational Handoff / Training | 1.06.5.1 | 2026-11-06 | 2026-11-19 |  |  |  |  | 10 | P06-A23 |  | FALSE | TRUE | P06-CA05 | P06-WP051 | Task | Project-type realism | Semantic WBS mapping corrected: operational handoff/training is acceptance/commissioning scope ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-06 | 2026-11-19 | 2026-11-06 | 2026-11-19 | 0
P06-A25 | P06 | Documentation & Turnover | 1.06.6.1 | 2026-11-20 | 2026-12-03 |  |  |  |  | 10 | P06-A24 |  | FALSE | TRUE | P06-CA06 | P06-WP061 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-20 | 2026-12-03 | 2026-11-20 | 2026-12-03 | 0
P06-M3 | P06 | Substantial Completion | 1.06.4.1 | 2026-11-19 | 2026-11-19 |  |  |  |  | 0 | P06-A24 |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-19 | 2026-11-19 | 2026-12-24 | 2026-12-24 | 25
P06-MOPACC | P06 | MOPACC | 1.06.4.1 | 2026-11-19 | 2026-11-19 |  |  |  |  | 0 | P06-A24 |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-19 | 2026-11-19 | 2026-12-24 | 2026-12-24 | 25
P06-A26 | P06 | Financial Closeout | 1.06.6.2 | 2026-12-04 | 2026-12-24 |  |  |  |  | 15 | P06-A25 |  | FALSE | TRUE | P06-CA06 | P06-WP062 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-04 | 2026-12-24 | 2026-12-04 | 2026-12-24 | 0
P06-M4 | P06 | Final Completion | 1.06.4.1 | 2026-12-24 | 2026-12-24 |  |  |  |  | 0 | P06-A26 |  | TRUE | TRUE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 0
P07-A1 | P07 | Hydraulic & Operational Assessment | 1.07.1.1 | 2025-10-01 | 2025-10-21 |  |  |  |  | 15 |  |  | FALSE | TRUE | P07-CA01 | P07-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-01 | 2025-10-21 | 2025-10-01 | 2025-10-21 | 0
P07-A2 | P07 | Project Definition & Pressure-Zone Strategy | 1.07.1.2 | 2025-10-22 | 2025-11-04 |  |  |  |  | 10 | P07-A1 |  | FALSE | TRUE | P07-CA01 | P07-WP012 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-22 | 2025-11-04 | 2025-10-22 | 2025-11-04 | 0
P07-A3 | P07 | Preliminary Design — PRV/Valve Siting & Instrumentation Plan | 1.07.2.1 | 2025-11-05 | 2025-12-02 |  |  |  |  | 20 | P07-A2 |  | FALSE | TRUE | P07-CA02 | P07-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2025-11-05 | 2025-12-02 | 2025-11-05 | 2025-12-02 | 0
P07-A4 | P07 | Final Design (100%) | 1.07.2.2 | 2025-12-10 | 2026-01-06 |  |  |  |  | 20 | P07-A3 |  | FALSE | TRUE | P07-CA02 | P07-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network | 2025-12-10 | 2026-01-06 | 2025-12-10 | 2026-01-06 | 0
P07-A5 | P07 | Bid Advertisement | 1.07.3.1 | 2025-12-24 | 2026-01-13 |  |  |  |  | 15 | P07-A4 |  | FALSE | TRUE | P07-CA03 | P07-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-24 | 2026-01-13 | 2025-12-24 | 2026-01-13 | 0
P07-M1 | P07 | Design Complete | 1.07.4.1 | 2026-01-06 | 2026-01-06 |  |  |  |  | 0 | P07-A4 |  | TRUE | FALSE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-01-06 | 2026-01-06 | 2026-09-01 | 2026-09-01 | 170
P07-A4b | P07 | Regulatory Plan Review & Approval | 1.07.2.2 | 2026-01-07 | 2026-01-27 |  |  |  |  | 15 | P07-A4 |  | FALSE | FALSE | P07-CA02 | P07-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-07 | 2026-01-27 | 2026-02-04 | 2026-02-24 | 20
P07-A5b | P07 | Evaluation & Award | 1.07.3.1 | 2026-01-14 | 2026-01-27 |  |  |  |  | 10 | P07-A5 |  | FALSE | TRUE | P07-CA03 | P07-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-14 | 2026-01-27 | 2026-01-14 | 2026-01-27 | 0
P07-A5c | P07 | Governing Body Approval | 1.07.3.2 | 2026-01-28 | 2026-02-10 |  |  |  |  | 10 | P07-A5b |  | FALSE | TRUE | P07-CA03 | P07-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-28 | 2026-02-10 | 2026-01-28 | 2026-02-10 | 0
P07-M2 | P07 | Contract Award / NTP | 1.07.4.1 | 2026-02-24 | 2026-02-24 |  |  |  |  | 0 | P07-A5c, P07-A4b |  | TRUE | TRUE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 0
P07-A6 | P07 | Contractor Mobilization | 1.07.3.2 | 2026-02-25 | 2026-03-10 |  |  |  |  | 10 | P07-M2 |  | FALSE | FALSE | P07-CA03 | P07-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2026-02-25 | 2026-03-10 | 2026-03-25 | 2026-04-07 | 20
P07-A7 | P07 | Utility Coordination & Locate Requests | 1.07.4.1 | 2026-02-25 | 2026-03-10 |  |  |  |  | 10 | P07-M2 |  | FALSE | FALSE | P07-CA04 | P07-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-02-25 | 2026-03-10 | 2026-03-25 | 2026-04-07 | 20
P07-A8 | P07 | PRV/Valve/Instrumentation Submittal Review | 1.07.3.1 | 2026-02-25 | 2026-03-17 |  |  |  |  | 15 | P07-M2 |  | FALSE | TRUE | P07-CA03 | P07-WP031 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-02-25 | 2026-03-17 | 2026-02-25 | 2026-03-17 | 0
P07-A10 | P07 | PRV Station Vault/Enclosure Construction | 1.07.4.1 | 2026-03-11 | 2026-03-31 |  |  |  |  | 15 | P07-A6, P07-A7 |  | FALSE | FALSE | P07-CA04 | P07-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-11 | 2026-03-31 | 2026-04-08 | 2026-04-28 | 20
P07-A9 | P07 | PRV/Valve/Instrumentation Procurement | 1.07.4.3 | 2026-03-18 | 2026-04-28 |  |  |  |  | 30 | P07-A8 |  | FALSE | TRUE | P07-CA04 | P07-WP043 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-03-18 | 2026-04-28 | 2026-03-18 | 2026-04-28 | 0
P07-A11 | P07 | PRV & Isolation Valve Installation | 1.07.4.2 | 2026-04-29 | 2026-05-19 |  |  |  |  | 15 | P07-A10, P07-A9 |  | FALSE | TRUE | P07-CA04 | P07-WP042 | Task | Project-type realism | Source-derived / reconstructed network | 2026-04-29 | 2026-05-19 | 2026-04-29 | 2026-05-19 | 0
P07-A12 | P07 | Instrumentation & Monitoring Installation | 1.07.4.3 | 2026-05-20 | 2026-06-02 |  |  |  |  | 10 | P07-A11 |  | FALSE | TRUE | P07-CA04 | P07-WP043 | Task | Project-type realism | Source-derived / reconstructed network | 2026-05-20 | 2026-06-02 | 2026-05-20 | 2026-06-02 | 0
P07-A13 | P07 | Electrical/Controls Integration | 1.07.4.3 | 2026-06-03 | 2026-06-16 |  |  |  |  | 10 | P07-A12 |  | FALSE | TRUE | P07-CA04 | P07-WP043 | Task | Project-type realism | Source-derived / reconstructed network | 2026-06-03 | 2026-06-16 | 2026-06-03 | 2026-06-16 | 0
P07-A14 | P07 | Pressure Testing & Commissioning | 1.07.5.1 | 2026-06-17 | 2026-06-30 |  |  |  |  | 10 | P07-A13 |  | FALSE | TRUE | P07-CA05 | P07-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2026-06-17 | 2026-06-30 | 2026-06-17 | 2026-06-30 | 0
P07-MCOMM | P07 | MCOMM | 1.07.4.1 | 2026-06-30 | 2026-06-30 |  |  |  |  | 0 | P07-A14 |  | TRUE | FALSE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-06-30 | 2026-06-30 | 2026-09-01 | 2026-09-01 | 45
P07-A15 | P07 | System Balancing & Optimization | 1.07.5.1 | 2026-07-01 | 2026-07-21 |  |  |  |  | 15 | P07-A14 |  | FALSE | TRUE | P07-CA05 | P07-WP051 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-07-01 | 2026-07-21 | 2026-07-01 | 2026-07-21 | 0
P07-MBAL | P07 | MBAL | 1.07.4.1 | 2026-07-21 | 2026-07-21 |  |  |  |  | 0 | P07-A15 |  | TRUE | FALSE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-07-21 | 2026-07-21 | 2026-09-01 | 2026-09-01 | 30
P07-A16 | P07 | Final Inspection & Punch List | 1.07.4.1 | 2026-07-22 | 2026-08-04 |  |  |  |  | 10 | P07-A15 |  | FALSE | TRUE | P07-CA04 | P07-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-07-22 | 2026-08-04 | 2026-07-22 | 2026-08-04 | 0
P07-M3 | P07 | Substantial Completion | 1.07.4.1 | 2026-08-04 | 2026-08-04 |  |  |  |  | 0 | P07-A16 |  | TRUE | FALSE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-08-04 | 2026-08-04 | 2026-09-01 | 2026-09-01 | 20
P07-A17 | P07 | Documentation & Turnover | 1.07.6.1 | 2026-08-05 | 2026-08-18 |  |  |  |  | 10 | P07-A16 |  | FALSE | TRUE | P07-CA06 | P07-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-18 | 0
P07-A18 | P07 | Financial Closeout | 1.07.6.2 | 2026-08-12 | 2026-09-01 |  |  |  |  | 15 | P07-A17, P07-A16 |  | FALSE | TRUE | P07-CA06 | P07-WP062 | Task | Project-type realism | Recovered from approved P07 M3/M4 dates + SS+5 closeout overlap | 2026-08-12 | 2026-09-01 | 2026-08-12 | 2026-09-01 | 0
P07-M4 | P07 | Final Completion | 1.07.4.1 | 2026-09-01 | 2026-09-01 |  |  |  |  | 0 | P07-A18 |  | TRUE | TRUE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-01 | 0
P08-A1 | P08 | Electrical Load / Resiliency Assessment | 1.08.1.1 | 2025-12-01 | 2025-12-19 |  |  |  |  | 15 |  |  | FALSE | TRUE | P08-CA01 | P08-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-01 | 2025-12-19 | 2025-12-01 | 2025-12-19 | 0
P08-A2 | P08 | Project Definition & Generator Sizing Basis | 1.08.1.2 | 2025-12-22 | 2026-01-02 |  |  |  |  | 10 | P08-A1 |  | FALSE | TRUE | P08-CA01 | P08-WP012 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-22 | 2026-01-02 | 2025-12-22 | 2026-01-02 | 0
P08-A3 | P08 | Preliminary Design — Switchgear/ATS & Site Layout | 1.08.2.1 | 2026-01-05 | 2026-01-30 |  |  |  |  | 20 | P08-A2 |  | FALSE | TRUE | P08-CA02 | P08-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-05 | 2026-01-30 | 2026-01-05 | 2026-01-30 | 0
P08-A7 | P08 | Electric Utility Coordination | 1.08.4.1 | 2026-01-19 | 2026-02-06 |  |  |  |  | 15 | P08-A3 |  | FALSE | FALSE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-19 | 2026-02-06 | 2026-12-21 | 2027-01-08 | 240
P08-A4 | P08 | Final Design — Switchgear/ATS & Site Layout | 1.08.2.2 | 2026-02-09 | 2026-03-06 |  |  |  |  | 20 | P08-A3 |  | FALSE | TRUE | P08-CA02 | P08-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network | 2026-02-09 | 2026-03-06 | 2026-02-09 | 2026-03-06 | 0
P08-A5 | P08 | Bid Advertisement | 1.08.3.1 | 2026-02-23 | 2026-03-13 |  |  |  |  | 15 | P08-A4 |  | FALSE | TRUE | P08-CA03 | P08-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-02-23 | 2026-03-13 | 2026-02-23 | 2026-03-13 | 0
P08-I-P08-01 | P08 | Generator/ATS Controls Design Freeze | 1.08.4.2 | 2026-03-06 | 2026-03-06 |  |  |  |  | 0 | P08-M1 |  | TRUE | FALSE | P08-CA04 | P08-WP042 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-03-06 | 2026-03-06 | 2027-01-08 | 2027-01-08 | 220
P08-M1 | P08 | Design Complete | 1.08.4.1 | 2026-03-06 | 2026-03-06 |  |  |  |  | 0 | P08-A4 |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-03-06 | 2026-03-06 | 2027-01-08 | 2027-01-08 | 220
P08-A4b | P08 | Regulatory Plan Review & Approval | 1.08.2.2 | 2026-03-09 | 2026-03-27 |  |  |  |  | 15 | P08-A4 |  | FALSE | FALSE | P08-CA02 | P08-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-09 | 2026-03-27 | 2026-04-06 | 2026-04-24 | 20
P08-A5b | P08 | Evaluation & Award | 1.08.3.1 | 2026-03-16 | 2026-03-27 |  |  |  |  | 10 | P08-A5 |  | FALSE | TRUE | P08-CA03 | P08-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-16 | 2026-03-27 | 2026-03-16 | 2026-03-27 | 0
P08-A5c | P08 | Governing Body Approval | 1.08.3.2 | 2026-03-30 | 2026-04-10 |  |  |  |  | 10 | P08-A5b |  | FALSE | TRUE | P08-CA03 | P08-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-30 | 2026-04-10 | 2026-03-30 | 2026-04-10 | 0
P08-M2 | P08 | Contract Award / NTP | 1.08.4.1 | 2026-04-24 | 2026-04-24 |  |  |  |  | 0 | P08-A5c, P08-A4b |  | TRUE | TRUE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 0
P08-A13 | P08 | Site/Civil Preparation & Concrete Pad/Enclosure Work | 1.08.4.1 | 2026-04-27 | 2026-05-15 |  |  |  |  | 15 | P08-M2 |  | FALSE | FALSE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-04-27 | 2026-05-15 | 2026-08-31 | 2026-09-18 | 90
P08-A14 | P08 | Outage/Shutdown Planning & Operations Coordination | 1.08.4.1 | 2026-04-27 | 2026-05-08 |  |  |  |  | 10 | P08-M2 |  | FALSE | FALSE | P08-CA04 | P08-WP041 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-04-27 | 2026-05-08 | 2026-05-11 | 2026-05-22 | 10
P08-A6 | P08 | Contractor Mobilization | 1.08.3.2 | 2026-04-27 | 2026-05-08 |  |  |  |  | 10 | P08-M2 |  | FALSE | FALSE | P08-CA03 | P08-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2026-04-27 | 2026-05-08 | 2026-12-28 | 2027-01-08 | 175
P08-A8 | P08 | Generator/Switchgear Submittal Review | 1.08.3.1 | 2026-04-27 | 2026-05-15 |  |  |  |  | 15 | P08-M2 |  | FALSE | TRUE | P08-CA03 | P08-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-04-27 | 2026-05-15 | 2026-04-27 | 2026-05-15 | 0
P08-I-P08-02 | P08 | Approved Point List Available | 1.08.4.1 | 2026-05-15 | 2026-05-15 |  |  |  |  | 0 | P08-A8 |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-05-15 | 2026-05-15 | 2026-11-17 | 2026-11-17 | 132
P08-A10 | P08 | Switchgear/ATS Fabrication | 1.08.4.2 | 2026-05-18 | 2026-08-07 |  |  |  |  | 60 | P08-A8 |  | FALSE | FALSE | P08-CA04 | P08-WP042 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-05-18 | 2026-08-07 | 2026-06-05 | 2026-08-27 | 14
P08-A9 | P08 | Generator Fabrication | 1.08.4.1 | 2026-05-18 | 2026-08-28 |  |  |  |  | 75 | P08-A8 |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-05-18 | 2026-08-28 | 2026-05-18 | 2026-08-28 | 0
P08-MOUTAGE | P08 | MOUTAGE | 1.08.4.1 | 2026-05-22 | 2026-05-22 |  |  |  |  | 0 | P08-A14 |  | TRUE | TRUE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 0
P08-A10fat | P08 | FAT — Switchgear/ATS | 1.08.4.2 | 2026-08-10 | 2026-08-19 |  |  |  |  | 8 | P08-A10 |  | FALSE | FALSE | P08-CA04 | P08-WP042 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-08-10 | 2026-08-19 | 2026-08-28 | 2026-09-08 | 14
P08-A12 | P08 | Delivery & Receiving — Switchgear/ATS | 1.08.4.2 | 2026-08-20 | 2026-08-31 |  |  |  |  | 8 | P08-A10fat |  | FALSE | FALSE | P08-CA04 | P08-WP042 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-20 | 2026-08-31 | 2026-09-09 | 2026-09-18 | 14
P08-A9fat | P08 | FAT — Generator | 1.08.4.1 | 2026-08-31 | 2026-09-11 |  |  |  |  | 10 | P08-A9 |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | 0
P08-A16 | P08 | ATS-Switchgear Installation | 1.08.4.2 | 2026-09-01 | 2026-09-21 |  |  |  |  | 15 | P08-A13, P08-A12, P08-A14 |  | FALSE | FALSE | P08-CA04 | P08-WP042 | Task | Project-type realism | Source-derived / reconstructed network | 2026-09-01 | 2026-09-21 | 2026-09-21 | 2026-10-09 | 14
P08-A11 | P08 | Delivery & Rigging — Generator | 1.08.4.1 | 2026-09-14 | 2026-09-25 |  |  |  |  | 10 | P08-A9fat |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-09-14 | 2026-09-25 | 2026-09-14 | 2026-09-25 | 0
P08-A15 | P08 | Generator Installation & Rigging Set | 1.08.4.1 | 2026-09-28 | 2026-10-09 |  |  |  |  | 10 | P08-A13, P08-A11, P08-A14 |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-09-28 | 2026-10-09 | 2026-09-28 | 2026-10-09 | 0
P08-A17 | P08 | Electrical/Controls Integration | 1.08.4.1 | 2026-10-12 | 2026-10-23 |  |  |  |  | 10 | P08-A15, P08-A16 |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-10-12 | 2026-10-23 | 2026-10-12 | 2026-10-23 | 0
P08-A18 | P08 | Startup | 1.08.5.1 | 2026-10-26 | 2026-11-06 |  |  |  |  | 10 | P08-A17 |  | FALSE | TRUE | P08-CA05 | P08-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2026-10-26 | 2026-11-06 | 2026-10-26 | 2026-11-06 | 0
P08-I-P08-03 | P08 | Controls Available for Integration | 1.08.4.1 | 2026-11-06 | 2026-11-06 |  |  |  |  | 0 | P08-MSTART |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-11-06 | 2026-11-06 | 2027-01-08 | 2027-01-08 | 45
P08-MSTART | P08 | MSTART | 1.08.4.1 | 2026-11-06 | 2026-11-06 |  |  |  |  | 0 | P08-A18 |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-11-06 | 2026-11-06 | 2027-01-08 | 2027-01-08 | 45
P08-A19 | P08 | Load-Bank Testing | 1.08.5.1 | 2026-11-09 | 2026-11-20 |  |  |  |  | 10 | P08-A18 |  | FALSE | TRUE | P08-CA05 | P08-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2026-11-09 | 2026-11-20 | 2026-11-09 | 2026-11-20 | 0
P08-A20 | P08 | Emergency-Transfer (ATS) Testing | 1.08.5.1 | 2026-11-23 | 2026-11-27 |  |  |  |  | 5 | P08-A19 |  | FALSE | TRUE | P08-CA05 | P08-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2026-11-23 | 2026-11-27 | 2026-11-23 | 2026-11-27 | 0
P08-MOPACC | P08 | MOPACC | 1.08.4.1 | 2026-11-27 | 2026-11-27 |  |  |  |  | 0 | P08-A20 |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-11-27 | 2026-11-27 | 2027-01-08 | 2027-01-08 | 30
P08-A21 | P08 | Final Inspection & Punch List | 1.08.4.1 | 2026-11-30 | 2026-12-11 |  |  |  |  | 10 | P08-A20 |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-11-30 | 2026-12-11 | 2026-11-30 | 2026-12-11 | 0
P08-M3 | P08 | Substantial Completion | 1.08.4.1 | 2026-12-11 | 2026-12-11 |  |  |  |  | 0 | P08-A21 |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-12-11 | 2026-12-11 | 2027-01-08 | 2027-01-08 | 20
P08-A22 | P08 | Documentation & Turnover | 1.08.6.1 | 2026-12-14 | 2026-12-25 |  |  |  |  | 10 | P08-A21 |  | FALSE | TRUE | P08-CA06 | P08-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2026-12-14 | 2026-12-25 | 2026-12-14 | 2026-12-25 | 0
P08-A23 | P08 | Financial Closeout | 1.08.6.2 | 2026-12-21 | 2027-01-08 |  |  |  |  | 15 | P08-A22, P08-A21 |  | FALSE | TRUE | P08-CA06 | P08-WP062 | Task | Project-type realism | Recovered from approved P08 M3/M4 dates + SS+5 closeout overlap | 2026-12-21 | 2027-01-08 | 2026-12-21 | 2027-01-08 | 0
P08-M4 | P08 | Final Completion | 1.08.4.1 | 2027-01-08 | 2027-01-08 |  |  |  |  | 0 | P08-A23 |  | TRUE | TRUE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2027-01-08 | 2027-01-08 | 2027-01-08 | 2027-01-08 | 0
P09-A1 | P09 | Route & Condition Assessment | 1.09.1.1 | 2026-02-02 | 2026-02-20 |  |  |  |  | 15 |  |  | FALSE | TRUE | P09-CA01 | P09-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2026-02-02 | 2026-02-20 | 2026-02-02 | 2026-02-20 | 0
P09-A2 | P09 | Project Definition & Construction Method Selection (HDD) | 1.09.1.2 | 2026-02-23 | 2026-03-06 |  |  |  |  | 10 | P09-A1 |  | FALSE | TRUE | P09-CA01 | P09-WP012 | Task | Synthetic project assumption | Source-derived / reconstructed network | 2026-02-23 | 2026-03-06 | 2026-02-23 | 2026-03-06 | 0
P09-A3a | P09 | Survey / Geotechnical & Subsurface Investigation | 1.09.2.1 | 2026-03-09 | 2026-04-03 |  |  |  |  | 20 | P09-A2 |  | FALSE | TRUE | P09-CA02 | P09-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-09 | 2026-04-03 | 2026-03-09 | 2026-04-03 | 0
P09-A3 | P09 | Preliminary Design | 1.09.2.1 | 2026-04-06 | 2026-05-01 |  |  |  |  | 20 | P09-A3a |  | FALSE | TRUE | P09-CA02 | P09-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | 0
P09-A4 | P09 | Final Design | 1.09.2.2 | 2026-05-11 | 2026-06-05 |  |  |  |  | 20 | P09-A3 |  | FALSE | TRUE | P09-CA02 | P09-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network | 2026-05-11 | 2026-06-05 | 2026-05-11 | 2026-06-05 | 0
P09-A5 | P09 | Bid Advertisement | 1.09.3.1 | 2026-05-25 | 2026-06-12 |  |  |  |  | 15 | P09-A4 |  | FALSE | FALSE | P09-CA03 | P09-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-05-25 | 2026-06-12 | 2026-06-08 | 2026-06-26 | 10
P09-M1 | P09 | Design Complete | 1.09.4.1 | 2026-06-05 | 2026-06-05 |  |  |  |  | 0 | P09-A4 |  | TRUE | FALSE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-06-05 | 2026-06-05 | 2027-03-03 | 2027-03-03 | 193
P09-A4b | P09 | Environmental/Regulatory Review | 1.09.2.2 | 2026-06-08 | 2026-07-17 |  |  |  |  | 30 | P09-A4 |  | FALSE | FALSE | P09-CA02 | P09-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2026-06-08 | 2026-07-17 | 2026-06-22 | 2026-07-31 | 10
P09-A4c | P09 | Waterway / Environmental Crossing Permit | 1.09.2.2 | 2026-06-08 | 2026-07-31 |  |  |  |  | 40 | P09-A4 |  | FALSE | TRUE | P09-CA02 | P09-WP022 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-06-08 | 2026-07-31 | 2026-06-08 | 2026-07-31 | 0
P09-A5b | P09 | Evaluation & Selection — specialty contractor pool | 1.09.3.1 | 2026-06-15 | 2026-07-03 |  |  |  |  | 15 | P09-A5 |  | FALSE | FALSE | P09-CA03 | P09-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-06-15 | 2026-07-03 | 2026-06-29 | 2026-07-17 | 10
P09-A5c | P09 | Governing Body Approval | 1.09.3.2 | 2026-07-06 | 2026-07-17 |  |  |  |  | 10 | P09-A5b |  | FALSE | FALSE | P09-CA03 | P09-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2026-07-06 | 2026-07-17 | 2026-07-20 | 2026-07-31 | 10
P09-M2 | P09 | Contract Award / NTP | 1.09.4.1 | 2026-07-31 | 2026-07-31 |  |  |  |  | 0 | P09-A5c, P09-A4b, P09-A4c |  | TRUE | TRUE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 0
P09-MPERMIT | P09 | MPERMIT | 1.09.2.2 | 2026-07-31 | 2026-07-31 |  |  |  |  | 0 | P09-A4c |  | TRUE | FALSE | P09-CA02 | P09-WP022 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-07-31 | 2026-07-31 | 2027-03-03 | 2027-03-03 | 153
P09-A10 | P09 | HDPE Pipe Submittal Review | 1.09.3.1 | 2026-08-03 | 2026-08-21 |  |  |  |  | 15 | P09-M2 |  | FALSE | TRUE | P09-CA03 | P09-WP031 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-08-03 | 2026-08-21 | 2026-08-03 | 2026-08-21 | 0
P09-A6 | P09 | Specialty (HDD) Contractor Mobilization | 1.09.3.2 | 2026-08-03 | 2026-08-28 |  |  |  |  | 20 | P09-M2 |  | FALSE | FALSE | P09-CA03 | P09-WP032 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-08-03 | 2026-08-28 | 2026-08-27 | 2026-09-23 | 18
P09-A7 | P09 | Utility Coordination & Locate Requests | 1.09.4.1 | 2026-08-03 | 2026-08-21 |  |  |  |  | 15 | P09-M2 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-03 | 2026-08-21 | 2026-09-03 | 2026-09-23 | 23
P09-A8 | P09 | Temporary Bypass/Interconnection Planning | 1.09.4.1 | 2026-08-03 | 2026-08-21 |  |  |  |  | 15 | P09-M2 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-08-03 | 2026-08-21 | 2026-11-12 | 2026-12-02 | 73
P09-A11 | P09 | HDPE Fabrication / Fusion Prep | 1.09.4.2 | 2026-08-24 | 2026-10-23 |  |  |  |  | 45 | P09-A10 |  | FALSE | TRUE | P09-CA04 | P09-WP042 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-08-24 | 2026-10-23 | 2026-08-24 | 2026-10-23 | 0
P09-A9 | P09 | Install Temporary Interconnection/Bypass | 1.09.4.1 | 2026-08-24 | 2026-09-04 |  |  |  |  | 10 | P09-A8 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-08-24 | 2026-09-04 | 2026-12-03 | 2026-12-16 | 73
P09-MSPECMOB | P09 | MSPECMOB | 1.09.4.1 | 2026-08-28 | 2026-08-28 |  |  |  |  | 0 | P09-A6 |  | TRUE | FALSE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-08-28 | 2026-08-28 | 2027-03-03 | 2027-03-03 | 133
P09-A13 | P09 | Entry/Exit Pit Excavation & Site Setup | 1.09.4.1 | 2026-08-31 | 2026-09-11 |  |  |  |  | 10 | P09-A6, P09-A7 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-31 | 2026-09-11 | 2026-09-24 | 2026-10-07 | 18
P09-A14 | P09 | HDD Pilot Bore | 1.09.4.1 | 2026-09-14 | 2026-10-09 |  |  |  |  | 20 | P09-A13 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Synthetic, industry-informed planning assumption | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-09-14 | 2026-10-09 | 2026-10-08 | 2026-11-04 | 18
P09-A12 | P09 | Delivery & Receiving | 1.09.4.1 | 2026-10-26 | 2026-11-04 |  |  |  |  | 8 | P09-A11 |  | FALSE | TRUE | P09-CA04 | P09-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-10-26 | 2026-11-04 | 2026-10-26 | 2026-11-04 | 0
P09-A15 | P09 | Reaming & Pullback | 1.09.4.1 | 2026-11-05 | 2026-11-25 |  |  |  |  | 15 | P09-A12, P09-A14 |  | FALSE | TRUE | P09-CA04 | P09-WP041 | Task | Synthetic, industry-informed planning assumption | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-11-05 | 2026-11-25 | 2026-11-05 | 2026-11-25 | 0
P09-MCROSSDONE | P09 | MCROSSDONE | 1.09.4.1 | 2026-11-25 | 2026-11-25 |  |  |  |  | 0 | P09-A15 |  | TRUE | FALSE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-11-25 | 2026-11-25 | 2027-03-03 | 2027-03-03 | 70
P09-A16 | P09 | Tie-In — Entry Side | 1.09.4.1 | 2026-11-26 | 2026-12-09 |  |  |  |  | 10 | P09-A15 |  | FALSE | TRUE | P09-CA04 | P09-WP041 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-11-26 | 2026-12-09 | 2026-11-26 | 2026-12-09 | 0
P09-A17 | P09 | Tie-In — Exit Side | 1.09.4.1 | 2026-11-26 | 2026-12-09 |  |  |  |  | 10 | P09-A15 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-11-26 | 2026-12-09 | 2026-12-03 | 2026-12-16 | 5
P09-A18 | P09 | Pressure Testing & Disinfection | 1.09.5.1 | 2026-12-17 | 2026-12-23 |  |  |  |  | 5 | P09-A16, P09-A17, P09-A9 |  | FALSE | TRUE | P09-CA05 | P09-WP051 | Task | Project-type realism; +5bd settling lag in logic | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-12-17 | 2026-12-23 | 2026-12-17 | 2026-12-23 | 0
P09-A19 | P09 | Bacteriological Sampling & Regulatory Clearance | 1.09.2.2 | 2026-12-24 | 2026-12-30 |  |  |  |  | 5 | P09-A18 |  | FALSE | TRUE | P09-CA02 | P09-WP022 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-12-24 | 2026-12-30 | 2026-12-24 | 2026-12-30 | 0
P09-MINSERVICE | P09 | MINSERVICE | 1.09.4.1 | 2026-12-30 | 2026-12-30 |  |  |  |  | 0 | P09-A19 |  | TRUE | FALSE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-12-30 | 2026-12-30 | 2027-03-03 | 2027-03-03 | 45
P09-A20 | P09 | Riverbank & Pit Restoration | 1.09.4.3 | 2026-12-31 | 2027-01-20 |  |  |  |  | 15 | P09-A19 |  | FALSE | TRUE | P09-CA04 | P09-WP043 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-12-31 | 2027-01-20 | 2026-12-31 | 2027-01-20 | 0
P09-A21 | P09 | Final Inspection & Punch List | 1.09.4.1 | 2027-01-21 | 2027-02-03 |  |  |  |  | 10 | P09-A20 |  | FALSE | TRUE | P09-CA04 | P09-WP041 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2027-01-21 | 2027-02-03 | 2027-01-21 | 2027-02-03 | 0
P09-M3 | P09 | Substantial Completion | 1.09.4.1 | 2027-02-03 | 2027-02-03 |  |  |  |  | 0 | P09-A21 |  | TRUE | FALSE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2027-02-03 | 2027-02-03 | 2027-03-03 | 2027-03-03 | 20
P09-A22 | P09 | Documentation & Turnover | 1.09.6.1 | 2027-02-04 | 2027-02-17 |  |  |  |  | 10 | P09-A21 |  | FALSE | TRUE | P09-CA06 | P09-WP061 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2027-02-04 | 2027-02-17 | 2027-02-04 | 2027-02-17 | 0
P09-A23 | P09 | Financial Closeout | 1.09.6.2 | 2027-02-11 | 2027-03-03 |  |  |  |  | 15 | P09-A22, P09-A21 |  | FALSE | TRUE | P09-CA06 | P09-WP062 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2027-02-11 | 2027-03-03 | 2027-02-11 | 2027-03-03 | 0
P09-M4 | P09 | Final Completion | 1.09.4.1 | 2027-03-03 | 2027-03-03 |  |  |  |  | 0 | P09-A23 |  | TRUE | TRUE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2027-03-03 | 2027-03-03 | 2027-03-03 | 2027-03-03 | 0
P10-A1 | P10 | Existing-System / Controls Inventory Assessment | 1.10.1.1 | 2026-04-01 | 2026-04-21 |  |  |  |  | 15 |  |  | FALSE | TRUE | P10-CA01 | P10-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-01 | 2026-04-21 | 2026-04-01 | 2026-04-21 | 0
P10-A2 | P10 | Project Definition & Network/Architecture Assessment | 1.10.1.1 | 2026-04-22 | 2026-05-05 |  |  |  |  | 10 | P10-A1 |  | FALSE | TRUE | P10-CA01 | P10-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-22 | 2026-05-05 | 2026-04-22 | 2026-05-05 | 0
P10-A3 | P10 | Control Narrative / Functional Requirements | 1.10.2.2 | 2026-05-06 | 2026-05-26 |  |  |  |  | 15 | P10-A2 |  | FALSE | TRUE | P10-CA02 | P10-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-06 | 2026-05-26 | 2026-05-06 | 2026-05-26 | 0
P10-A4 | P10 | PLC/HMI/SCADA Preliminary Design (30%) | 1.10.2.1 | 2026-05-27 | 2026-06-23 |  |  |  |  | 20 | P10-A3 |  | FALSE | TRUE | P10-CA02 | P10-WP021 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-27 | 2026-06-23 | 2026-05-27 | 2026-06-23 | 0
P10-A5 | P10 | Communications/Network Design | 1.10.2.2 | 2026-06-10 | 2026-06-30 |  |  |  |  | 15 | P10-A4 |  | FALSE | TRUE | P10-CA02 | P10-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-06-10 | 2026-06-30 | 2026-06-10 | 2026-06-30 | 0
P10-A6b | P10 | Cybersecurity & IT Coordination | 1.10.2.2 | 2026-06-10 | 2026-06-30 |  |  |  |  | 15 | P10-A4 |  | FALSE | TRUE | P10-CA02 | P10-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-06-10 | 2026-06-30 | 2026-06-10 | 2026-06-30 | 0
P10-A6 | P10 | Final Design (100%) | 1.10.2.2 | 2026-06-24 | 2026-07-21 |  |  |  |  | 20 | P10-A5, P10-A6b |  | FALSE | TRUE | P10-CA02 | P10-WP022 | Task | Project-type realism | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-06-24 | 2026-07-21 | 2026-06-24 | 2026-07-21 | 0
P10-A7 | P10 | Bid Advertisement | 1.10.3.1 | 2026-07-08 | 2026-07-28 |  |  |  |  | 15 | P10-A6 |  | FALSE | TRUE | P10-CA03 | P10-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-08 | 2026-07-28 | 2026-07-08 | 2026-07-28 | 0
P10-M1 | P10 | Controls Design Approved | 1.10.4.1 | 2026-07-21 | 2026-07-21 |  |  |  |  | 0 | P10-A6 |  | TRUE | FALSE | P10-CA04 | P10-WP041 | Milestone | Approved milestone / interface milestone | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-21 | 2026-07-21 | 2026-11-17 | 2026-11-17 | 85
P10-IF-01 | P10 | Final I/O Mapping & Tag Reconciliation | 1.10.4.1 | 2026-07-22 | 2026-08-04 |  |  |  |  | 10 | P03-I-P03-02, P08-I-P08-02, P10-M1 |  | FALSE | FALSE | P10-CA04 | P10-WP041 | Task | Approved synthetic project-specific planning assumption | ID normalized to approved interface naming convention ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-22 | 2026-08-04 | 2026-11-18 | 2026-12-01 | 85
P10-MIF01 | P10 | Final I/O Mapping Complete | 1.10.4.1 | 2026-08-04 | 2026-08-04 |  |  |  |  | 0 | P10-IF-01 |  | TRUE | FALSE | P10-CA04 | P10-WP041 | Milestone | Approved milestone / interface milestone | ID normalized to approved interface naming convention ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-04 | 2026-08-04 | 2026-12-01 | 2026-12-01 | 85
P10-A7b | P10 | Evaluation & Award | 1.10.3.1 | 2026-07-29 | 2026-08-11 |  |  |  |  | 10 | P10-A7 |  | FALSE | TRUE | P10-CA03 | P10-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-29 | 2026-08-11 | 2026-07-29 | 2026-08-11 | 0
P10-A7c | P10 | Governing Body Approval | 1.10.3.2 | 2026-08-12 | 2026-08-25 |  |  |  |  | 10 | P10-A7b |  | FALSE | TRUE | P10-CA03 | P10-WP032 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-12 | 2026-08-25 | 2026-08-12 | 2026-08-25 | 0
P10-M2 | P10 | Contract Award / NTP | 1.10.4.1 | 2026-08-25 | 2026-08-25 |  |  |  |  | 0 | P10-A7c |  | TRUE | TRUE | P10-CA04 | P10-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 0
P10-A11 | P10 | SCADA Software Licensing & Base System Procurement | 1.10.4.2 | 2026-08-26 | 2026-09-15 |  |  |  |  | 15 | P10-M2 |  | FALSE | FALSE | P10-CA04 | P10-WP042 | Task | Synthetic project assumption | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-09-15 | 2027-07-19 | 2027-08-06 | 233
P10-A14 | P10 | PLC Programming / Configuration | 1.10.4.1 | 2026-08-26 | 2026-10-06 |  |  |  |  | 30 | P10-M2 |  | FALSE | FALSE | P10-CA04 | P10-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-10-06 | 2026-10-21 | 2026-12-01 | 40
P10-A15 | P10 | HMI Screen Development & SCADA Software Configuration | 1.10.4.2 | 2026-08-26 | 2026-09-29 |  |  |  |  | 25 | P10-M2 |  | FALSE | FALSE | P10-CA04 | P10-WP042 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-09-29 | 2026-10-28 | 2026-12-01 | 45
P10-A8 | P10 | Contractor/Integrator Mobilization | 1.10.3.2 | 2026-08-26 | 2026-09-08 |  |  |  |  | 10 | P10-M2 |  | FALSE | FALSE | P10-CA03 | P10-WP032 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-09-08 | 2026-12-21 | 2027-01-01 | 83
P10-A9 | P10 | PLC/HMI/Network Hardware Submittal Review | 1.10.3.1 | 2026-08-26 | 2026-09-15 |  |  |  |  | 15 | P10-M2 |  | FALSE | TRUE | P10-CA03 | P10-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-09-15 | 2026-08-26 | 2026-09-15 | 0
P10-A10 | P10 | Hardware Procurement & Delivery | 1.10.4.3 | 2026-09-16 | 2026-10-27 |  |  |  |  | 30 | P10-A9 |  | FALSE | TRUE | P10-CA04 | P10-WP043 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-09-16 | 2026-10-27 | 2026-09-16 | 2026-10-27 | 0
P10-MIF02 | P10 | Integration Configuration Complete | 1.10.4.1 | 2026-10-06 | 2026-10-06 |  |  |  |  | 0 | P10-MIF01, P10-A14, P10-A15 |  | TRUE | FALSE | P10-CA04 | P10-WP041 | Milestone | Approved milestone / interface milestone | ID normalized to approved interface naming convention ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-06 | 2026-10-06 | 2026-12-01 | 2026-12-01 | 40
P10-A12 | P10 | Control Panel Fabrication & Shop Assembly | 1.10.4.3 | 2026-10-28 | 2026-12-01 |  |  |  |  | 25 | P10-A10 |  | FALSE | TRUE | P10-CA04 | P10-WP043 | Task | Synthetic project assumption | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-28 | 2026-12-01 | 2026-10-28 | 2026-12-01 | 0
P10-A13 | P10 | FAT / Bench Test | 1.10.5.1 | 2026-12-02 | 2026-12-22 |  |  |  |  | 15 | P10-A12, P10-A14, P10-A15, P10-MIF02 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Synthetic project-specific planning assumption | Semantic WBS mapping corrected: FAT/bench test is testing & commissioning ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-02 | 2026-12-22 | 2026-12-02 | 2026-12-22 | 0
P10-MFAT | P10 | MFAT | 1.10.5.1 | 2026-12-22 | 2026-12-22 |  |  |  |  | 0 | P10-A13 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: FAT completion milestone ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-22 | 2026-12-22 | 2027-08-06 | 2027-08-06 | 163
P10-A16 | P10 | Delivery & Receiving — Panels/Network Equipment | 1.10.4.3 | 2026-12-23 | 2027-01-01 |  |  |  |  | 8 | P10-A13 |  | FALSE | TRUE | P10-CA04 | P10-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-23 | 2027-01-01 | 2026-12-23 | 2027-01-01 | 0
P10-A17 | P10 | Site Installation — Panels & Network Infrastructure | 1.10.4.3 | 2027-01-04 | 2027-02-05 |  |  |  |  | 25 | P10-A8, P10-A16 |  | FALSE | TRUE | P10-CA04 | P10-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-01-04 | 2027-02-05 | 2027-01-04 | 2027-02-05 | 0
P10-MSITEINSTALL | P10 | MSITEINSTALL | 1.10.4.3 | 2027-02-05 | 2027-02-05 |  |  |  |  | 0 | P10-A17 |  | TRUE | FALSE | P10-CA04 | P10-WP043 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: site installation milestone maps to Network & Communications Infrastructure ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-02-05 | 2027-02-05 | 2027-03-12 | 2027-03-12 | 25
P10-A18 | P10 | I/O Checkout & Point-to-Point Verification | 1.10.5.1 | 2027-02-08 | 2027-02-26 |  |  |  |  | 15 | P10-A17 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-02-08 | 2027-02-26 | 2027-02-08 | 2027-02-26 | 0
P10-MIOCHECK | P10 | MIOCHECK | 1.10.5.1 | 2027-02-26 | 2027-02-26 |  |  |  |  | 0 | P10-A18 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: I/O checkout milestone ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-02-26 | 2027-02-26 | 2027-03-12 | 2027-03-12 | 10
P10-A19 | P10 | Communications/Network Testing | 1.10.5.1 | 2027-03-01 | 2027-03-12 |  |  |  |  | 10 | P10-A18 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-03-01 | 2027-03-12 | 2027-03-01 | 2027-03-12 | 0
P10-MIF03 | P10 | Site Integration Ready | 1.10.5.1 | 2027-03-12 | 2027-03-12 |  |  |  |  | 0 | P03-I-P03-03, P08-I-P08-03, P10-MSITEINSTALL, P10-MIOCHECK, P10-A19 |  | TRUE | TRUE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: site integration readiness is a testing/integration gate ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-03-12 | 2027-03-12 | 2027-03-12 | 2027-03-12 | 0
P10-A20 | P10 | System Integration — head-end / PLCs / historian | 1.10.5.1 | 2027-03-15 | 2027-04-02 |  |  |  |  | 15 | P10-MIF03 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-03-15 | 2027-04-02 | 2027-03-15 | 2027-04-02 | 0
P10-A21 | P10 | Site Acceptance Testing (SAT) | 1.10.5.1 | 2027-04-05 | 2027-04-23 |  |  |  |  | 15 | P10-A20 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-04-05 | 2027-04-23 | 2027-04-05 | 2027-04-23 | 0
P10-MSAT | P10 | MSAT | 1.10.5.1 | 2027-04-23 | 2027-04-23 |  |  |  |  | 0 | P10-A21 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-04-23 | 2027-04-23 | 2027-08-06 | 2027-08-06 | 75
P10-A22 | P10 | Operator Training | 1.10.5.1 | 2027-04-26 | 2027-05-07 |  |  |  |  | 10 | P10-A21 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Semantic WBS mapping corrected: operator training is acceptance/commissioning scope ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-04-26 | 2027-05-07 | 2027-04-26 | 2027-05-07 | 0
P10-A23 | P10 | Cutover Planning | 1.10.5.1 | 2027-04-26 | 2027-05-07 |  |  |  |  | 10 | P10-A21 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-04-26 | 2027-05-07 | 2027-04-26 | 2027-05-07 | 0
P10-A24 | P10 | Phased Cutover / Migration from Legacy System | 1.10.5.1 | 2027-05-10 | 2027-05-28 |  |  |  |  | 15 | P10-A22, P10-A23 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-05-10 | 2027-05-28 | 2027-05-10 | 2027-05-28 | 0
P10-MCUTOVER | P10 | MCUTOVER | 1.10.5.1 | 2027-05-28 | 2027-05-28 |  |  |  |  | 0 | P10-A24 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-05-28 | 2027-05-28 | 2027-08-06 | 2027-08-06 | 50
P10-A25 | P10 | Post-Cutover Monitoring & Stabilization | 1.10.5.1 | 2027-05-31 | 2027-06-18 |  |  |  |  | 15 | P10-A24 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-05-31 | 2027-06-18 | 2027-05-31 | 2027-06-18 | 0
P10-MOPACC | P10 | MOPACC | 1.10.5.1 | 2027-06-18 | 2027-06-18 |  |  |  |  | 0 | P10-A25 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: operational acceptance milestone ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-06-18 | 2027-06-18 | 2027-08-06 | 2027-08-06 | 35
P10-A26 | P10 | Documentation, Backup & Turnover | 1.10.6.1 | 2027-06-21 | 2027-07-09 |  |  |  |  | 15 | P10-A25 |  | FALSE | TRUE | P10-CA06 | P10-WP061 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-06-21 | 2027-07-09 | 2027-06-21 | 2027-07-09 | 0
P10-A27 | P10 | Final Inspection & Punch List | 1.10.5.1 | 2027-06-21 | 2027-07-02 |  |  |  |  | 10 | P10-A25 |  | FALSE | FALSE | P10-CA05 | P10-WP051 | Task | Project-type realism | Semantic WBS mapping corrected: final inspection/punch list is acceptance/commissioning scope ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-06-21 | 2027-07-02 | 2027-07-26 | 2027-08-06 | 25
P10-M3 | P10 | Substantial Completion | 1.10.5.1 | 2027-07-02 | 2027-07-02 |  |  |  |  | 0 | P10-A27 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: substantial completion follows acceptance/testing ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-07-02 | 2027-07-02 | 2027-08-06 | 2027-08-06 | 25
P10-A28 | P10 | Financial Closeout | 1.10.6.2 | 2027-07-19 | 2027-08-06 |  |  |  |  | 15 | P10-A26, P10-A27 |  | FALSE | TRUE | P10-CA06 | P10-WP062 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-07-19 | 2027-08-06 | 2027-07-19 | 2027-08-06 | 0
P10-M4 | P10 | Final Completion | 1.10.6.2 | 2027-08-06 | 2027-08-06 |  |  |  |  | 0 | P10-A28 |  | TRUE | TRUE | P10-CA06 | P10-WP062 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: final completion aligns with financial closeout ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-08-06 | 2027-08-06 | 2027-08-06 | 2027-08-06 | 0
P11-A1 | P11 | Valve Inventory / Condition Prioritization | 1.11.1.1 | 2025-04-01 | 2025-04-21 |  |  |  |  | 15 |  |  | FALSE | TRUE | P11-CA01 | P11-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-04-01 | 2025-04-21 | 2025-04-01 | 2025-04-21 | 0
P11-A2 | P11 | Project Definition & Isolation-Zone Planning | 1.11.1.2 | 2025-04-22 | 2025-05-05 |  |  |  |  | 10 | P11-A1 |  | FALSE | TRUE | P11-CA01 | P11-WP012 | Task | Project-type realism | Source-derived / reconstructed network | 2025-04-22 | 2025-05-05 | 2025-04-22 | 2025-05-05 | 0
P11-A3 | P11 | Preliminary Design | 1.11.2.1 | 2025-05-06 | 2025-05-26 |  |  |  |  | 15 | P11-A2 |  | FALSE | TRUE | P11-CA02 | P11-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2025-05-06 | 2025-05-26 | 2025-05-06 | 2025-05-26 | 0
P11-A4 | P11 | Final Design | 1.11.2.2 | 2025-06-03 | 2025-06-23 |  |  |  |  | 15 | P11-A3 |  | FALSE | TRUE | P11-CA02 | P11-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network | 2025-06-03 | 2025-06-23 | 2025-06-03 | 2025-06-23 | 0
P11-A5 | P11 | Bid Advertisement | 1.11.3.1 | 2025-06-17 | 2025-07-07 |  |  |  |  | 15 | P11-A4 |  | FALSE | TRUE | P11-CA03 | P11-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-17 | 2025-07-07 | 2025-06-17 | 2025-07-07 | 0
P11-M1 | P11 | Design Complete | 1.11.4.1 | 2025-06-23 | 2025-06-23 |  |  |  |  | 0 | P11-A4 |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-06-23 | 2025-06-23 | 2026-03-09 | 2026-03-09 | 185
P11-A5b | P11 | Evaluation & Award | 1.11.3.1 | 2025-07-08 | 2025-07-21 |  |  |  |  | 10 | P11-A5 |  | FALSE | TRUE | P11-CA03 | P11-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-07-08 | 2025-07-21 | 2025-07-08 | 2025-07-21 | 0
P11-A5c | P11 | Governing Body Approval | 1.11.3.2 | 2025-07-22 | 2025-08-04 |  |  |  |  | 10 | P11-A5b |  | FALSE | TRUE | P11-CA03 | P11-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-07-22 | 2025-08-04 | 2025-07-22 | 2025-08-04 | 0
P11-M2 | P11 | Contract Award / NTP | 1.11.4.1 | 2025-08-11 | 2025-08-11 |  |  |  |  | 0 | P11-A5c |  | TRUE | TRUE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | 0
P11-A10 | P11 | Shutdown & Customer/Service Coordination Planning | 1.11.4.1 | 2025-08-12 | 2025-09-01 |  |  |  |  | 15 | P11-M2 |  | FALSE | FALSE | P11-CA04 | P11-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2025-08-12 | 2025-09-01 | 2025-08-26 | 2025-09-15 | 10
P11-A6 | P11 | Mobilization | 1.11.3.2 | 2025-08-12 | 2025-08-25 |  |  |  |  | 10 | P11-M2 |  | FALSE | FALSE | P11-CA03 | P11-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-08-12 | 2025-08-25 | 2025-09-02 | 2025-09-15 | 15
P11-A7 | P11 | Field Verification / Utility Locating | 1.11.5.1 | 2025-08-12 | 2025-09-01 |  |  |  |  | 15 | P11-M2 |  | FALSE | FALSE | P11-CA05 | P11-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2025-08-12 | 2025-09-01 | 2025-08-26 | 2025-09-15 | 10
P11-A8 | P11 | Traffic / Street-Opening Coordination & Permitting | 1.11.2.2 | 2025-08-12 | 2025-08-25 |  |  |  |  | 10 | P11-M2 |  | FALSE | FALSE | P11-CA02 | P11-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2025-08-12 | 2025-08-25 | 2025-09-02 | 2025-09-15 | 15
P11-A9 | P11 | Material Procurement — Valves & Fittings | 1.11.4.1 | 2025-08-12 | 2025-09-15 |  |  |  |  | 25 | P11-M2 |  | FALSE | TRUE | P11-CA04 | P11-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2025-08-12 | 2025-09-15 | 2025-08-12 | 2025-09-15 | 0
P11-AFIRST | P11 | Complete First Valve Replacement | 1.11.4.1 | 2025-09-16 | 2025-09-17 |  |  |  |  | 2 | P11-B1inst |  | FALSE | FALSE | P11-CA04 | P11-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2025-09-16 | 2025-09-17 | 2026-03-06 | 2026-03-09 | 123
P11-B1inst | P11 | Batch 1 Valve Installation | 1.11.4.1 | 2025-09-16 | 2025-11-10 |  |  |  |  | 40 | P11-A6, P11-A7, P11-A8, P11-A9, P11-A10 |  | FALSE | TRUE | P11-CA04 | P11-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2025-09-16 | 2025-11-10 | 2025-09-16 | 2025-11-10 | 0
P11-MFIRST | P11 | MFIRST | 1.11.4.1 | 2025-09-17 | 2025-09-17 |  |  |  |  | 0 | P11-AFIRST |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-09-17 | 2025-09-17 | 2026-03-09 | 2026-03-09 | 123
P11-B1rest | P11 | Batch 1 Restoration | 1.11.4.3 | 2025-10-14 | 2025-12-08 |  |  |  |  | 40 | P11-B1inst |  | FALSE | FALSE | P11-CA04 | P11-WP043 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2025-10-14 | 2025-12-08 | 2025-11-18 | 2026-01-12 | 25
P11-B2inst | P11 | Batch 2 Valve Installation | 1.11.4.1 | 2025-10-21 | 2025-12-15 |  |  |  |  | 40 | P11-B1inst |  | FALSE | TRUE | P11-CA04 | P11-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2025-10-21 | 2025-12-15 | 2025-10-21 | 2025-12-15 | 0
P11-MBATCH1 | P11 | MBATCH1 | 1.11.4.1 | 2025-11-10 | 2025-11-10 |  |  |  |  | 0 | P11-B1inst |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-11-10 | 2025-11-10 | 2026-03-09 | 2026-03-09 | 85
P11-B1test | P11 | Batch 1 Testing / Return to Service | 1.11.5.1 | 2025-11-11 | 2025-11-24 |  |  |  |  | 10 | P11-B1inst |  | FALSE | FALSE | P11-CA05 | P11-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2025-11-11 | 2025-11-24 | 2026-02-24 | 2026-03-09 | 75
P11-B2rest | P11 | Batch 2 Restoration | 1.11.4.3 | 2025-11-18 | 2026-01-12 |  |  |  |  | 40 | P11-B2inst |  | FALSE | TRUE | P11-CA04 | P11-WP043 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2025-11-18 | 2026-01-12 | 2025-11-18 | 2026-01-12 | 0
P11-B1gis | P11 | Batch 1 Records/GIS Update | 1.11.6.1 | 2025-12-09 | 2025-12-22 |  |  |  |  | 10 | P11-B1rest |  | FALSE | FALSE | P11-CA06 | P11-WP061 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2025-12-09 | 2025-12-22 | 2026-01-13 | 2026-01-26 | 25
P11-MTARGET | P11 | MTARGET | 1.11.4.1 | 2025-12-15 | 2025-12-15 |  |  |  |  | 0 | P11-B2inst |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-12-15 | 2025-12-15 | 2026-03-09 | 2026-03-09 | 60
P11-B2test | P11 | Batch 2 Testing / Return to Service | 1.11.5.1 | 2025-12-16 | 2025-12-29 |  |  |  |  | 10 | P11-B2inst |  | FALSE | FALSE | P11-CA05 | P11-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-16 | 2025-12-29 | 2026-02-24 | 2026-03-09 | 50
P11-B2gis | P11 | Batch 2 Records/GIS Update | 1.11.6.1 | 2026-01-13 | 2026-01-26 |  |  |  |  | 10 | P11-B2rest |  | FALSE | TRUE | P11-CA06 | P11-WP061 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2026-01-13 | 2026-01-26 | 2026-01-13 | 2026-01-26 | 0
P11-A11 | P11 | Final Inspection & Punch List / Isolation Function Verification | 1.11.5.1 | 2026-01-27 | 2026-02-09 |  |  |  |  | 10 | P11-B1gis, P11-B2gis |  | FALSE | TRUE | P11-CA05 | P11-WP051 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2026-01-27 | 2026-02-09 | 2026-01-27 | 2026-02-09 | 0
P11-M3 | P11 | Substantial Completion | 1.11.4.1 | 2026-02-09 | 2026-02-09 |  |  |  |  | 0 | P11-A11 |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-02-09 | 2026-02-09 | 2026-03-09 | 2026-03-09 | 20
P11-MISOVERIFY | P11 | MISOVERIFY | 1.11.4.1 | 2026-02-09 | 2026-02-09 |  |  |  |  | 0 | P11-A11 |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-02-09 | 2026-02-09 | 2026-03-09 | 2026-03-09 | 20
P11-A12 | P11 | Documentation & Turnover | 1.11.6.1 | 2026-02-10 | 2026-02-23 |  |  |  |  | 10 | P11-A11 |  | FALSE | TRUE | P11-CA06 | P11-WP061 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2026-02-10 | 2026-02-23 | 2026-02-10 | 2026-02-23 | 0
P11-A13 | P11 | Financial Closeout | 1.11.6.2 | 2026-02-17 | 2026-03-09 |  |  |  |  | 15 | P11-A12 |  | FALSE | TRUE | P11-CA06 | P11-WP062 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2026-02-17 | 2026-03-09 | 2026-02-17 | 2026-03-09 | 0
P11-M4 | P11 | Final Completion | 1.11.4.1 | 2026-03-09 | 2026-03-09 |  |  |  |  | 0 | P11-A13 |  | TRUE | TRUE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 0
P12-Y1A1 | P12 | Year 1 Annual Planning & Prioritization Window | 1.12.1.1 | 2025-01-02 | 2025-01-22 |  |  |  |  | 15 |  |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-01-02 | 2025-01-22 | 2025-01-02 | 2025-01-22 | 0
P12-MPLANY1 | P12 | MPLANY1 | 1.12.1.1 | 2025-01-22 | 2025-01-22 |  |  |  |  | 0 | P12-Y1A1 |  | TRUE | FALSE | P12-CA01 | P12-WP011 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: annual planning milestone belongs in Planning & Prioritization | 2025-01-22 | 2025-01-22 | 2027-06-23 | 2027-06-23 | 630
P12-Y1A2 | P12 | Year 1 Intake & Triage of Small-Capital/Emergency Needs | 1.12.1.1 | 2025-01-23 | 2025-02-19 |  |  |  |  | 20 | P12-Y1A1 |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-01-23 | 2025-02-19 | 2025-01-23 | 2025-02-19 | 0
P12-Y1A3 | P12 | Year 1 Scope Development | 1.12.2.1 | 2025-02-20 | 2025-03-19 |  |  |  |  | 20 | P12-Y1A2 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Semantic WBS mapping corrected: scope development belongs in Design / Scope Development | 2025-02-20 | 2025-03-19 | 2025-02-20 | 2025-03-19 | 0
P12-Y1A4 | P12 | Year 1 Rapid Design / Standard-Detail Development | 1.12.2.1 | 2025-03-20 | 2025-04-09 |  |  |  |  | 15 | P12-Y1A3 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2025-03-20 | 2025-04-09 | 2025-03-20 | 2025-04-09 | 0
P12-Y1A5 | P12 | Year 1 Procurement / Task-Order Assignment | 1.12.3.1 | 2025-04-10 | 2025-05-14 |  |  |  |  | 25 | P12-Y1A4 |  | FALSE | TRUE | P12-CA03 | P12-WP031 | Task | Synthetic project assumption — standing on-call/task-order contract | Semantic WBS mapping corrected: procurement/task-order assignment belongs in Procurement | 2025-04-10 | 2025-05-14 | 2025-04-10 | 2025-05-14 | 0
P12-Y1A6 | P12 | Year 1 Field Execution | 1.12.4.1 | 2025-05-15 | 2025-09-17 |  |  |  |  | 90 | P12-Y1A5 |  | FALSE | TRUE | P12-CA04 | P12-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2025-05-15 | 2025-09-17 | 2025-05-15 | 2025-09-17 | 0
P12-MY1DONE | P12 | MY1DONE | 1.12.4.1 | 2025-09-17 | 2025-09-17 |  |  |  |  | 0 | P12-Y1A6 |  | TRUE | FALSE | P12-CA04 | P12-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-09-17 | 2025-09-17 | 2027-06-23 | 2027-06-23 | 460
P12-Y1A7 | P12 | Year 1 Verification / Acceptance | 1.12.5.1 | 2025-09-18 | 2025-10-08 |  |  |  |  | 15 | P12-Y1A6 |  | FALSE | TRUE | P12-CA05 | P12-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2025-09-18 | 2025-10-08 | 2025-09-18 | 2025-10-08 | 0
P12-Y1A8 | P12 | Year 1 Closeout | 1.12.6.1 | 2025-10-09 | 2025-10-29 |  |  |  |  | 15 | P12-Y1A7 |  | FALSE | TRUE | P12-CA06 | P12-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-09 | 2025-10-29 | 2025-10-09 | 2025-10-29 | 0
P12-Y2A1 | P12 | Year 2 Annual Planning & Prioritization Window | 1.12.1.1 | 2025-10-30 | 2025-11-19 |  |  |  |  | 15 | P12-Y1A8 |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-30 | 2025-11-19 | 2025-10-30 | 2025-11-19 | 0
P12-MPLANY2 | P12 | MPLANY2 | 1.12.1.1 | 2025-11-19 | 2025-11-19 |  |  |  |  | 0 | P12-Y2A1 |  | TRUE | FALSE | P12-CA01 | P12-WP011 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: annual planning milestone belongs in Planning & Prioritization | 2025-11-19 | 2025-11-19 | 2027-06-23 | 2027-06-23 | 415
P12-Y2A2 | P12 | Year 2 Intake & Triage of Small-Capital/Emergency Needs | 1.12.1.1 | 2025-11-20 | 2025-12-17 |  |  |  |  | 20 | P12-Y2A1 |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-11-20 | 2025-12-17 | 2025-11-20 | 2025-12-17 | 0
P12-Y2A3 | P12 | Year 2 Scope Development | 1.12.2.1 | 2025-12-18 | 2026-01-14 |  |  |  |  | 20 | P12-Y2A2 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Semantic WBS mapping corrected: scope development belongs in Design / Scope Development | 2025-12-18 | 2026-01-14 | 2025-12-18 | 2026-01-14 | 0
P12-Y2A4 | P12 | Year 2 Rapid Design / Standard-Detail Development | 1.12.2.1 | 2026-01-15 | 2026-02-04 |  |  |  |  | 15 | P12-Y2A3 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-15 | 2026-02-04 | 2026-01-15 | 2026-02-04 | 0
P12-Y2A5 | P12 | Year 2 Procurement / Task-Order Assignment | 1.12.3.1 | 2026-02-05 | 2026-03-11 |  |  |  |  | 25 | P12-Y2A4 |  | FALSE | TRUE | P12-CA03 | P12-WP031 | Task | Synthetic project assumption — standing on-call/task-order contract | Semantic WBS mapping corrected: procurement/task-order assignment belongs in Procurement | 2026-02-05 | 2026-03-11 | 2026-02-05 | 2026-03-11 | 0
P12-Y2A6 | P12 | Year 2 Field Execution | 1.12.4.1 | 2026-03-12 | 2026-07-15 |  |  |  |  | 90 | P12-Y2A5 |  | FALSE | TRUE | P12-CA04 | P12-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-03-12 | 2026-07-15 | 2026-03-12 | 2026-07-15 | 0
P12-MY2DONE | P12 | MY2DONE | 1.12.4.1 | 2026-07-15 | 2026-07-15 |  |  |  |  | 0 | P12-Y2A6 |  | TRUE | FALSE | P12-CA04 | P12-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-07-15 | 2026-07-15 | 2027-06-23 | 2027-06-23 | 245
P12-Y2A7 | P12 | Year 2 Verification / Acceptance | 1.12.5.1 | 2026-07-16 | 2026-08-05 |  |  |  |  | 15 | P12-Y2A6 |  | FALSE | TRUE | P12-CA05 | P12-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2026-07-16 | 2026-08-05 | 2026-07-16 | 2026-08-05 | 0
P12-Y2A8 | P12 | Year 2 Closeout | 1.12.6.1 | 2026-08-06 | 2026-08-26 |  |  |  |  | 15 | P12-Y2A7 |  | FALSE | TRUE | P12-CA06 | P12-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-06 | 2026-08-26 | 2026-08-06 | 2026-08-26 | 0
P12-Y3A1 | P12 | Year 3 Annual Planning & Prioritization Window | 1.12.1.1 | 2026-08-27 | 2026-09-16 |  |  |  |  | 15 | P12-Y2A8 |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-27 | 2026-09-16 | 2026-08-27 | 2026-09-16 | 0
P12-MPLANY3 | P12 | MPLANY3 | 1.12.1.1 | 2026-09-16 | 2026-09-16 |  |  |  |  | 0 | P12-Y3A1 |  | TRUE | FALSE | P12-CA01 | P12-WP011 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: annual planning milestone belongs in Planning & Prioritization | 2026-09-16 | 2026-09-16 | 2027-06-23 | 2027-06-23 | 200
P12-Y3A2 | P12 | Year 3 Intake & Triage of Small-Capital/Emergency Needs | 1.12.1.1 | 2026-09-17 | 2026-10-14 |  |  |  |  | 20 | P12-Y3A1 |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2026-09-17 | 2026-10-14 | 2026-09-17 | 2026-10-14 | 0
P12-Y3A3 | P12 | Year 3 Scope Development | 1.12.2.1 | 2026-10-15 | 2026-11-11 |  |  |  |  | 20 | P12-Y3A2 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Semantic WBS mapping corrected: scope development belongs in Design / Scope Development | 2026-10-15 | 2026-11-11 | 2026-10-15 | 2026-11-11 | 0
P12-Y3A4 | P12 | Year 3 Rapid Design / Standard-Detail Development | 1.12.2.1 | 2026-11-12 | 2026-12-02 |  |  |  |  | 15 | P12-Y3A3 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2026-11-12 | 2026-12-02 | 2026-11-12 | 2026-12-02 | 0
P12-Y3A5 | P12 | Year 3 Procurement / Task-Order Assignment | 1.12.3.1 | 2026-12-03 | 2027-01-06 |  |  |  |  | 25 | P12-Y3A4 |  | FALSE | TRUE | P12-CA03 | P12-WP031 | Task | Synthetic project assumption — standing on-call/task-order contract | Semantic WBS mapping corrected: procurement/task-order assignment belongs in Procurement | 2026-12-03 | 2027-01-06 | 2026-12-03 | 2027-01-06 | 0
P12-Y3A6 | P12 | Year 3 Field Execution | 1.12.4.1 | 2027-01-07 | 2027-05-12 |  |  |  |  | 90 | P12-Y3A5 |  | FALSE | TRUE | P12-CA04 | P12-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2027-01-07 | 2027-05-12 | 2027-01-07 | 2027-05-12 | 0
P12-MY3DONE | P12 | MY3DONE | 1.12.4.1 | 2027-05-12 | 2027-05-12 |  |  |  |  | 0 | P12-Y3A6 |  | TRUE | FALSE | P12-CA04 | P12-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2027-05-12 | 2027-05-12 | 2027-06-23 | 2027-06-23 | 30
P12-Y3A7 | P12 | Year 3 Verification / Acceptance | 1.12.5.1 | 2027-05-13 | 2027-06-02 |  |  |  |  | 15 | P12-Y3A6 |  | FALSE | TRUE | P12-CA05 | P12-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2027-05-13 | 2027-06-02 | 2027-05-13 | 2027-06-02 | 0
P12-Y3A8 | P12 | Year 3 Closeout | 1.12.6.1 | 2027-06-03 | 2027-06-23 |  |  |  |  | 15 | P12-Y3A7 |  | FALSE | TRUE | P12-CA06 | P12-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2027-06-03 | 2027-06-23 | 2027-06-03 | 2027-06-23 | 0
P12-MPROGCLOSE | P12 | MPROGCLOSE | 1.12.6.1 | 2027-06-23 | 2027-06-23 |  |  |  |  | 0 | P12-Y3A8 |  | TRUE | TRUE | P12-CA06 | P12-WP061 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: program close milestone belongs in Closeout | 2027-06-23 | 2027-06-23 | 2027-06-23 | 2027-06-23 | 0

## 04_MONTHLY_COSTS
Monthly Planned Value (PV) — approved HWSD synthetic cost baseline
Monthly PV is budgeted scheduled work, not cash or actual progress. Actual/committed/forecast columns intentionally blank. Detail: COST_MONTHLY_PV_DETAIL.
month | project_id | baseline_monthly | baseline_cumulative | actual_monthly | actual_cumulative | committed_cost | forecast_remaining | forecast_at_completion
2025-01-01 | P01 | 285455 | 285455
2025-01-01 | P02 | 0 | 0
2025-01-01 | P03 | 508515 | 508515
2025-01-01 | P04 | 0 | 0
2025-01-01 | P05 | 0 | 0
2025-01-01 | P06 | 0 | 0
2025-01-01 | P07 | 0 | 0
2025-01-01 | P08 | 0 | 0
2025-01-01 | P09 | 0 | 0
2025-01-01 | P10 | 0 | 0
2025-01-01 | P11 | 0 | 0
2025-01-01 | P12 | 38556 | 38556
2025-02-01 | P01 | 341621 | 627076
2025-02-01 | P02 | 745140 | 745140
2025-02-01 | P03 | 289681 | 798196
2025-02-01 | P04 | 0 | 0
2025-02-01 | P05 | 0 | 0
2025-02-01 | P06 | 0 | 0
2025-02-01 | P07 | 0 | 0
2025-02-01 | P08 | 0 | 0
2025-02-01 | P09 | 0 | 0
2025-02-01 | P10 | 0 | 0
2025-02-01 | P11 | 0 | 0
2025-02-01 | P12 | 33558 | 72114
2025-03-01 | P01 | 170323.38 | 797399.38
2025-03-01 | P02 | 269676 | 1014816
2025-03-01 | P03 | 153468 | 951664
2025-03-01 | P04 | 0 | 0
2025-03-01 | P05 | 189440 | 189440
2025-03-01 | P06 | 0 | 0
2025-03-01 | P07 | 0 | 0
2025-03-01 | P08 | 0 | 0
2025-03-01 | P09 | 0 | 0
2025-03-01 | P10 | 0 | 0
2025-03-01 | P11 | 0 | 0
2025-03-01 | P12 | 50694 | 122808
2025-04-01 | P01 | 232063.62 | 1029463
2025-04-01 | P02 | 327660.58 | 1342476.58
2025-04-01 | P03 | 282576 | 1234240
2025-04-01 | P04 | 0 | 0
2025-04-01 | P05 | 261960 | 451400
2025-04-01 | P06 | 0 | 0
2025-04-01 | P07 | 0 | 0
2025-04-01 | P08 | 0 | 0
2025-04-01 | P09 | 0 | 0
2025-04-01 | P10 | 0 | 0
2025-04-01 | P11 | 112640 | 112640
2025-04-01 | P12 | 77112 | 199920
2025-05-01 | P01 | 363093.56 | 1392556.56
2025-05-01 | P02 | 340963.42 | 1683440
2025-05-01 | P03 | 332108 | 1566348
2025-05-01 | P04 | 0 | 0
2025-05-01 | P05 | 284900 | 736300
2025-05-01 | P06 | 0 | 0
2025-05-01 | P07 | 0 | 0
2025-05-01 | P08 | 0 | 0
2025-05-01 | P09 | 0 | 0
2025-05-01 | P10 | 0 | 0
2025-05-01 | P11 | 72960 | 185600
2025-05-01 | P12 | 201823.92 | 401743.92
2025-06-01 | P01 | 730133.44 | 2122690
2025-06-01 | P02 | 1014992 | 2698432
2025-06-01 | P03 | 273779.28 | 1840127.28
2025-06-01 | P04 | 205425 | 205425
2025-06-01 | P05 | 302290 | 1038590
2025-06-01 | P06 | 0 | 0
2025-06-01 | P07 | 0 | 0
2025-06-01 | P08 | 0 | 0
2025-06-01 | P09 | 0 | 0
2025-06-01 | P10 | 0 | 0
2025-06-01 | P11 | 100800 | 286400
2025-06-01 | P12 | 253231.86 | 654975.78
2025-07-01 | P01 | 1939392 | 4062082
2025-07-01 | P02 | 792000 | 3490432
2025-07-01 | P03 | 408300.7 | 2248427.98
2025-07-01 | P04 | 94325 | 299750
2025-07-01 | P05 | 431280.1 | 1469870.1
2025-07-01 | P06 | 0 | 0
2025-07-01 | P07 | 0 | 0
2025-07-01 | P08 | 0 | 0
2025-07-01 | P09 | 0 | 0
2025-07-01 | P10 | 0 | 0
2025-07-01 | P11 | 142080 | 428480
2025-07-01 | P12 | 277349.18 | 932324.96
2025-08-01 | P01 | 575424 | 4637506
2025-08-01 | P02 | 842688 | 4333120
2025-08-01 | P03 | 456614.59 | 2705042.57
2025-08-01 | P04 | 94967 | 394717
2025-08-01 | P05 | 1395923.65 | 2865793.75
2025-08-01 | P06 | 150420 | 150420
2025-08-01 | P07 | 0 | 0
2025-08-01 | P08 | 0 | 0
2025-08-01 | P09 | 0 | 0
2025-08-01 | P10 | 0 | 0
2025-08-01 | P11 | 460598.32 | 889078.32
2025-08-01 | P12 | 253231.86 | 1185556.82
2025-09-01 | P01 | 575424 | 5212930
2025-09-01 | P02 | 266112 | 4599232
2025-09-01 | P03 | 856826.48 | 3561869.05
2025-09-01 | P04 | 252495.5 | 647212.5
2025-09-01 | P05 | 939560.81 | 3805354.56
2025-09-01 | P06 | 288765 | 439185
2025-09-01 | P07 | 0 | 0
2025-09-01 | P08 | 0 | 0
2025-09-01 | P09 | 0 | 0
2025-09-01 | P10 | 0 | 0
2025-09-01 | P11 | 681255.15 | 1570333.47
2025-09-01 | P12 | 156763.18 | 1342320
2025-10-01 | P01 | 1069966 | 6282896
2025-10-01 | P02 | 779328 | 5378560
2025-10-01 | P03 | 1086055.35 | 4647924.4
2025-10-01 | P04 | 182630.65 | 829843.15
2025-10-01 | P05 | 1487064.44 | 5292419
2025-10-01 | P06 | 161115.4 | 600300.4
2025-10-01 | P07 | 110700 | 110700
2025-10-01 | P08 | 0 | 0
2025-10-01 | P09 | 0 | 0
2025-10-01 | P10 | 0 | 0
2025-10-01 | P11 | 442088.64 | 2012422.11
2025-10-01 | P12 | 90576 | 1432896
2025-11-01 | P01 | 895104 | 7178000
2025-11-01 | P02 | 1985702.4 | 7364262.4
2025-11-01 | P03 | 816657.1 | 5464581.5
2025-11-01 | P04 | 557746.5 | 1387589.65
2025-11-01 | P05 | 1582531 | 6874950
2025-11-01 | P06 | 300495.6 | 900796
2025-11-01 | P07 | 128535 | 239235
2025-11-01 | P08 | 0 | 0
2025-11-01 | P09 | 0 | 0
2025-11-01 | P10 | 0 | 0
2025-11-01 | P11 | 497222.22 | 2509644.33
2025-11-01 | P12 | 44676 | 1477572
2025-12-01 | P01 | 222000 | 7400000
2025-12-01 | P02 | 263577.6 | 7627840
2025-12-01 | P03 | 1871540 | 7336121.5
2025-12-01 | P04 | 1036041.34 | 2423630.99
2025-12-01 | P05 | 1780659.68 | 8655609.68
2025-12-01 | P06 | 837717.34 | 1738513.34
2025-12-01 | P07 | 127988.58 | 367223.58
2025-12-01 | P08 | 122820 | 122820
2025-12-01 | P09 | 0 | 0
2025-12-01 | P10 | 0 | 0
2025-12-01 | P11 | 429555.67 | 2939200
2025-12-01 | P12 | 51408 | 1528980
2026-01-01 | P01 | 0 | 7400000
2026-01-01 | P02 | 528000 | 8155840
2026-01-01 | P03 | 426300 | 7762421.5
2026-01-01 | P04 | 846899.01 | 3270530
2026-01-01 | P05 | 1038292.52 | 9693902.2
2026-01-01 | P06 | 499657.82 | 2238171.16
2026-01-01 | P07 | 260418.42 | 627642
2026-01-01 | P08 | 212173.3 | 334993.3
2026-01-01 | P09 | 0 | 0
2026-01-01 | P10 | 0 | 0
2026-01-01 | P11 | 145600 | 3084800
2026-01-01 | P12 | 71604 | 1600584
2026-02-01 | P01 | 0 | 7400000
2026-02-01 | P02 | 644160 | 8800000
2026-02-01 | P03 | 2297840.5 | 10060262
2026-02-01 | P04 | 866571 | 4137101
2026-02-01 | P05 | 347732.8 | 10041635
2026-02-01 | P06 | 470976.94 | 2709148.1
2026-02-01 | P07 | 276640.6 | 904282.6
2026-02-01 | P08 | 143423.35 | 478416.65
2026-02-01 | P09 | 175500 | 175500
2026-02-01 | P10 | 0 | 0
2026-02-01 | P11 | 86400 | 3171200
2026-02-01 | P12 | 84456 | 1685040
2026-03-01 | P01 | 0 | 7400000
2026-03-01 | P02 | 0 | 8800000
2026-03-01 | P03 | 1414313 | 11474575
2026-03-01 | P04 | 1197899 | 5335000
2026-03-01 | P05 | 244200 | 10285835
2026-03-01 | P06 | 346948.9 | 3056097
2026-03-01 | P07 | 906605.4 | 1810888
2026-03-01 | P08 | 285169.35 | 763586
2026-03-01 | P09 | 164580 | 340080
2026-03-01 | P10 | 0 | 0
2026-03-01 | P11 | 28800 | 3200000
2026-03-01 | P12 | 290495.86 | 1975535.86
2026-04-01 | P01 | 0 | 7400000
2026-04-01 | P02 | 0 | 8800000
2026-04-01 | P03 | 1970452.96 | 13445027.96
2026-04-01 | P04 | 165000 | 5500000
2026-04-01 | P05 | 481165 | 10767000
2026-04-01 | P06 | 867301.3 | 3923398.3
2026-04-01 | P07 | 144976 | 1955864
2026-04-01 | P08 | 305184.92 | 1068770.92
2026-04-01 | P09 | 137280 | 477360
2026-04-01 | P10 | 66600 | 66600
2026-04-01 | P11 | 0 | 3200000
2026-04-01 | P12 | 341087.78 | 2316623.64
2026-05-01 | P01 | 0 | 7400000
2026-05-01 | P02 | 0 | 8800000
2026-05-01 | P03 | 1292580.37 | 14737608.33
2026-05-01 | P04 | 0 | 5500000
2026-05-01 | P05 | 333000 | 11100000
2026-05-01 | P06 | 353390.01 | 4276788.31
2026-05-01 | P07 | 708152 | 2664016
2026-05-01 | P08 | 296098.08 | 1364869
2026-05-01 | P09 | 86666.65 | 564026.65
2026-05-01 | P10 | 221260 | 287860
2026-05-01 | P11 | 0 | 3200000
2026-05-01 | P12 | 325583.79 | 2642207.43
2026-06-01 | P01 | 0 | 7400000
2026-06-01 | P02 | 0 | 8800000
2026-06-01 | P03 | 1650421.58 | 16388029.91
2026-06-01 | P04 | 0 | 5500000
2026-06-01 | P05 | 0 | 11100000
2026-06-01 | P06 | 292239.3 | 4569027.61
2026-06-01 | P07 | 325157 | 2989173
2026-06-01 | P08 | 226348.6 | 1591217.6
2026-06-01 | P09 | 199749.31 | 763775.96
2026-06-01 | P10 | 451215 | 739075
2026-06-01 | P11 | 0 | 3200000
2026-06-01 | P12 | 341087.78 | 2983295.21
2026-07-01 | P01 | 0 | 7400000
2026-07-01 | P02 | 0 | 8800000
2026-07-01 | P03 | 480284.59 | 16868314.5
2026-07-01 | P04 | 0 | 5500000
2026-07-01 | P05 | 0 | 11100000
2026-07-01 | P06 | 628678.27 | 5197705.88
2026-07-01 | P07 | 95667 | 3084840
2026-07-01 | P08 | 209457.6 | 1800675.2
2026-07-01 | P09 | 292864.04 | 1056640
2026-07-01 | P10 | 268484.9 | 1007559.9
2026-07-01 | P11 | 0 | 3200000
2026-07-01 | P12 | 170544.79 | 3153840
2026-08-01 | P01 | 0 | 7400000
2026-08-01 | P02 | 0 | 8800000
2026-08-01 | P03 | 499888.5 | 17368203
2026-08-01 | P04 | 0 | 5500000
2026-08-01 | P05 | 0 | 11100000
2026-08-01 | P06 | 575173.94 | 5772879.82
2026-08-01 | P07 | 972110 | 4056950
2026-08-01 | P08 | 633905.7 | 2434580.9
2026-08-01 | P09 | 1098746.3 | 2155386.3
2026-08-01 | P10 | 470099.5 | 1477659.4
2026-08-01 | P11 | 0 | 3200000
2026-08-01 | P12 | 117504 | 3271344
2026-09-01 | P01 | 0 | 7400000
2026-09-01 | P02 | 0 | 8800000
2026-09-01 | P03 | 991118 | 18359321
2026-09-01 | P04 | 0 | 5500000
2026-09-01 | P05 | 0 | 11100000
2026-09-01 | P06 | 334258.18 | 6107138
2026-09-01 | P07 | 43050 | 4100000
2026-09-01 | P08 | 840740.5 | 3275321.4
2026-09-01 | P09 | 1043774.55 | 3199160.85
2026-09-01 | P10 | 909506.6 | 2387166
2026-09-01 | P11 | 0 | 3200000
2026-09-01 | P12 | 47736 | 3319080
2026-10-01 | P01 | 0 | 7400000
2026-10-01 | P02 | 0 | 8800000
2026-10-01 | P03 | 446599 | 18805920
2026-10-01 | P04 | 0 | 5500000
2026-10-01 | P05 | 0 | 11100000
2026-10-01 | P06 | 332862 | 6440000
2026-10-01 | P07 | 0 | 4100000
2026-10-01 | P08 | 568099.6 | 3843421
2026-10-01 | P09 | 1165721.15 | 4364882
2026-10-01 | P10 | 156954 | 2544120
2026-10-01 | P11 | 0 | 3200000
2026-10-01 | P12 | 51408 | 3370488
2026-11-01 | P01 | 0 | 7400000
2026-11-01 | P02 | 0 | 8800000
2026-11-01 | P03 | 487200 | 19293120
2026-11-01 | P04 | 0 | 5500000
2026-11-01 | P05 | 0 | 11100000
2026-11-01 | P06 | 253000 | 6693000
2026-11-01 | P07 | 0 | 4100000
2026-11-01 | P08 | 414000 | 4257421
2026-11-01 | P09 | 1097525.8 | 5462407.8
2026-11-01 | P10 | 99456 | 2643576
2026-11-01 | P11 | 0 | 3200000
2026-11-01 | P12 | 69768 | 3440256
2026-12-01 | P01 | 0 | 7400000
2026-12-01 | P02 | 0 | 8800000
2026-12-01 | P03 | 824180 | 20117300
2026-12-01 | P04 | 0 | 5500000
2026-12-01 | P05 | 0 | 11100000
2026-12-01 | P06 | 207000 | 6900000
2026-12-01 | P07 | 0 | 4100000
2026-12-01 | P08 | 294279 | 4551700
2026-12-01 | P09 | 1074527.2 | 6536935
2026-12-01 | P10 | 165673 | 2809249
2026-12-01 | P11 | 0 | 3200000
2026-12-01 | P12 | 124848 | 3565104
2027-01-01 | P01 | 0 | 7400000
2027-01-01 | P02 | 0 | 8800000
2027-01-01 | P03 | 182700 | 20300000
2027-01-01 | P04 | 0 | 5500000
2027-01-01 | P05 | 0 | 11100000
2027-01-01 | P06 | 0 | 6900000
2027-01-01 | P07 | 0 | 4100000
2027-01-01 | P08 | 48300 | 4600000
2027-01-01 | P09 | 419328 | 6956263
2027-01-01 | P10 | 99456 | 2908705
2027-01-01 | P11 | 0 | 3200000
2027-01-01 | P12 | 292943.83 | 3858047.83
2027-02-01 | P01 | 0 | 7400000
2027-02-01 | P02 | 0 | 8800000
2027-02-01 | P03 | 0 | 20300000
2027-02-01 | P04 | 0 | 5500000
2027-02-01 | P05 | 0 | 11100000
2027-02-01 | P06 | 0 | 6900000
2027-02-01 | P07 | 0 | 4100000
2027-02-01 | P08 | 0 | 4600000
2027-02-01 | P09 | 761837 | 7718100
2027-02-01 | P10 | 101354 | 3010059
2027-02-01 | P11 | 0 | 3200000
2027-02-01 | P12 | 310079.8 | 4168127.63
2027-03-01 | P01 | 0 | 7400000
2027-03-01 | P02 | 0 | 8800000
2027-03-01 | P03 | 0 | 20300000
2027-03-01 | P04 | 0 | 5500000
2027-03-01 | P05 | 0 | 11100000
2027-03-01 | P06 | 0 | 6900000
2027-03-01 | P07 | 0 | 4100000
2027-03-01 | P08 | 0 | 4600000
2027-03-01 | P09 | 81900 | 7800000
2027-03-01 | P10 | 118545.18 | 3128604.18
2027-03-01 | P11 | 0 | 3200000
2027-03-01 | P12 | 356591.77 | 4524719.4
2027-04-01 | P01 | 0 | 7400000
2027-04-01 | P02 | 0 | 8800000
2027-04-01 | P03 | 0 | 20300000
2027-04-01 | P04 | 0 | 5500000
2027-04-01 | P05 | 0 | 11100000
2027-04-01 | P06 | 0 | 6900000
2027-04-01 | P07 | 0 | 4100000
2027-04-01 | P08 | 0 | 4600000
2027-04-01 | P09 | 0 | 7800000
2027-04-01 | P10 | 108896.32 | 3237500.5
2027-04-01 | P11 | 0 | 3200000
2027-04-01 | P12 | 341087.78 | 4865807.18
2027-05-01 | P01 | 0 | 7400000
2027-05-01 | P02 | 0 | 8800000
2027-05-01 | P03 | 0 | 20300000
2027-05-01 | P04 | 0 | 5500000
2027-05-01 | P05 | 0 | 11100000
2027-05-01 | P06 | 0 | 6900000
2027-05-01 | P07 | 0 | 4100000
2027-05-01 | P08 | 0 | 4600000
2027-05-01 | P09 | 0 | 7800000
2027-05-01 | P10 | 186088.5 | 3423589
2027-05-01 | P11 | 0 | 3200000
2027-05-01 | P12 | 124032.82 | 4989840
2027-06-01 | P01 | 0 | 7400000
2027-06-01 | P02 | 0 | 8800000
2027-06-01 | P03 | 0 | 20300000
2027-06-01 | P04 | 0 | 5500000
2027-06-01 | P05 | 0 | 11100000
2027-06-01 | P06 | 0 | 6900000
2027-06-01 | P07 | 0 | 4100000
2027-06-01 | P08 | 0 | 4600000
2027-06-01 | P09 | 0 | 7800000
2027-06-01 | P10 | 82706 | 3506295
2027-06-01 | P11 | 0 | 3200000
2027-06-01 | P12 | 110160 | 5100000
2027-07-01 | P01 | 0 | 7400000
2027-07-01 | P02 | 0 | 8800000
2027-07-01 | P03 | 0 | 20300000
2027-07-01 | P04 | 0 | 5500000
2027-07-01 | P05 | 0 | 11100000
2027-07-01 | P06 | 0 | 6900000
2027-07-01 | P07 | 0 | 4100000
2027-07-01 | P08 | 0 | 4600000
2027-07-01 | P09 | 0 | 7800000
2027-07-01 | P10 | 160405 | 3666700
2027-07-01 | P11 | 0 | 3200000
2027-07-01 | P12 | 0 | 5100000
2027-08-01 | P01 | 0 | 7400000
2027-08-01 | P02 | 0 | 8800000
2027-08-01 | P03 | 0 | 20300000
2027-08-01 | P04 | 0 | 5500000
2027-08-01 | P05 | 0 | 11100000
2027-08-01 | P06 | 0 | 6900000
2027-08-01 | P07 | 0 | 4100000
2027-08-01 | P08 | 0 | 4600000
2027-08-01 | P09 | 0 | 7800000
2027-08-01 | P10 | 33300 | 3700000
2027-08-01 | P11 | 0 | 3200000
2027-08-01 | P12 | 0 | 5100000
2027-09-01 | P01 | 0 | 7400000
2027-09-01 | P02 | 0 | 8800000
2027-09-01 | P03 | 0 | 20300000
2027-09-01 | P04 | 0 | 5500000
2027-09-01 | P05 | 0 | 11100000
2027-09-01 | P06 | 0 | 6900000
2027-09-01 | P07 | 0 | 4100000
2027-09-01 | P08 | 0 | 4600000
2027-09-01 | P09 | 0 | 7800000
2027-09-01 | P10 | 0 | 3700000
2027-09-01 | P11 | 0 | 3200000
2027-09-01 | P12 | 0 | 5100000
2027-10-01 | P01 | 0 | 7400000
2027-10-01 | P02 | 0 | 8800000
2027-10-01 | P03 | 0 | 20300000
2027-10-01 | P04 | 0 | 5500000
2027-10-01 | P05 | 0 | 11100000
2027-10-01 | P06 | 0 | 6900000
2027-10-01 | P07 | 0 | 4100000
2027-10-01 | P08 | 0 | 4600000
2027-10-01 | P09 | 0 | 7800000
2027-10-01 | P10 | 0 | 3700000
2027-10-01 | P11 | 0 | 3200000
2027-10-01 | P12 | 0 | 5100000
2027-11-01 | P01 | 0 | 7400000
2027-11-01 | P02 | 0 | 8800000
2027-11-01 | P03 | 0 | 20300000
2027-11-01 | P04 | 0 | 5500000
2027-11-01 | P05 | 0 | 11100000
2027-11-01 | P06 | 0 | 6900000
2027-11-01 | P07 | 0 | 4100000
2027-11-01 | P08 | 0 | 4600000
2027-11-01 | P09 | 0 | 7800000
2027-11-01 | P10 | 0 | 3700000
2027-11-01 | P11 | 0 | 3200000
2027-11-01 | P12 | 0 | 5100000
2027-12-01 | P01 | 0 | 7400000
2027-12-01 | P02 | 0 | 8800000
2027-12-01 | P03 | 0 | 20300000
2027-12-01 | P04 | 0 | 5500000
2027-12-01 | P05 | 0 | 11100000
2027-12-01 | P06 | 0 | 6900000
2027-12-01 | P07 | 0 | 4100000
2027-12-01 | P08 | 0 | 4600000
2027-12-01 | P09 | 0 | 7800000
2027-12-01 | P10 | 0 | 3700000
2027-12-01 | P11 | 0 | 3200000
2027-12-01 | P12 | 0 | 5100000

## 05_EVM
HWSD synthetic EVM snapshot — 2026-03-31
PV approved baseline; EV/AC and commitment inputs simulated, not real HWSD records. EAC is illustrative.
project_id | bac | pv | ev | ac | cv | sv | cpi | spi | eac | etc | vac | rag_status
Project_ID | Status_Date | Scenario_Status | BAC_USD | PV_USD | EV_USD | AC_USD | CV_USD | SV_USD | CPI | SPI | EAC_USD | ETC_USD | VAC_USD | EAC_Method | Data_Provenance
P01 | 2026-03-31 | CLOSED | 7400000.00 | 7400000.00 | 7400000.00 | 7452530.14 | -52530.14 | 0.00 | 0.9930 | 1.0000 | 7452530.14 | 0.00 | -52530.14 | FINAL_INCURRED_COST_ASSUMED_NO_REMAINING_WORK | SYNTHETIC_SCENARIO_V1
P02 | 2026-03-31 | CLOSED | 8800000.00 | 8800000.00 | 8800000.00 | 9754131.20 | -954131.20 | 0.00 | 0.9022 | 1.0000 | 9754131.20 | 0.00 | -954131.20 | FINAL_INCURRED_COST_ASSUMED_NO_REMAINING_WORK | SYNTHETIC_SCENARIO_V1
P03 | 2026-03-31 | ACTIVE | 20300000.00 | 11474575.00 | 10909518.50 | 12087428.39 | -1177909.89 | -565056.50 | 0.9026 | 0.9508 | 22491808.08 | 10404379.69 | -2191808.08 | BAC_DIVIDED_BY_CPI_INDICATIVE | SYNTHETIC_SCENARIO_V1
P04 | 2026-03-31 | ACTIVE | 5500000.00 | 5335000.00 | 4839817.00 | 5447822.80 | -608005.80 | -495183.00 | 0.8884 | 0.9072 | 6190941.81 | 743119.01 | -690941.81 | BAC_DIVIDED_BY_CPI_INDICATIVE | SYNTHETIC_SCENARIO_V1
P05 | 2026-03-31 | ACTIVE | 11100000.00 | 10285835.00 | 10285835.00 | 11920477.64 | -1634642.64 | 0.00 | 0.8629 | 1.0000 | 12864031.15 | 943553.51 | -1764031.15 | BAC_DIVIDED_BY_CPI_INDICATIVE | SYNTHETIC_SCENARIO_V1
P06 | 2026-03-31 | ACTIVE | 6900000.00 | 3056097.00 | 2945024.30 | 3198678.38 | -253654.08 | -111072.70 | 0.9207 | 0.9637 | 7494294.98 | 4295616.60 | -594294.98 | BAC_DIVIDED_BY_CPI_INDICATIVE | SYNTHETIC_SCENARIO_V1
P07 | 2026-03-31 | ACTIVE | 4100000.00 | 1810888.00 | 1835980.00 | 1769659.75 | 66320.25 | 25092.00 | 1.0375 | 1.0139 | 3951897.61 | 2182237.86 | 148102.39 | BAC_DIVIDED_BY_CPI_INDICATIVE | SYNTHETIC_SCENARIO_V1
P08 | 2026-03-31 | ACTIVE | 4600000.00 | 763586.00 | 614362.00 | 670320.66 | -55958.66 | -149224.00 | 0.9165 | 0.8046 | 5018987.24 | 4348666.58 | -418987.24 | BAC_DIVIDED_BY_CPI_INDICATIVE | SYNTHETIC_SCENARIO_V1
P09 | 2026-03-31 | EARLY | 7800000.00 | 340080.00 | 315120.00 | 324573.60 | -9453.60 | -24960.00 | 0.9709 | 0.9266 | 8034000.00 | 7709426.40 | -234000.00 | BAC_DIVIDED_BY_CPI_INDICATIVE | SYNTHETIC_SCENARIO_V1
P10 | 2026-03-31 | FUTURE | 3700000.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |  |  | 3700000.00 | 3700000.00 | 0.00 | BAC_UNCHANGED_NOT_PERFORMANCE_FORECAST | SYNTHETIC_SCENARIO_V1
P11 | 2026-03-31 | CLOSED | 3200000.00 | 3200000.00 | 3200000.00 | 3047665.78 | 152334.22 | 0.00 | 1.0500 | 1.0000 | 3047665.78 | 0.00 | 152334.22 | FINAL_INCURRED_COST_ASSUMED_NO_REMAINING_WORK | SYNTHETIC_SCENARIO_V1
P12 | 2026-03-31 | STANDING | 5100000.00 | 1975535.86 | 1901643.94 | 2026350.56 | -124706.62 | -73891.92 | 0.9385 | 0.9626 | 5434449.45 | 3408098.89 | -334449.45 | BAC_DIVIDED_BY_CPI_INDICATIVE | SYNTHETIC_SCENARIO_V1
PROGRAM | 2026-03-31 | AGGREGATED | 88500000.00 | 54441596.86 | 53047300.74 | 57699638.90 | -4652338.16 | -1394296.12 | 0.9194 | 0.9744 | 95434737.44 | 37735098.54 | -6934737.44 | SUM_OF_PROJECT_EACS_NOT_PROGRAM_BAC_DIV_CPI | SYNTHETIC_SCENARIO_V1

## 06_RISKS
Risks
Not yet populated - built in Phase 5 (Risk Register). 25-40 risks planned across the program.
risk_id | project_id | risk_category | risk_statement | probability_score | impact_score | inherent_score | owner | response_strategy | mitigation | residual_probability | residual_impact | residual_score | status

## 07_CHANGES
Changes
Not yet populated - built in Phase 6 (Change Control), including the featured $600K / six-week contractor change scenario.
change_id | project_id | change_description | cause | requested_date | approval_status | cost_impact | schedule_impact_days | contingency_drawdown | approved_by

## 08_RESOURCES
Resources
Not yet populated - built in Phase 7 (Staffing / Resource Plan).
month | project_id | role | planned_fte | notes

## 09_VENDORS
Vendors
Not yet populated - built in Phase 7 (Contractor / Vendor Tracker).
vendor_id | vendor_name | role | project_id | contract_value | status | performance_notes

## 10_MILESTONES
Milestones
Not yet populated - built in Phase 8 (Milestone Tracker). 35-50 milestones planned across the program.
milestone_id | project_id | milestone_name | baseline_date | forecast_date | actual_date | variance_days | status

## 11_KPI_THRESHOLDS
Kpi Thresholds
Not yet populated - built in Phase 4, alongside EVM. Defines RAG (Red/Amber/Green) status logic. These are project assumptions, not industry-mandated values.
kpi | green_threshold | amber_threshold | red_threshold

## 12_DASHBOARD_DATA
Dashboard Data
Not yet populated - built in Phase 9 (Power BI Prep). Flattened export tables consumed by the Power BI dashboard.
table_name | description | refreshed_from

## 03_SCHEDULE_RELATIONSHIPS
HWSD — Approved Baseline Dependency Network
498 relationships, including four P03/P08→P10 cross-project interfaces. FS/SS/FF business-day lags; schedule CPM not yet certified.
Relationship_ID | Project_ID | Predecessor_Activity_ID | Successor_Activity_ID | Relationship_Type | Lag_Days | Relationship_Scope | Recovery_Status
R0001 | P01 | P01-A1 | P01-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0002 | P01 | P01-A2 | P01-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0003 | P01 | P01-A3 | P01-A4 | FS | 10 | Within Project | Reconstructed from approved narrative/logic
R0004 | P01 | P01-A3 | P01-A4u | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0005 | P01 | P01-A4 | P01-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0007 | P01 | P01-A4 | P01-A5 | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0008 | P01 | P01-A5 | P01-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0013 | P01 | P01-A7a | P01-A7b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0014 | P01 | P01-A7b | P01-A7c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0015 | P01 | P01-A6 | P01-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0016 | P01 | P01-A7c | P01-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0017 | P01 | P01-A4u | P01-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0018 | P01 | P01-A8 | P01-A9 | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0019 | P01 | P01-A8 | P01-A9b | SS | 20 | Within Project | Reconstructed from approved narrative/logic
R0020 | P01 | P01-A8 | P01-A11 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0021 | P01 | P01-A9 | P01-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0022 | P01 | P01-A9b | P01-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0023 | P01 | P01-A11 | P01-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0024 | P01 | P01-A12 | P01-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0025 | P01 | P01-A10 | P01-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0026 | P01 | P01-M3 | P01-A13 | FS | 0 | Within Project | PROPOSED: completion-gated turnover after accepted substantial completion; replaces early documentation overlap; synthetic recovery, pending approval
R0028 | P01 | P01-A13 | P01-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0029 | P01 | P01-A15 | P01-A14 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0030 | P01 | P01-A14 | P01-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0031 | P02 | P02-A1 | P02-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0032 | P02 | P02-A2 | P02-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0033 | P02 | P02-A3 | P02-A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0035 | P02 | P02-A4 | P02-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0036 | P02 | P02-A4 | P02-A5 | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0037 | P02 | P02-A5 | P02-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0045 | P02 | P02-A7a | P02-A7b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0046 | P02 | P02-A7b | P02-A7c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0047 | P02 | P02-A7c | P02-A7d | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0048 | P02 | P02-A11a | P02-A11b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0049 | P02 | P02-A11b | P02-A11c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0050 | P02 | P02-A11c | P02-A11d | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0051 | P02 | P02-A6 | P02-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0052 | P02 | P02-A6b | P02-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0053 | P02 | P02-A8 | P02-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0054 | P02 | P02-A9 | P02-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0055 | P02 | P02-A7d | P02-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0056 | P02 | P02-A9 | P02-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0057 | P02 | P02-A11d | P02-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0058 | P02 | P02-A6c | P02-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0059 | P02 | P02-A9 | P02-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0060 | P02 | P02-A10 | P02-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0061 | P02 | P02-A12 | P02-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0062 | P02 | P02-A13 | P02-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0063 | P02 | P02-A14 | P02-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0064 | P02 | P02-A15 | P02-A15b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0066 | P02 | P02-A15 | P02-A16 | SS | 5 | Within Project | Reconstructed from approved narrative/logic
R0067 | P02 | P02-A16 | P02-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0068 | P02 | P02-A15b | P02-A17 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0069 | P02 | P02-A17 | P02-M5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0070 | P03 | P03-A1 | P03-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0071 | P03 | P03-A2 | P03-A2b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0072 | P03 | P03-A2b | P03-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0073 | P03 | P03-A3 | P03-A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0074 | P03 | P03-A4 | P03-A5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0075 | P03 | P03-A5 | P03-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0076 | P03 | P03-A6 | P03-A7 | SS | 5 | Within Project | PROPOSED synthetic recovery: Final design overlaps 90%-design review; reconciles 20bd design to published M1 if upstream dates hold.
R0077 | P03 | P03-A7 | P03-M1 | FS | 0 | Within Project | BLOCKED: documented relationship incompatible with existing reconstructed date(s); see QA report
R0078 | P03 | P03-A7 | P03-A7b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0079 | P03 | P03-A7 | P03-A8 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0080 | P03 | P03-A8 | P03-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0081 | P03 | P03-A9 | P03-A9b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0082 | P03 | P03-A9b | P03-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0083 | P03 | P03-A7b | P03-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0084 | P03 | P03-M2 | P03-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0085 | P03 | P03-M2 | P03-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0086 | P03 | P03-M2 | P03-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0087 | P03 | P03-M2 | P03-A21 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0088 | P03 | P03-A11 | P03-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0089 | P03 | P03-A12 | P03-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0090 | P03 | P03-A13 | P03-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0091 | P03 | P03-A14 | P03-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0092 | P03 | P03-A16 | P03-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0093 | P03 | P03-A17 | P03-A18 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0094 | P03 | P03-A18 | P03-A19 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0095 | P03 | P03-A21 | P03-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0096 | P03 | P03-A22 | P03-A23 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0097 | P03 | P03-A15 | P03-A20 | SS | 20 | Within Project | Reconstructed from approved narrative/logic
R0098 | P03 | P03-A19 | P03-A20 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0099 | P03 | P03-A15 | P03-A24 | SS | 30 | Within Project | Reconstructed from approved narrative/logic
R0100 | P03 | P03-A23 | P03-A24 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0101 | P03 | P03-A15 | P03-A25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0102 | P03 | P03-A20 | P03-A25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0103 | P03 | P03-A15 | P03-A26 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0104 | P03 | P03-A25 | P03-A26 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0105 | P03 | P03-A24 | P03-A26 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0106 | P03 | P03-A26 | P03-A27 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0107 | P03 | P03-A27 | P03-A28 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0108 | P03 | P03-A27 | P03-A29 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0109 | P03 | P03-A28 | P03-A30 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0110 | P03 | P03-A29 | P03-A30 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0111 | P03 | P03-A30 | P03-A31 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0112 | P03 | P03-A30 | P03-A32 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0113 | P03 | P03-A32 | P03-A33 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0114 | P03 | P03-A31 | P03-A33 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0115 | P03 | P03-A14 | P03-M5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0116 | P03 | P03-A26 | P03-M6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0117 | P03 | P03-A27 | P03-M7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0118 | P03 | P03-A28 | P03-M8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0119 | P03 | P03-A30 | P03-M9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0120 | P03 | P03-A30 | P03-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0121 | P03 | P03-A33 | P03-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0122 | P03 | P03-M1 | P03-I-P03-01 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0123 | P03 | P03-A16 | P03-I-P03-02 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0124 | P03 | P03-M6 | P03-I-P03-03 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0125 | P04 | P04-A1 | P04-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0126 | P04 | P04-A2 | P04-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0127 | P04 | P04-A3 | P04-A4 | FS | 10 | Within Project | Reconstructed from approved narrative/logic
R0128 | P04 | P04-A4 | P04-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0129 | P04 | P04-A4 | P04-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0130 | P04 | P04-A4 | P04-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0131 | P04 | P04-A5 | P04-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0132 | P04 | P04-A5b | P04-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0133 | P04 | P04-A5c | P04-M2 | FS | 15 | Within Project | Reconstructed from approved narrative/logic ¦ USER-APPROVED SYNTHETIC POST-GOVERNING-APPROVAL NTP RELEASE HOLD: 15 business days (not recovered original)
R0134 | P04 | P04-A4b | P04-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0135 | P04 | P04-M2 | P04-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0136 | P04 | P04-M2 | P04-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0137 | P04 | P04-A6 | P04-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0138 | P04 | P04-A7 | P04-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0139 | P04 | P04-A8 | P04-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0140 | P04 | P04-A9 | P04-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0141 | P04 | P04-A10 | P04-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0142 | P04 | P04-A11 | P04-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0143 | P04 | P04-A12 | P04-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0144 | P04 | P04-A13 | P04-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0145 | P04 | P04-A14 | P04-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0146 | P04 | P04-A15 | P04-M5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0147 | P04 | P04-A15 | P04-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0148 | P04 | P04-A16 | P04-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0149 | P04 | P04-A16 | P04-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0150 | P04 | P04-A17 | P04-A18 | SS | 5 | Within Project | Recovered by reconciliation to approved M3/M4 dates and published closeout durations
R0151 | P04 | P04-A16 | P04-A18 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0152 | P04 | P04-A18 | P04-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0153 | P05 | P05-A1 | P05-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0154 | P05 | P05-A2 | P05-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0155 | P05 | P05-A3 | P05-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0156 | P05 | P05-A4 | P05-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0157 | P05 | P05-A4 | P05-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0158 | P05 | P05-A4 | P05-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0159 | P05 | P05-A5 | P05-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0160 | P05 | P05-A5b | P05-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0161 | P05 | P05-A5c | P05-M2 | FS | 5 | Within Project | Reconstructed from approved narrative/logic ¦ USER-APPROVED SYNTHETIC POST-GOVERNING-APPROVAL NTP RELEASE HOLD: 5 business days (not recovered original)
R0162 | P05 | P05-A4b | P05-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0163 | P05 | P05-M2 | P05-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0164 | P05 | P05-M2 | P05-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0165 | P05 | P05-A7 | P05-A8 | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0166 | P05 | P05-A7 | P05-A9 | SS | 10 | Within Project | Recovered by reconciliation to approved P05 field milestone dates
R0167 | P05 | P05-M2 | P05-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0168 | P05 | P05-M2 | P05-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0169 | P05 | P05-A6 | P05-A12a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0170 | P05 | P05-A9 | P05-A12a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0171 | P05 | P05-A10 | P05-A12a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0172 | P05 | P05-A11 | P05-A12a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0173 | P05 | P05-A12a | P05-A13a | SS | 20 | Within Project | Reconstructed from approved narrative/logic
R0174 | P05 | P05-A13a | P05-A14a | SS | 20 | Within Project | Reconstructed from approved narrative/logic
R0175 | P05 | P05-A14a | P05-A15a | SS | 20 | Within Project | Reconstructed from approved narrative/logic
R0176 | P05 | P05-A12a | P05-AFIRST | SS | 0 | Within Project | Reconstructed from approved narrative/logic
R0177 | P05 | P05-AFIRST | P05-MFIRST | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0178 | P05 | P05-A12a | P05-A12b | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0179 | P05 | P05-A12b | P05-A12c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0180 | P05 | P05-A13a | P05-A13b | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0181 | P05 | P05-A13b | P05-A13c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0182 | P05 | P05-A14a | P05-A14b | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0183 | P05 | P05-A14b | P05-A14c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0184 | P05 | P05-A15a | P05-A15b | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0185 | P05 | P05-A15b | P05-A15c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0186 | P05 | P05-A12a | P05-M25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0187 | P05 | P05-A13a | P05-M50 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0188 | P05 | P05-A14a | P05-M75 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0189 | P05 | P05-A15a | P05-MTARGET | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0190 | P05 | P05-A12c | P05-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0191 | P05 | P05-A13c | P05-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0192 | P05 | P05-A14c | P05-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0193 | P05 | P05-A15c | P05-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0194 | P05 | P05-A16 | P05-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0195 | P05 | P05-A16 | P05-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0196 | P05 | P05-A17 | P05-A18 | SS | 10 | Within Project | Recovered by reconciliation to approved P05 M4 date and published closeout durations
R0197 | P05 | P05-A18 | P05-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0198 | P06 | P06-A1 | P06-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0199 | P06 | P06-A2 | P06-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0200 | P06 | P06-A3 | P06-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0201 | P06 | P06-A4 | P06-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0202 | P06 | P06-A4 | P06-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0203 | P06 | P06-A4 | P06-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0204 | P06 | P06-A5 | P06-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0205 | P06 | P06-A5b | P06-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0206 | P06 | P06-A5c | P06-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0207 | P06 | P06-A4b | P06-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0208 | P06 | P06-M2 | P06-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0209 | P06 | P06-M2 | P06-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0210 | P06 | P06-M2 | P06-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0211 | P06 | P06-M2 | P06-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0212 | P06 | P06-M2 | P06-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0213 | P06 | P06-A11 | P06-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0214 | P06 | P06-A12 | P06-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0215 | P06 | P06-A7 | P06-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0216 | P06 | P06-A9 | P06-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0217 | P06 | P06-A8 | P06-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0218 | P06 | P06-M2 | P06-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0219 | P06 | P06-A13 | P06-APILOTSTAGE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0220 | P06 | P06-A14 | P06-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0221 | P06 | P06-A15 | P06-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0222 | P06 | P06-APILOTSTAGE | P06-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0223 | P06 | P06-A8 | P06-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0224 | P06 | P06-A6 | P06-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0225 | P06 | P06-A16 | P06-AFIRSTPILOT | SS | 0 | Within Project | Reconstructed from approved narrative/logic
R0226 | P06 | P06-A16 | P06-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0227 | P06 | P06-A17 | P06-MPILOTDONE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0228 | P06 | P06-A14 | P06-MSYSINT | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0229 | P06 | P06-A17 | P06-A18a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0230 | P06 | P06-A17 | P06-A19a | FS | 15 | Within Project | Reconstructed from approved narrative/logic
R0231 | P06 | P06-A17 | P06-A20a | FS | 30 | Within Project | Reconstructed from approved narrative/logic
R0232 | P06 | P06-A17 | P06-A21a | FS | 45 | Within Project | Reconstructed from approved narrative/logic
R0233 | P06 | P06-A18a | P06-A18b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0234 | P06 | P06-A19a | P06-A19b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0235 | P06 | P06-A20a | P06-A20b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0236 | P06 | P06-A21a | P06-A21b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0237 | P06 | P06-A18a | P06-M25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0238 | P06 | P06-A19a | P06-M50 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0239 | P06 | P06-A20a | P06-M75 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0240 | P06 | P06-A21a | P06-MFULL | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0241 | P06 | P06-A18b | P06-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0242 | P06 | P06-A19b | P06-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0243 | P06 | P06-A20b | P06-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0244 | P06 | P06-A21b | P06-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0245 | P06 | P06-A22 | P06-A23 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0246 | P06 | P06-A23 | P06-A24 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0247 | P06 | P06-A24 | P06-A25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0248 | P06 | P06-A25 | P06-A26 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0249 | P06 | P06-A24 | P06-MOPACC | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0250 | P06 | P06-A24 | P06-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0251 | P06 | P06-A26 | P06-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0252 | P07 | P07-A1 | P07-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0253 | P07 | P07-A2 | P07-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0254 | P07 | P07-A3 | P07-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0255 | P07 | P07-A4 | P07-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0256 | P07 | P07-A4 | P07-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0257 | P07 | P07-A4 | P07-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0258 | P07 | P07-A5 | P07-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0259 | P07 | P07-A5b | P07-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0260 | P07 | P07-A5c | P07-M2 | FS | 10 | Within Project | Reconstructed from approved narrative/logic ¦ USER-APPROVED SYNTHETIC POST-GOVERNING-APPROVAL NTP RELEASE HOLD: 10 business days (not recovered original)
R0261 | P07 | P07-A4b | P07-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0262 | P07 | P07-M2 | P07-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0263 | P07 | P07-M2 | P07-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0264 | P07 | P07-M2 | P07-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0265 | P07 | P07-A8 | P07-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0266 | P07 | P07-A6 | P07-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0267 | P07 | P07-A7 | P07-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0268 | P07 | P07-A10 | P07-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0269 | P07 | P07-A9 | P07-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0270 | P07 | P07-A11 | P07-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0271 | P07 | P07-A12 | P07-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0272 | P07 | P07-A13 | P07-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0273 | P07 | P07-A14 | P07-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0274 | P07 | P07-A15 | P07-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0275 | P07 | P07-A14 | P07-MCOMM | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0276 | P07 | P07-A15 | P07-MBAL | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0277 | P07 | P07-A16 | P07-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0278 | P07 | P07-A16 | P07-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0279 | P07 | P07-A17 | P07-A18 | SS | 5 | Within Project | Recovered by reconciliation to approved M3/M4 dates and published closeout durations
R0280 | P07 | P07-A16 | P07-A18 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0281 | P07 | P07-A18 | P07-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0282 | P08 | P08-A1 | P08-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0283 | P08 | P08-A2 | P08-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0284 | P08 | P08-A3 | P08-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0285 | P08 | P08-A4 | P08-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0286 | P08 | P08-A4 | P08-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0287 | P08 | P08-A3 | P08-A7 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0288 | P08 | P08-A4 | P08-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0289 | P08 | P08-A5 | P08-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0290 | P08 | P08-A5b | P08-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0291 | P08 | P08-A5c | P08-M2 | FS | 10 | Within Project | Reconstructed from approved narrative/logic ¦ USER-APPROVED SYNTHETIC POST-GOVERNING-APPROVAL NTP RELEASE HOLD: 10 business days (not recovered original)
R0292 | P08 | P08-A4b | P08-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0293 | P08 | P08-M2 | P08-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0294 | P08 | P08-M2 | P08-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0295 | P08 | P08-M2 | P08-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0296 | P08 | P08-M2 | P08-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0297 | P08 | P08-A8 | P08-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0298 | P08 | P08-A9 | P08-A9fat | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0299 | P08 | P08-A9fat | P08-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0300 | P08 | P08-A8 | P08-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0301 | P08 | P08-A10 | P08-A10fat | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0302 | P08 | P08-A10fat | P08-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0303 | P08 | P08-A14 | P08-MOUTAGE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0304 | P08 | P08-A13 | P08-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0305 | P08 | P08-A11 | P08-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0306 | P08 | P08-A14 | P08-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0307 | P08 | P08-A13 | P08-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0308 | P08 | P08-A12 | P08-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0309 | P08 | P08-A14 | P08-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0310 | P08 | P08-A15 | P08-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0311 | P08 | P08-A16 | P08-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0312 | P08 | P08-A17 | P08-A18 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0313 | P08 | P08-A18 | P08-A19 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0314 | P08 | P08-A19 | P08-A20 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0315 | P08 | P08-A20 | P08-A21 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0316 | P08 | P08-A18 | P08-MSTART | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0317 | P08 | P08-A20 | P08-MOPACC | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0318 | P08 | P08-A21 | P08-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0319 | P08 | P08-A21 | P08-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0320 | P08 | P08-A22 | P08-A23 | SS | 5 | Within Project | Recovered by reconciliation to approved M3/M4 dates and published closeout durations
R0321 | P08 | P08-A21 | P08-A23 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0322 | P08 | P08-A23 | P08-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0323 | P08 | P08-M1 | P08-I-P08-01 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0324 | P08 | P08-A8 | P08-I-P08-02 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0325 | P08 | P08-MSTART | P08-I-P08-03 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0326 | P09 | P09-A1 | P09-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0327 | P09 | P09-A2 | P09-A3a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0328 | P09 | P09-A3a | P09-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0329 | P09 | P09-A3 | P09-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0330 | P09 | P09-A4 | P09-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0331 | P09 | P09-A4 | P09-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0332 | P09 | P09-A4 | P09-A4c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0333 | P09 | P09-A4 | P09-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0334 | P09 | P09-A5 | P09-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0335 | P09 | P09-A5b | P09-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0336 | P09 | P09-A4c | P09-MPERMIT | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0337 | P09 | P09-A5c | P09-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0338 | P09 | P09-A4b | P09-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0339 | P09 | P09-A4c | P09-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0340 | P09 | P09-M2 | P09-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0341 | P09 | P09-M2 | P09-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0342 | P09 | P09-M2 | P09-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0343 | P09 | P09-M2 | P09-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0344 | P09 | P09-A6 | P09-MSPECMOB | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0345 | P09 | P09-A10 | P09-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0346 | P09 | P09-A11 | P09-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0347 | P09 | P09-A6 | P09-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0348 | P09 | P09-A7 | P09-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0349 | P09 | P09-A13 | P09-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0350 | P09 | P09-A12 | P09-A15 | FS | 0 | Within Project | Restored from approved P09 relationship highlight (A14 + A12 -> A15)
R0351 | P09 | P09-A14 | P09-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0352 | P09 | P09-A15 | P09-MCROSSDONE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0353 | P09 | P09-A15 | P09-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0354 | P09 | P09-A15 | P09-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0355 | P09 | P09-A8 | P09-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0356 | P09 | P09-A16 | P09-A18 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0357 | P09 | P09-A17 | P09-A18 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0358 | P09 | P09-A9 | P09-A18 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0359 | P09 | P09-A18 | P09-A19 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0360 | P09 | P09-A19 | P09-MINSERVICE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0361 | P09 | P09-A19 | P09-A20 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0362 | P09 | P09-A20 | P09-A21 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0363 | P09 | P09-A21 | P09-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0364 | P09 | P09-A21 | P09-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0365 | P09 | P09-A22 | P09-A23 | SS | 5 | Within Project | Recovered by reconciliation to approved P09 M3/M4 dates and published closeout durations
R0366 | P09 | P09-A21 | P09-A23 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0367 | P09 | P09-A23 | P09-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0368 | P10 | P10-A1 | P10-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0369 | P10 | P10-A2 | P10-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0370 | P10 | P10-A3 | P10-A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0371 | P10 | P10-A4 | P10-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0372 | P10 | P10-A4 | P10-A6b | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0373 | P10 | P10-A5 | P10-A6 | SS | 10 | Within Project | PROPOSED synthetic recovery: Final controls design overlaps network/cybersecurity coordination; allows approval at reported July 21 if upstream dates hold.
R0374 | P10 | P10-A6b | P10-A6 | SS | 10 | Within Project | PROPOSED synthetic recovery: Final controls design overlaps network/cybersecurity coordination; allows approval at reported July 21 if upstream dates hold.
R0375 | P10 | P10-A6 | P10-M1 | FS | 0 | Within Project | BLOCKED: documented relationship incompatible with existing reconstructed date(s); see QA report
R0376 | P10 | P10-A6 | P10-A7 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0377 | P10 | P10-A7 | P10-A7b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0378 | P10 | P10-A7b | P10-A7c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0379 | P10 | P10-A7c | P10-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0380 | P10 | P10-M2 | P10-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0381 | P10 | P10-M2 | P10-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0382 | P10 | P10-M2 | P10-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0383 | P10 | P10-M2 | P10-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0384 | P10 | P10-M2 | P10-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0385 | P10 | P10-A9 | P10-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0386 | P10 | P10-A10 | P10-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0387 | P10 | P10-A12 | P10-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0388 | P10 | P10-A14 | P10-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0389 | P10 | P10-A15 | P10-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0390 | P10 | P10-A13 | P10-MFAT | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0391 | P10 | P10-A13 | P10-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0392 | P10 | P10-A8 | P10-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0393 | P10 | P10-A16 | P10-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0394 | P10 | P10-A17 | P10-MSITEINSTALL | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0395 | P10 | P10-A17 | P10-A18 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0396 | P10 | P10-A18 | P10-A19 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0397 | P10 | P10-A18 | P10-MIOCHECK | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0398 | P03→P10 | P03-I-P03-02 | P10-IF-01 | FS | 0 | Inter-Project | Reconstructed from approved narrative/logic
R0399 | P08→P10 | P08-I-P08-02 | P10-IF-01 | FS | 0 | Inter-Project | Reconstructed from approved narrative/logic
R0400 | P10 | P10-M1 | P10-IF-01 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0401 | P10 | P10-IF-01 | P10-MIF01 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0402 | P10 | P10-MIF01 | P10-MIF02 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0403 | P10 | P10-A14 | P10-MIF02 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0404 | P10 | P10-A15 | P10-MIF02 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0405 | P10 | P10-MIF02 | P10-A13 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0406 | P03→P10 | P03-I-P03-03 | P10-MIF03 | FS | 0 | Inter-Project | Reconstructed from approved narrative/logic
R0407 | P08→P10 | P08-I-P08-03 | P10-MIF03 | FS | 0 | Inter-Project | Reconstructed from approved narrative/logic
R0408 | P10 | P10-MSITEINSTALL | P10-MIF03 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0409 | P10 | P10-MIOCHECK | P10-MIF03 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0410 | P10 | P10-A19 | P10-MIF03 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0411 | P10 | P10-MIF03 | P10-A20 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0412 | P10 | P10-A20 | P10-A21 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0413 | P10 | P10-A21 | P10-MSAT | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0414 | P10 | P10-A21 | P10-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0415 | P10 | P10-A21 | P10-A23 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0416 | P10 | P10-A22 | P10-A24 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0417 | P10 | P10-A23 | P10-A24 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0418 | P10 | P10-A24 | P10-A25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0419 | P10 | P10-A24 | P10-MCUTOVER | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0420 | P10 | P10-A25 | P10-MOPACC | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0421 | P10 | P10-A25 | P10-A27 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0422 | P10 | P10-A25 | P10-A26 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0423 | P10 | P10-A27 | P10-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0424 | P10 | P10-A26 | P10-A28 | FS | 5 | Within Project | Recovered by reconciliation to approved P10 M4 date; original executable script unavailable
R0425 | P10 | P10-A27 | P10-A28 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0426 | P10 | P10-A28 | P10-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0427 | P11 | P11-A1 | P11-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0428 | P11 | P11-A2 | P11-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0429 | P11 | P11-A3 | P11-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0430 | P11 | P11-A4 | P11-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0431 | P11 | P11-A4 | P11-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0432 | P11 | P11-A5 | P11-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0433 | P11 | P11-A5b | P11-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0434 | P11 | P11-A5c | P11-M2 | FS | 5 | Within Project | Reconstructed from approved narrative/logic ¦ USER-APPROVED SYNTHETIC POST-GOVERNING-APPROVAL NTP RELEASE HOLD: 5 business days (not recovered original)
R0435 | P11 | P11-M2 | P11-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0436 | P11 | P11-M2 | P11-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0437 | P11 | P11-M2 | P11-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0438 | P11 | P11-M2 | P11-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0439 | P11 | P11-M2 | P11-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0440 | P11 | P11-A6 | P11-B1inst | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0441 | P11 | P11-A7 | P11-B1inst | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0442 | P11 | P11-A8 | P11-B1inst | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0443 | P11 | P11-A9 | P11-B1inst | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0444 | P11 | P11-A10 | P11-B1inst | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0445 | P11 | P11-B1inst | P11-B2inst | SS | 25 | Within Project | Reconstructed from approved narrative/logic
R0446 | P11 | P11-B1inst | P11-AFIRST | SS | 0 | Within Project | Reconstructed from approved narrative/logic
R0447 | P11 | P11-AFIRST | P11-MFIRST | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0448 | P11 | P11-B1inst | P11-MBATCH1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0449 | P11 | P11-B2inst | P11-MTARGET | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0450 | P11 | P11-B1inst | P11-B1test | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0451 | P11 | P11-B1inst | P11-B1rest | SS | 20 | Within Project | Recovered by milestone/duration reconciliation; original executable script unavailable
R0452 | P11 | P11-B1rest | P11-B1gis | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0453 | P11 | P11-B2inst | P11-B2test | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0454 | P11 | P11-B2inst | P11-B2rest | SS | 20 | Within Project | Recovered by milestone/duration reconciliation; original executable script unavailable
R0455 | P11 | P11-B2rest | P11-B2gis | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0456 | P11 | P11-B1gis | P11-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0457 | P11 | P11-B2gis | P11-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0458 | P11 | P11-A11 | P11-MISOVERIFY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0459 | P11 | P11-A11 | P11-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0460 | P11 | P11-A11 | P11-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0461 | P11 | P11-A12 | P11-A13 | SS | 5 | Within Project | Recovered by reconciliation to approved P11 M4 date and published closeout durations
R0462 | P11 | P11-A13 | P11-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0463 | P12 | P12-Y1A1 | P12-Y1A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0464 | P12 | P12-Y1A2 | P12-Y1A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0465 | P12 | P12-Y1A3 | P12-Y1A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0466 | P12 | P12-Y1A4 | P12-Y1A5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0467 | P12 | P12-Y1A5 | P12-Y1A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0468 | P12 | P12-Y1A6 | P12-Y1A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0469 | P12 | P12-Y1A7 | P12-Y1A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0470 | P12 | P12-Y1A1 | P12-MPLANY1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0471 | P12 | P12-Y1A6 | P12-MY1DONE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0472 | P12 | P12-Y1A8 | P12-Y2A1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0473 | P12 | P12-Y2A1 | P12-Y2A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0474 | P12 | P12-Y2A2 | P12-Y2A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0475 | P12 | P12-Y2A3 | P12-Y2A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0476 | P12 | P12-Y2A4 | P12-Y2A5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0477 | P12 | P12-Y2A5 | P12-Y2A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0478 | P12 | P12-Y2A6 | P12-Y2A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0479 | P12 | P12-Y2A7 | P12-Y2A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0480 | P12 | P12-Y2A1 | P12-MPLANY2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0481 | P12 | P12-Y2A6 | P12-MY2DONE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0482 | P12 | P12-Y2A8 | P12-Y3A1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0483 | P12 | P12-Y3A1 | P12-Y3A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0484 | P12 | P12-Y3A2 | P12-Y3A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0485 | P12 | P12-Y3A3 | P12-Y3A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0486 | P12 | P12-Y3A4 | P12-Y3A5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0487 | P12 | P12-Y3A5 | P12-Y3A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0488 | P12 | P12-Y3A6 | P12-Y3A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0489 | P12 | P12-Y3A7 | P12-Y3A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0490 | P12 | P12-Y3A1 | P12-MPLANY3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0491 | P12 | P12-Y3A6 | P12-MY3DONE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0492 | P12 | P12-Y3A8 | P12-MPROGCLOSE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0493 | P01 | P01-A4 | P01-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0494 | P01 | P01-A5b | P01-M2 | FS | 10 | Within Project | Reconstructed from approved narrative/logic
R0495 | P01 | P01-A4b | P01-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0496 | P01 | P01-A15 | P01-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0497 | P02 | P02-A4 | P02-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0498 | P02 | P02-A5b | P02-M2 | FS | 10 | Within Project | Reconstructed from approved narrative/logic
R0499 | P02 | P02-A4b | P02-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0500 | P02 | P02-A8 | P02-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0501 | P02 | P02-A15b | P02-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0502 | P06 | P06-MSYSINT | P06-MPILOTREADY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0503 | P06 | P06-A15 | P06-MPILOTREADY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0504 | P06 | P06-APILOTSTAGE | P06-MPILOTREADY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0505 | P06 | P06-A8 | P06-MPILOTREADY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0506 | P06 | P06-A6 | P06-MPILOTREADY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0507 | P06 | P06-MPILOTREADY | P06-A16 | FS | 0 | Within Project | BLOCKED: documented relationship incompatible with existing reconstructed date(s); see QA report
R0508 | P06 | P06-AFIRSTPILOT | P06-MFIRSTPILOT | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0509 | P01 | P01-M2 | P01-A6 | FS | 0 | Within Project | PROPOSED synthetic recovery: Contractor mobilization/submittals cannot begin before award/NTP; procurement and mobilization run in parallel.
R0510 | P01 | P01-M2 | P01-A7a | FS | 0 | Within Project | PROPOSED synthetic recovery: Contractor mobilization/submittals cannot begin before award/NTP; procurement and mobilization run in parallel.
R0511 | P02 | P02-M2 | P02-A6 | FS | 0 | Within Project | PROPOSED synthetic recovery: Contractor mobilization/submittals cannot begin before award/NTP; procurement and mobilization run in parallel.
R0512 | P02 | P02-M2 | P02-A7a | FS | 0 | Within Project | PROPOSED synthetic recovery: Contractor mobilization/submittals cannot begin before award/NTP; procurement and mobilization run in parallel.
R0513 | P02 | P02-M2 | P02-A11a | FS | 0 | Within Project | PROPOSED synthetic recovery: Contractor mobilization/submittals cannot begin before award/NTP; procurement and mobilization run in parallel.

## SCHEDULE_VERSION_LOG
HWSD — Schedule Version & Approval History
Previous approved coordination dates are retained; synthetic recovery authorized by user. P12 standing-work scope is excluded from ordinary substantial-completion comparisons.
Project_ID | Version | Status | Version_Basis | Start | Finish | Change_Calendar_Days | Approval_Note
P01 | Prior coordinated baseline | SUPERSEDED | Original approved coordinated scheduling version | 2025-01-02 | 2026-01-05 | 0 | Historical date comparator; no baseline overwrite
P01 | Synthetic recovery baseline | APPROVED | Reconstructed network with accepted documented assumptions | 2025-01-02 | 2025-12-29 | -7 | User-approved synthetic baseline + release holds; CPM/float calculated, all approved finish dates retained
P02 | Prior coordinated baseline | SUPERSEDED | Original approved coordinated scheduling version | 2025-02-03 | 2026-04-01 | 0 | Historical date comparator; no baseline overwrite
P02 | Synthetic recovery baseline | APPROVED | Reconstructed network with accepted documented assumptions | 2025-02-03 | 2026-02-25 | -35 | User-approved synthetic baseline + release holds; CPM/float calculated, all approved finish dates retained
P03 | Prior coordinated baseline | SUPERSEDED | Original approved coordinated scheduling version | 2025-01-02 | 2027-02-17 | 0 | Historical date comparator; no baseline overwrite
P03 | Synthetic recovery baseline | APPROVED | Reconstructed network with accepted documented assumptions | 2025-01-02 | 2027-01-27 | -21 | User-approved synthetic baseline + release holds; CPM/float calculated, all approved finish dates retained
P04 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-06-02 | 2026-04-24 | 0 | Historical date comparator; no baseline overwrite
P04 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-06-02 | 2026-04-24 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P05 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-03-03 | 2026-05-15 | 0 | Historical date comparator; no baseline overwrite
P05 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-03-03 | 2026-05-15 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P06 | Prior coordinated baseline | SUPERSEDED | Original approved coordinated scheduling version | 2025-08-01 | 2027-01-07 | 0 | Historical date comparator; no baseline overwrite
P06 | Synthetic recovery baseline | APPROVED | Reconstructed network with accepted documented assumptions | 2025-08-01 | 2026-12-24 | -14 | User-approved synthetic baseline + release holds; CPM/float calculated, all approved finish dates retained
P07 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-10-01 | 2026-09-01 | 0 | Historical date comparator; no baseline overwrite
P07 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-10-01 | 2026-09-01 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P08 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-12-01 | 2027-01-08 | 0 | Historical date comparator; no baseline overwrite
P08 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-12-01 | 2027-01-08 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P09 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2026-02-02 | 2027-03-03 | 0 | Historical date comparator; no baseline overwrite
P09 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2026-02-02 | 2027-03-03 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P10 | Prior coordinated baseline | SUPERSEDED | Original approved coordinated scheduling version | 2026-04-01 | 2027-08-20 | 0 | Historical date comparator; no baseline overwrite
P10 | Synthetic recovery baseline | APPROVED | Reconstructed network with accepted documented assumptions | 2026-04-01 | 2027-08-06 | -14 | User-approved synthetic baseline + release holds; CPM/float calculated, all approved finish dates retained
P11 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-04-01 | 2026-03-09 | 0 | Historical date comparator; no baseline overwrite
P11 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-04-01 | 2026-03-09 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P12 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-01-02 | 2027-06-23 | 0 | Historical date comparator; no baseline overwrite
P12 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-01-02 | 2027-06-23 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.

## RESOURCE_ASSUMPTIONS
HWSD — Resource Capacity Assumptions
Planning assumptions are synthetic. Six concurrent distribution crews at peak vs seven-unit baseline; commissioning demand three vs two internal + one temporary specialist.
Assumption_ID | Resource_or_Issue | Approved_Assumption | Sensitivity_or_Note
RA-01 | Distribution/excavation contractors | 7 concurrent crew groups available | Approved baseline capacity
RA-02 | Distribution constrained sensitivity | 4 concurrent crews | Sensitivity only; not baseline
RA-03 | P05 field delivery | Maximum 3 concurrent field crew groups | Existing approved schedule assumption
RA-04 | P11 field delivery | Maximum 2 concurrent field crew groups | Existing approved schedule assumption
RA-05 | P12 recurring work | 1 standing field crew/group per active annual cycle | Synthetic portfolio assumption
RA-06 | Owner commissioning | 2 internal commissioning/acceptance teams | Approved baseline capacity
RA-07 | Late-2026 commissioning peak | +1 temporary specialist/vendor commissioning resource | Preserves P03/P06/P08 dates
RA-08 | Electrical resources | Multiple contractor packages may support approved overlap | Monitor P08/P10 overlap; capacity not hard-leveled
RA-09 | Controls/I&C resources | Multiple specialist resources may operate concurrently | Interface logic manages dependency rather than delaying all P10
RA-10 | Owner inspection | Capacity not hard-leveled yet | Track detailed demand before treating as a hard constraint
RA-11 | PM / project-controls staff | Management workload KPI, not hard schedule constraint | Revisit if staffing model is added
RA-12 | Baseline feasibility | Dates feasible conditional on approved capacity assumptions | Portfolio baseline disclaimer

## SCHEDULE_RECONCILIATION
HWSD — Baseline Date Reconciliation
Phase 1 placeholders → previously approved coordinated dates → user-approved synthetic recovery dates. P12 is recurring standing work.
Project_ID | Phase_1_Planned_Start | Phase_1_Planned_Finish | Prior_Approved_Baseline_Start | Prior_Approved_Baseline_Finish | Approved_Recovery_Baseline_Start | Approved_Recovery_Baseline_Finish | Finish_Variance_Calendar_Days | Status | Notes
P01 | 2025-01-01 | 2026-02-01 | 2025-01-02 | 2026-01-05 | 2025-01-02 | 2025-12-29 | -7 | APPROVED SYNTHETIC RECOVERY | Synthetic recovery of original unavailable executable schedule
P02 | 2025-02-01 | 2026-09-01 | 2025-02-03 | 2026-04-01 | 2025-02-03 | 2026-02-25 | -35 | APPROVED SYNTHETIC RECOVERY | Synthetic recovery of original unavailable executable schedule
P03 | 2025-01-01 | 2027-09-01 | 2025-01-02 | 2027-02-17 | 2025-01-02 | 2027-01-27 | -21 | APPROVED SYNTHETIC RECOVERY | Synthetic recovery of original unavailable executable schedule
P04 | 2025-06-01 | 2026-04-01 | 2025-06-02 | 2026-04-24 | 2025-06-02 | 2026-04-24 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P05 | 2025-03-01 | 2026-12-01 | 2025-03-03 | 2026-05-15 | 2025-03-03 | 2026-05-15 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P06 | 2025-08-01 | 2026-10-01 | 2025-08-01 | 2027-01-07 | 2025-08-01 | 2026-12-24 | -14 | APPROVED SYNTHETIC RECOVERY | Synthetic recovery of original unavailable executable schedule
P07 | 2025-10-01 | 2026-06-01 | 2025-10-01 | 2026-09-01 | 2025-10-01 | 2026-09-01 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P08 | 2025-12-01 | 2027-02-01 | 2025-12-01 | 2027-01-08 | 2025-12-01 | 2027-01-08 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P09 | 2026-02-01 | 2027-04-01 | 2026-02-02 | 2027-03-03 | 2026-02-02 | 2027-03-03 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P10 | 2026-04-01 | 2027-03-01 | 2026-04-01 | 2027-08-20 | 2026-04-01 | 2027-08-06 | -14 | APPROVED SYNTHETIC RECOVERY | Synthetic recovery of original unavailable executable schedule
P11 | 2025-04-01 | 2026-08-01 | 2025-04-01 | 2026-03-09 | 2025-04-01 | 2026-03-09 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P12 | 2025-01-01 | 2027-12-01 | 2025-01-02 | 2027-06-23 | 2025-01-02 | 2027-06-23 | 0 | UNCHANGED REFERENCE | P12 is standing work, not a discrete program-level substantial-completion gate

## CPM_METHOD
HWSD — CPM, Calendar & Baseline Constraints
Approved synthetic recovery, project-finish anchored CPM snapshot — not resource-leveled or a forecast.
Method / Assumption | Applied Convention / Limitation
Calendar | Monday–Friday business days, no holidays; all task durations inclusive, milestones zero duration.
FS milestone convention | For FS+0, zero-duration successor milestones fire on predecessor finish date; task successors start next business day. Lag is in business days.
SS / FF conventions | SS lag constrains successor start against predecessor start. FF lag constrains successor finish against predecessor finish.
Early dates | Forward pass uses approved per-project start as the lower anchor, all cross-project dependencies, and approved release holds.
Late dates | Backward pass constrains every activity finish no later than its own approved project finish and honors cross-project dependencies.
Total Float | Late Start minus Early Start in business days; float is relative to each approved project finish, not a common program finish.
Critical Flag | TRUE when total float is zero business days. Near-critical is 1–5 business days. Critical paths are based on tight relationships, not just a label.
P08 MOUTAGE fixed event | P08-MOUTAGE (Outage Planning Complete) retains its previously approved 2026-05-22 date as an explicit fixed-date milestone; A14 planning finishes 2026-05-08. No unsourced 10bd causal hold was added; the milestone may have constraint-driven zero float and is not itself evidence of a driving construction path.
Five approved NTP release holds | P04 R0133 +15bd; P05 R0161 +5bd; P07 R0260 +10bd; P08 R0291 +10bd; P11 R0434 +5bd. Synthetic, explicitly user approved; NOT recovered originals.
P12 standing program | P12 uses its own June 23, 2027 finish for float. It is standing work, not an ordinary program Substantial Completion gate.
Capacity screening | Distribution peak 6 vs baseline 7 contractor crew groups (4-crew sensitivity deficit 2). Commissioning peak 3 vs 2 internal +1 temporary specialist; temporary resource not booked.
Data limitations | Seven P01/P02 activity durations remain provisional synthetic planning assumptions. Other reconstructed activity/relationship logic is model-derived, not original-script recovered.
Approval and source | User approved synthetic recovery project finishes and five date-neutral release holds; previously approved project boundaries preserved.

## CPM_SUMMARY
HWSD — Baseline Critical Path Summary
Project-finish anchored float; critical=0bd, near-critical=1–5bd. P08 outage has a separately constrained milestone.
Project_ID | Approved_Baseline_Start | Approved_Baseline_Finish | Schedule_Rows | Critical_Rows | Near_Critical_Rows | Critical_Link_Count | Critical_Start_Activities | Critical_End_Activities
P01 | 2025-01-02 | 2025-12-29 | 25 | 19 | 0 | 18 | P01-A1 | P01-M4
P02 | 2025-02-03 | 2026-02-25 | 33 | 17 | 1 | 16 | P02-A1 | P02-M5
P03 | 2025-01-02 | 2027-01-27 | 48 | 26 | 0 | 25 | P03-A1 | P03-M4
P04 | 2025-06-02 | 2026-04-24 | 26 | 21 | 1 | 20 | P04-A1 | P04-M4
P05 | 2025-03-03 | 2026-05-15 | 39 | 21 | 0 | 21 | P05-A1 | P05-M4
P06 | 2025-08-01 | 2026-12-24 | 48 | 23 | 0 | 23 | P06-A1 | P06-M4
P07 | 2025-10-01 | 2026-09-01 | 27 | 19 | 0 | 18 | P07-A1 | P07-M4
P08 | 2025-12-01 | 2027-01-08 | 38 | 22 | 0 | 20 | P08-A1, P08-MOUTAGE | P08-MOUTAGE, P08-M4
P09 | 2026-02-02 | 2027-03-03 | 36 | 19 | 1 | 18 | P09-A1 | P09-M4
P10 | 2026-04-01 | 2027-08-06 | 45 | 29 | 0 | 30 | P10-A1 | P10-M4
P11 | 2025-04-01 | 2026-03-09 | 32 | 17 | 0 | 16 | P11-A1 | P11-M4
P12 | 2025-01-02 | 2027-06-23 | 31 | 25 | 0 | 24 | P12-Y1A1 | P12-MPROGCLOSE

## COST_CONTROL_ACCOUNTS
Project_ID | Control_Account_ID | Control_Account_Name | Standard_Lifecycle_Phase | Project_BAC_USD | Proposed_CA_Share_Pct | Proposed_CA_BAC_USD | Allocation_Basis | Approval_Status | Candidate_Loaded_BAC_USD | Unresolved_BAC_USD | Phase3B_Status
P01 | P01-CA01 | Planning | Planning | 7400000 | 3 | 222000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 222000 | 0 | RESOLVED_PHASE3G
P01 | P01-CA02 | Design | Design | 7400000 | 7 | 518000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 518000 | 0 | RESOLVED_PHASE3G
P01 | P01-CA03 | Procurement | Procurement | 7400000 | 8 | 592000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 592000 | 0 | RESOLVED_PHASE3G
P01 | P01-CA04 | Construction | Construction | 7400000 | 72 | 5328000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 5328000 | 0 | RESOLVED_PHASE3G
P01 | P01-CA05 | Testing & Commissioning | Testing & Commissioning | 7400000 | 7 | 518000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 518000 | 0 | RESOLVED_PHASE3G
P01 | P01-CA06 | Closeout | Closeout | 7400000 | 3 | 222000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 222000 | 0 | RESOLVED_PHASE3G
P02 | P02-CA01 | Planning | Planning | 8800000 | 3 | 264000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 264000 | 0 | RESOLVED_PHASE3G
P02 | P02-CA02 | Design | Design | 8800000 | 9 | 792000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 792000 | 0 | RESOLVED_PHASE3G
P02 | P02-CA03 | Procurement | Procurement | 8800000 | 7 | 616000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 616000 | 0 | RESOLVED_PHASE3G
P02 | P02-CA04 | Construction | Construction | 8800000 | 72 | 6336000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 6336000 | 0 | RESOLVED_PHASE3G
P02 | P02-CA05 | Testing & Commissioning | Testing & Commissioning | 8800000 | 6 | 528000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 528000 | 0 | RESOLVED_PHASE3G
P02 | P02-CA06 | Closeout | Closeout | 8800000 | 3 | 264000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 264000 | 0 | RESOLVED_PHASE3G
P03 | P03-CA01 | Planning | Planning | 20300000 | 3 | 609000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 609000 | 0 | RESOLVED_PHASE3G
P03 | P03-CA02 | Design | Design | 20300000 | 9 | 1827000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 1827000 | 0 | RESOLVED_PHASE3G
P03 | P03-CA03 | Procurement | Procurement | 20300000 | 7 | 1421000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 1421000 | 0 | RESOLVED_PHASE3G
P03 | P03-CA04 | Construction | Construction | 20300000 | 70 | 14210000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 14210000 | 0 | RESOLVED_PHASE3G
P03 | P03-CA05 | Testing & Commissioning | Testing & Commissioning | 20300000 | 8 | 1624000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 1624000 | 0 | RESOLVED_PHASE3G
P03 | P03-CA06 | Closeout | Closeout | 20300000 | 3 | 609000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 609000 | 0 | RESOLVED_PHASE3G
P04 | P04-CA01 | Planning | Planning | 5500000 | 3 | 165000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 165000 | 0 | RESOLVED_PHASE3G
P04 | P04-CA02 | Design | Design | 5500000 | 7 | 385000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 385000 | 0 | RESOLVED_PHASE3G
P04 | P04-CA03 | Procurement | Procurement | 5500000 | 7 | 385000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 385000 | 0 | RESOLVED_PHASE3G
P04 | P04-CA04 | Construction | Construction | 5500000 | 74 | 4070000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 4070000 | 0 | RESOLVED_PHASE3G
P04 | P04-CA05 | Testing & Commissioning | Testing & Commissioning | 5500000 | 6 | 330000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 330000 | 0 | RESOLVED_PHASE3G
P04 | P04-CA06 | Closeout | Closeout | 5500000 | 3 | 165000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 165000 | 0 | RESOLVED_PHASE3G
P05 | P05-CA01 | Planning | Planning | 11100000 | 4 | 444000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 444000 | 0 | RESOLVED_PHASE3G
P05 | P05-CA02 | Design | Design | 11100000 | 6 | 666000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 666000 | 0 | RESOLVED_PHASE3G
P05 | P05-CA03 | Procurement | Procurement | 11100000 | 6 | 666000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 666000 | 0 | RESOLVED_PHASE3G
P05 | P05-CA04 | Construction | Construction | 11100000 | 76 | 8436000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 8436000 | 0 | RESOLVED_PHASE3G
P05 | P05-CA05 | Testing & Commissioning | Testing & Commissioning | 11100000 | 5 | 555000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 555000 | 0 | RESOLVED_PHASE3G
P05 | P05-CA06 | Closeout | Closeout | 11100000 | 3 | 333000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 333000 | 0 | RESOLVED_PHASE3G
P06 | P06-CA01 | Planning | Planning | 6900000 | 4 | 276000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 276000 | 0 | RESOLVED_PHASE3G
P06 | P06-CA02 | Design | Design | 6900000 | 11 | 759000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 759000 | 0 | RESOLVED_PHASE3G
P06 | P06-CA03 | Procurement | Procurement | 6900000 | 13 | 897000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 897000 | 0 | RESOLVED_PHASE3G
P06 | P06-CA04 | Construction | Construction | 6900000 | 59 | 4071000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 4071000 | 0 | RESOLVED_PHASE3G
P06 | P06-CA05 | Testing & Commissioning | Testing & Commissioning | 6900000 | 10 | 690000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 690000 | 0 | RESOLVED_PHASE3G
P06 | P06-CA06 | Closeout | Closeout | 6900000 | 3 | 207000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 207000 | 0 | RESOLVED_PHASE3G
P07 | P07-CA01 | Planning | Planning | 4100000 | 3 | 123000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 123000 | 0 | RESOLVED_PHASE3G
P07 | P07-CA02 | Design | Design | 4100000 | 9 | 369000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 369000 | 0 | RESOLVED_PHASE3G
P07 | P07-CA03 | Procurement | Procurement | 4100000 | 10 | 410000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 410000 | 0 | RESOLVED_PHASE3G
P07 | P07-CA04 | Construction | Construction | 4100000 | 68 | 2788000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 2788000 | 0 | RESOLVED_PHASE3G
P07 | P07-CA05 | Testing & Commissioning | Testing & Commissioning | 4100000 | 7 | 287000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 287000 | 0 | RESOLVED_PHASE3G
P07 | P07-CA06 | Closeout | Closeout | 4100000 | 3 | 123000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 123000 | 0 | RESOLVED_PHASE3G
P08 | P08-CA01 | Planning | Planning | 4600000 | 3 | 138000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 138000 | 0 | RESOLVED_PHASE3G
P08 | P08-CA02 | Design | Design | 4600000 | 8 | 368000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 368000 | 0 | RESOLVED_PHASE3G
P08 | P08-CA03 | Procurement | Procurement | 4600000 | 12 | 552000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 552000 | 0 | RESOLVED_PHASE3G
P08 | P08-CA04 | Construction | Construction | 4600000 | 65 | 2990000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 2990000 | 0 | RESOLVED_PHASE3G
P08 | P08-CA05 | Testing & Commissioning | Testing & Commissioning | 4600000 | 9 | 414000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 414000 | 0 | RESOLVED_PHASE3G
P08 | P08-CA06 | Closeout | Closeout | 4600000 | 3 | 138000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 138000 | 0 | RESOLVED_PHASE3G
P09 | P09-CA01 | Planning | Planning | 7800000 | 3 | 234000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 234000 | 0 | RESOLVED_PHASE3G
P09 | P09-CA02 | Design | Design | 7800000 | 8 | 624000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 624000 | 0 | RESOLVED_PHASE3G
P09 | P09-CA03 | Procurement | Procurement | 7800000 | 8 | 624000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 624000 | 0 | RESOLVED_PHASE3G
P09 | P09-CA04 | Construction | Construction | 7800000 | 72 | 5616000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 5616000 | 0 | RESOLVED_PHASE3G
P09 | P09-CA05 | Testing & Commissioning | Testing & Commissioning | 7800000 | 6 | 468000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 468000 | 0 | RESOLVED_PHASE3G
P09 | P09-CA06 | Closeout | Closeout | 7800000 | 3 | 234000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 234000 | 0 | RESOLVED_PHASE3G
P10 | P10-CA01 | Planning | Planning | 3700000 | 4 | 148000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 148000 | 0 | RESOLVED_PHASE3G
P10 | P10-CA02 | Design | Design | 3700000 | 18 | 666000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 666000 | 0 | RESOLVED_PHASE3G
P10 | P10-CA03 | Procurement | Procurement | 3700000 | 14 | 518000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 518000 | 0 | RESOLVED_PHASE3G
P10 | P10-CA04 | Construction | Construction | 3700000 | 42 | 1554000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 1554000 | 0 | RESOLVED_PHASE3G
P10 | P10-CA05 | Testing & Commissioning | Testing & Commissioning | 3700000 | 19 | 703000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 703000 | 0 | RESOLVED_PHASE3G
P10 | P10-CA06 | Closeout | Closeout | 3700000 | 3 | 111000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 111000 | 0 | RESOLVED_PHASE3G
P11 | P11-CA01 | Planning | Planning | 3200000 | 4 | 128000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 128000 | 0 | RESOLVED_PHASE3G
P11 | P11-CA02 | Design | Design | 3200000 | 6 | 192000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 192000 | 0 | RESOLVED_PHASE3G
P11 | P11-CA03 | Procurement | Procurement | 3200000 | 9 | 288000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 288000 | 0 | RESOLVED_PHASE3G
P11 | P11-CA04 | Construction | Construction | 3200000 | 70 | 2240000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 2240000 | 0 | RESOLVED_PHASE3G
P11 | P11-CA05 | Testing & Commissioning | Testing & Commissioning | 3200000 | 8 | 256000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 256000 | 0 | RESOLVED_PHASE3G
P11 | P11-CA06 | Closeout | Closeout | 3200000 | 3 | 96000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 96000 | 0 | RESOLVED_PHASE3G
P12 | P12-CA01 | Planning & Prioritization | Planning | 5100000 | 4 | 204000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 204000 | 0 | RESOLVED_PHASE3G
P12 | P12-CA02 | Design / Scope Development | Design | 5100000 | 6 | 306000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 306000 | 0 | RESOLVED_PHASE3G
P12 | P12-CA03 | Procurement | Procurement | 5100000 | 8 | 408000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 408000 | 0 | RESOLVED_PHASE3G
P12 | P12-CA04 | Execution | Construction | 5100000 | 76 | 3876000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 3876000 | 0 | RESOLVED_PHASE3G
P12 | P12-CA05 | Verification / Acceptance | Testing & Commissioning | 5100000 | 4 | 204000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 204000 | 0 | RESOLVED_PHASE3G
P12 | P12-CA06 | Closeout | Closeout | 5100000 | 2 | 102000 | Synthetic scope-based project-specific phase budget; review required | APPROVED_SYNTHETIC_PORTFOLIO | 102000 | 0 | RESOLVED_PHASE3G

## COST_WORK_PACKAGES
Project_ID | Control_Account_ID | Work_Package_ID | WBS_Code | Work_Package_Name | Control_Account_BAC_USD | Proposed_WP_Share_Pct | Proposed_WP_BAC_USD | Mapped_Task_Count | Coverage_Status | Allocation_Basis | Approval_Status | Candidate_Loaded_BAC_USD | Unresolved_BAC_USD | Phase3B_Status
P01 | P01-CA01 | P01-WP011 | 1.01.1.1 | Needs Assessment | 222000 | 55 | 122100 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 122100 | 0 | RESOLVED_PHASE3G
P01 | P01-CA01 | P01-WP012 | 1.01.1.2 | Project Definition | 222000 | 45 | 99900 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 99900 | 0 | RESOLVED_PHASE3G
P01 | P01-CA02 | P01-WP021 | 1.01.2.1 | Preliminary Design (30%) | 518000 | 35 | 181300 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 181300 | 0 | RESOLVED_PHASE3G
P01 | P01-CA02 | P01-WP022 | 1.01.2.2 | Final Design (100%) | 518000 | 65 | 336700 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 336700 | 0 | RESOLVED_PHASE3G
P01 | P01-CA03 | P01-WP031 | 1.01.3.1 | Bid Package & Solicitation | 592000 | 35 | 207200 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 207200 | 0 | RESOLVED_PHASE3G
P01 | P01-CA03 | P01-WP032 | 1.01.3.2 | Award & Mobilization | 592000 | 65 | 384800 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 384800 | 0 | RESOLVED_PHASE3G
P01 | P01-CA04 | P01-WP041 | 1.01.4.1 | Pipe Installation & Jointing | 5328000 | 72 | 3836160 | 5 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 3836160 | 0 | RESOLVED_PHASE3G
P01 | P01-CA04 | P01-WP042 | 1.01.4.2 | Valve & Hydrant Tie-Ins | 5328000 | 16 | 852480 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 852480 | 0 | RESOLVED_PHASE3G
P01 | P01-CA04 | P01-WP043 | 1.01.4.3 | Pavement & Surface Restoration | 5328000 | 12 | 639360 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 639360 | 0 | RESOLVED_PHASE3G
P01 | P01-CA05 | P01-WP051 | 1.01.5.1 | Startup & Functional Testing | 518000 | 100 | 518000 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 518000 | 0 | RESOLVED_PHASE3G
P01 | P01-CA06 | P01-WP061 | 1.01.6.1 | Documentation & Turnover | 222000 | 65 | 144300 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 144300 | 0 | RESOLVED_PHASE3G
P01 | P01-CA06 | P01-WP062 | 1.01.6.2 | Financial Closeout | 222000 | 35 | 77700 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 77700 | 0 | RESOLVED_PHASE3G
P02 | P02-CA01 | P02-WP011 | 1.02.1.1 | Needs Assessment | 264000 | 50 | 132000 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 132000 | 0 | RESOLVED_PHASE3G
P02 | P02-CA01 | P02-WP012 | 1.02.1.2 | Project Definition | 264000 | 50 | 132000 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 132000 | 0 | RESOLVED_PHASE3G
P02 | P02-CA02 | P02-WP021 | 1.02.2.1 | Preliminary Design (30%) | 792000 | 35 | 277200 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 277200 | 0 | RESOLVED_PHASE3G
P02 | P02-CA02 | P02-WP022 | 1.02.2.2 | Final Design (100%) | 792000 | 65 | 514800 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 514800 | 0 | RESOLVED_PHASE3G
P02 | P02-CA03 | P02-WP031 | 1.02.3.1 | Bid Package & Solicitation | 616000 | 35 | 215600 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 215600 | 0 | RESOLVED_PHASE3G
P02 | P02-CA03 | P02-WP032 | 1.02.3.2 | Award & Mobilization | 616000 | 65 | 400400 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 400400 | 0 | RESOLVED_PHASE3G
P02 | P02-CA04 | P02-WP041 | 1.02.4.1 | Pump & Motor Replacement | 6336000 | 48 | 3041280 | 9 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 3041280 | 0 | RESOLVED_PHASE3G
P02 | P02-CA04 | P02-WP042 | 1.02.4.2 | Electrical Switchgear Upgrade | 6336000 | 42 | 2661120 | 6 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 2661120 | 0 | RESOLVED_PHASE3G
P02 | P02-CA04 | P02-WP043 | 1.02.4.3 | Wetwell Structural Rehabilitation | 6336000 | 10 | 633600 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 633600 | 0 | RESOLVED_PHASE3G
P02 | P02-CA05 | P02-WP051 | 1.02.5.1 | Startup & Functional Testing | 528000 | 100 | 528000 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 528000 | 0 | RESOLVED_PHASE3G
P02 | P02-CA06 | P02-WP061 | 1.02.6.1 | Documentation & Turnover | 264000 | 65 | 171600 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 171600 | 0 | RESOLVED_PHASE3G
P02 | P02-CA06 | P02-WP062 | 1.02.6.2 | Financial Closeout | 264000 | 35 | 92400 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 92400 | 0 | RESOLVED_PHASE3G
P03 | P03-CA01 | P03-WP011 | 1.03.1.1 | Needs Assessment | 609000 | 45 | 274050 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 274050 | 0 | RESOLVED_PHASE3G
P03 | P03-CA01 | P03-WP012 | 1.03.1.2 | Project Definition | 609000 | 55 | 334950 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 334950 | 0 | RESOLVED_PHASE3G
P03 | P03-CA02 | P03-WP021 | 1.03.2.1 | Preliminary Design (30%) | 1827000 | 32 | 584640 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 584640 | 0 | RESOLVED_PHASE3G
P03 | P03-CA02 | P03-WP022 | 1.03.2.2 | Final Design (100%) | 1827000 | 68 | 1242360 | 6 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 1242360 | 0 | RESOLVED_PHASE3G
P03 | P03-CA03 | P03-WP031 | 1.03.3.1 | Bid Package & Solicitation | 1421000 | 35 | 497350 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 497350 | 0 | RESOLVED_PHASE3G
P03 | P03-CA03 | P03-WP032 | 1.03.3.2 | Award & Mobilization | 1421000 | 65 | 923650 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 923650 | 0 | RESOLVED_PHASE3G
P03 | P03-CA04 | P03-WP041 | 1.03.4.1 | Process Mechanical Installation | 14210000 | 52 | 7389200 | 6 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 7389200 | 0 | RESOLVED_PHASE3G
P03 | P03-CA04 | P03-WP042 | 1.03.4.2 | Electrical & Instrumentation Installation | 14210000 | 35 | 4973500 | 6 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 4973500 | 0 | RESOLVED_PHASE3G
P03 | P03-CA04 | P03-WP043 | 1.03.4.3 | Chemical Feed System Installation | 14210000 | 13 | 1847300 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 1847300 | 0 | RESOLVED_PHASE3G
P03 | P03-CA05 | P03-WP051 | 1.03.5.1 | Process Startup & Functional Testing | 1624000 | 55 | 893200 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 893200 | 0 | RESOLVED_PHASE3G
P03 | P03-CA05 | P03-WP052 | 1.03.5.2 | Performance / Acceptance Testing | 1624000 | 30 | 487200 | 0 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 487200 | 0 | RESOLVED_PHASE3G
P03 | P03-CA05 | P03-WP053 | 1.03.5.3 | Regulatory Sign-off & SCADA Integration Checkout | 1624000 | 15 | 243600 | 0 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 243600 | 0 | RESOLVED_PHASE3G
P03 | P03-CA06 | P03-WP061 | 1.03.6.1 | Documentation & Turnover | 609000 | 70 | 426300 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 426300 | 0 | RESOLVED_PHASE3G
P03 | P03-CA06 | P03-WP062 | 1.03.6.2 | Financial Closeout | 609000 | 30 | 182700 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 182700 | 0 | RESOLVED_PHASE3G
P04 | P04-CA01 | P04-WP011 | 1.04.1.1 | Needs Assessment | 165000 | 50 | 82500 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 82500 | 0 | RESOLVED_PHASE3G
P04 | P04-CA01 | P04-WP012 | 1.04.1.2 | Project Definition | 165000 | 50 | 82500 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 82500 | 0 | RESOLVED_PHASE3G
P04 | P04-CA02 | P04-WP021 | 1.04.2.1 | Preliminary Design (30%) | 385000 | 35 | 134750 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 134750 | 0 | RESOLVED_PHASE3G
P04 | P04-CA02 | P04-WP022 | 1.04.2.2 | Final Design (100%) | 385000 | 65 | 250250 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 250250 | 0 | RESOLVED_PHASE3G
P04 | P04-CA03 | P04-WP031 | 1.04.3.1 | Bid Package & Solicitation | 385000 | 35 | 134750 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 134750 | 0 | RESOLVED_PHASE3G
P04 | P04-CA03 | P04-WP032 | 1.04.3.2 | Award & Mobilization | 385000 | 65 | 250250 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 250250 | 0 | RESOLVED_PHASE3G
P04 | P04-CA04 | P04-WP041 | 1.04.4.1 | Tank Interior/Exterior Coating | 4070000 | 73 | 2971100 | 7 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 2971100 | 0 | RESOLVED_PHASE3G
P04 | P04-CA04 | P04-WP042 | 1.04.4.2 | Structural Steel Repairs | 4070000 | 20 | 814000 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 814000 | 0 | RESOLVED_PHASE3G
P04 | P04-CA04 | P04-WP043 | 1.04.4.3 | Cathodic Protection System Installation | 4070000 | 7 | 284900 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 284900 | 0 | RESOLVED_PHASE3G
P04 | P04-CA05 | P04-WP051 | 1.04.5.1 | Startup & Functional Testing | 330000 | 100 | 330000 | 0 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 330000 | 0 | RESOLVED_PHASE3G
P04 | P04-CA06 | P04-WP061 | 1.04.6.1 | Documentation & Turnover | 165000 | 65 | 107250 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 107250 | 0 | RESOLVED_PHASE3G
P04 | P04-CA06 | P04-WP062 | 1.04.6.2 | Financial Closeout | 165000 | 35 | 57750 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 57750 | 0 | RESOLVED_PHASE3G
P05 | P05-CA01 | P05-WP011 | 1.05.1.1 | Needs Assessment | 444000 | 65 | 288600 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 288600 | 0 | RESOLVED_PHASE3G
P05 | P05-CA01 | P05-WP012 | 1.05.1.2 | Project Definition | 444000 | 35 | 155400 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 155400 | 0 | RESOLVED_PHASE3G
P05 | P05-CA02 | P05-WP021 | 1.05.2.1 | Preliminary Design (30%) | 666000 | 30 | 199800 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 199800 | 0 | RESOLVED_PHASE3G
P05 | P05-CA02 | P05-WP022 | 1.05.2.2 | Final Design (100%) | 666000 | 70 | 466200 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 466200 | 0 | RESOLVED_PHASE3G
P05 | P05-CA03 | P05-WP031 | 1.05.3.1 | Bid Package & Solicitation | 666000 | 35 | 233100 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 233100 | 0 | RESOLVED_PHASE3G
P05 | P05-CA03 | P05-WP032 | 1.05.3.2 | Award & Mobilization | 666000 | 65 | 432900 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 432900 | 0 | RESOLVED_PHASE3G
P05 | P05-CA04 | P05-WP041 | 1.05.4.1 | Service Line Excavation & Replacement | 8436000 | 77 | 6495720 | 8 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 6495720 | 0 | RESOLVED_PHASE3G
P05 | P05-CA04 | P05-WP042 | 1.05.4.2 | Property Restoration | 8436000 | 18 | 1518480 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 1518480 | 0 | RESOLVED_PHASE3G
P05 | P05-CA04 | P05-WP043 | 1.05.4.3 | Water Quality Sampling & Verification | 8436000 | 5 | 421800 | 0 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 421800 | 0 | RESOLVED_PHASE3G
P05 | P05-CA05 | P05-WP051 | 1.05.5.1 | Startup & Functional Testing | 555000 | 100 | 555000 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 555000 | 0 | RESOLVED_PHASE3G
P05 | P05-CA06 | P05-WP061 | 1.05.6.1 | Documentation & Turnover | 333000 | 75 | 249750 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 249750 | 0 | RESOLVED_PHASE3G
P05 | P05-CA06 | P05-WP062 | 1.05.6.2 | Financial Closeout | 333000 | 25 | 83250 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 83250 | 0 | RESOLVED_PHASE3G
P06 | P06-CA01 | P06-WP011 | 1.06.1.1 | Needs Assessment | 276000 | 55 | 151800 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 151800 | 0 | RESOLVED_PHASE3G
P06 | P06-CA01 | P06-WP012 | 1.06.1.2 | Project Definition | 276000 | 45 | 124200 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 124200 | 0 | RESOLVED_PHASE3G
P06 | P06-CA02 | P06-WP021 | 1.06.2.1 | Preliminary Design (30%) | 759000 | 35 | 265650 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 265650 | 0 | RESOLVED_PHASE3G
P06 | P06-CA02 | P06-WP022 | 1.06.2.2 | Final Design (100%) | 759000 | 65 | 493350 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 493350 | 0 | RESOLVED_PHASE3G
P06 | P06-CA03 | P06-WP031 | 1.06.3.1 | Bid Package & Solicitation | 897000 | 30 | 269100 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 269100 | 0 | RESOLVED_PHASE3G
P06 | P06-CA03 | P06-WP032 | 1.06.3.2 | Award & Mobilization | 897000 | 70 | 627900 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 627900 | 0 | RESOLVED_PHASE3G
P06 | P06-CA04 | P06-WP041 | 1.06.4.1 | Meter Deployment & Installation | 4071000 | 67 | 2727570 | 9 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 2727570 | 0 | RESOLVED_PHASE3G
P06 | P06-CA04 | P06-WP042 | 1.06.4.2 | Head-End System Integration | 4071000 | 21 | 854910 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 854910 | 0 | RESOLVED_PHASE3G
P06 | P06-CA04 | P06-WP043 | 1.06.4.3 | Customer Data Migration & Validation | 4071000 | 12 | 488520 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 488520 | 0 | RESOLVED_PHASE3G
P06 | P06-CA05 | P06-WP051 | 1.06.5.1 | Startup & Functional Testing | 690000 | 100 | 690000 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 690000 | 0 | RESOLVED_PHASE3G
P06 | P06-CA06 | P06-WP061 | 1.06.6.1 | Documentation & Turnover | 207000 | 70 | 144900 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 144900 | 0 | RESOLVED_PHASE3G
P06 | P06-CA06 | P06-WP062 | 1.06.6.2 | Financial Closeout | 207000 | 30 | 62100 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 62100 | 0 | RESOLVED_PHASE3G
P07 | P07-CA01 | P07-WP011 | 1.07.1.1 | Needs Assessment | 123000 | 50 | 61500 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 61500 | 0 | RESOLVED_PHASE3G
P07 | P07-CA01 | P07-WP012 | 1.07.1.2 | Project Definition | 123000 | 50 | 61500 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 61500 | 0 | RESOLVED_PHASE3G
P07 | P07-CA02 | P07-WP021 | 1.07.2.1 | Preliminary Design (30%) | 369000 | 35 | 129150 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 129150 | 0 | RESOLVED_PHASE3G
P07 | P07-CA02 | P07-WP022 | 1.07.2.2 | Final Design (100%) | 369000 | 65 | 239850 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 239850 | 0 | RESOLVED_PHASE3G
P07 | P07-CA03 | P07-WP031 | 1.07.3.1 | Bid Package & Solicitation | 410000 | 35 | 143500 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 143500 | 0 | RESOLVED_PHASE3G
P07 | P07-CA03 | P07-WP032 | 1.07.3.2 | Award & Mobilization | 410000 | 65 | 266500 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 266500 | 0 | RESOLVED_PHASE3G
P07 | P07-CA04 | P07-WP041 | 1.07.4.1 | PRV Station Installation | 2788000 | 64 | 1784320 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 1784320 | 0 | RESOLVED_PHASE3G
P07 | P07-CA04 | P07-WP042 | 1.07.4.2 | Zone Isolation Valve Installation | 2788000 | 21 | 585480 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 585480 | 0 | RESOLVED_PHASE3G
P07 | P07-CA04 | P07-WP043 | 1.07.4.3 | Pressure Monitoring Instrumentation | 2788000 | 15 | 418200 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 418200 | 0 | RESOLVED_PHASE3G
P07 | P07-CA05 | P07-WP051 | 1.07.5.1 | Startup & Functional Testing | 287000 | 100 | 287000 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 287000 | 0 | RESOLVED_PHASE3G
P07 | P07-CA06 | P07-WP061 | 1.07.6.1 | Documentation & Turnover | 123000 | 65 | 79950 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 79950 | 0 | RESOLVED_PHASE3G
P07 | P07-CA06 | P07-WP062 | 1.07.6.2 | Financial Closeout | 123000 | 35 | 43050 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 43050 | 0 | RESOLVED_PHASE3G
P08 | P08-CA01 | P08-WP011 | 1.08.1.1 | Needs Assessment | 138000 | 45 | 62100 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 62100 | 0 | RESOLVED_PHASE3G
P08 | P08-CA01 | P08-WP012 | 1.08.1.2 | Project Definition | 138000 | 55 | 75900 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 75900 | 0 | RESOLVED_PHASE3G
P08 | P08-CA02 | P08-WP021 | 1.08.2.1 | Preliminary Design (30%) | 368000 | 35 | 128800 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 128800 | 0 | RESOLVED_PHASE3G
P08 | P08-CA02 | P08-WP022 | 1.08.2.2 | Final Design (100%) | 368000 | 65 | 239200 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 239200 | 0 | RESOLVED_PHASE3G
P08 | P08-CA03 | P08-WP031 | 1.08.3.1 | Bid Package & Solicitation | 552000 | 32 | 176640 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 176640 | 0 | RESOLVED_PHASE3G
P08 | P08-CA03 | P08-WP032 | 1.08.3.2 | Award & Mobilization | 552000 | 68 | 375360 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 375360 | 0 | RESOLVED_PHASE3G
P08 | P08-CA04 | P08-WP041 | 1.08.4.1 | Generator Installation | 2990000 | 65 | 1943500 | 9 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 1943500 | 0 | RESOLVED_PHASE3G
P08 | P08-CA04 | P08-WP042 | 1.08.4.2 | Automatic Transfer Switch Installation | 2990000 | 29 | 867100 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 867100 | 0 | RESOLVED_PHASE3G
P08 | P08-CA04 | P08-WP043 | 1.08.4.3 | Fuel Storage System Installation | 2990000 | 6 | 179400 | 0 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 179400 | 0 | RESOLVED_PHASE3G
P08 | P08-CA05 | P08-WP051 | 1.08.5.1 | Startup & Functional Testing | 414000 | 100 | 414000 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 414000 | 0 | RESOLVED_PHASE3G
P08 | P08-CA06 | P08-WP061 | 1.08.6.1 | Documentation & Turnover | 138000 | 65 | 89700 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 89700 | 0 | RESOLVED_PHASE3G
P08 | P08-CA06 | P08-WP062 | 1.08.6.2 | Financial Closeout | 138000 | 35 | 48300 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 48300 | 0 | RESOLVED_PHASE3G
P09 | P09-CA01 | P09-WP011 | 1.09.1.1 | Needs Assessment | 234000 | 50 | 117000 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 117000 | 0 | RESOLVED_PHASE3G
P09 | P09-CA01 | P09-WP012 | 1.09.1.2 | Project Definition | 234000 | 50 | 117000 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 117000 | 0 | RESOLVED_PHASE3G
P09 | P09-CA02 | P09-WP021 | 1.09.2.1 | Preliminary Design (30%) | 624000 | 40 | 249600 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 249600 | 0 | RESOLVED_PHASE3G
P09 | P09-CA02 | P09-WP022 | 1.09.2.2 | Final Design (100%) | 624000 | 60 | 374400 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 374400 | 0 | RESOLVED_PHASE3G
P09 | P09-CA03 | P09-WP031 | 1.09.3.1 | Bid Package & Solicitation | 624000 | 35 | 218400 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 218400 | 0 | RESOLVED_PHASE3G
P09 | P09-CA03 | P09-WP032 | 1.09.3.2 | Award & Mobilization | 624000 | 65 | 405600 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 405600 | 0 | RESOLVED_PHASE3G
P09 | P09-CA04 | P09-WP041 | 1.09.4.1 | Directional Drilling / Crossing Installation | 5616000 | 76 | 4268160 | 10 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 4268160 | 0 | RESOLVED_PHASE3G
P09 | P09-CA04 | P09-WP042 | 1.09.4.2 | Pipe Fusion & Pressure Testing | 5616000 | 16 | 898560 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 898560 | 0 | RESOLVED_PHASE3G
P09 | P09-CA04 | P09-WP043 | 1.09.4.3 | Riverbank Restoration | 5616000 | 8 | 449280 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 449280 | 0 | RESOLVED_PHASE3G
P09 | P09-CA05 | P09-WP051 | 1.09.5.1 | Startup & Functional Testing | 468000 | 100 | 468000 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 468000 | 0 | RESOLVED_PHASE3G
P09 | P09-CA06 | P09-WP061 | 1.09.6.1 | Documentation & Turnover | 234000 | 65 | 152100 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 152100 | 0 | RESOLVED_PHASE3G
P09 | P09-CA06 | P09-WP062 | 1.09.6.2 | Financial Closeout | 234000 | 35 | 81900 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 81900 | 0 | RESOLVED_PHASE3G
P10 | P10-CA01 | P10-WP011 | 1.10.1.1 | Needs Assessment | 148000 | 45 | 66600 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 66600 | 0 | RESOLVED_PHASE3G
P10 | P10-CA01 | P10-WP012 | 1.10.1.2 | Project Definition | 148000 | 55 | 81400 | 0 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 81400 | 0 | RESOLVED_PHASE3G
P10 | P10-CA02 | P10-WP021 | 1.10.2.1 | Preliminary Design (30%) | 666000 | 40 | 266400 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 266400 | 0 | RESOLVED_PHASE3G
P10 | P10-CA02 | P10-WP022 | 1.10.2.2 | Final Design (100%) | 666000 | 60 | 399600 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 399600 | 0 | RESOLVED_PHASE3G
P10 | P10-CA03 | P10-WP031 | 1.10.3.1 | Bid Package & Solicitation | 518000 | 35 | 181300 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 181300 | 0 | RESOLVED_PHASE3G
P10 | P10-CA03 | P10-WP032 | 1.10.3.2 | Award & Mobilization | 518000 | 65 | 336700 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 336700 | 0 | RESOLVED_PHASE3G
P10 | P10-CA04 | P10-WP041 | 1.10.4.1 | PLC Programming & Configuration | 1554000 | 37 | 574980 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 574980 | 0 | RESOLVED_PHASE3G
P10 | P10-CA04 | P10-WP042 | 1.10.4.2 | HMI Development | 1554000 | 33 | 512820 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 512820 | 0 | RESOLVED_PHASE3G
P10 | P10-CA04 | P10-WP043 | 1.10.4.3 | Network & Communications Infrastructure | 1554000 | 30 | 466200 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 466200 | 0 | RESOLVED_PHASE3G
P10 | P10-CA05 | P10-WP051 | 1.10.5.1 | Startup & Functional Testing | 703000 | 100 | 703000 | 10 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 703000 | 0 | RESOLVED_PHASE3G
P10 | P10-CA06 | P10-WP061 | 1.10.6.1 | Documentation & Turnover | 111000 | 70 | 77700 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 77700 | 0 | RESOLVED_PHASE3G
P10 | P10-CA06 | P10-WP062 | 1.10.6.2 | Financial Closeout | 111000 | 30 | 33300 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 33300 | 0 | RESOLVED_PHASE3G
P11 | P11-CA01 | P11-WP011 | 1.11.1.1 | Needs Assessment | 128000 | 60 | 76800 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 76800 | 0 | RESOLVED_PHASE3G
P11 | P11-CA01 | P11-WP012 | 1.11.1.2 | Project Definition | 128000 | 40 | 51200 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 51200 | 0 | RESOLVED_PHASE3G
P11 | P11-CA02 | P11-WP021 | 1.11.2.1 | Preliminary Design (30%) | 192000 | 30 | 57600 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 57600 | 0 | RESOLVED_PHASE3G
P11 | P11-CA02 | P11-WP022 | 1.11.2.2 | Final Design (100%) | 192000 | 70 | 134400 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 134400 | 0 | RESOLVED_PHASE3G
P11 | P11-CA03 | P11-WP031 | 1.11.3.1 | Bid Package & Solicitation | 288000 | 35 | 100800 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 100800 | 0 | RESOLVED_PHASE3G
P11 | P11-CA03 | P11-WP032 | 1.11.3.2 | Award & Mobilization | 288000 | 65 | 187200 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 187200 | 0 | RESOLVED_PHASE3G
P11 | P11-CA04 | P11-WP041 | 1.11.4.1 | Isolation Valve Installation | 2240000 | 77 | 1724800 | 5 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 1724800 | 0 | RESOLVED_PHASE3G
P11 | P11-CA04 | P11-WP042 | 1.11.4.2 | Distribution System Mapping Update | 2240000 | 8 | 179200 | 0 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 179200 | 0 | RESOLVED_PHASE3G
P11 | P11-CA04 | P11-WP043 | 1.11.4.3 | Site Restoration | 2240000 | 15 | 336000 | 2 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 336000 | 0 | RESOLVED_PHASE3G
P11 | P11-CA05 | P11-WP051 | 1.11.5.1 | Startup & Functional Testing | 256000 | 100 | 256000 | 4 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 256000 | 0 | RESOLVED_PHASE3G
P11 | P11-CA06 | P11-WP061 | 1.11.6.1 | Documentation & Turnover | 96000 | 70 | 67200 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 67200 | 0 | RESOLVED_PHASE3G
P11 | P11-CA06 | P11-WP062 | 1.11.6.2 | Financial Closeout | 96000 | 30 | 28800 | 1 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 28800 | 0 | RESOLVED_PHASE3G
P12 | P12-CA01 | P12-WP011 | 1.12.1.1 | Work Order Intake & Prioritization | 204000 | 100 | 204000 | 6 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 204000 | 0 | RESOLVED_PHASE3G
P12 | P12-CA02 | P12-WP021 | 1.12.2.1 | Field Scoping & Estimate | 306000 | 100 | 306000 | 6 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 306000 | 0 | RESOLVED_PHASE3G
P12 | P12-CA03 | P12-WP031 | 1.12.3.1 | Contractor / Materials Procurement | 408000 | 100 | 408000 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 408000 | 0 | RESOLVED_PHASE3G
P12 | P12-CA04 | P12-WP041 | 1.12.4.1 | Small Capital Repair Execution | 3876000 | 87 | 3372120 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 3372120 | 0 | RESOLVED_PHASE3G
P12 | P12-CA04 | P12-WP042 | 1.12.4.2 | Emergency Response Work Execution | 3876000 | 13 | 503880 | 0 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 503880 | 0 | RESOLVED_PHASE3G
P12 | P12-CA05 | P12-WP051 | 1.12.5.1 | Work Order Acceptance & Sign-off | 204000 | 100 | 204000 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 204000 | 0 | RESOLVED_PHASE3G
P12 | P12-CA06 | P12-WP061 | 1.12.6.1 | Documentation & Work Order Closeout | 102000 | 100 | 102000 | 3 | APPROVED_COST_OWNERSHIP_BRIDGE | Synthetic scope-weighted WP split; percentage of parent CA | APPROVED_SYNTHETIC_PORTFOLIO | 102000 | 0 | RESOLVED_PHASE3G

## COST_ACTIVITY_OWNERSHIP
Project_ID | Schedule_Activity_ID | Schedule_WP_ID | Cost_Control_Account_ID | Cost_WP_ID | Cost_Component | Candidate_Component_BAC_USD | PV_Recognition_Method | Evidence_or_Assumption | Mapping_Status | Candidate_Share_of_Cost_WP_Pct | Cost_Ownership_Line_ID | Approval_Status
P01 | P01-A1 | P01-WP011 | P01-CA01 | P01-WP011 | SOURCE_WP_SCOPE | 122100 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0001 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A2 | P01-WP012 | P01-CA01 | P01-WP012 | SOURCE_WP_SCOPE | 99900 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0002 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A3 | P01-WP021 | P01-CA02 | P01-WP021 | SOURCE_WP_SCOPE | 181300 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0003 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A4 | P01-WP022 | P01-CA02 | P01-WP022 | SOURCE_WP_SCOPE | 84175 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0004 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A4b | P01-WP022 | P01-CA02 | P01-WP022 | SOURCE_WP_SCOPE | 84175 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0005 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A12 | P01-WP022 | P01-CA02 | P01-WP022 | SOURCE_WP_SCOPE | 168350 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0006 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A7a | P01-WP031 | P01-CA03 | P01-WP031 | SOURCE_WP_SCOPE | 69067 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333494 | CL0007 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A5 | P01-WP031 | P01-CA03 | P01-WP031 | SOURCE_WP_SCOPE | 69067 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333494 | CL0008 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A5b | P01-WP031 | P01-CA03 | P01-WP031 | SOURCE_WP_SCOPE | 69066 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333012 | CL0009 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A6 | P01-WP032 | P01-CA03 | P01-WP032 | SOURCE_WP_SCOPE | 384800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0010 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A7b | P01-WP041 | P01-CA04 | P01-WP041 | SOURCE_WP_SCOPE | 1278720 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0011 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A4u | P01-WP041 | P01-CA04 | P01-WP041 | SOURCE_WP_SCOPE | 319680 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333333 | CL0012 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A7c | P01-WP041 | P01-CA04 | P01-WP041 | SOURCE_WP_SCOPE | 1278720 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0013 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A8 | P01-WP041 | P01-CA04 | P01-WP041 | SOURCE_WP_SCOPE | 319680 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333333 | CL0014 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A15 | P01-WP041 | P01-CA04 | P01-WP041 | SOURCE_WP_SCOPE | 639360 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 16.666667 | CL0015 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A9 | P01-WP042 | P01-CA04 | P01-WP042 | SOURCE_WP_SCOPE | 426240 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0016 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A9b | P01-WP042 | P01-CA04 | P01-WP042 | SOURCE_WP_SCOPE | 426240 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0017 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A10 | P01-WP043 | P01-CA04 | P01-WP043 | SOURCE_WP_SCOPE | 639360 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0018 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A11 | P01-WP051 | P01-CA05 | P01-WP051 | SOURCE_WP_SCOPE | 518000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0019 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A13 | P01-WP061 | P01-CA06 | P01-WP061 | SOURCE_WP_SCOPE | 144300 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0020 | APPROVED_SYNTHETIC_PORTFOLIO
P01 | P01-A14 | P01-WP062 | P01-CA06 | P01-WP062 | SOURCE_WP_SCOPE | 77700 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0021 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A1 | P02-WP011 | P02-CA01 | P02-WP011 | SOURCE_WP_SCOPE | 132000 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0022 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A2 | P02-WP012 | P02-CA01 | P02-WP012 | SOURCE_WP_SCOPE | 132000 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0023 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A3 | P02-WP021 | P02-CA02 | P02-WP021 | SOURCE_WP_SCOPE | 277200 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0024 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A4 | P02-WP022 | P02-CA02 | P02-WP022 | SOURCE_WP_SCOPE | 257400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0025 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A4b | P02-WP022 | P02-CA02 | P02-WP022 | SOURCE_WP_SCOPE | 257400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0026 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A5 | P02-WP031 | P02-CA03 | P02-WP031 | SOURCE_WP_SCOPE | 107800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0027 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A5b | P02-WP031 | P02-CA03 | P02-WP031 | SOURCE_WP_SCOPE | 107800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0028 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A6 | P02-WP032 | P02-CA03 | P02-WP032 | SOURCE_WP_SCOPE | 400400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0029 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A6b | P02-WP041 | P02-CA04 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 6.250000 | CL0030 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A7a | P02-WP041 | P02-CA04 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 6.250000 | CL0031 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A8 | P02-WP041 | P02-CA04 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 6.250000 | CL0032 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A7b | P02-WP041 | P02-CA04 | P02-WP041 | SOURCE_WP_SCOPE | 760320 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0033 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A9 | P02-WP041 | P02-CA04 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 6.250000 | CL0034 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A7c | P02-WP041 | P02-CA04 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 6.250000 | CL0035 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A7d | P02-WP041 | P02-CA04 | P02-WP041 | SOURCE_WP_SCOPE | 760320 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0036 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A10 | P02-WP041 | P02-CA04 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 6.250000 | CL0037 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A15b | P02-WP041 | P02-CA04 | P02-WP041 | SOURCE_WP_SCOPE | 380160 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 12.500000 | CL0038 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A11a | P02-WP042 | P02-CA04 | P02-WP042 | SOURCE_WP_SCOPE | 221760 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333333 | CL0039 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A6c | P02-WP042 | P02-CA04 | P02-WP042 | SOURCE_WP_SCOPE | 221760 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333333 | CL0040 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A11b | P02-WP042 | P02-CA04 | P02-WP042 | SOURCE_WP_SCOPE | 887040 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0041 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A11c | P02-WP042 | P02-CA04 | P02-WP042 | SOURCE_WP_SCOPE | 221760 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333333 | CL0042 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A11d | P02-WP042 | P02-CA04 | P02-WP042 | SOURCE_WP_SCOPE | 887040 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0043 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A12 | P02-WP042 | P02-CA04 | P02-WP042 | SOURCE_WP_SCOPE | 221760 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333333 | CL0044 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A13 | P02-WP043 | P02-CA04 | P02-WP043 | SOURCE_WP_SCOPE | 633600 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0045 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A14 | P02-WP051 | P02-CA05 | P02-WP051 | SOURCE_WP_SCOPE | 264000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0046 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A15 | P02-WP051 | P02-CA05 | P02-WP051 | SOURCE_WP_SCOPE | 264000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0047 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A16 | P02-WP061 | P02-CA06 | P02-WP061 | SOURCE_WP_SCOPE | 171600 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0048 | APPROVED_SYNTHETIC_PORTFOLIO
P02 | P02-A17 | P02-WP062 | P02-CA06 | P02-WP062 | SOURCE_WP_SCOPE | 92400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0049 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A1 | P03-WP011 | P03-CA01 | P03-WP011 | SOURCE_WP_SCOPE | 274050 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0050 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A2 | P03-WP012 | P03-CA01 | P03-WP012 | SOURCE_WP_SCOPE | 334950 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0051 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A3 | P03-WP021 | P03-CA02 | P03-WP021 | SOURCE_WP_SCOPE | 292320 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0052 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A4 | P03-WP021 | P03-CA02 | P03-WP021 | SOURCE_WP_SCOPE | 292320 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0053 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A2b | P03-WP022 | P03-CA02 | P03-WP022 | SOURCE_WP_SCOPE | 138040 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.111111 | CL0054 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A5 | P03-WP022 | P03-CA02 | P03-WP022 | SOURCE_WP_SCOPE | 414120 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0055 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A6 | P03-WP022 | P03-CA02 | P03-WP022 | SOURCE_WP_SCOPE | 138040 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.111111 | CL0056 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A7 | P03-WP022 | P03-CA02 | P03-WP022 | SOURCE_WP_SCOPE | 138040 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.111111 | CL0057 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A7b | P03-WP022 | P03-CA02 | P03-WP022 | SOURCE_WP_SCOPE | 138040 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.111111 | CL0058 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A30 | P03-WP022 | P03-CA02 | P03-WP022 | SOURCE_WP_SCOPE | 276080 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 22.222222 | CL0059 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A8 | P03-WP031 | P03-CA03 | P03-WP031 | SOURCE_WP_SCOPE | 248675 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0060 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A9 | P03-WP031 | P03-CA03 | P03-WP031 | SOURCE_WP_SCOPE | 248675 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0061 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A9b | P03-WP032 | P03-CA03 | P03-WP032 | SOURCE_WP_SCOPE | 461825 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0062 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A10 | P03-WP032 | P03-CA03 | P03-WP032 | SOURCE_WP_SCOPE | 461825 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0063 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A11 | P03-WP041 | P03-CA04 | P03-WP041 | SOURCE_WP_SCOPE | 434659 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.882355 | CL0064 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A12 | P03-WP041 | P03-CA04 | P03-WP041 | SOURCE_WP_SCOPE | 1738635 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 23.529408 | CL0065 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A13 | P03-WP041 | P03-CA04 | P03-WP041 | SOURCE_WP_SCOPE | 434659 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.882355 | CL0066 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A14 | P03-WP041 | P03-CA04 | P03-WP041 | SOURCE_WP_SCOPE | 1738635 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 23.529408 | CL0067 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A15 | P03-WP041 | P03-CA04 | P03-WP041 | SOURCE_WP_SCOPE | 2173294 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 29.411763 | CL0068 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A29 | P03-WP041 | P03-CA04 | P03-WP041 | SOURCE_WP_SCOPE | 869318 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.764711 | CL0069 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A16 | P03-WP042 | P03-CA04 | P03-WP042 | SOURCE_WP_SCOPE | 355250 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142857 | CL0070 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A17 | P03-WP042 | P03-CA04 | P03-WP042 | SOURCE_WP_SCOPE | 1421000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 28.571429 | CL0071 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A18 | P03-WP042 | P03-CA04 | P03-WP042 | SOURCE_WP_SCOPE | 355250 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142857 | CL0072 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A19 | P03-WP042 | P03-CA04 | P03-WP042 | SOURCE_WP_SCOPE | 1421000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 28.571429 | CL0073 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A20 | P03-WP042 | P03-CA04 | P03-WP042 | SOURCE_WP_SCOPE | 1065750 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 21.428571 | CL0074 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A25 | P03-WP042 | P03-CA04 | P03-WP042 | SOURCE_WP_SCOPE | 355250 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142857 | CL0075 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A21 | P03-WP043 | P03-CA04 | P03-WP043 | SOURCE_WP_SCOPE | 153942 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333351 | CL0076 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A22 | P03-WP043 | P03-CA04 | P03-WP043 | SOURCE_WP_SCOPE | 615767 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333351 | CL0077 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A23 | P03-WP043 | P03-CA04 | P03-WP043 | SOURCE_WP_SCOPE | 615766 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333297 | CL0078 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A24 | P03-WP043 | P03-CA04 | P03-WP043 | SOURCE_WP_SCOPE | 461825 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0079 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A26 | P03-WP051 | P03-CA05 | P03-WP051 | SOURCE_WP_SCOPE | 446601 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000112 | CL0080 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A27 | P03-WP051 | P03-CA05 | P03-WP051 | SOURCE_WP_SCOPE | 446599 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 49.999888 | CL0081 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A31 | P03-WP061 | P03-CA06 | P03-WP061 | SOURCE_WP_SCOPE | 284200 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 66.666667 | CL0082 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A32 | P03-WP061 | P03-CA06 | P03-WP061 | SOURCE_WP_SCOPE | 142100 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0083 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A33 | P03-WP062 | P03-CA06 | P03-WP062 | SOURCE_WP_SCOPE | 182700 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0084 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A1 | P04-WP011 | P04-CA01 | P04-WP011 | SOURCE_WP_SCOPE | 82500 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0085 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A2 | P04-WP012 | P04-CA01 | P04-WP012 | SOURCE_WP_SCOPE | 82500 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0086 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A3 | P04-WP021 | P04-CA02 | P04-WP021 | SOURCE_WP_SCOPE | 134750 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0087 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A4 | P04-WP022 | P04-CA02 | P04-WP022 | SOURCE_WP_SCOPE | 62563 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000200 | CL0088 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A4b | P04-WP022 | P04-CA02 | P04-WP022 | SOURCE_WP_SCOPE | 62562 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 24.999800 | CL0089 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A15 | P04-WP022 | P04-CA02 | P04-WP022 | SOURCE_WP_SCOPE | 125125 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0090 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A5 | P04-WP031 | P04-CA03 | P04-WP031 | SOURCE_WP_SCOPE | 67375 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0091 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A5b | P04-WP031 | P04-CA03 | P04-WP031 | SOURCE_WP_SCOPE | 67375 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0092 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A5c | P04-WP032 | P04-CA03 | P04-WP032 | SOURCE_WP_SCOPE | 125125 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0093 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A6 | P04-WP032 | P04-CA03 | P04-WP032 | SOURCE_WP_SCOPE | 125125 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0094 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A7 | P04-WP041 | P04-CA04 | P04-WP041 | SOURCE_WP_SCOPE | 247592 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333345 | CL0095 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A8 | P04-WP041 | P04-CA04 | P04-WP041 | SOURCE_WP_SCOPE | 247592 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333345 | CL0096 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A9 | P04-WP041 | P04-CA04 | P04-WP041 | SOURCE_WP_SCOPE | 247592 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333345 | CL0097 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A12 | P04-WP041 | P04-CA04 | P04-WP041 | SOURCE_WP_SCOPE | 1237958 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 41.666655 | CL0098 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A13 | P04-WP041 | P04-CA04 | P04-WP041 | SOURCE_WP_SCOPE | 247592 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333345 | CL0099 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A14 | P04-WP041 | P04-CA04 | P04-WP041 | SOURCE_WP_SCOPE | 247591 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333311 | CL0100 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A16 | P04-WP041 | P04-CA04 | P04-WP041 | SOURCE_WP_SCOPE | 495183 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 16.666655 | CL0101 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A10 | P04-WP042 | P04-CA04 | P04-WP042 | SOURCE_WP_SCOPE | 814000 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0102 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A11 | P04-WP043 | P04-CA04 | P04-WP043 | SOURCE_WP_SCOPE | 284900 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0103 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A17 | P04-WP061 | P04-CA06 | P04-WP061 | SOURCE_WP_SCOPE | 107250 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0104 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A18 | P04-WP062 | P04-CA06 | P04-WP062 | SOURCE_WP_SCOPE | 57750 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0105 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A1 | P05-WP011 | P05-CA01 | P05-WP011 | SOURCE_WP_SCOPE | 96200 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0106 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A8 | P05-WP011 | P05-CA01 | P05-WP011 | SOURCE_WP_SCOPE | 192400 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 66.666667 | CL0107 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A2 | P05-WP012 | P05-CA01 | P05-WP012 | SOURCE_WP_SCOPE | 155400 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0108 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A3 | P05-WP021 | P05-CA02 | P05-WP021 | SOURCE_WP_SCOPE | 199800 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0109 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A4 | P05-WP022 | P05-CA02 | P05-WP022 | SOURCE_WP_SCOPE | 155400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0110 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A4b | P05-WP022 | P05-CA02 | P05-WP022 | SOURCE_WP_SCOPE | 155400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0111 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A10 | P05-WP022 | P05-CA02 | P05-WP022 | SOURCE_WP_SCOPE | 155400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0112 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A5 | P05-WP031 | P05-CA03 | P05-WP031 | SOURCE_WP_SCOPE | 116550 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0113 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A5b | P05-WP031 | P05-CA03 | P05-WP031 | SOURCE_WP_SCOPE | 116550 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0114 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A5c | P05-WP032 | P05-CA03 | P05-WP032 | SOURCE_WP_SCOPE | 72150 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 16.666667 | CL0115 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A11 | P05-WP032 | P05-CA03 | P05-WP032 | SOURCE_WP_SCOPE | 288600 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 66.666667 | CL0116 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A6 | P05-WP032 | P05-CA03 | P05-WP032 | SOURCE_WP_SCOPE | 72150 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 16.666667 | CL0117 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A7 | P05-WP041 | P05-CA04 | P05-WP041 | SOURCE_WP_SCOPE | 240582 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 3.703700 | CL0118 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A9 | P05-WP041 | P05-CA04 | P05-WP041 | SOURCE_WP_SCOPE | 240582 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 3.703700 | CL0119 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A12a | P05-WP041 | P05-CA04 | P05-WP041 | SOURCE_WP_SCOPE | 1202911 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.518517 | CL0120 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-AFIRST | P05-WP041 | P05-CA04 | P05-WP041 | SOURCE_WP_SCOPE | 721747 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.111116 | CL0121 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A13a | P05-WP041 | P05-CA04 | P05-WP041 | SOURCE_WP_SCOPE | 1202911 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.518517 | CL0122 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A14a | P05-WP041 | P05-CA04 | P05-WP041 | SOURCE_WP_SCOPE | 1202911 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.518517 | CL0123 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A15a | P05-WP041 | P05-CA04 | P05-WP041 | SOURCE_WP_SCOPE | 1202911 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.518517 | CL0124 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A16 | P05-WP041 | P05-CA04 | P05-WP041 | SOURCE_WP_SCOPE | 481165 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.407416 | CL0125 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A12b | P05-WP042 | P05-CA04 | P05-WP042 | SOURCE_WP_SCOPE | 379620 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0126 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A13b | P05-WP042 | P05-CA04 | P05-WP042 | SOURCE_WP_SCOPE | 379620 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0127 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A14b | P05-WP042 | P05-CA04 | P05-WP042 | SOURCE_WP_SCOPE | 379620 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0128 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A15b | P05-WP042 | P05-CA04 | P05-WP042 | SOURCE_WP_SCOPE | 379620 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0129 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A12c | P05-WP051 | P05-CA05 | P05-WP051 | SOURCE_WP_SCOPE | 138750 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0130 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A13c | P05-WP051 | P05-CA05 | P05-WP051 | SOURCE_WP_SCOPE | 138750 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0131 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A14c | P05-WP051 | P05-CA05 | P05-WP051 | SOURCE_WP_SCOPE | 138750 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0132 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A15c | P05-WP051 | P05-CA05 | P05-WP051 | SOURCE_WP_SCOPE | 138750 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0133 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A17 | P05-WP061 | P05-CA06 | P05-WP061 | SOURCE_WP_SCOPE | 249750 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0134 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A18 | P05-WP062 | P05-CA06 | P05-WP062 | SOURCE_WP_SCOPE | 83250 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0135 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A1 | P06-WP011 | P06-CA01 | P06-WP011 | SOURCE_WP_SCOPE | 75900 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0136 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A10 | P06-WP011 | P06-CA01 | P06-WP011 | SOURCE_WP_SCOPE | 75900 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0137 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A2 | P06-WP012 | P06-CA01 | P06-WP012 | SOURCE_WP_SCOPE | 124200 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0138 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A3 | P06-WP021 | P06-CA02 | P06-WP021 | SOURCE_WP_SCOPE | 265650 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0139 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A4 | P06-WP022 | P06-CA02 | P06-WP022 | SOURCE_WP_SCOPE | 123338 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000101 | CL0140 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A4b | P06-WP022 | P06-CA02 | P06-WP022 | SOURCE_WP_SCOPE | 123338 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000101 | CL0141 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A7 | P06-WP022 | P06-CA02 | P06-WP022 | SOURCE_WP_SCOPE | 123337 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 24.999899 | CL0142 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A8 | P06-WP022 | P06-CA02 | P06-WP022 | SOURCE_WP_SCOPE | 123337 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 24.999899 | CL0143 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A5 | P06-WP031 | P06-CA03 | P06-WP031 | SOURCE_WP_SCOPE | 89700 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0144 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A5b | P06-WP031 | P06-CA03 | P06-WP031 | SOURCE_WP_SCOPE | 89700 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0145 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A11 | P06-WP031 | P06-CA03 | P06-WP031 | SOURCE_WP_SCOPE | 89700 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0146 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A5c | P06-WP032 | P06-CA03 | P06-WP032 | SOURCE_WP_SCOPE | 89700 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 14.285714 | CL0147 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A6 | P06-WP032 | P06-CA03 | P06-WP032 | SOURCE_WP_SCOPE | 89700 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 14.285714 | CL0148 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A12 | P06-WP032 | P06-CA03 | P06-WP032 | SOURCE_WP_SCOPE | 358800 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 57.142857 | CL0149 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A13 | P06-WP032 | P06-CA03 | P06-WP032 | SOURCE_WP_SCOPE | 89700 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 14.285714 | CL0150 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A15 | P06-WP041 | P06-CA04 | P06-WP041 | SOURCE_WP_SCOPE | 340947 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 12.500027 | CL0151 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-APILOTSTAGE | P06-WP041 | P06-CA04 | P06-WP041 | SOURCE_WP_SCOPE | 454595 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 16.666667 | CL0152 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A16 | P06-WP041 | P06-CA04 | P06-WP041 | SOURCE_WP_SCOPE | 340946 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 12.499991 | CL0153 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-AFIRSTPILOT | P06-WP041 | P06-CA04 | P06-WP041 | SOURCE_WP_SCOPE | 113649 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 4.166676 | CL0154 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A18a | P06-WP041 | P06-CA04 | P06-WP041 | SOURCE_WP_SCOPE | 340946 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 12.499991 | CL0155 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A19a | P06-WP041 | P06-CA04 | P06-WP041 | SOURCE_WP_SCOPE | 340946 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 12.499991 | CL0156 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A20a | P06-WP041 | P06-CA04 | P06-WP041 | SOURCE_WP_SCOPE | 340946 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 12.499991 | CL0157 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A21a | P06-WP041 | P06-CA04 | P06-WP041 | SOURCE_WP_SCOPE | 340946 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 12.499991 | CL0158 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A22 | P06-WP041 | P06-CA04 | P06-WP041 | SOURCE_WP_SCOPE | 113649 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 4.166676 | CL0159 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A9 | P06-WP042 | P06-CA04 | P06-WP042 | SOURCE_WP_SCOPE | 641183 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 75.000058 | CL0160 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A14 | P06-WP042 | P06-CA04 | P06-WP042 | SOURCE_WP_SCOPE | 213727 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 24.999942 | CL0161 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A18b | P06-WP043 | P06-CA04 | P06-WP043 | SOURCE_WP_SCOPE | 122130 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0162 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A19b | P06-WP043 | P06-CA04 | P06-WP043 | SOURCE_WP_SCOPE | 122130 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0163 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A20b | P06-WP043 | P06-CA04 | P06-WP043 | SOURCE_WP_SCOPE | 122130 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0164 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A21b | P06-WP043 | P06-CA04 | P06-WP043 | SOURCE_WP_SCOPE | 122130 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0165 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A17 | P06-WP051 | P06-CA05 | P06-WP051 | SOURCE_WP_SCOPE | 230000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0166 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A23 | P06-WP051 | P06-CA05 | P06-WP051 | SOURCE_WP_SCOPE | 345000 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0167 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A24 | P06-WP051 | P06-CA05 | P06-WP051 | SOURCE_WP_SCOPE | 115000 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 16.666667 | CL0168 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A25 | P06-WP061 | P06-CA06 | P06-WP061 | SOURCE_WP_SCOPE | 144900 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0169 | APPROVED_SYNTHETIC_PORTFOLIO
P06 | P06-A26 | P06-WP062 | P06-CA06 | P06-WP062 | SOURCE_WP_SCOPE | 62100 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0170 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A1 | P07-WP011 | P07-CA01 | P07-WP011 | SOURCE_WP_SCOPE | 61500 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0171 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A2 | P07-WP012 | P07-CA01 | P07-WP012 | SOURCE_WP_SCOPE | 61500 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0172 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A3 | P07-WP021 | P07-CA02 | P07-WP021 | SOURCE_WP_SCOPE | 129150 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0173 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A4 | P07-WP022 | P07-CA02 | P07-WP022 | SOURCE_WP_SCOPE | 119925 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0174 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A4b | P07-WP022 | P07-CA02 | P07-WP022 | SOURCE_WP_SCOPE | 119925 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0175 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A5 | P07-WP031 | P07-CA03 | P07-WP031 | SOURCE_WP_SCOPE | 47834 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333798 | CL0176 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A5b | P07-WP031 | P07-CA03 | P07-WP031 | SOURCE_WP_SCOPE | 47833 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333101 | CL0177 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A8 | P07-WP031 | P07-CA03 | P07-WP031 | SOURCE_WP_SCOPE | 47833 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333101 | CL0178 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A5c | P07-WP032 | P07-CA03 | P07-WP032 | SOURCE_WP_SCOPE | 133250 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0179 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A6 | P07-WP032 | P07-CA03 | P07-WP032 | SOURCE_WP_SCOPE | 133250 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0180 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A7 | P07-WP041 | P07-CA04 | P07-WP041 | SOURCE_WP_SCOPE | 446080 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0181 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A10 | P07-WP041 | P07-CA04 | P07-WP041 | SOURCE_WP_SCOPE | 446080 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0182 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A16 | P07-WP041 | P07-CA04 | P07-WP041 | SOURCE_WP_SCOPE | 892160 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0183 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A11 | P07-WP042 | P07-CA04 | P07-WP042 | SOURCE_WP_SCOPE | 585480 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0184 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A9 | P07-WP043 | P07-CA04 | P07-WP043 | SOURCE_WP_SCOPE | 83640 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 20.000000 | CL0185 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A12 | P07-WP043 | P07-CA04 | P07-WP043 | SOURCE_WP_SCOPE | 250920 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 60.000000 | CL0186 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A13 | P07-WP043 | P07-CA04 | P07-WP043 | SOURCE_WP_SCOPE | 83640 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 20.000000 | CL0187 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A14 | P07-WP051 | P07-CA05 | P07-WP051 | SOURCE_WP_SCOPE | 191333 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 66.666551 | CL0188 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A15 | P07-WP051 | P07-CA05 | P07-WP051 | SOURCE_WP_SCOPE | 95667 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333449 | CL0189 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A17 | P07-WP061 | P07-CA06 | P07-WP061 | SOURCE_WP_SCOPE | 79950 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0190 | APPROVED_SYNTHETIC_PORTFOLIO
P07 | P07-A18 | P07-WP062 | P07-CA06 | P07-WP062 | SOURCE_WP_SCOPE | 43050 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0191 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A1 | P08-WP011 | P08-CA01 | P08-WP011 | SOURCE_WP_SCOPE | 62100 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0192 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A2 | P08-WP012 | P08-CA01 | P08-WP012 | SOURCE_WP_SCOPE | 75900 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0193 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A3 | P08-WP021 | P08-CA02 | P08-WP021 | SOURCE_WP_SCOPE | 128800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0194 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A4 | P08-WP022 | P08-CA02 | P08-WP022 | SOURCE_WP_SCOPE | 119600 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0195 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A4b | P08-WP022 | P08-CA02 | P08-WP022 | SOURCE_WP_SCOPE | 119600 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0196 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A5 | P08-WP031 | P08-CA03 | P08-WP031 | SOURCE_WP_SCOPE | 58880 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0197 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A5b | P08-WP031 | P08-CA03 | P08-WP031 | SOURCE_WP_SCOPE | 58880 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0198 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A8 | P08-WP031 | P08-CA03 | P08-WP031 | SOURCE_WP_SCOPE | 58880 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0199 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A5c | P08-WP032 | P08-CA03 | P08-WP032 | SOURCE_WP_SCOPE | 187680 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0200 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A6 | P08-WP032 | P08-CA03 | P08-WP032 | SOURCE_WP_SCOPE | 187680 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0201 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A7 | P08-WP041 | P08-CA04 | P08-WP041 | SOURCE_WP_SCOPE | 102290 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.263185 | CL0202 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A13 | P08-WP041 | P08-CA04 | P08-WP041 | SOURCE_WP_SCOPE | 102290 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.263185 | CL0203 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A14 | P08-WP041 | P08-CA04 | P08-WP041 | SOURCE_WP_SCOPE | 102289 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.263134 | CL0204 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A9 | P08-WP041 | P08-CA04 | P08-WP041 | SOURCE_WP_SCOPE | 409158 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 21.052637 | CL0205 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A9fat | P08-WP041 | P08-CA04 | P08-WP041 | SOURCE_WP_SCOPE | 102289 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.263134 | CL0206 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A11 | P08-WP041 | P08-CA04 | P08-WP041 | SOURCE_WP_SCOPE | 409158 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 21.052637 | CL0207 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A15 | P08-WP041 | P08-CA04 | P08-WP041 | SOURCE_WP_SCOPE | 409158 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 21.052637 | CL0208 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A17 | P08-WP041 | P08-CA04 | P08-WP041 | SOURCE_WP_SCOPE | 102289 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.263134 | CL0209 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A21 | P08-WP041 | P08-CA04 | P08-WP041 | SOURCE_WP_SCOPE | 204579 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 10.526318 | CL0210 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A10 | P08-WP042 | P08-CA04 | P08-WP042 | SOURCE_WP_SCOPE | 289034 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333410 | CL0211 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A10fat | P08-WP042 | P08-CA04 | P08-WP042 | SOURCE_WP_SCOPE | 72258 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 8.333295 | CL0212 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A12 | P08-WP042 | P08-CA04 | P08-WP042 | SOURCE_WP_SCOPE | 289033 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333295 | CL0213 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A16 | P08-WP042 | P08-CA04 | P08-WP042 | SOURCE_WP_SCOPE | 216775 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0214 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A18 | P08-WP051 | P08-CA05 | P08-WP051 | SOURCE_WP_SCOPE | 138000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0215 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A19 | P08-WP051 | P08-CA05 | P08-WP051 | SOURCE_WP_SCOPE | 138000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0216 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A20 | P08-WP051 | P08-CA05 | P08-WP051 | SOURCE_WP_SCOPE | 138000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0217 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A22 | P08-WP061 | P08-CA06 | P08-WP061 | SOURCE_WP_SCOPE | 89700 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0218 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A23 | P08-WP062 | P08-CA06 | P08-WP062 | SOURCE_WP_SCOPE | 48300 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0219 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A1 | P09-WP011 | P09-CA01 | P09-WP011 | SOURCE_WP_SCOPE | 117000 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0220 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A2 | P09-WP012 | P09-CA01 | P09-WP012 | SOURCE_WP_SCOPE | 117000 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0221 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A3a | P09-WP021 | P09-CA02 | P09-WP021 | SOURCE_WP_SCOPE | 124800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0222 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A3 | P09-WP021 | P09-CA02 | P09-WP021 | SOURCE_WP_SCOPE | 124800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0223 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A4 | P09-WP022 | P09-CA02 | P09-WP022 | SOURCE_WP_SCOPE | 74880 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 20.000000 | CL0224 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A4b | P09-WP022 | P09-CA02 | P09-WP022 | SOURCE_WP_SCOPE | 74880 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 20.000000 | CL0225 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A4c | P09-WP022 | P09-CA02 | P09-WP022 | SOURCE_WP_SCOPE | 74880 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 20.000000 | CL0226 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A19 | P09-WP022 | P09-CA02 | P09-WP022 | SOURCE_WP_SCOPE | 149760 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 40.000000 | CL0227 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A5 | P09-WP031 | P09-CA03 | P09-WP031 | SOURCE_WP_SCOPE | 72800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0228 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A5b | P09-WP031 | P09-CA03 | P09-WP031 | SOURCE_WP_SCOPE | 72800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0229 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A10 | P09-WP031 | P09-CA03 | P09-WP031 | SOURCE_WP_SCOPE | 72800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0230 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A5c | P09-WP032 | P09-CA03 | P09-WP032 | SOURCE_WP_SCOPE | 202800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0231 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A6 | P09-WP032 | P09-CA03 | P09-WP032 | SOURCE_WP_SCOPE | 202800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0232 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A7 | P09-WP041 | P09-CA04 | P09-WP041 | SOURCE_WP_SCOPE | 304869 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142867 | CL0233 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A8 | P09-WP041 | P09-CA04 | P09-WP041 | SOURCE_WP_SCOPE | 304869 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142867 | CL0234 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A9 | P09-WP041 | P09-CA04 | P09-WP041 | SOURCE_WP_SCOPE | 304869 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142867 | CL0235 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A13 | P09-WP041 | P09-CA04 | P09-WP041 | SOURCE_WP_SCOPE | 304869 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142867 | CL0236 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A14 | P09-WP041 | P09-CA04 | P09-WP041 | SOURCE_WP_SCOPE | 304869 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142867 | CL0237 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A12 | P09-WP041 | P09-CA04 | P09-WP041 | SOURCE_WP_SCOPE | 1219474 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 28.571422 | CL0238 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A15 | P09-WP041 | P09-CA04 | P09-WP041 | SOURCE_WP_SCOPE | 304868 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142844 | CL0239 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A16 | P09-WP041 | P09-CA04 | P09-WP041 | SOURCE_WP_SCOPE | 304868 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142844 | CL0240 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A17 | P09-WP041 | P09-CA04 | P09-WP041 | SOURCE_WP_SCOPE | 304868 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 7.142844 | CL0241 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A21 | P09-WP041 | P09-CA04 | P09-WP041 | SOURCE_WP_SCOPE | 609737 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 14.285711 | CL0242 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A11 | P09-WP042 | P09-CA04 | P09-WP042 | SOURCE_WP_SCOPE | 898560 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0243 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A20 | P09-WP043 | P09-CA04 | P09-WP043 | SOURCE_WP_SCOPE | 449280 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0244 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A18 | P09-WP051 | P09-CA05 | P09-WP051 | SOURCE_WP_SCOPE | 468000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0245 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A22 | P09-WP061 | P09-CA06 | P09-WP061 | SOURCE_WP_SCOPE | 152100 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0246 | APPROVED_SYNTHETIC_PORTFOLIO
P09 | P09-A23 | P09-WP062 | P09-CA06 | P09-WP062 | SOURCE_WP_SCOPE | 81900 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0247 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A1 | P10-WP011 | P10-CA01 | P10-WP011 | SOURCE_WP_SCOPE | 66600 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0248 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A4 | P10-WP021 | P10-CA02 | P10-WP021 | SOURCE_WP_SCOPE | 266400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0249 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A3 | P10-WP022 | P10-CA02 | P10-WP022 | SOURCE_WP_SCOPE | 99900 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0250 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A5 | P10-WP022 | P10-CA02 | P10-WP022 | SOURCE_WP_SCOPE | 99900 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0251 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A6b | P10-WP022 | P10-CA02 | P10-WP022 | SOURCE_WP_SCOPE | 99900 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0252 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A6 | P10-WP022 | P10-CA02 | P10-WP022 | SOURCE_WP_SCOPE | 99900 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0253 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A7 | P10-WP031 | P10-CA03 | P10-WP031 | SOURCE_WP_SCOPE | 60434 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333701 | CL0254 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A7b | P10-WP031 | P10-CA03 | P10-WP031 | SOURCE_WP_SCOPE | 60433 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333149 | CL0255 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A9 | P10-WP031 | P10-CA03 | P10-WP031 | SOURCE_WP_SCOPE | 60433 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333149 | CL0256 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A7c | P10-WP032 | P10-CA03 | P10-WP032 | SOURCE_WP_SCOPE | 168350 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0257 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A8 | P10-WP032 | P10-CA03 | P10-WP032 | SOURCE_WP_SCOPE | 168350 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0258 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-IF-01 | P10-WP041 | P10-CA04 | P10-WP041 | SOURCE_WP_SCOPE | 143745 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0259 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A14 | P10-WP041 | P10-CA04 | P10-WP041 | SOURCE_WP_SCOPE | 431235 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 75.000000 | CL0260 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A11 | P10-WP042 | P10-CA04 | P10-WP042 | SOURCE_WP_SCOPE | 293040 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 57.142857 | CL0261 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A15 | P10-WP042 | P10-CA04 | P10-WP042 | SOURCE_WP_SCOPE | 219780 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 42.857143 | CL0262 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A10 | P10-WP043 | P10-CA04 | P10-WP043 | SOURCE_WP_SCOPE | 124320 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 26.666667 | CL0263 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A12 | P10-WP043 | P10-CA04 | P10-WP043 | SOURCE_WP_SCOPE | 124320 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 26.666667 | CL0264 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A16 | P10-WP043 | P10-CA04 | P10-WP043 | SOURCE_WP_SCOPE | 124320 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 26.666667 | CL0265 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A17 | P10-WP043 | P10-CA04 | P10-WP043 | SOURCE_WP_SCOPE | 93240 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 20.000000 | CL0266 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A13 | P10-WP051 | P10-CA05 | P10-WP051 | SOURCE_WP_SCOPE | 41353 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.882361 | CL0267 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A18 | P10-WP051 | P10-CA05 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.764723 | CL0268 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A19 | P10-WP051 | P10-CA05 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.764723 | CL0269 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A20 | P10-WP051 | P10-CA05 | P10-WP051 | SOURCE_WP_SCOPE | 41353 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.882361 | CL0270 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A21 | P10-WP051 | P10-CA05 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.764723 | CL0271 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A22 | P10-WP051 | P10-CA05 | P10-WP051 | SOURCE_WP_SCOPE | 41353 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.882361 | CL0272 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A23 | P10-WP051 | P10-CA05 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.764723 | CL0273 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A24 | P10-WP051 | P10-CA05 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.764723 | CL0274 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A25 | P10-WP051 | P10-CA05 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.764723 | CL0275 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A27 | P10-WP051 | P10-CA05 | P10-WP051 | SOURCE_WP_SCOPE | 82705 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 11.764580 | CL0276 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A26 | P10-WP061 | P10-CA06 | P10-WP061 | SOURCE_WP_SCOPE | 77700 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0277 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A28 | P10-WP062 | P10-CA06 | P10-WP062 | SOURCE_WP_SCOPE | 33300 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0278 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A1 | P11-WP011 | P11-CA01 | P11-WP011 | SOURCE_WP_SCOPE | 76800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0279 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A2 | P11-WP012 | P11-CA01 | P11-WP012 | SOURCE_WP_SCOPE | 51200 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0280 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A3 | P11-WP021 | P11-CA02 | P11-WP021 | SOURCE_WP_SCOPE | 57600 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0281 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A4 | P11-WP022 | P11-CA02 | P11-WP022 | SOURCE_WP_SCOPE | 67200 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0282 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A8 | P11-WP022 | P11-CA02 | P11-WP022 | SOURCE_WP_SCOPE | 67200 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0283 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A5 | P11-WP031 | P11-CA03 | P11-WP031 | SOURCE_WP_SCOPE | 50400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0284 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A5b | P11-WP031 | P11-CA03 | P11-WP031 | SOURCE_WP_SCOPE | 50400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0285 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A5c | P11-WP032 | P11-CA03 | P11-WP032 | SOURCE_WP_SCOPE | 93600 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0286 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A6 | P11-WP032 | P11-CA03 | P11-WP032 | SOURCE_WP_SCOPE | 93600 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0287 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A10 | P11-WP041 | P11-CA04 | P11-WP041 | SOURCE_WP_SCOPE | 95822 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 5.555543 | CL0288 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A9 | P11-WP041 | P11-CA04 | P11-WP041 | SOURCE_WP_SCOPE | 383289 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 22.222229 | CL0289 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-AFIRST | P11-WP041 | P11-CA04 | P11-WP041 | SOURCE_WP_SCOPE | 287467 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 16.666686 | CL0290 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-B1inst | P11-WP041 | P11-CA04 | P11-WP041 | SOURCE_WP_SCOPE | 479111 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 27.777771 | CL0291 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-B2inst | P11-WP041 | P11-CA04 | P11-WP041 | SOURCE_WP_SCOPE | 479111 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 27.777771 | CL0292 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-B1rest | P11-WP043 | P11-CA04 | P11-WP043 | SOURCE_WP_SCOPE | 168000 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0293 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-B2rest | P11-WP043 | P11-CA04 | P11-WP043 | SOURCE_WP_SCOPE | 168000 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 50.000000 | CL0294 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A7 | P11-WP051 | P11-CA05 | P11-WP051 | SOURCE_WP_SCOPE | 64000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0295 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-B1test | P11-WP051 | P11-CA05 | P11-WP051 | SOURCE_WP_SCOPE | 64000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0296 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-B2test | P11-WP051 | P11-CA05 | P11-WP051 | SOURCE_WP_SCOPE | 64000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0297 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A11 | P11-WP051 | P11-CA05 | P11-WP051 | SOURCE_WP_SCOPE | 64000 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 25.000000 | CL0298 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-B1gis | P11-WP061 | P11-CA06 | P11-WP061 | SOURCE_WP_SCOPE | 22400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0299 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-B2gis | P11-WP061 | P11-CA06 | P11-WP061 | SOURCE_WP_SCOPE | 22400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0300 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A12 | P11-WP061 | P11-CA06 | P11-WP061 | SOURCE_WP_SCOPE | 22400 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 33.333333 | CL0301 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-A13 | P11-WP062 | P11-CA06 | P11-WP062 | SOURCE_WP_SCOPE | 28800 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 100.000000 | CL0302 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y1A1 | P12-WP011 | P12-CA01 | P12-WP011 | SOURCE_WP_SCOPE | 28560 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 14.000000 | CL0303 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y1A2 | P12-WP011 | P12-CA01 | P12-WP011 | SOURCE_WP_SCOPE | 28560 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 14.000000 | CL0304 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y2A1 | P12-WP011 | P12-CA01 | P12-WP011 | SOURCE_WP_SCOPE | 36720 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.000000 | CL0305 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y2A2 | P12-WP011 | P12-CA01 | P12-WP011 | SOURCE_WP_SCOPE | 36720 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.000000 | CL0306 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y3A1 | P12-WP011 | P12-CA01 | P12-WP011 | SOURCE_WP_SCOPE | 36720 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.000000 | CL0307 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y3A2 | P12-WP011 | P12-CA01 | P12-WP011 | SOURCE_WP_SCOPE | 36720 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.000000 | CL0308 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y1A3 | P12-WP021 | P12-CA02 | P12-WP021 | SOURCE_WP_SCOPE | 42840 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 14.000000 | CL0309 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y1A4 | P12-WP021 | P12-CA02 | P12-WP021 | SOURCE_WP_SCOPE | 42840 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 14.000000 | CL0310 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y2A3 | P12-WP021 | P12-CA02 | P12-WP021 | SOURCE_WP_SCOPE | 55080 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.000000 | CL0311 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y2A4 | P12-WP021 | P12-CA02 | P12-WP021 | SOURCE_WP_SCOPE | 55080 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.000000 | CL0312 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y3A3 | P12-WP021 | P12-CA02 | P12-WP021 | SOURCE_WP_SCOPE | 55080 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.000000 | CL0313 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y3A4 | P12-WP021 | P12-CA02 | P12-WP021 | SOURCE_WP_SCOPE | 55080 | QUANTITY_OR_WEIGHTED | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 18.000000 | CL0314 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y1A5 | P12-WP031 | P12-CA03 | P12-WP031 | SOURCE_WP_SCOPE | 114240 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 28.000000 | CL0315 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y2A5 | P12-WP031 | P12-CA03 | P12-WP031 | SOURCE_WP_SCOPE | 146880 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 36.000000 | CL0316 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y3A5 | P12-WP031 | P12-CA03 | P12-WP031 | SOURCE_WP_SCOPE | 146880 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 36.000000 | CL0317 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y1A6 | P12-WP041 | P12-CA04 | P12-WP041 | SOURCE_WP_SCOPE | 944194 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 28.000012 | CL0318 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y2A6 | P12-WP041 | P12-CA04 | P12-WP041 | SOURCE_WP_SCOPE | 1213963 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 35.999994 | CL0319 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y3A6 | P12-WP041 | P12-CA04 | P12-WP041 | SOURCE_WP_SCOPE | 1213963 | QUANTITY_DRIVEN_PROVISIONAL | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 35.999994 | CL0320 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y1A7 | P12-WP051 | P12-CA05 | P12-WP051 | SOURCE_WP_SCOPE | 57120 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 28.000000 | CL0321 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y2A7 | P12-WP051 | P12-CA05 | P12-WP051 | SOURCE_WP_SCOPE | 73440 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 36.000000 | CL0322 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y3A7 | P12-WP051 | P12-CA05 | P12-WP051 | SOURCE_WP_SCOPE | 73440 | WEIGHTED_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 36.000000 | CL0323 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y1A8 | P12-WP061 | P12-CA06 | P12-WP061 | SOURCE_WP_SCOPE | 28560 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 28.000000 | CL0324 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y2A8 | P12-WP061 | P12-CA06 | P12-WP061 | SOURCE_WP_SCOPE | 36720 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 36.000000 | CL0325 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y3A8 | P12-WP061 | P12-CA06 | P12-WP061 | SOURCE_WP_SCOPE | 36720 | WORKDAY_OR_DELIVERABLE | Original Phase 3A activity allocation (synthetic), repartitioned when noted | PROPOSED_NOT_APPROVED | 36.000000 | CL0326 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A28 | P03-WP051 | P03-CA05 | P03-WP052 | Performance / Acceptance Testing | 487200 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Exact-name match; A28 previous WP051 share redistributed to A26/A27 | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 100.000000 | CL0327 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A29 | P03-WP041 | P03-CA05 | P03-WP053 | SCADA checkout / regulatory sign-off | 121800 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Cross-CA cost owner. Assumed equal split; original A29/A30 allocations must represent different non-overlapping work; UNVERIFIED | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 50.000000 | CL0328 | APPROVED_SYNTHETIC_PORTFOLIO
P03 | P03-A30 | P03-WP022 | P03-CA05 | P03-WP053 | SCADA checkout / regulatory sign-off | 121800 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Cross-CA cost owner. Assumed equal split; original A29/A30 allocations must represent different non-overlapping work; UNVERIFIED | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 50.000000 | CL0329 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A12c | P05-WP051 | P05-CA04 | P05-WP043 | Zone sampling / water quality | 105450 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Cross-CA. Assumed equal split. Existing WP051 activity budgets must represent distinct notification/startup tasks; UNVERIFIED | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 25.000000 | CL0330 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A13c | P05-WP051 | P05-CA04 | P05-WP043 | Zone sampling / water quality | 105450 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Cross-CA. Assumed equal split. Existing WP051 activity budgets must represent distinct notification/startup tasks; UNVERIFIED | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 25.000000 | CL0331 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A14c | P05-WP051 | P05-CA04 | P05-WP043 | Zone sampling / water quality | 105450 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Cross-CA. Assumed equal split. Existing WP051 activity budgets must represent distinct notification/startup tasks; UNVERIFIED | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 25.000000 | CL0332 | APPROVED_SYNTHETIC_PORTFOLIO
P05 | P05-A15c | P05-WP051 | P05-CA04 | P05-WP043 | Zone sampling / water quality | 105450 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Cross-CA. Assumed equal split. Existing WP051 activity budgets must represent distinct notification/startup tasks; UNVERIFIED | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 25.000000 | CL0333 | APPROVED_SYNTHETIC_PORTFOLIO
P10 | P10-A2 | P10-WP011 | P10-CA01 | P10-WP012 | Project definition | 81400 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Exact-name match; former WP011 share of A2 moved to A1 | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 100.000000 | CL0334 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-B1gis | P11-WP061 | P11-CA04 | P11-WP042 | GIS mapping | 89600 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Cross-CA. Assumed equal split; existing WP061 budgets must represent distinct documentation/turnover; UNVERIFIED | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 50.000000 | CL0335 | APPROVED_SYNTHETIC_PORTFOLIO
P11 | P11-B2gis | P11-WP061 | P11-CA04 | P11-WP042 | GIS mapping | 89600 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Cross-CA. Assumed equal split; existing WP061 budgets must represent distinct documentation/turnover; UNVERIFIED | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 50.000000 | CL0336 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y1A6 | P12-WP041 | P12-CA04 | P12-WP042 | Emergency work orders | 141086 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Existing annual field execution; emergency work-order proportions 28/36/36 are synthetic and not individually evidenced | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 27.999921 | CL0337 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y2A6 | P12-WP041 | P12-CA04 | P12-WP042 | Emergency work orders | 181397 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Existing annual field execution; emergency work-order proportions 28/36/36 are synthetic and not individually evidenced | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 36.000040 | CL0338 | APPROVED_SYNTHETIC_PORTFOLIO
P12 | P12-Y3A6 | P12-WP041 | P12-CA04 | P12-WP042 | Emergency work orders | 181397 | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | Existing annual field execution; emergency work-order proportions 28/36/36 are synthetic and not individually evidenced | CONDITIONAL_SCOPE_OR_ACCOUNTING_APPROVAL | 36.000040 | CL0339 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A14 | P04-WP041 | P04-CA05 | P04-WP051 | FUNCTIONAL_TEST_PREPARATION_REFILL_DISINFECTION_COMPONENT | 132000 | WEIGHTED_ACCEPTANCE_GATE | P04-TEST-01: synthetic separate refill/disinfection functional-preparation component; A14 existing WP041 line is tank construction/refill work; no independent test plan | CONDITIONAL_SCOPE_ASSUMPTION_NOT_APPROVED | 40.000000 | CL0340 | APPROVED_SYNTHETIC_PORTFOLIO
P04 | P04-A15 | P04-WP022 | P04-CA05 | P04-WP051 | FUNCTIONAL_ACCEPTANCE_CLEARANCE_COMPONENT | 198000 | WEIGHTED_ACCEPTANCE_GATE | P04-TEST-01: synthetic separate commissioning acceptance/clearance evidence; A15 existing WP022 line is regulatory sampling/design-review cost; independent acceptance protocol not verified | CONDITIONAL_SCOPE_ASSUMPTION_NOT_APPROVED | 60.000000 | CL0341 | APPROVED_SYNTHETIC_PORTFOLIO
P08 | P08-A15 | P08-WP041 | P08-CA04 | P08-WP043 | VENDOR_INTEGRATED_FUEL_TANK_PIPING_INSTALLATION | 179400 | WEIGHTED_VENDOR_DELIVERABLE | P08-FUEL-01: synthetic explicit vendor inclusion of tank, supply piping, containment inspection within installation window; existing WP041 A15 line remains generator rigging only; vendor package not verified | CONDITIONAL_SCOPE_ASSUMPTION_NOT_APPROVED | 100.000000 | CL0342 | APPROVED_SYNTHETIC_PORTFOLIO

## COST_EARNING_RULES
Cost_Ownership_Line_ID | Project_ID | Schedule_Activity_ID | Schedule_WP_ID | Funded_Cost_WP_ID | Cost_Component | Component_BAC_USD | Activity_Start | Activity_Finish | Calendar | Proposed_Rule_Code | Weights_Pct | Synthetic_Planned_Event_Dates | Scheduled_Recognition_Definition | Future_EV_Evidence_Requirement | Source_Method | Prior_Readiness_Status | Provenance | Approval_Status
CL0001 | P01 | P01-A1 | P01-WP011 | P01-WP011 | SOURCE_WP_SCOPE | 122100 | 2025-01-02 | 2025-01-15 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0002 | P01 | P01-A2 | P01-WP012 | P01-WP012 | SOURCE_WP_SCOPE | 99900 | 2025-01-16 | 2025-01-22 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0003 | P01 | P01-A3 | P01-WP021 | P01-WP021 | SOURCE_WP_SCOPE | 181300 | 2025-01-23 | 2025-02-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0004 | P01 | P01-A4 | P01-WP022 | P01-WP022 | SOURCE_WP_SCOPE | 84175 | 2025-03-06 | 2025-04-09 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0005 | P01 | P01-A4b | P01-WP022 | P01-WP022 | SOURCE_WP_SCOPE | 84175 | 2025-04-10 | 2025-04-30 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0006 | P01 | P01-A12 | P01-WP022 | P01-WP022 | SOURCE_WP_SCOPE | 168350 | 2025-10-14 | 2025-10-20 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-10-20 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0007 | P01 | P01-A7a | P01-WP031 | P01-WP031 | SOURCE_WP_SCOPE | 69067 | 2025-05-15 | 2025-06-04 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-05-19¦2025-05-26¦2025-05-30¦2025-06-04 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0008 | P01 | P01-A5 | P01-WP031 | P01-WP031 | SOURCE_WP_SCOPE | 69067 | 2025-03-27 | 2025-04-16 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0009 | P01 | P01-A5b | P01-WP031 | P01-WP031 | SOURCE_WP_SCOPE | 69066 | 2025-04-17 | 2025-04-30 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0010 | P01 | P01-A6 | P01-WP032 | P01-WP032 | SOURCE_WP_SCOPE | 384800 | 2025-05-15 | 2025-06-04 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0011 | P01 | P01-A7b | P01-WP041 | P01-WP041 | SOURCE_WP_SCOPE | 1278720 | 2025-06-05 | 2025-07-16 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-06-12¦2025-06-25¦2025-07-08¦2025-07-16 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0012 | P01 | P01-A4u | P01-WP041 | P01-WP041 | SOURCE_WP_SCOPE | 319680 | 2025-02-20 | 2025-03-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0013 | P01 | P01-A7c | P01-WP041 | P01-WP041 | SOURCE_WP_SCOPE | 1278720 | 2025-07-17 | 2025-07-28 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-07-18¦2025-07-22¦2025-07-25¦2025-07-28 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0014 | P01 | P01-A8 | P01-WP041 | P01-WP041 | SOURCE_WP_SCOPE | 319680 | 2025-07-29 | 2025-09-29 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0015 | P01 | P01-A15 | P01-WP041 | P01-WP041 | SOURCE_WP_SCOPE | 639360 | 2025-11-11 | 2025-11-24 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-11-24 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0016 | P01 | P01-A9 | P01-WP042 | P01-WP042 | SOURCE_WP_SCOPE | 426240 | 2025-08-19 | 2025-09-08 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0017 | P01 | P01-A9b | P01-WP042 | P01-WP042 | SOURCE_WP_SCOPE | 426240 | 2025-08-26 | 2025-09-08 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0018 | P01 | P01-A10 | P01-WP043 | P01-WP043 | SOURCE_WP_SCOPE | 639360 | 2025-10-21 | 2025-11-10 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0019 | P01 | P01-A11 | P01-WP051 | P01-WP051 | SOURCE_WP_SCOPE | 518000 | 2025-10-07 | 2025-10-13 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-10-13 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0020 | P01 | P01-A13 | P01-WP061 | P01-WP061 | SOURCE_WP_SCOPE | 144300 | 2025-11-25 | 2025-12-08 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-12-08 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0021 | P01 | P01-A14 | P01-WP062 | P01-WP062 | SOURCE_WP_SCOPE | 77700 | 2025-12-09 | 2025-12-29 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-12-29 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0022 | P02 | P02-A1 | P02-WP011 | P02-WP011 | SOURCE_WP_SCOPE | 132000 | 2025-02-03 | 2025-02-14 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0023 | P02 | P02-A2 | P02-WP012 | P02-WP012 | SOURCE_WP_SCOPE | 132000 | 2025-02-17 | 2025-02-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0024 | P02 | P02-A3 | P02-WP021 | P02-WP021 | SOURCE_WP_SCOPE | 277200 | 2025-02-24 | 2025-03-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0025 | P02 | P02-A4 | P02-WP022 | P02-WP022 | SOURCE_WP_SCOPE | 257400 | 2025-03-24 | 2025-04-25 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0026 | P02 | P02-A4b | P02-WP022 | P02-WP022 | SOURCE_WP_SCOPE | 257400 | 2025-04-28 | 2025-05-23 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0027 | P02 | P02-A5 | P02-WP031 | P02-WP031 | SOURCE_WP_SCOPE | 107800 | 2025-04-14 | 2025-05-02 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0028 | P02 | P02-A5b | P02-WP031 | P02-WP031 | SOURCE_WP_SCOPE | 107800 | 2025-05-05 | 2025-05-16 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0029 | P02 | P02-A6 | P02-WP032 | P02-WP032 | SOURCE_WP_SCOPE | 400400 | 2025-06-02 | 2025-06-13 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0030 | P02 | P02-A6b | P02-WP041 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | 2025-02-03 | 2025-02-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0031 | P02 | P02-A7a | P02-WP041 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | 2025-06-02 | 2025-06-27 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-06-05¦2025-06-13¦2025-06-23¦2025-06-27 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0032 | P02 | P02-A8 | P02-WP041 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | 2025-06-16 | 2025-06-27 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0033 | P02 | P02-A7b | P02-WP041 | P02-WP041 | SOURCE_WP_SCOPE | 760320 | 2025-06-30 | 2025-10-31 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-07-23¦2025-08-29¦2025-10-07¦2025-10-31 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0034 | P02 | P02-A9 | P02-WP041 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | 2025-06-30 | 2025-07-18 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0035 | P02 | P02-A7c | P02-WP041 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | 2025-11-03 | 2025-11-14 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0036 | P02 | P02-A7d | P02-WP041 | P02-WP041 | SOURCE_WP_SCOPE | 760320 | 2025-11-17 | 2025-11-26 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-11-18¦2025-11-20¦2025-11-25¦2025-11-26 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0037 | P02 | P02-A10 | P02-WP041 | P02-WP041 | SOURCE_WP_SCOPE | 190080 | 2025-11-27 | 2025-12-31 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0038 | P02 | P02-A15b | P02-WP041 | P02-WP041 | SOURCE_WP_SCOPE | 380160 | 2026-01-22 | 2026-02-04 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-02-04 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0039 | P02 | P02-A11a | P02-WP042 | P02-WP042 | SOURCE_WP_SCOPE | 221760 | 2025-06-02 | 2025-06-27 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-06-05¦2025-06-13¦2025-06-23¦2025-06-27 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0040 | P02 | P02-A6c | P02-WP042 | P02-WP042 | SOURCE_WP_SCOPE | 221760 | 2025-02-03 | 2025-02-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0041 | P02 | P02-A11b | P02-WP042 | P02-WP042 | SOURCE_WP_SCOPE | 887040 | 2025-06-30 | 2025-10-17 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-07-21¦2025-08-22¦2025-09-25¦2025-10-17 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0042 | P02 | P02-A11c | P02-WP042 | P02-WP042 | SOURCE_WP_SCOPE | 221760 | 2025-10-20 | 2025-10-31 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0043 | P02 | P02-A11d | P02-WP042 | P02-WP042 | SOURCE_WP_SCOPE | 887040 | 2025-11-03 | 2025-11-12 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-11-04¦2025-11-06¦2025-11-11¦2025-11-12 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0044 | P02 | P02-A12 | P02-WP042 | P02-WP042 | SOURCE_WP_SCOPE | 221760 | 2025-11-13 | 2025-12-10 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0045 | P02 | P02-A13 | P02-WP043 | P02-WP043 | SOURCE_WP_SCOPE | 633600 | 2025-07-21 | 2025-08-15 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0046 | P02 | P02-A14 | P02-WP051 | P02-WP051 | SOURCE_WP_SCOPE | 264000 | 2026-01-01 | 2026-01-14 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-01-14 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0047 | P02 | P02-A15 | P02-WP051 | P02-WP051 | SOURCE_WP_SCOPE | 264000 | 2026-01-15 | 2026-01-21 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-01-21 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0048 | P02 | P02-A16 | P02-WP061 | P02-WP061 | SOURCE_WP_SCOPE | 171600 | 2026-01-22 | 2026-02-04 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-02-04 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0049 | P02 | P02-A17 | P02-WP062 | P02-WP062 | SOURCE_WP_SCOPE | 92400 | 2026-02-05 | 2026-02-25 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-02-25 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0050 | P03 | P03-A1 | P03-WP011 | P03-WP011 | SOURCE_WP_SCOPE | 274050 | 2025-01-02 | 2025-01-22 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0051 | P03 | P03-A2 | P03-WP012 | P03-WP012 | SOURCE_WP_SCOPE | 334950 | 2025-01-23 | 2025-02-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0052 | P03 | P03-A3 | P03-WP021 | P03-WP021 | SOURCE_WP_SCOPE | 292320 | 2025-02-20 | 2025-04-16 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0053 | P03 | P03-A4 | P03-WP021 | P03-WP021 | SOURCE_WP_SCOPE | 292320 | 2025-04-17 | 2025-05-07 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0054 | P03 | P03-A2b | P03-WP022 | P03-WP022 | SOURCE_WP_SCOPE | 138040 | 2025-02-06 | 2025-02-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0055 | P03 | P03-A5 | P03-WP022 | P03-WP022 | SOURCE_WP_SCOPE | 414120 | 2025-05-08 | 2025-06-18 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0056 | P03 | P03-A6 | P03-WP022 | P03-WP022 | SOURCE_WP_SCOPE | 138040 | 2025-06-19 | 2025-07-09 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0057 | P03 | P03-A7 | P03-WP022 | P03-WP022 | SOURCE_WP_SCOPE | 138040 | 2025-06-26 | 2025-07-23 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0058 | P03 | P03-A7b | P03-WP022 | P03-WP022 | SOURCE_WP_SCOPE | 138040 | 2025-07-24 | 2025-09-03 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0059 | P03 | P03-A30 | P03-WP022 | P03-WP022 | SOURCE_WP_SCOPE | 276080 | 2026-11-05 | 2026-12-02 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-02 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0060 | P03 | P03-A8 | P03-WP031 | P03-WP031 | SOURCE_WP_SCOPE | 248675 | 2025-07-10 | 2025-08-06 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0061 | P03 | P03-A9 | P03-WP031 | P03-WP031 | SOURCE_WP_SCOPE | 248675 | 2025-08-07 | 2025-08-27 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0062 | P03 | P03-A9b | P03-WP032 | P03-WP032 | SOURCE_WP_SCOPE | 461825 | 2025-08-28 | 2025-09-17 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0063 | P03 | P03-A10 | P03-WP032 | P03-WP032 | SOURCE_WP_SCOPE | 461825 | 2025-09-18 | 2025-10-15 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0064 | P03 | P03-A11 | P03-WP041 | P03-WP041 | SOURCE_WP_SCOPE | 434659 | 2025-09-18 | 2025-10-15 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-09-23¦2025-10-01¦2025-10-09¦2025-10-15 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0065 | P03 | P03-A12 | P03-WP041 | P03-WP041 | SOURCE_WP_SCOPE | 1738635 | 2025-10-16 | 2026-03-04 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-11-12¦2025-12-24¦2026-02-04¦2026-03-04 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0066 | P03 | P03-A13 | P03-WP041 | P03-WP041 | SOURCE_WP_SCOPE | 434659 | 2026-03-05 | 2026-03-25 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-03-09¦2026-03-16¦2026-03-20¦2026-03-25 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0067 | P03 | P03-A14 | P03-WP041 | P03-WP041 | SOURCE_WP_SCOPE | 1738635 | 2026-03-26 | 2026-04-08 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-03-27¦2026-04-01¦2026-04-06¦2026-04-08 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0068 | P03 | P03-A15 | P03-WP041 | P03-WP041 | SOURCE_WP_SCOPE | 2173294 | 2026-04-09 | 2026-07-01 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0069 | P03 | P03-A29 | P03-WP041 | P03-WP041 | SOURCE_WP_SCOPE | 869318 | 2026-09-10 | 2026-09-30 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-09-30 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0070 | P03 | P03-A16 | P03-WP042 | P03-WP042 | SOURCE_WP_SCOPE | 355250 | 2025-09-18 | 2025-10-15 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-09-23¦2025-10-01¦2025-10-09¦2025-10-15 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0071 | P03 | P03-A17 | P03-WP042 | P03-WP042 | SOURCE_WP_SCOPE | 1421000 | 2025-10-16 | 2026-02-04 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-11-06¦2025-12-10¦2026-01-13¦2026-02-04 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0072 | P03 | P03-A18 | P03-WP042 | P03-WP042 | SOURCE_WP_SCOPE | 355250 | 2026-02-05 | 2026-02-18 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0073 | P03 | P03-A19 | P03-WP042 | P03-WP042 | SOURCE_WP_SCOPE | 1421000 | 2026-02-19 | 2026-03-02 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-02-20¦2026-02-24¦2026-02-27¦2026-03-02 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0074 | P03 | P03-A20 | P03-WP042 | P03-WP042 | SOURCE_WP_SCOPE | 1065750 | 2026-05-07 | 2026-07-08 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0075 | P03 | P03-A25 | P03-WP042 | P03-WP042 | SOURCE_WP_SCOPE | 355250 | 2026-07-09 | 2026-08-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0076 | P03 | P03-A21 | P03-WP043 | P03-WP043 | SOURCE_WP_SCOPE | 153942 | 2025-09-18 | 2025-10-08 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-09-22¦2025-09-29¦2025-10-03¦2025-10-08 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0077 | P03 | P03-A22 | P03-WP043 | P03-WP043 | SOURCE_WP_SCOPE | 615767 | 2025-10-09 | 2025-12-17 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-10-22¦2025-11-12¦2025-12-03¦2025-12-17 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0078 | P03 | P03-A23 | P03-WP043 | P03-WP043 | SOURCE_WP_SCOPE | 615766 | 2025-12-18 | 2025-12-29 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-12-19¦2025-12-23¦2025-12-26¦2025-12-29 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0079 | P03 | P03-A24 | P03-WP043 | P03-WP043 | SOURCE_WP_SCOPE | 461825 | 2026-05-21 | 2026-06-24 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0080 | P03 | P03-A26 | P03-WP051 | P03-WP051 | SOURCE_WP_SCOPE | 446601 | 2026-08-06 | 2026-08-26 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-08-26 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0081 | P03 | P03-A27 | P03-WP051 | P03-WP051 | SOURCE_WP_SCOPE | 446599 | 2026-08-27 | 2026-10-07 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-10-07 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0082 | P03 | P03-A31 | P03-WP061 | P03-WP061 | SOURCE_WP_SCOPE | 284200 | 2026-12-03 | 2026-12-23 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-23 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0083 | P03 | P03-A32 | P03-WP061 | P03-WP061 | SOURCE_WP_SCOPE | 142100 | 2026-12-03 | 2026-12-30 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-30 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0084 | P03 | P03-A33 | P03-WP062 | P03-WP062 | SOURCE_WP_SCOPE | 182700 | 2026-12-31 | 2027-01-27 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-01-27 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0085 | P04 | P04-A1 | P04-WP011 | P04-WP011 | SOURCE_WP_SCOPE | 82500 | 2025-06-02 | 2025-06-13 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0086 | P04 | P04-A2 | P04-WP012 | P04-WP012 | SOURCE_WP_SCOPE | 82500 | 2025-06-16 | 2025-06-20 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0087 | P04 | P04-A3 | P04-WP021 | P04-WP021 | SOURCE_WP_SCOPE | 134750 | 2025-06-23 | 2025-07-18 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0088 | P04 | P04-A4 | P04-WP022 | P04-WP022 | SOURCE_WP_SCOPE | 62563 | 2025-08-04 | 2025-09-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0089 | P04 | P04-A4b | P04-WP022 | P04-WP022 | SOURCE_WP_SCOPE | 62562 | 2025-09-08 | 2025-09-26 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0090 | P04 | P04-A15 | P04-WP022 | P04-WP022 | SOURCE_WP_SCOPE | 125125 | 2026-03-09 | 2026-03-13 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-03-13 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0091 | P04 | P04-A5 | P04-WP031 | P04-WP031 | SOURCE_WP_SCOPE | 67375 | 2025-08-18 | 2025-09-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0092 | P04 | P04-A5b | P04-WP031 | P04-WP031 | SOURCE_WP_SCOPE | 67375 | 2025-09-08 | 2025-09-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0093 | P04 | P04-A5c | P04-WP032 | P04-WP032 | SOURCE_WP_SCOPE | 125125 | 2025-09-22 | 2025-10-03 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0094 | P04 | P04-A6 | P04-WP032 | P04-WP032 | SOURCE_WP_SCOPE | 125125 | 2025-10-27 | 2025-11-07 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0095 | P04 | P04-A7 | P04-WP041 | P04-WP041 | SOURCE_WP_SCOPE | 247592 | 2025-10-27 | 2025-11-14 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0096 | P04 | P04-A8 | P04-WP041 | P04-WP041 | SOURCE_WP_SCOPE | 247592 | 2025-11-17 | 2025-11-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0097 | P04 | P04-A9 | P04-WP041 | P04-WP041 | SOURCE_WP_SCOPE | 247592 | 2025-11-24 | 2025-12-12 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0098 | P04 | P04-A12 | P04-WP041 | P04-WP041 | SOURCE_WP_SCOPE | 1237958 | 2026-01-19 | 2026-02-13 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0099 | P04 | P04-A13 | P04-WP041 | P04-WP041 | SOURCE_WP_SCOPE | 247592 | 2026-02-16 | 2026-02-27 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0100 | P04 | P04-A14 | P04-WP041 | P04-WP041 | SOURCE_WP_SCOPE | 247591 | 2026-03-02 | 2026-03-06 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0101 | P04 | P04-A16 | P04-WP041 | P04-WP041 | SOURCE_WP_SCOPE | 495183 | 2026-03-16 | 2026-03-27 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-03-27 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0102 | P04 | P04-A10 | P04-WP042 | P04-WP042 | SOURCE_WP_SCOPE | 814000 | 2025-12-15 | 2025-12-26 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0103 | P04 | P04-A11 | P04-WP043 | P04-WP043 | SOURCE_WP_SCOPE | 284900 | 2025-12-29 | 2026-01-16 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0104 | P04 | P04-A17 | P04-WP061 | P04-WP061 | SOURCE_WP_SCOPE | 107250 | 2026-03-30 | 2026-04-10 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-04-10 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0105 | P04 | P04-A18 | P04-WP062 | P04-WP062 | SOURCE_WP_SCOPE | 57750 | 2026-04-06 | 2026-04-24 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-04-24 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0106 | P05 | P05-A1 | P05-WP011 | P05-WP011 | SOURCE_WP_SCOPE | 96200 | 2025-03-03 | 2025-03-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0107 | P05 | P05-A8 | P05-WP011 | P05-WP011 | SOURCE_WP_SCOPE | 192400 | 2025-08-04 | 2025-09-12 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-09-12 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0108 | P05 | P05-A2 | P05-WP012 | P05-WP012 | SOURCE_WP_SCOPE | 155400 | 2025-03-24 | 2025-04-04 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0109 | P05 | P05-A3 | P05-WP021 | P05-WP021 | SOURCE_WP_SCOPE | 199800 | 2025-04-07 | 2025-04-25 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0110 | P05 | P05-A4 | P05-WP022 | P05-WP022 | SOURCE_WP_SCOPE | 155400 | 2025-05-05 | 2025-05-23 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0111 | P05 | P05-A4b | P05-WP022 | P05-WP022 | SOURCE_WP_SCOPE | 155400 | 2025-05-26 | 2025-06-13 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0112 | P05 | P05-A10 | P05-WP022 | P05-WP022 | SOURCE_WP_SCOPE | 155400 | 2025-07-14 | 2025-08-01 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0113 | P05 | P05-A5 | P05-WP031 | P05-WP031 | SOURCE_WP_SCOPE | 116550 | 2025-05-19 | 2025-06-06 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0114 | P05 | P05-A5b | P05-WP031 | P05-WP031 | SOURCE_WP_SCOPE | 116550 | 2025-06-09 | 2025-06-20 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0115 | P05 | P05-A5c | P05-WP032 | P05-WP032 | SOURCE_WP_SCOPE | 72150 | 2025-06-23 | 2025-07-04 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0116 | P05 | P05-A11 | P05-WP032 | P05-WP032 | SOURCE_WP_SCOPE | 288600 | 2025-07-14 | 2025-08-22 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-07-21¦2025-08-01¦2025-08-14¦2025-08-22 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0117 | P05 | P05-A6 | P05-WP032 | P05-WP032 | SOURCE_WP_SCOPE | 72150 | 2025-07-14 | 2025-08-01 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0118 | P05 | P05-A7 | P05-WP041 | P05-WP041 | SOURCE_WP_SCOPE | 240582 | 2025-07-14 | 2025-09-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0119 | P05 | P05-A9 | P05-WP041 | P05-WP041 | SOURCE_WP_SCOPE | 240582 | 2025-07-28 | 2025-08-22 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0120 | P05 | P05-A12a | P05-WP041 | P05-WP041 | SOURCE_WP_SCOPE | 1202911 | 2025-08-25 | 2025-11-07 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0121 | P05 | P05-AFIRST | P05-WP041 | P05-WP041 | SOURCE_WP_SCOPE | 721747 | 2025-08-25 | 2025-08-26 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0122 | P05 | P05-A13a | P05-WP041 | P05-WP041 | SOURCE_WP_SCOPE | 1202911 | 2025-09-22 | 2025-12-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0123 | P05 | P05-A14a | P05-WP041 | P05-WP041 | SOURCE_WP_SCOPE | 1202911 | 2025-10-20 | 2026-01-02 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0124 | P05 | P05-A15a | P05-WP041 | P05-WP041 | SOURCE_WP_SCOPE | 1202911 | 2025-11-17 | 2026-01-30 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0125 | P05 | P05-A16 | P05-WP041 | P05-WP041 | SOURCE_WP_SCOPE | 481165 | 2026-03-16 | 2026-04-03 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-04-03 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0126 | P05 | P05-A12b | P05-WP042 | P05-WP042 | SOURCE_WP_SCOPE | 379620 | 2025-09-15 | 2025-11-28 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0127 | P05 | P05-A13b | P05-WP042 | P05-WP042 | SOURCE_WP_SCOPE | 379620 | 2025-10-13 | 2025-12-26 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0128 | P05 | P05-A14b | P05-WP042 | P05-WP042 | SOURCE_WP_SCOPE | 379620 | 2025-11-10 | 2026-01-23 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0129 | P05 | P05-A15b | P05-WP042 | P05-WP042 | SOURCE_WP_SCOPE | 379620 | 2025-12-08 | 2026-02-20 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0130 | P05 | P05-A12c | P05-WP051 | P05-WP051 | SOURCE_WP_SCOPE | 138750 | 2025-12-01 | 2025-12-19 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-12-19 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0131 | P05 | P05-A13c | P05-WP051 | P05-WP051 | SOURCE_WP_SCOPE | 138750 | 2025-12-29 | 2026-01-16 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-01-16 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0132 | P05 | P05-A14c | P05-WP051 | P05-WP051 | SOURCE_WP_SCOPE | 138750 | 2026-01-26 | 2026-02-13 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-02-13 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0133 | P05 | P05-A15c | P05-WP051 | P05-WP051 | SOURCE_WP_SCOPE | 138750 | 2026-02-23 | 2026-03-13 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-03-13 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0134 | P05 | P05-A17 | P05-WP061 | P05-WP061 | SOURCE_WP_SCOPE | 249750 | 2026-04-06 | 2026-05-01 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-05-01 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0135 | P05 | P05-A18 | P05-WP062 | P05-WP062 | SOURCE_WP_SCOPE | 83250 | 2026-04-20 | 2026-05-15 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-05-15 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0136 | P06 | P06-A1 | P06-WP011 | P06-WP011 | SOURCE_WP_SCOPE | 75900 | 2025-08-01 | 2025-08-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0137 | P06 | P06-A10 | P06-WP011 | P06-WP011 | SOURCE_WP_SCOPE | 75900 | 2025-12-12 | 2026-01-08 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0138 | P06 | P06-A2 | P06-WP012 | P06-WP012 | SOURCE_WP_SCOPE | 124200 | 2025-08-22 | 2025-09-04 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0139 | P06 | P06-A3 | P06-WP021 | P06-WP021 | SOURCE_WP_SCOPE | 265650 | 2025-09-05 | 2025-10-02 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0140 | P06 | P06-A4 | P06-WP022 | P06-WP022 | SOURCE_WP_SCOPE | 123338 | 2025-10-10 | 2025-11-06 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0141 | P06 | P06-A4b | P06-WP022 | P06-WP022 | SOURCE_WP_SCOPE | 123338 | 2025-11-07 | 2025-11-20 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0142 | P06 | P06-A7 | P06-WP022 | P06-WP022 | SOURCE_WP_SCOPE | 123337 | 2025-12-12 | 2026-01-08 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0143 | P06 | P06-A8 | P06-WP022 | P06-WP022 | SOURCE_WP_SCOPE | 123337 | 2025-12-12 | 2026-01-01 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0144 | P06 | P06-A5 | P06-WP031 | P06-WP031 | SOURCE_WP_SCOPE | 89700 | 2025-10-24 | 2025-11-13 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0145 | P06 | P06-A5b | P06-WP031 | P06-WP031 | SOURCE_WP_SCOPE | 89700 | 2025-11-14 | 2025-11-27 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0146 | P06 | P06-A11 | P06-WP031 | P06-WP031 | SOURCE_WP_SCOPE | 89700 | 2025-12-12 | 2026-01-01 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-12-16¦2025-12-23¦2025-12-29¦2026-01-01 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0147 | P06 | P06-A5c | P06-WP032 | P06-WP032 | SOURCE_WP_SCOPE | 89700 | 2025-11-28 | 2025-12-11 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0148 | P06 | P06-A6 | P06-WP032 | P06-WP032 | SOURCE_WP_SCOPE | 89700 | 2025-12-12 | 2025-12-25 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0149 | P06 | P06-A12 | P06-WP032 | P06-WP032 | SOURCE_WP_SCOPE | 358800 | 2026-01-02 | 2026-03-26 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-01-19¦2026-02-12¦2026-03-10¦2026-03-26 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0150 | P06 | P06-A13 | P06-WP032 | P06-WP032 | SOURCE_WP_SCOPE | 89700 | 2026-03-27 | 2026-04-09 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-03-30¦2026-04-02¦2026-04-07¦2026-04-09 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0151 | P06 | P06-A15 | P06-WP041 | P06-WP041 | SOURCE_WP_SCOPE | 340947 | 2025-12-12 | 2025-12-25 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0152 | P06 | P06-APILOTSTAGE | P06-WP041 | P06-WP041 | SOURCE_WP_SCOPE | 454595 | 2026-04-10 | 2026-04-16 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-04-10¦2026-04-14¦2026-04-15¦2026-04-16 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0153 | P06 | P06-A16 | P06-WP041 | P06-WP041 | SOURCE_WP_SCOPE | 340946 | 2026-04-17 | 2026-05-07 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0154 | P06 | P06-AFIRSTPILOT | P06-WP041 | P06-WP041 | SOURCE_WP_SCOPE | 113649 | 2026-04-17 | 2026-04-20 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0155 | P06 | P06-A18a | P06-WP041 | P06-WP041 | SOURCE_WP_SCOPE | 340946 | 2026-05-29 | 2026-07-16 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0156 | P06 | P06-A19a | P06-WP041 | P06-WP041 | SOURCE_WP_SCOPE | 340946 | 2026-06-19 | 2026-08-06 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0157 | P06 | P06-A20a | P06-WP041 | P06-WP041 | SOURCE_WP_SCOPE | 340946 | 2026-07-10 | 2026-08-27 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0158 | P06 | P06-A21a | P06-WP041 | P06-WP041 | SOURCE_WP_SCOPE | 340946 | 2026-07-31 | 2026-09-17 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0159 | P06 | P06-A22 | P06-WP041 | P06-WP041 | SOURCE_WP_SCOPE | 113649 | 2026-10-02 | 2026-10-22 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0160 | P06 | P06-A9 | P06-WP042 | P06-WP042 | SOURCE_WP_SCOPE | 641183 | 2026-01-09 | 2026-02-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0161 | P06 | P06-A14 | P06-WP042 | P06-WP042 | SOURCE_WP_SCOPE | 213727 | 2026-02-20 | 2026-03-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0162 | P06 | P06-A18b | P06-WP043 | P06-WP043 | SOURCE_WP_SCOPE | 122130 | 2026-07-17 | 2026-07-30 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0163 | P06 | P06-A19b | P06-WP043 | P06-WP043 | SOURCE_WP_SCOPE | 122130 | 2026-08-07 | 2026-08-20 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0164 | P06 | P06-A20b | P06-WP043 | P06-WP043 | SOURCE_WP_SCOPE | 122130 | 2026-08-28 | 2026-09-10 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0165 | P06 | P06-A21b | P06-WP043 | P06-WP043 | SOURCE_WP_SCOPE | 122130 | 2026-09-18 | 2026-10-01 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0166 | P06 | P06-A17 | P06-WP051 | P06-WP051 | SOURCE_WP_SCOPE | 230000 | 2026-05-08 | 2026-05-28 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-05-28 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0167 | P06 | P06-A23 | P06-WP051 | P06-WP051 | SOURCE_WP_SCOPE | 345000 | 2026-10-23 | 2026-11-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0168 | P06 | P06-A24 | P06-WP051 | P06-WP051 | SOURCE_WP_SCOPE | 115000 | 2026-11-06 | 2026-11-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0169 | P06 | P06-A25 | P06-WP061 | P06-WP061 | SOURCE_WP_SCOPE | 144900 | 2026-11-20 | 2026-12-03 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-03 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0170 | P06 | P06-A26 | P06-WP062 | P06-WP062 | SOURCE_WP_SCOPE | 62100 | 2026-12-04 | 2026-12-24 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-24 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0171 | P07 | P07-A1 | P07-WP011 | P07-WP011 | SOURCE_WP_SCOPE | 61500 | 2025-10-01 | 2025-10-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0172 | P07 | P07-A2 | P07-WP012 | P07-WP012 | SOURCE_WP_SCOPE | 61500 | 2025-10-22 | 2025-11-04 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0173 | P07 | P07-A3 | P07-WP021 | P07-WP021 | SOURCE_WP_SCOPE | 129150 | 2025-11-05 | 2025-12-02 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0174 | P07 | P07-A4 | P07-WP022 | P07-WP022 | SOURCE_WP_SCOPE | 119925 | 2025-12-10 | 2026-01-06 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0175 | P07 | P07-A4b | P07-WP022 | P07-WP022 | SOURCE_WP_SCOPE | 119925 | 2026-01-07 | 2026-01-27 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0176 | P07 | P07-A5 | P07-WP031 | P07-WP031 | SOURCE_WP_SCOPE | 47834 | 2025-12-24 | 2026-01-13 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0177 | P07 | P07-A5b | P07-WP031 | P07-WP031 | SOURCE_WP_SCOPE | 47833 | 2026-01-14 | 2026-01-27 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0178 | P07 | P07-A8 | P07-WP031 | P07-WP031 | SOURCE_WP_SCOPE | 47833 | 2026-02-25 | 2026-03-17 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-02-27¦2026-03-06¦2026-03-12¦2026-03-17 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0179 | P07 | P07-A5c | P07-WP032 | P07-WP032 | SOURCE_WP_SCOPE | 133250 | 2026-01-28 | 2026-02-10 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0180 | P07 | P07-A6 | P07-WP032 | P07-WP032 | SOURCE_WP_SCOPE | 133250 | 2026-02-25 | 2026-03-10 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0181 | P07 | P07-A7 | P07-WP041 | P07-WP041 | SOURCE_WP_SCOPE | 446080 | 2026-02-25 | 2026-03-10 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0182 | P07 | P07-A10 | P07-WP041 | P07-WP041 | SOURCE_WP_SCOPE | 446080 | 2026-03-11 | 2026-03-31 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0183 | P07 | P07-A16 | P07-WP041 | P07-WP041 | SOURCE_WP_SCOPE | 892160 | 2026-07-22 | 2026-08-04 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-08-04 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0184 | P07 | P07-A11 | P07-WP042 | P07-WP042 | SOURCE_WP_SCOPE | 585480 | 2026-04-29 | 2026-05-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0185 | P07 | P07-A9 | P07-WP043 | P07-WP043 | SOURCE_WP_SCOPE | 83640 | 2026-03-18 | 2026-04-28 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-03-25¦2026-04-07¦2026-04-20¦2026-04-28 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0186 | P07 | P07-A12 | P07-WP043 | P07-WP043 | SOURCE_WP_SCOPE | 250920 | 2026-05-20 | 2026-06-02 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0187 | P07 | P07-A13 | P07-WP043 | P07-WP043 | SOURCE_WP_SCOPE | 83640 | 2026-06-03 | 2026-06-16 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0188 | P07 | P07-A14 | P07-WP051 | P07-WP051 | SOURCE_WP_SCOPE | 191333 | 2026-06-17 | 2026-06-30 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-06-30 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0189 | P07 | P07-A15 | P07-WP051 | P07-WP051 | SOURCE_WP_SCOPE | 95667 | 2026-07-01 | 2026-07-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0190 | P07 | P07-A17 | P07-WP061 | P07-WP061 | SOURCE_WP_SCOPE | 79950 | 2026-08-05 | 2026-08-18 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-08-18 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0191 | P07 | P07-A18 | P07-WP062 | P07-WP062 | SOURCE_WP_SCOPE | 43050 | 2026-08-12 | 2026-09-01 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-09-01 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0192 | P08 | P08-A1 | P08-WP011 | P08-WP011 | SOURCE_WP_SCOPE | 62100 | 2025-12-01 | 2025-12-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0193 | P08 | P08-A2 | P08-WP012 | P08-WP012 | SOURCE_WP_SCOPE | 75900 | 2025-12-22 | 2026-01-02 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0194 | P08 | P08-A3 | P08-WP021 | P08-WP021 | SOURCE_WP_SCOPE | 128800 | 2026-01-05 | 2026-01-30 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0195 | P08 | P08-A4 | P08-WP022 | P08-WP022 | SOURCE_WP_SCOPE | 119600 | 2026-02-09 | 2026-03-06 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0196 | P08 | P08-A4b | P08-WP022 | P08-WP022 | SOURCE_WP_SCOPE | 119600 | 2026-03-09 | 2026-03-27 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0197 | P08 | P08-A5 | P08-WP031 | P08-WP031 | SOURCE_WP_SCOPE | 58880 | 2026-02-23 | 2026-03-13 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0198 | P08 | P08-A5b | P08-WP031 | P08-WP031 | SOURCE_WP_SCOPE | 58880 | 2026-03-16 | 2026-03-27 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0199 | P08 | P08-A8 | P08-WP031 | P08-WP031 | SOURCE_WP_SCOPE | 58880 | 2026-04-27 | 2026-05-15 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-04-29¦2026-05-06¦2026-05-12¦2026-05-15 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0200 | P08 | P08-A5c | P08-WP032 | P08-WP032 | SOURCE_WP_SCOPE | 187680 | 2026-03-30 | 2026-04-10 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0201 | P08 | P08-A6 | P08-WP032 | P08-WP032 | SOURCE_WP_SCOPE | 187680 | 2026-04-27 | 2026-05-08 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0202 | P08 | P08-A7 | P08-WP041 | P08-WP041 | SOURCE_WP_SCOPE | 102290 | 2026-01-19 | 2026-02-06 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0203 | P08 | P08-A13 | P08-WP041 | P08-WP041 | SOURCE_WP_SCOPE | 102290 | 2026-04-27 | 2026-05-15 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0204 | P08 | P08-A14 | P08-WP041 | P08-WP041 | SOURCE_WP_SCOPE | 102289 | 2026-04-27 | 2026-05-08 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0205 | P08 | P08-A9 | P08-WP041 | P08-WP041 | SOURCE_WP_SCOPE | 409158 | 2026-05-18 | 2026-08-28 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-06-05¦2026-07-08¦2026-08-07¦2026-08-28 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0206 | P08 | P08-A9fat | P08-WP041 | P08-WP041 | SOURCE_WP_SCOPE | 102289 | 2026-08-31 | 2026-09-11 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0207 | P08 | P08-A11 | P08-WP041 | P08-WP041 | SOURCE_WP_SCOPE | 409158 | 2026-09-14 | 2026-09-25 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-09-15¦2026-09-18¦2026-09-23¦2026-09-25 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0208 | P08 | P08-A15 | P08-WP041 | P08-WP041 | SOURCE_WP_SCOPE | 409158 | 2026-09-28 | 2026-10-09 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0209 | P08 | P08-A17 | P08-WP041 | P08-WP041 | SOURCE_WP_SCOPE | 102289 | 2026-10-12 | 2026-10-23 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0210 | P08 | P08-A21 | P08-WP041 | P08-WP041 | SOURCE_WP_SCOPE | 204579 | 2026-11-30 | 2026-12-11 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-11 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0211 | P08 | P08-A10 | P08-WP042 | P08-WP042 | SOURCE_WP_SCOPE | 289034 | 2026-05-18 | 2026-08-07 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-06-02¦2026-06-26¦2026-07-22¦2026-08-07 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0212 | P08 | P08-A10fat | P08-WP042 | P08-WP042 | SOURCE_WP_SCOPE | 72258 | 2026-08-10 | 2026-08-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0213 | P08 | P08-A12 | P08-WP042 | P08-WP042 | SOURCE_WP_SCOPE | 289033 | 2026-08-20 | 2026-08-31 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-08-21¦2026-08-25¦2026-08-28¦2026-08-31 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0214 | P08 | P08-A16 | P08-WP042 | P08-WP042 | SOURCE_WP_SCOPE | 216775 | 2026-09-01 | 2026-09-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0215 | P08 | P08-A18 | P08-WP051 | P08-WP051 | SOURCE_WP_SCOPE | 138000 | 2026-10-26 | 2026-11-06 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-11-06 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0216 | P08 | P08-A19 | P08-WP051 | P08-WP051 | SOURCE_WP_SCOPE | 138000 | 2026-11-09 | 2026-11-20 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-11-20 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0217 | P08 | P08-A20 | P08-WP051 | P08-WP051 | SOURCE_WP_SCOPE | 138000 | 2026-11-23 | 2026-11-27 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-11-27 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0218 | P08 | P08-A22 | P08-WP061 | P08-WP061 | SOURCE_WP_SCOPE | 89700 | 2026-12-14 | 2026-12-25 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-25 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0219 | P08 | P08-A23 | P08-WP062 | P08-WP062 | SOURCE_WP_SCOPE | 48300 | 2026-12-21 | 2027-01-08 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-01-08 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0220 | P09 | P09-A1 | P09-WP011 | P09-WP011 | SOURCE_WP_SCOPE | 117000 | 2026-02-02 | 2026-02-20 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0221 | P09 | P09-A2 | P09-WP012 | P09-WP012 | SOURCE_WP_SCOPE | 117000 | 2026-02-23 | 2026-03-06 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0222 | P09 | P09-A3a | P09-WP021 | P09-WP021 | SOURCE_WP_SCOPE | 124800 | 2026-03-09 | 2026-04-03 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0223 | P09 | P09-A3 | P09-WP021 | P09-WP021 | SOURCE_WP_SCOPE | 124800 | 2026-04-06 | 2026-05-01 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0224 | P09 | P09-A4 | P09-WP022 | P09-WP022 | SOURCE_WP_SCOPE | 74880 | 2026-05-11 | 2026-06-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0225 | P09 | P09-A4b | P09-WP022 | P09-WP022 | SOURCE_WP_SCOPE | 74880 | 2026-06-08 | 2026-07-17 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0226 | P09 | P09-A4c | P09-WP022 | P09-WP022 | SOURCE_WP_SCOPE | 74880 | 2026-06-08 | 2026-07-31 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0227 | P09 | P09-A19 | P09-WP022 | P09-WP022 | SOURCE_WP_SCOPE | 149760 | 2026-12-24 | 2026-12-30 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-30 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0228 | P09 | P09-A5 | P09-WP031 | P09-WP031 | SOURCE_WP_SCOPE | 72800 | 2026-05-25 | 2026-06-12 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0229 | P09 | P09-A5b | P09-WP031 | P09-WP031 | SOURCE_WP_SCOPE | 72800 | 2026-06-15 | 2026-07-03 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0230 | P09 | P09-A10 | P09-WP031 | P09-WP031 | SOURCE_WP_SCOPE | 72800 | 2026-08-03 | 2026-08-21 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-08-05¦2026-08-12¦2026-08-18¦2026-08-21 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0231 | P09 | P09-A5c | P09-WP032 | P09-WP032 | SOURCE_WP_SCOPE | 202800 | 2026-07-06 | 2026-07-17 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0232 | P09 | P09-A6 | P09-WP032 | P09-WP032 | SOURCE_WP_SCOPE | 202800 | 2026-08-03 | 2026-08-28 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0233 | P09 | P09-A7 | P09-WP041 | P09-WP041 | SOURCE_WP_SCOPE | 304869 | 2026-08-03 | 2026-08-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0234 | P09 | P09-A8 | P09-WP041 | P09-WP041 | SOURCE_WP_SCOPE | 304869 | 2026-08-03 | 2026-08-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0235 | P09 | P09-A9 | P09-WP041 | P09-WP041 | SOURCE_WP_SCOPE | 304869 | 2026-08-24 | 2026-09-04 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0236 | P09 | P09-A13 | P09-WP041 | P09-WP041 | SOURCE_WP_SCOPE | 304869 | 2026-08-31 | 2026-09-11 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | WORKDAY_OR_DELIVERABLE | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0237 | P09 | P09-A14 | P09-WP041 | P09-WP041 | SOURCE_WP_SCOPE | 304869 | 2026-09-14 | 2026-10-09 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0238 | P09 | P09-A12 | P09-WP041 | P09-WP041 | SOURCE_WP_SCOPE | 1219474 | 2026-10-26 | 2026-11-04 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-10-27¦2026-10-29¦2026-11-03¦2026-11-04 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0239 | P09 | P09-A15 | P09-WP041 | P09-WP041 | SOURCE_WP_SCOPE | 304868 | 2026-11-05 | 2026-11-25 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0240 | P09 | P09-A16 | P09-WP041 | P09-WP041 | SOURCE_WP_SCOPE | 304868 | 2026-11-26 | 2026-12-09 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0241 | P09 | P09-A17 | P09-WP041 | P09-WP041 | SOURCE_WP_SCOPE | 304868 | 2026-11-26 | 2026-12-09 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0242 | P09 | P09-A21 | P09-WP041 | P09-WP041 | SOURCE_WP_SCOPE | 609737 | 2027-01-21 | 2027-02-03 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-02-03 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0243 | P09 | P09-A11 | P09-WP042 | P09-WP042 | SOURCE_WP_SCOPE | 898560 | 2026-08-24 | 2026-10-23 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-09-03¦2026-09-23¦2026-10-12¦2026-10-23 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0244 | P09 | P09-A20 | P09-WP043 | P09-WP043 | SOURCE_WP_SCOPE | 449280 | 2026-12-31 | 2027-01-20 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0245 | P09 | P09-A18 | P09-WP051 | P09-WP051 | SOURCE_WP_SCOPE | 468000 | 2026-12-17 | 2026-12-23 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-23 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0246 | P09 | P09-A22 | P09-WP061 | P09-WP061 | SOURCE_WP_SCOPE | 152100 | 2027-02-04 | 2027-02-17 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-02-17 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0247 | P09 | P09-A23 | P09-WP062 | P09-WP062 | SOURCE_WP_SCOPE | 81900 | 2027-02-11 | 2027-03-03 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-03-03 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0248 | P10 | P10-A1 | P10-WP011 | P10-WP011 | SOURCE_WP_SCOPE | 66600 | 2026-04-01 | 2026-04-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0249 | P10 | P10-A4 | P10-WP021 | P10-WP021 | SOURCE_WP_SCOPE | 266400 | 2026-05-27 | 2026-06-23 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0250 | P10 | P10-A3 | P10-WP022 | P10-WP022 | SOURCE_WP_SCOPE | 99900 | 2026-05-06 | 2026-05-26 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0251 | P10 | P10-A5 | P10-WP022 | P10-WP022 | SOURCE_WP_SCOPE | 99900 | 2026-06-10 | 2026-06-30 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0252 | P10 | P10-A6b | P10-WP022 | P10-WP022 | SOURCE_WP_SCOPE | 99900 | 2026-06-10 | 2026-06-30 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0253 | P10 | P10-A6 | P10-WP022 | P10-WP022 | SOURCE_WP_SCOPE | 99900 | 2026-06-24 | 2026-07-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0254 | P10 | P10-A7 | P10-WP031 | P10-WP031 | SOURCE_WP_SCOPE | 60434 | 2026-07-08 | 2026-07-28 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0255 | P10 | P10-A7b | P10-WP031 | P10-WP031 | SOURCE_WP_SCOPE | 60433 | 2026-07-29 | 2026-08-11 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0256 | P10 | P10-A9 | P10-WP031 | P10-WP031 | SOURCE_WP_SCOPE | 60433 | 2026-08-26 | 2026-09-15 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-08-28¦2026-09-04¦2026-09-10¦2026-09-15 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0257 | P10 | P10-A7c | P10-WP032 | P10-WP032 | SOURCE_WP_SCOPE | 168350 | 2026-08-12 | 2026-08-25 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0258 | P10 | P10-A8 | P10-WP032 | P10-WP032 | SOURCE_WP_SCOPE | 168350 | 2026-08-26 | 2026-09-08 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0259 | P10 | P10-IF-01 | P10-WP041 | P10-WP041 | SOURCE_WP_SCOPE | 143745 | 2026-07-22 | 2026-08-04 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0260 | P10 | P10-A14 | P10-WP041 | P10-WP041 | SOURCE_WP_SCOPE | 431235 | 2026-08-26 | 2026-10-06 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0261 | P10 | P10-A11 | P10-WP042 | P10-WP042 | SOURCE_WP_SCOPE | 293040 | 2026-08-26 | 2026-09-15 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-08-28¦2026-09-04¦2026-09-10¦2026-09-15 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0262 | P10 | P10-A15 | P10-WP042 | P10-WP042 | SOURCE_WP_SCOPE | 219780 | 2026-08-26 | 2026-09-29 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0263 | P10 | P10-A10 | P10-WP043 | P10-WP043 | SOURCE_WP_SCOPE | 124320 | 2026-09-16 | 2026-10-27 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-09-23¦2026-10-06¦2026-10-19¦2026-10-27 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0264 | P10 | P10-A12 | P10-WP043 | P10-WP043 | SOURCE_WP_SCOPE | 124320 | 2026-10-28 | 2026-12-01 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-11-03¦2026-11-13¦2026-11-24¦2026-12-01 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0265 | P10 | P10-A16 | P10-WP043 | P10-WP043 | SOURCE_WP_SCOPE | 124320 | 2026-12-23 | 2027-01-01 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-12-24¦2026-12-28¦2026-12-31¦2027-01-01 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0266 | P10 | P10-A17 | P10-WP043 | P10-WP043 | SOURCE_WP_SCOPE | 93240 | 2027-01-04 | 2027-02-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0267 | P10 | P10-A13 | P10-WP051 | P10-WP051 | SOURCE_WP_SCOPE | 41353 | 2026-12-02 | 2026-12-22 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-22 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0268 | P10 | P10-A18 | P10-WP051 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | 2027-02-08 | 2027-02-26 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-02-26 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0269 | P10 | P10-A19 | P10-WP051 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | 2027-03-01 | 2027-03-12 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-03-12 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0270 | P10 | P10-A20 | P10-WP051 | P10-WP051 | SOURCE_WP_SCOPE | 41353 | 2027-03-15 | 2027-04-02 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0271 | P10 | P10-A21 | P10-WP051 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | 2027-04-05 | 2027-04-23 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-04-23 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0272 | P10 | P10-A22 | P10-WP051 | P10-WP051 | SOURCE_WP_SCOPE | 41353 | 2027-04-26 | 2027-05-07 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0273 | P10 | P10-A23 | P10-WP051 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | 2027-04-26 | 2027-05-07 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-05-07 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0274 | P10 | P10-A24 | P10-WP051 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | 2027-05-10 | 2027-05-28 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-05-28 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0275 | P10 | P10-A25 | P10-WP051 | P10-WP051 | SOURCE_WP_SCOPE | 82706 | 2027-05-31 | 2027-06-18 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-06-18 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0276 | P10 | P10-A27 | P10-WP051 | P10-WP051 | SOURCE_WP_SCOPE | 82705 | 2027-06-21 | 2027-07-02 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-07-02 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0277 | P10 | P10-A26 | P10-WP061 | P10-WP061 | SOURCE_WP_SCOPE | 77700 | 2027-06-21 | 2027-07-09 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-07-09 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0278 | P10 | P10-A28 | P10-WP062 | P10-WP062 | SOURCE_WP_SCOPE | 33300 | 2027-07-19 | 2027-08-06 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-08-06 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0279 | P11 | P11-A1 | P11-WP011 | P11-WP011 | SOURCE_WP_SCOPE | 76800 | 2025-04-01 | 2025-04-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0280 | P11 | P11-A2 | P11-WP012 | P11-WP012 | SOURCE_WP_SCOPE | 51200 | 2025-04-22 | 2025-05-05 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0281 | P11 | P11-A3 | P11-WP021 | P11-WP021 | SOURCE_WP_SCOPE | 57600 | 2025-05-06 | 2025-05-26 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0282 | P11 | P11-A4 | P11-WP022 | P11-WP022 | SOURCE_WP_SCOPE | 67200 | 2025-06-03 | 2025-06-23 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0283 | P11 | P11-A8 | P11-WP022 | P11-WP022 | SOURCE_WP_SCOPE | 67200 | 2025-08-12 | 2025-08-25 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0284 | P11 | P11-A5 | P11-WP031 | P11-WP031 | SOURCE_WP_SCOPE | 50400 | 2025-06-17 | 2025-07-07 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0285 | P11 | P11-A5b | P11-WP031 | P11-WP031 | SOURCE_WP_SCOPE | 50400 | 2025-07-08 | 2025-07-21 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0286 | P11 | P11-A5c | P11-WP032 | P11-WP032 | SOURCE_WP_SCOPE | 93600 | 2025-07-22 | 2025-08-04 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0287 | P11 | P11-A6 | P11-WP032 | P11-WP032 | SOURCE_WP_SCOPE | 93600 | 2025-08-12 | 2025-08-25 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0288 | P11 | P11-A10 | P11-WP041 | P11-WP041 | SOURCE_WP_SCOPE | 95822 | 2025-08-12 | 2025-09-01 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0289 | P11 | P11-A9 | P11-WP041 | P11-WP041 | SOURCE_WP_SCOPE | 383289 | 2025-08-12 | 2025-09-15 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-08-18¦2025-08-28¦2025-09-08¦2025-09-15 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WEIGHTED_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0290 | P11 | P11-AFIRST | P11-WP041 | P11-WP041 | SOURCE_WP_SCOPE | 287467 | 2025-09-16 | 2025-09-17 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0291 | P11 | P11-B1inst | P11-WP041 | P11-WP041 | SOURCE_WP_SCOPE | 479111 | 2025-09-16 | 2025-11-10 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0292 | P11 | P11-B2inst | P11-WP041 | P11-WP041 | SOURCE_WP_SCOPE | 479111 | 2025-10-21 | 2025-12-15 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0293 | P11 | P11-B1rest | P11-WP043 | P11-WP043 | SOURCE_WP_SCOPE | 168000 | 2025-10-14 | 2025-12-08 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0294 | P11 | P11-B2rest | P11-WP043 | P11-WP043 | SOURCE_WP_SCOPE | 168000 | 2025-11-18 | 2026-01-12 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0295 | P11 | P11-A7 | P11-WP051 | P11-WP051 | SOURCE_WP_SCOPE | 64000 | 2025-08-12 | 2025-09-01 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-09-01 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0296 | P11 | P11-B1test | P11-WP051 | P11-WP051 | SOURCE_WP_SCOPE | 64000 | 2025-11-11 | 2025-11-24 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-11-24 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0297 | P11 | P11-B2test | P11-WP051 | P11-WP051 | SOURCE_WP_SCOPE | 64000 | 2025-12-16 | 2025-12-29 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-12-29 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0298 | P11 | P11-A11 | P11-WP051 | P11-WP051 | SOURCE_WP_SCOPE | 64000 | 2026-01-27 | 2026-02-09 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-02-09 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0299 | P11 | P11-B1gis | P11-WP061 | P11-WP061 | SOURCE_WP_SCOPE | 22400 | 2025-12-09 | 2025-12-22 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0300 | P11 | P11-B2gis | P11-WP061 | P11-WP061 | SOURCE_WP_SCOPE | 22400 | 2026-01-13 | 2026-01-26 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0301 | P11 | P11-A12 | P11-WP061 | P11-WP061 | SOURCE_WP_SCOPE | 22400 | 2026-02-10 | 2026-02-23 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-02-23 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0302 | P11 | P11-A13 | P11-WP062 | P11-WP062 | SOURCE_WP_SCOPE | 28800 | 2026-02-17 | 2026-03-09 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-03-09 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0303 | P12 | P12-Y1A1 | P12-WP011 | P12-WP011 | SOURCE_WP_SCOPE | 28560 | 2025-01-02 | 2025-01-22 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0304 | P12 | P12-Y1A2 | P12-WP011 | P12-WP011 | SOURCE_WP_SCOPE | 28560 | 2025-01-23 | 2025-02-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0305 | P12 | P12-Y2A1 | P12-WP011 | P12-WP011 | SOURCE_WP_SCOPE | 36720 | 2025-10-30 | 2025-11-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0306 | P12 | P12-Y2A2 | P12-WP011 | P12-WP011 | SOURCE_WP_SCOPE | 36720 | 2025-11-20 | 2025-12-17 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0307 | P12 | P12-Y3A1 | P12-WP011 | P12-WP011 | SOURCE_WP_SCOPE | 36720 | 2026-08-27 | 2026-09-16 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0308 | P12 | P12-Y3A2 | P12-WP011 | P12-WP011 | SOURCE_WP_SCOPE | 36720 | 2026-09-17 | 2026-10-14 | MON_FRI_NO_HOLIDAYS | WORKDAY_SPREAD | PER_WORKDAY | ALL_BUSINESS_DAYS | Evenly across inclusive scheduled Monday-Friday workdays, no holidays; final cent residual on last day. | Approve this LOE/planned-work proxy and physical progress EV rule separately | WORKDAY_OR_DELIVERABLE | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0309 | P12 | P12-Y1A3 | P12-WP021 | P12-WP021 | SOURCE_WP_SCOPE | 42840 | 2025-02-20 | 2025-03-19 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0310 | P12 | P12-Y1A4 | P12-WP021 | P12-WP021 | SOURCE_WP_SCOPE | 42840 | 2025-03-20 | 2025-04-09 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0311 | P12 | P12-Y2A3 | P12-WP021 | P12-WP021 | SOURCE_WP_SCOPE | 55080 | 2025-12-18 | 2026-01-14 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0312 | P12 | P12-Y2A4 | P12-WP021 | P12-WP021 | SOURCE_WP_SCOPE | 55080 | 2026-01-15 | 2026-02-04 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0313 | P12 | P12-Y3A3 | P12-WP021 | P12-WP021 | SOURCE_WP_SCOPE | 55080 | 2026-10-15 | 2026-11-11 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0314 | P12 | P12-Y3A4 | P12-WP021 | P12-WP021 | SOURCE_WP_SCOPE | 55080 | 2026-11-12 | 2026-12-02 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_OR_WEIGHTED | DEFAULT_RULE_REQUIRES_APPROVAL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0315 | P12 | P12-Y1A5 | P12-WP031 | P12-WP031 | SOURCE_WP_SCOPE | 114240 | 2025-04-10 | 2025-05-14 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2025-04-16¦2025-04-28¦2025-05-07¦2025-05-14 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0316 | P12 | P12-Y2A5 | P12-WP031 | P12-WP031 | SOURCE_WP_SCOPE | 146880 | 2026-02-05 | 2026-03-11 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-02-11¦2026-02-23¦2026-03-04¦2026-03-11 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0317 | P12 | P12-Y3A5 | P12-WP031 | P12-WP031 | SOURCE_WP_SCOPE | 146880 | 2026-12-03 | 2027-01-06 | MON_FRI_NO_HOLIDAYS | PROCUREMENT_20_30_30_20 | 20¦30¦30¦20 | 2026-12-09¦2026-12-21¦2026-12-30¦2027-01-06 | Synthetic 20/30/30/20 stage weights at 20%, 50%, 80%, 100% of inclusive scheduled workdays; stage labels approval, fabrication, inspection, acceptance are proxies requiring substitution if inconsistent with activity scope. | Four distinct dated stage/acceptance records (provisional schedule-relative proxies) | WORKDAY_OR_DELIVERABLE | WEIGHTS_AND_EVENT_DATES_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0318 | P12 | P12-Y1A6 | P12-WP041 | P12-WP041 | SOURCE_WP_SCOPE | 944194 | 2025-05-15 | 2025-09-17 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0319 | P12 | P12-Y2A6 | P12-WP041 | P12-WP041 | SOURCE_WP_SCOPE | 1213963 | 2026-03-12 | 2026-07-15 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0320 | P12 | P12-Y3A6 | P12-WP041 | P12-WP041 | SOURCE_WP_SCOPE | 1213963 | 2027-01-07 | 2027-05-12 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Even workday spread pending planned installation quantities; do not describe workday progression as measured physical quantity. | Approved workday fallback or quantity schedule | QUANTITY_DRIVEN_PROVISIONAL | QUANTITY_PROFILE_OR_FALLBACK_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0321 | P12 | P12-Y1A7 | P12-WP051 | P12-WP051 | SOURCE_WP_SCOPE | 57120 | 2025-09-18 | 2025-10-08 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-10-08 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0322 | P12 | P12-Y2A7 | P12-WP051 | P12-WP051 | SOURCE_WP_SCOPE | 73440 | 2026-07-16 | 2026-08-05 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-08-05 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0323 | P12 | P12-Y3A7 | P12-WP051 | P12-WP051 | SOURCE_WP_SCOPE | 73440 | 2027-05-13 | 2027-06-02 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-06-02 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WEIGHTED_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0324 | P12 | P12-Y1A8 | P12-WP061 | P12-WP061 | SOURCE_WP_SCOPE | 28560 | 2025-10-09 | 2025-10-29 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-10-29 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0325 | P12 | P12-Y2A8 | P12-WP061 | P12-WP061 | SOURCE_WP_SCOPE | 36720 | 2026-08-06 | 2026-08-26 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-08-26 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0326 | P12 | P12-Y3A8 | P12-WP061 | P12-WP061 | SOURCE_WP_SCOPE | 36720 | 2027-06-03 | 2027-06-23 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2027-06-23 | 100% at activity finish as synthetic scheduled acceptance proxy; later EV requires independent deliverable evidence. | Task-specific approved acceptance deliverable | WORKDAY_OR_DELIVERABLE | ACCEPTANCE_EVIDENCE_UNSPECIFIED | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0327 | P03 | P03-A28 | P03-WP051 | P03-WP052 | Performance / Acceptance Testing | 487200 | 2026-10-08 | 2026-11-04 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-11-04 | 100% on documented performance acceptance (not startup completion). | Performance acceptance record | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_COMPONENT_EVIDENCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0328 | P03 | P03-A29 | P03-WP041 | P03-WP053 | SCADA checkout / regulatory sign-off | 121800 | 2026-09-10 | 2026-09-30 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-09-30 | 100% on separately defined SCADA checkout or regulatory acceptance evidence according to activity. | SCADA checkout/authority sign-off | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_COMPONENT_EVIDENCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0329 | P03 | P03-A30 | P03-WP022 | P03-WP053 | SCADA checkout / regulatory sign-off | 121800 | 2026-11-05 | 2026-12-02 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-12-02 | 100% on separately defined SCADA checkout or regulatory acceptance evidence according to activity. | SCADA checkout/authority sign-off | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_COMPONENT_EVIDENCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0330 | P05 | P05-A12c | P05-WP051 | P05-WP043 | Zone sampling / water quality | 105450 | 2025-12-01 | 2025-12-19 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-12-19 | 100% on zone-specific sampling clearance; never reused for field replacement. | Zone-specific water-quality clearance | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_COMPONENT_EVIDENCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0331 | P05 | P05-A13c | P05-WP051 | P05-WP043 | Zone sampling / water quality | 105450 | 2025-12-29 | 2026-01-16 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-01-16 | 100% on zone-specific sampling clearance; never reused for field replacement. | Zone-specific water-quality clearance | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_COMPONENT_EVIDENCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0332 | P05 | P05-A14c | P05-WP051 | P05-WP043 | Zone sampling / water quality | 105450 | 2026-01-26 | 2026-02-13 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-02-13 | 100% on zone-specific sampling clearance; never reused for field replacement. | Zone-specific water-quality clearance | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_COMPONENT_EVIDENCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0333 | P05 | P05-A15c | P05-WP051 | P05-WP043 | Zone sampling / water quality | 105450 | 2026-02-23 | 2026-03-13 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-03-13 | 100% on zone-specific sampling clearance; never reused for field replacement. | Zone-specific water-quality clearance | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_COMPONENT_EVIDENCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0334 | P10 | P10-A2 | P10-WP011 | P10-WP012 | Project definition | 81400 | 2026-04-22 | 2026-05-05 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-05-05 | 100% on signed project scope definition distinct from needs assessment. | Approved definition of scope | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_COMPONENT_EVIDENCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0335 | P11 | P11-B1gis | P11-WP061 | P11-WP042 | GIS mapping | 89600 | 2025-12-09 | 2025-12-22 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2025-12-22 | 100% on each batch GIS/asset-record update acceptance; separate from valve installation. | GIS deliverable acceptance | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_COMPONENT_EVIDENCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0336 | P11 | P11-B2gis | P11-WP061 | P11-WP042 | GIS mapping | 89600 | 2026-01-13 | 2026-01-26 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-01-26 | 100% on each batch GIS/asset-record update acceptance; separate from valve installation. | GIS deliverable acceptance | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_COMPONENT_EVIDENCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0337 | P12 | P12-Y1A6 | P12-WP041 | P12-WP042 | Emergency work orders | 141086 | 2025-05-15 | 2025-09-17 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Provisional even distribution over existing annual field-execution interval; actual EV later requires distinct documented emergency work-order quantities. | P12 segregated emergency work-order register | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_SYNTHETIC_QUANTITIES | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0338 | P12 | P12-Y2A6 | P12-WP041 | P12-WP042 | Emergency work orders | 181397 | 2026-03-12 | 2026-07-15 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Provisional even distribution over existing annual field-execution interval; actual EV later requires distinct documented emergency work-order quantities. | P12 segregated emergency work-order register | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_SYNTHETIC_QUANTITIES | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0339 | P12 | P12-Y3A6 | P12-WP041 | P12-WP042 | Emergency work orders | 181397 | 2027-01-07 | 2027-05-12 | MON_FRI_NO_HOLIDAYS | WORKDAY_FALLBACK | PER_WORKDAY | ALL_BUSINESS_DAYS | Provisional even distribution over existing annual field-execution interval; actual EV later requires distinct documented emergency work-order quantities. | P12 segregated emergency work-order register | DELIVERABLE_GATED_OR_QUANTITY_WEIGHTED__DEFINE_BEFORE_PV | REQUIRES_SYNTHETIC_QUANTITIES | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0340 | P04 | P04-A14 | P04-WP041 | P04-WP051 | FUNCTIONAL_TEST_PREPARATION_REFILL_DISINFECTION_COMPONENT | 132000 | 2026-03-02 | 2026-03-06 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-03-06 | 100% upon synthetic functional-readiness sign-off for tank refill/disinfection; excludes water-quality acceptance. | P04 functional readiness certificate | WEIGHTED_ACCEPTANCE_GATE | REQUIRES_SYNTHETIC_EVIDENCE_PROTOCOL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0341 | P04 | P04-A15 | P04-WP022 | P04-WP051 | FUNCTIONAL_ACCEPTANCE_CLEARANCE_COMPONENT | 198000 | 2026-03-09 | 2026-03-13 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-03-13 | 100% upon separate synthetic functional acceptance after bacteriological and regulatory clearance; excludes earlier readiness. | P04 functional acceptance certificate | WEIGHTED_ACCEPTANCE_GATE | REQUIRES_SYNTHETIC_EVIDENCE_PROTOCOL | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE
CL0342 | P08 | P08-A15 | P08-WP041 | P08-WP043 | VENDOR_INTEGRATED_FUEL_TANK_PIPING_INSTALLATION | 179400 | 2026-09-28 | 2026-10-09 | MON_FRI_NO_HOLIDAYS | FINAL_GATE | 100 | 2026-10-09 | 100% upon independent synthetic fuel system installation inspection and acceptance; separate from generator rigging. | P08 fuel-system inspection and acceptance | WEIGHTED_VENDOR_DELIVERABLE | REQUIRES_SYNTHETIC_VENDOR_ACCEPTANCE | User-approved synthetic cost ownership; PV rule/date proxies newly proposed Phase 3F | APPROVED_SYNTHETIC_PV_RULE

## COST_MONTHLY_PV_DETAIL
Cost_Ownership_Line_ID | Project_ID | Funded_Cost_WP_ID | Schedule_Activity_ID | Reporting_Month | Monthly_PV_USD | PV_Rule | Synthetic_Recognition_Proxy
CL0001 | P01 | P01-WP011 | P01-A1 | 2025-01 | 122100.00 | WORKDAY_SPREAD | YES
CL0002 | P01 | P01-WP012 | P01-A2 | 2025-01 | 99900.00 | WORKDAY_SPREAD | YES
CL0003 | P01 | P01-WP021 | P01-A3 | 2025-01 | 63455.00 | WORKDAY_SPREAD | YES
CL0003 | P01 | P01-WP021 | P01-A3 | 2025-02 | 117845.00 | WORKDAY_SPREAD | YES
CL0004 | P01 | P01-WP022 | P01-A4 | 2025-03 | 60606.00 | WORKDAY_SPREAD | YES
CL0004 | P01 | P01-WP022 | P01-A4 | 2025-04 | 23569.00 | WORKDAY_SPREAD | YES
CL0005 | P01 | P01-WP022 | P01-A4b | 2025-04 | 84175.00 | WORKDAY_SPREAD | YES
CL0006 | P01 | P01-WP022 | P01-A12 | 2025-10 | 168350.00 | FINAL_GATE | YES
CL0007 | P01 | P01-WP031 | P01-A7a | 2025-05 | 55253.60 | PROCUREMENT_20_30_30_20 | YES
CL0007 | P01 | P01-WP031 | P01-A7a | 2025-06 | 13813.40 | PROCUREMENT_20_30_30_20 | YES
CL0008 | P01 | P01-WP031 | P01-A5 | 2025-03 | 13813.38 | WORKDAY_SPREAD | YES
CL0008 | P01 | P01-WP031 | P01-A5 | 2025-04 | 55253.62 | WORKDAY_SPREAD | YES
CL0009 | P01 | P01-WP031 | P01-A5b | 2025-04 | 69066.00 | WORKDAY_SPREAD | YES
CL0010 | P01 | P01-WP032 | P01-A6 | 2025-05 | 307839.96 | WORKDAY_SPREAD | YES
CL0010 | P01 | P01-WP032 | P01-A6 | 2025-06 | 76960.04 | WORKDAY_SPREAD | YES
CL0011 | P01 | P01-WP041 | P01-A7b | 2025-06 | 639360.00 | PROCUREMENT_20_30_30_20 | YES
CL0011 | P01 | P01-WP041 | P01-A7b | 2025-07 | 639360.00 | PROCUREMENT_20_30_30_20 | YES
CL0012 | P01 | P01-WP041 | P01-A4u | 2025-02 | 223776.00 | WORKDAY_SPREAD | YES
CL0012 | P01 | P01-WP041 | P01-A4u | 2025-03 | 95904.00 | WORKDAY_SPREAD | YES
CL0013 | P01 | P01-WP041 | P01-A7c | 2025-07 | 1278720.00 | PROCUREMENT_20_30_30_20 | YES
CL0014 | P01 | P01-WP041 | P01-A8 | 2025-07 | 21312.00 | WORKDAY_FALLBACK | YES
CL0014 | P01 | P01-WP041 | P01-A8 | 2025-08 | 149184.00 | WORKDAY_FALLBACK | YES
CL0014 | P01 | P01-WP041 | P01-A8 | 2025-09 | 149184.00 | WORKDAY_FALLBACK | YES
CL0015 | P01 | P01-WP041 | P01-A15 | 2025-11 | 639360.00 | FINAL_GATE | YES
CL0016 | P01 | P01-WP042 | P01-A9 | 2025-08 | 255744.00 | WORKDAY_FALLBACK | YES
CL0016 | P01 | P01-WP042 | P01-A9 | 2025-09 | 170496.00 | WORKDAY_FALLBACK | YES
CL0017 | P01 | P01-WP042 | P01-A9b | 2025-08 | 170496.00 | WORKDAY_SPREAD | YES
CL0017 | P01 | P01-WP042 | P01-A9b | 2025-09 | 255744.00 | WORKDAY_SPREAD | YES
CL0018 | P01 | P01-WP043 | P01-A10 | 2025-10 | 383616.00 | WORKDAY_FALLBACK | YES
CL0018 | P01 | P01-WP043 | P01-A10 | 2025-11 | 255744.00 | WORKDAY_FALLBACK | YES
CL0019 | P01 | P01-WP051 | P01-A11 | 2025-10 | 518000.00 | FINAL_GATE | YES
CL0020 | P01 | P01-WP061 | P01-A13 | 2025-12 | 144300.00 | FINAL_GATE | YES
CL0021 | P01 | P01-WP062 | P01-A14 | 2025-12 | 77700.00 | FINAL_GATE | YES
CL0022 | P02 | P02-WP011 | P02-A1 | 2025-02 | 132000.00 | WORKDAY_SPREAD | YES
CL0023 | P02 | P02-WP012 | P02-A2 | 2025-02 | 132000.00 | WORKDAY_SPREAD | YES
CL0024 | P02 | P02-WP021 | P02-A3 | 2025-02 | 69300.00 | WORKDAY_SPREAD | YES
CL0024 | P02 | P02-WP021 | P02-A3 | 2025-03 | 207900.00 | WORKDAY_SPREAD | YES
CL0025 | P02 | P02-WP022 | P02-A4 | 2025-03 | 61776.00 | WORKDAY_SPREAD | YES
CL0025 | P02 | P02-WP022 | P02-A4 | 2025-04 | 195624.00 | WORKDAY_SPREAD | YES
CL0026 | P02 | P02-WP022 | P02-A4b | 2025-04 | 38610.00 | WORKDAY_SPREAD | YES
CL0026 | P02 | P02-WP022 | P02-A4b | 2025-05 | 218790.00 | WORKDAY_SPREAD | YES
CL0027 | P02 | P02-WP031 | P02-A5 | 2025-04 | 93426.58 | WORKDAY_SPREAD | YES
CL0027 | P02 | P02-WP031 | P02-A5 | 2025-05 | 14373.42 | WORKDAY_SPREAD | YES
CL0028 | P02 | P02-WP031 | P02-A5b | 2025-05 | 107800.00 | WORKDAY_SPREAD | YES
CL0029 | P02 | P02-WP032 | P02-A6 | 2025-06 | 400400.00 | WORKDAY_SPREAD | YES
CL0030 | P02 | P02-WP041 | P02-A6b | 2025-02 | 190080.00 | WORKDAY_SPREAD | YES
CL0031 | P02 | P02-WP041 | P02-A7a | 2025-06 | 190080.00 | PROCUREMENT_20_30_30_20 | YES
CL0032 | P02 | P02-WP041 | P02-A8 | 2025-06 | 190080.00 | WORKDAY_FALLBACK | YES
CL0033 | P02 | P02-WP041 | P02-A7b | 2025-07 | 152064.00 | PROCUREMENT_20_30_30_20 | YES
CL0033 | P02 | P02-WP041 | P02-A7b | 2025-08 | 228096.00 | PROCUREMENT_20_30_30_20 | YES
CL0033 | P02 | P02-WP041 | P02-A7b | 2025-10 | 380160.00 | PROCUREMENT_20_30_30_20 | YES
CL0034 | P02 | P02-WP041 | P02-A9 | 2025-06 | 12672.00 | WORKDAY_SPREAD | YES
CL0034 | P02 | P02-WP041 | P02-A9 | 2025-07 | 177408.00 | WORKDAY_SPREAD | YES
CL0035 | P02 | P02-WP041 | P02-A7c | 2025-11 | 190080.00 | WORKDAY_SPREAD | YES
CL0036 | P02 | P02-WP041 | P02-A7d | 2025-11 | 760320.00 | PROCUREMENT_20_30_30_20 | YES
CL0037 | P02 | P02-WP041 | P02-A10 | 2025-11 | 15206.40 | WORKDAY_FALLBACK | YES
CL0037 | P02 | P02-WP041 | P02-A10 | 2025-12 | 174873.60 | WORKDAY_FALLBACK | YES
CL0038 | P02 | P02-WP041 | P02-A15b | 2026-02 | 380160.00 | FINAL_GATE | YES
CL0039 | P02 | P02-WP042 | P02-A11a | 2025-06 | 221760.00 | PROCUREMENT_20_30_30_20 | YES
CL0040 | P02 | P02-WP042 | P02-A6c | 2025-02 | 221760.00 | WORKDAY_SPREAD | YES
CL0041 | P02 | P02-WP042 | P02-A11b | 2025-07 | 177408.00 | PROCUREMENT_20_30_30_20 | YES
CL0041 | P02 | P02-WP042 | P02-A11b | 2025-08 | 266112.00 | PROCUREMENT_20_30_30_20 | YES
CL0041 | P02 | P02-WP042 | P02-A11b | 2025-09 | 266112.00 | PROCUREMENT_20_30_30_20 | YES
CL0041 | P02 | P02-WP042 | P02-A11b | 2025-10 | 177408.00 | PROCUREMENT_20_30_30_20 | YES
CL0042 | P02 | P02-WP042 | P02-A11c | 2025-10 | 221760.00 | WORKDAY_SPREAD | YES
CL0043 | P02 | P02-WP042 | P02-A11d | 2025-11 | 887040.00 | PROCUREMENT_20_30_30_20 | YES
CL0044 | P02 | P02-WP042 | P02-A12 | 2025-11 | 133056.00 | WORKDAY_FALLBACK | YES
CL0044 | P02 | P02-WP042 | P02-A12 | 2025-12 | 88704.00 | WORKDAY_FALLBACK | YES
CL0045 | P02 | P02-WP043 | P02-A13 | 2025-07 | 285120.00 | WORKDAY_SPREAD | YES
CL0045 | P02 | P02-WP043 | P02-A13 | 2025-08 | 348480.00 | WORKDAY_SPREAD | YES
CL0046 | P02 | P02-WP051 | P02-A14 | 2026-01 | 264000.00 | FINAL_GATE | YES
CL0047 | P02 | P02-WP051 | P02-A15 | 2026-01 | 264000.00 | FINAL_GATE | YES
CL0048 | P02 | P02-WP061 | P02-A16 | 2026-02 | 171600.00 | FINAL_GATE | YES
CL0049 | P02 | P02-WP062 | P02-A17 | 2026-02 | 92400.00 | FINAL_GATE | YES
CL0050 | P03 | P03-WP011 | P03-A1 | 2025-01 | 274050.00 | WORKDAY_SPREAD | YES
CL0051 | P03 | P03-WP012 | P03-A2 | 2025-01 | 234465.00 | WORKDAY_SPREAD | YES
CL0051 | P03 | P03-WP012 | P03-A2 | 2025-02 | 100485.00 | WORKDAY_SPREAD | YES
CL0052 | P03 | P03-WP021 | P03-A3 | 2025-02 | 51156.00 | WORKDAY_SPREAD | YES
CL0052 | P03 | P03-WP021 | P03-A3 | 2025-03 | 153468.00 | WORKDAY_SPREAD | YES
CL0052 | P03 | P03-WP021 | P03-A3 | 2025-04 | 87696.00 | WORKDAY_SPREAD | YES
CL0053 | P03 | P03-WP021 | P03-A4 | 2025-04 | 194880.00 | WORKDAY_SPREAD | YES
CL0053 | P03 | P03-WP021 | P03-A4 | 2025-05 | 97440.00 | WORKDAY_SPREAD | YES
CL0054 | P03 | P03-WP022 | P03-A2b | 2025-02 | 138040.00 | WORKDAY_SPREAD | YES
CL0055 | P03 | P03-WP022 | P03-A5 | 2025-05 | 234668.00 | WORKDAY_FALLBACK | YES
CL0055 | P03 | P03-WP022 | P03-A5 | 2025-06 | 179452.00 | WORKDAY_FALLBACK | YES
CL0056 | P03 | P03-WP022 | P03-A6 | 2025-06 | 73621.28 | WORKDAY_SPREAD | YES
CL0056 | P03 | P03-WP022 | P03-A6 | 2025-07 | 64418.72 | WORKDAY_SPREAD | YES
CL0057 | P03 | P03-WP022 | P03-A7 | 2025-06 | 20706.00 | WORKDAY_SPREAD | YES
CL0057 | P03 | P03-WP022 | P03-A7 | 2025-07 | 117334.00 | WORKDAY_SPREAD | YES
CL0058 | P03 | P03-WP022 | P03-A7b | 2025-07 | 27607.98 | WORKDAY_SPREAD | YES
CL0058 | P03 | P03-WP022 | P03-A7b | 2025-08 | 96627.93 | WORKDAY_SPREAD | YES
CL0058 | P03 | P03-WP022 | P03-A7b | 2025-09 | 13804.09 | WORKDAY_SPREAD | YES
CL0059 | P03 | P03-WP022 | P03-A30 | 2026-12 | 276080.00 | FINAL_GATE | YES
CL0060 | P03 | P03-WP031 | P03-A8 | 2025-07 | 198940.00 | WORKDAY_SPREAD | YES
CL0060 | P03 | P03-WP031 | P03-A8 | 2025-08 | 49735.00 | WORKDAY_SPREAD | YES
CL0061 | P03 | P03-WP031 | P03-A9 | 2025-08 | 248675.00 | WORKDAY_SPREAD | YES
CL0062 | P03 | P03-WP032 | P03-A9b | 2025-08 | 61576.66 | WORKDAY_SPREAD | YES
CL0062 | P03 | P03-WP032 | P03-A9b | 2025-09 | 400248.34 | WORKDAY_SPREAD | YES
CL0063 | P03 | P03-WP032 | P03-A10 | 2025-09 | 207821.25 | WORKDAY_SPREAD | YES
CL0063 | P03 | P03-WP032 | P03-A10 | 2025-10 | 254003.75 | WORKDAY_SPREAD | YES
CL0064 | P03 | P03-WP041 | P03-A11 | 2025-09 | 86931.80 | PROCUREMENT_20_30_30_20 | YES
CL0064 | P03 | P03-WP041 | P03-A11 | 2025-10 | 347727.20 | PROCUREMENT_20_30_30_20 | YES
CL0065 | P03 | P03-WP041 | P03-A12 | 2025-11 | 347727.00 | PROCUREMENT_20_30_30_20 | YES
CL0065 | P03 | P03-WP041 | P03-A12 | 2025-12 | 521590.50 | PROCUREMENT_20_30_30_20 | YES
CL0065 | P03 | P03-WP041 | P03-A12 | 2026-02 | 521590.50 | PROCUREMENT_20_30_30_20 | YES
CL0065 | P03 | P03-WP041 | P03-A12 | 2026-03 | 347727.00 | PROCUREMENT_20_30_30_20 | YES
CL0066 | P03 | P03-WP041 | P03-A13 | 2026-03 | 434659.00 | PROCUREMENT_20_30_30_20 | YES
CL0067 | P03 | P03-WP041 | P03-A14 | 2026-03 | 347727.00 | PROCUREMENT_20_30_30_20 | YES
CL0067 | P03 | P03-WP041 | P03-A14 | 2026-04 | 1390908.00 | PROCUREMENT_20_30_30_20 | YES
CL0068 | P03 | P03-WP041 | P03-A15 | 2026-04 | 579544.96 | WORKDAY_FALLBACK | YES
CL0068 | P03 | P03-WP041 | P03-A15 | 2026-05 | 760652.76 | WORKDAY_FALLBACK | YES
CL0068 | P03 | P03-WP041 | P03-A15 | 2026-06 | 796874.32 | WORKDAY_FALLBACK | YES
CL0068 | P03 | P03-WP041 | P03-A15 | 2026-07 | 36221.96 | WORKDAY_FALLBACK | YES
CL0069 | P03 | P03-WP041 | P03-A29 | 2026-09 | 869318.00 | FINAL_GATE | YES
CL0070 | P03 | P03-WP042 | P03-A16 | 2025-09 | 71050.00 | PROCUREMENT_20_30_30_20 | YES
CL0070 | P03 | P03-WP042 | P03-A16 | 2025-10 | 284200.00 | PROCUREMENT_20_30_30_20 | YES
CL0071 | P03 | P03-WP042 | P03-A17 | 2025-11 | 284200.00 | PROCUREMENT_20_30_30_20 | YES
CL0071 | P03 | P03-WP042 | P03-A17 | 2025-12 | 426300.00 | PROCUREMENT_20_30_30_20 | YES
CL0071 | P03 | P03-WP042 | P03-A17 | 2026-01 | 426300.00 | PROCUREMENT_20_30_30_20 | YES
CL0071 | P03 | P03-WP042 | P03-A17 | 2026-02 | 284200.00 | PROCUREMENT_20_30_30_20 | YES
CL0072 | P03 | P03-WP042 | P03-A18 | 2026-02 | 355250.00 | WORKDAY_SPREAD | YES
CL0073 | P03 | P03-WP042 | P03-A19 | 2026-02 | 1136800.00 | PROCUREMENT_20_30_30_20 | YES
CL0073 | P03 | P03-WP042 | P03-A19 | 2026-03 | 284200.00 | PROCUREMENT_20_30_30_20 | YES
CL0074 | P03 | P03-WP042 | P03-A20 | 2026-05 | 402616.61 | WORKDAY_FALLBACK | YES
CL0074 | P03 | P03-WP042 | P03-A20 | 2026-06 | 521033.26 | WORKDAY_FALLBACK | YES
CL0074 | P03 | P03-WP042 | P03-A20 | 2026-07 | 142100.13 | WORKDAY_FALLBACK | YES
CL0075 | P03 | P03-WP042 | P03-A25 | 2026-07 | 301962.50 | WORKDAY_SPREAD | YES
CL0075 | P03 | P03-WP042 | P03-A25 | 2026-08 | 53287.50 | WORKDAY_SPREAD | YES
CL0076 | P03 | P03-WP043 | P03-A21 | 2025-09 | 76971.00 | PROCUREMENT_20_30_30_20 | YES
CL0076 | P03 | P03-WP043 | P03-A21 | 2025-10 | 76971.00 | PROCUREMENT_20_30_30_20 | YES
CL0077 | P03 | P03-WP043 | P03-A22 | 2025-10 | 123153.40 | PROCUREMENT_20_30_30_20 | YES
CL0077 | P03 | P03-WP043 | P03-A22 | 2025-11 | 184730.10 | PROCUREMENT_20_30_30_20 | YES
CL0077 | P03 | P03-WP043 | P03-A22 | 2025-12 | 307883.50 | PROCUREMENT_20_30_30_20 | YES
CL0078 | P03 | P03-WP043 | P03-A23 | 2025-12 | 615766.00 | PROCUREMENT_20_30_30_20 | YES
CL0079 | P03 | P03-WP043 | P03-A24 | 2026-05 | 129311.00 | WORKDAY_FALLBACK | YES
CL0079 | P03 | P03-WP043 | P03-A24 | 2026-06 | 332514.00 | WORKDAY_FALLBACK | YES
CL0080 | P03 | P03-WP051 | P03-A26 | 2026-08 | 446601.00 | FINAL_GATE | YES
CL0081 | P03 | P03-WP051 | P03-A27 | 2026-10 | 446599.00 | FINAL_GATE | YES
CL0082 | P03 | P03-WP061 | P03-A31 | 2026-12 | 284200.00 | FINAL_GATE | YES
CL0083 | P03 | P03-WP061 | P03-A32 | 2026-12 | 142100.00 | FINAL_GATE | YES
CL0084 | P03 | P03-WP062 | P03-A33 | 2027-01 | 182700.00 | FINAL_GATE | YES
CL0085 | P04 | P04-WP011 | P04-A1 | 2025-06 | 82500.00 | WORKDAY_SPREAD | YES
CL0086 | P04 | P04-WP012 | P04-A2 | 2025-06 | 82500.00 | WORKDAY_SPREAD | YES
CL0087 | P04 | P04-WP021 | P04-A3 | 2025-06 | 40425.00 | WORKDAY_SPREAD | YES
CL0087 | P04 | P04-WP021 | P04-A3 | 2025-07 | 94325.00 | WORKDAY_SPREAD | YES
CL0088 | P04 | P04-WP022 | P04-A4 | 2025-08 | 50050.40 | WORKDAY_SPREAD | YES
CL0088 | P04 | P04-WP022 | P04-A4 | 2025-09 | 12512.60 | WORKDAY_SPREAD | YES
CL0089 | P04 | P04-WP022 | P04-A4b | 2025-09 | 62562.00 | WORKDAY_SPREAD | YES
CL0090 | P04 | P04-WP022 | P04-A15 | 2026-03 | 125125.00 | FINAL_GATE | YES
CL0091 | P04 | P04-WP031 | P04-A5 | 2025-08 | 44916.60 | WORKDAY_SPREAD | YES
CL0091 | P04 | P04-WP031 | P04-A5 | 2025-09 | 22458.40 | WORKDAY_SPREAD | YES
CL0092 | P04 | P04-WP031 | P04-A5b | 2025-09 | 67375.00 | WORKDAY_SPREAD | YES
CL0093 | P04 | P04-WP032 | P04-A5c | 2025-09 | 87587.50 | WORKDAY_SPREAD | YES
CL0093 | P04 | P04-WP032 | P04-A5c | 2025-10 | 37537.50 | WORKDAY_SPREAD | YES
CL0094 | P04 | P04-WP032 | P04-A6 | 2025-10 | 62562.50 | WORKDAY_SPREAD | YES
CL0094 | P04 | P04-WP032 | P04-A6 | 2025-11 | 62562.50 | WORKDAY_SPREAD | YES
CL0095 | P04 | P04-WP041 | P04-A7 | 2025-10 | 82530.65 | WORKDAY_SPREAD | YES
CL0095 | P04 | P04-WP041 | P04-A7 | 2025-11 | 165061.35 | WORKDAY_SPREAD | YES
CL0096 | P04 | P04-WP041 | P04-A8 | 2025-11 | 247592.00 | WORKDAY_SPREAD | YES
CL0097 | P04 | P04-WP041 | P04-A9 | 2025-11 | 82530.65 | WORKDAY_SPREAD | YES
CL0097 | P04 | P04-WP041 | P04-A9 | 2025-12 | 165061.35 | WORKDAY_SPREAD | YES
CL0098 | P04 | P04-WP041 | P04-A12 | 2026-01 | 618979.00 | WORKDAY_FALLBACK | YES
CL0098 | P04 | P04-WP041 | P04-A12 | 2026-02 | 618979.00 | WORKDAY_FALLBACK | YES
CL0099 | P04 | P04-WP041 | P04-A13 | 2026-02 | 247592.00 | WORKDAY_FALLBACK | YES
CL0100 | P04 | P04-WP041 | P04-A14 | 2026-03 | 247591.00 | WORKDAY_SPREAD | YES
CL0101 | P04 | P04-WP041 | P04-A16 | 2026-03 | 495183.00 | FINAL_GATE | YES
CL0102 | P04 | P04-WP042 | P04-A10 | 2025-12 | 814000.00 | WORKDAY_FALLBACK | YES
CL0103 | P04 | P04-WP043 | P04-A11 | 2025-12 | 56979.99 | WORKDAY_FALLBACK | YES
CL0103 | P04 | P04-WP043 | P04-A11 | 2026-01 | 227920.01 | WORKDAY_FALLBACK | YES
CL0104 | P04 | P04-WP061 | P04-A17 | 2026-04 | 107250.00 | FINAL_GATE | YES
CL0105 | P04 | P04-WP062 | P04-A18 | 2026-04 | 57750.00 | FINAL_GATE | YES
CL0106 | P05 | P05-WP011 | P05-A1 | 2025-03 | 96200.00 | WORKDAY_SPREAD | YES
CL0107 | P05 | P05-WP011 | P05-A8 | 2025-09 | 192400.00 | FINAL_GATE | YES
CL0108 | P05 | P05-WP012 | P05-A2 | 2025-03 | 93240.00 | WORKDAY_FALLBACK | YES
CL0108 | P05 | P05-WP012 | P05-A2 | 2025-04 | 62160.00 | WORKDAY_FALLBACK | YES
CL0109 | P05 | P05-WP021 | P05-A3 | 2025-04 | 199800.00 | WORKDAY_FALLBACK | YES
CL0110 | P05 | P05-WP022 | P05-A4 | 2025-05 | 155400.00 | WORKDAY_SPREAD | YES
CL0111 | P05 | P05-WP022 | P05-A4b | 2025-05 | 51800.00 | WORKDAY_SPREAD | YES
CL0111 | P05 | P05-WP022 | P05-A4b | 2025-06 | 103600.00 | WORKDAY_SPREAD | YES
CL0112 | P05 | P05-WP022 | P05-A10 | 2025-07 | 145040.00 | WORKDAY_SPREAD | YES
CL0112 | P05 | P05-WP022 | P05-A10 | 2025-08 | 10360.00 | WORKDAY_SPREAD | YES
CL0113 | P05 | P05-WP031 | P05-A5 | 2025-05 | 77700.00 | WORKDAY_SPREAD | YES
CL0113 | P05 | P05-WP031 | P05-A5 | 2025-06 | 38850.00 | WORKDAY_SPREAD | YES
CL0114 | P05 | P05-WP031 | P05-A5b | 2025-06 | 116550.00 | WORKDAY_SPREAD | YES
CL0115 | P05 | P05-WP032 | P05-A5c | 2025-06 | 43290.00 | WORKDAY_SPREAD | YES
CL0115 | P05 | P05-WP032 | P05-A5c | 2025-07 | 28860.00 | WORKDAY_SPREAD | YES
CL0116 | P05 | P05-WP032 | P05-A11 | 2025-07 | 57720.00 | PROCUREMENT_20_30_30_20 | YES
CL0116 | P05 | P05-WP032 | P05-A11 | 2025-08 | 230880.00 | PROCUREMENT_20_30_30_20 | YES
CL0117 | P05 | P05-WP032 | P05-A6 | 2025-07 | 67340.00 | WORKDAY_SPREAD | YES
CL0117 | P05 | P05-WP032 | P05-A6 | 2025-08 | 4810.00 | WORKDAY_SPREAD | YES
CL0118 | P05 | P05-WP041 | P05-A7 | 2025-07 | 84203.70 | WORKDAY_SPREAD | YES
CL0118 | P05 | P05-WP041 | P05-A7 | 2025-08 | 126305.55 | WORKDAY_SPREAD | YES
CL0118 | P05 | P05-WP041 | P05-A7 | 2025-09 | 30072.75 | WORKDAY_SPREAD | YES
CL0119 | P05 | P05-WP041 | P05-A9 | 2025-07 | 48116.40 | WORKDAY_SPREAD | YES
CL0119 | P05 | P05-WP041 | P05-A9 | 2025-08 | 192465.60 | WORKDAY_SPREAD | YES
CL0120 | P05 | P05-WP041 | P05-A12a | 2025-08 | 109355.50 | WORKDAY_FALLBACK | YES
CL0120 | P05 | P05-WP041 | P05-A12a | 2025-09 | 481164.20 | WORKDAY_FALLBACK | YES
CL0120 | P05 | P05-WP041 | P05-A12a | 2025-10 | 503035.30 | WORKDAY_FALLBACK | YES
CL0120 | P05 | P05-WP041 | P05-A12a | 2025-11 | 109356.00 | WORKDAY_FALLBACK | YES
CL0121 | P05 | P05-WP041 | P05-AFIRST | 2025-08 | 721747.00 | WORKDAY_FALLBACK | YES
CL0122 | P05 | P05-WP041 | P05-A13a | 2025-09 | 153097.70 | WORKDAY_FALLBACK | YES
CL0122 | P05 | P05-WP041 | P05-A13a | 2025-10 | 503035.30 | WORKDAY_FALLBACK | YES
CL0122 | P05 | P05-WP041 | P05-A13a | 2025-11 | 437422.00 | WORKDAY_FALLBACK | YES
CL0122 | P05 | P05-WP041 | P05-A13a | 2025-12 | 109356.00 | WORKDAY_FALLBACK | YES
CL0123 | P05 | P05-WP041 | P05-A14a | 2025-10 | 218711.00 | WORKDAY_FALLBACK | YES
CL0123 | P05 | P05-WP041 | P05-A14a | 2025-11 | 437422.00 | WORKDAY_FALLBACK | YES
CL0123 | P05 | P05-WP041 | P05-A14a | 2025-12 | 503035.30 | WORKDAY_FALLBACK | YES
CL0123 | P05 | P05-WP041 | P05-A14a | 2026-01 | 43742.70 | WORKDAY_FALLBACK | YES
CL0124 | P05 | P05-WP041 | P05-A15a | 2025-11 | 218711.00 | WORKDAY_FALLBACK | YES
CL0124 | P05 | P05-WP041 | P05-A15a | 2025-12 | 503035.30 | WORKDAY_FALLBACK | YES
CL0124 | P05 | P05-WP041 | P05-A15a | 2026-01 | 481164.70 | WORKDAY_FALLBACK | YES
CL0125 | P05 | P05-WP041 | P05-A16 | 2026-04 | 481165.00 | FINAL_GATE | YES
CL0126 | P05 | P05-WP042 | P05-A12b | 2025-09 | 82826.16 | WORKDAY_FALLBACK | YES
CL0126 | P05 | P05-WP042 | P05-A12b | 2025-10 | 158750.14 | WORKDAY_FALLBACK | YES
CL0126 | P05 | P05-WP042 | P05-A12b | 2025-11 | 138043.70 | WORKDAY_FALLBACK | YES
CL0127 | P05 | P05-WP042 | P05-A13b | 2025-10 | 103532.70 | WORKDAY_FALLBACK | YES
CL0127 | P05 | P05-WP042 | P05-A13b | 2025-11 | 138043.60 | WORKDAY_FALLBACK | YES
CL0127 | P05 | P05-WP042 | P05-A13b | 2025-12 | 138043.70 | WORKDAY_FALLBACK | YES
CL0128 | P05 | P05-WP042 | P05-A14b | 2025-11 | 103532.70 | WORKDAY_FALLBACK | YES
CL0128 | P05 | P05-WP042 | P05-A14b | 2025-12 | 158750.14 | WORKDAY_FALLBACK | YES
CL0128 | P05 | P05-WP042 | P05-A14b | 2026-01 | 117337.16 | WORKDAY_FALLBACK | YES
CL0129 | P05 | P05-WP042 | P05-A15b | 2025-12 | 124239.24 | WORKDAY_FALLBACK | YES
CL0129 | P05 | P05-WP042 | P05-A15b | 2026-01 | 151847.96 | WORKDAY_FALLBACK | YES
CL0129 | P05 | P05-WP042 | P05-A15b | 2026-02 | 103532.80 | WORKDAY_FALLBACK | YES
CL0130 | P05 | P05-WP051 | P05-A12c | 2025-12 | 138750.00 | FINAL_GATE | YES
CL0131 | P05 | P05-WP051 | P05-A13c | 2026-01 | 138750.00 | FINAL_GATE | YES
CL0132 | P05 | P05-WP051 | P05-A14c | 2026-02 | 138750.00 | FINAL_GATE | YES
CL0133 | P05 | P05-WP051 | P05-A15c | 2026-03 | 138750.00 | FINAL_GATE | YES
CL0134 | P05 | P05-WP061 | P05-A17 | 2026-05 | 249750.00 | FINAL_GATE | YES
CL0135 | P05 | P05-WP062 | P05-A18 | 2026-05 | 83250.00 | FINAL_GATE | YES
CL0136 | P06 | P06-WP011 | P06-A1 | 2025-08 | 75900.00 | WORKDAY_SPREAD | YES
CL0137 | P06 | P06-WP011 | P06-A10 | 2025-12 | 53130.00 | WORKDAY_SPREAD | YES
CL0137 | P06 | P06-WP011 | P06-A10 | 2026-01 | 22770.00 | WORKDAY_SPREAD | YES
CL0138 | P06 | P06-WP012 | P06-A2 | 2025-08 | 74520.00 | WORKDAY_SPREAD | YES
CL0138 | P06 | P06-WP012 | P06-A2 | 2025-09 | 49680.00 | WORKDAY_SPREAD | YES
CL0139 | P06 | P06-WP021 | P06-A3 | 2025-09 | 239085.00 | WORKDAY_SPREAD | YES
CL0139 | P06 | P06-WP021 | P06-A3 | 2025-10 | 26565.00 | WORKDAY_SPREAD | YES
CL0140 | P06 | P06-WP022 | P06-A4 | 2025-10 | 98670.40 | WORKDAY_SPREAD | YES
CL0140 | P06 | P06-WP022 | P06-A4 | 2025-11 | 24667.60 | WORKDAY_SPREAD | YES
CL0141 | P06 | P06-WP022 | P06-A4b | 2025-11 | 123338.00 | WORKDAY_SPREAD | YES
CL0142 | P06 | P06-WP022 | P06-A7 | 2025-12 | 86335.90 | WORKDAY_SPREAD | YES
CL0142 | P06 | P06-WP022 | P06-A7 | 2026-01 | 37001.10 | WORKDAY_SPREAD | YES
CL0143 | P06 | P06-WP022 | P06-A8 | 2025-12 | 115114.44 | WORKDAY_SPREAD | YES
CL0143 | P06 | P06-WP022 | P06-A8 | 2026-01 | 8222.56 | WORKDAY_SPREAD | YES
CL0144 | P06 | P06-WP031 | P06-A5 | 2025-10 | 35880.00 | WORKDAY_SPREAD | YES
CL0144 | P06 | P06-WP031 | P06-A5 | 2025-11 | 53820.00 | WORKDAY_SPREAD | YES
CL0145 | P06 | P06-WP031 | P06-A5b | 2025-11 | 89700.00 | WORKDAY_SPREAD | YES
CL0146 | P06 | P06-WP031 | P06-A11 | 2025-12 | 71760.00 | PROCUREMENT_20_30_30_20 | YES
CL0146 | P06 | P06-WP031 | P06-A11 | 2026-01 | 17940.00 | PROCUREMENT_20_30_30_20 | YES
CL0147 | P06 | P06-WP032 | P06-A5c | 2025-11 | 8970.00 | WORKDAY_SPREAD | YES
CL0147 | P06 | P06-WP032 | P06-A5c | 2025-12 | 80730.00 | WORKDAY_SPREAD | YES
CL0148 | P06 | P06-WP032 | P06-A6 | 2025-12 | 89700.00 | WORKDAY_SPREAD | YES
CL0149 | P06 | P06-WP032 | P06-A12 | 2026-01 | 71760.00 | PROCUREMENT_20_30_30_20 | YES
CL0149 | P06 | P06-WP032 | P06-A12 | 2026-02 | 107640.00 | PROCUREMENT_20_30_30_20 | YES
CL0149 | P06 | P06-WP032 | P06-A12 | 2026-03 | 179400.00 | PROCUREMENT_20_30_30_20 | YES
CL0150 | P06 | P06-WP032 | P06-A13 | 2026-03 | 17940.00 | PROCUREMENT_20_30_30_20 | YES
CL0150 | P06 | P06-WP032 | P06-A13 | 2026-04 | 71760.00 | PROCUREMENT_20_30_30_20 | YES
CL0151 | P06 | P06-WP041 | P06-A15 | 2025-12 | 340947.00 | WORKDAY_FALLBACK | YES
CL0152 | P06 | P06-WP041 | P06-APILOTSTAGE | 2026-04 | 454595.00 | PROCUREMENT_20_30_30_20 | YES
CL0153 | P06 | P06-WP041 | P06-A16 | 2026-04 | 227297.30 | WORKDAY_FALLBACK | YES
CL0153 | P06 | P06-WP041 | P06-A16 | 2026-05 | 113648.70 | WORKDAY_FALLBACK | YES
CL0154 | P06 | P06-WP041 | P06-AFIRSTPILOT | 2026-04 | 113649.00 | WORKDAY_FALLBACK | YES
CL0155 | P06 | P06-WP041 | P06-A18a | 2026-05 | 9741.31 | WORKDAY_FALLBACK | YES
CL0155 | P06 | P06-WP041 | P06-A18a | 2026-06 | 214308.82 | WORKDAY_FALLBACK | YES
CL0155 | P06 | P06-WP041 | P06-A18a | 2026-07 | 116895.87 | WORKDAY_FALLBACK | YES
CL0156 | P06 | P06-WP041 | P06-A19a | 2026-06 | 77930.48 | WORKDAY_FALLBACK | YES
CL0156 | P06 | P06-WP041 | P06-A19a | 2026-07 | 224050.13 | WORKDAY_FALLBACK | YES
CL0156 | P06 | P06-WP041 | P06-A19a | 2026-08 | 38965.39 | WORKDAY_FALLBACK | YES
CL0157 | P06 | P06-WP041 | P06-A20a | 2026-07 | 155860.96 | WORKDAY_FALLBACK | YES
CL0157 | P06 | P06-WP041 | P06-A20a | 2026-08 | 185085.04 | WORKDAY_FALLBACK | YES
CL0158 | P06 | P06-WP041 | P06-A21a | 2026-07 | 9741.31 | WORKDAY_FALLBACK | YES
CL0158 | P06 | P06-WP041 | P06-A21a | 2026-08 | 204567.51 | WORKDAY_FALLBACK | YES
CL0158 | P06 | P06-WP041 | P06-A21a | 2026-09 | 126637.18 | WORKDAY_FALLBACK | YES
CL0159 | P06 | P06-WP041 | P06-A22 | 2026-10 | 113649.00 | WORKDAY_SPREAD | YES
CL0160 | P06 | P06-WP042 | P06-A9 | 2026-01 | 341964.16 | WORKDAY_FALLBACK | YES
CL0160 | P06 | P06-WP042 | P06-A9 | 2026-02 | 299218.84 | WORKDAY_FALLBACK | YES
CL0161 | P06 | P06-WP042 | P06-A14 | 2026-02 | 64118.10 | WORKDAY_SPREAD | YES
CL0161 | P06 | P06-WP042 | P06-A14 | 2026-03 | 149608.90 | WORKDAY_SPREAD | YES
CL0162 | P06 | P06-WP043 | P06-A18b | 2026-07 | 122130.00 | WORKDAY_SPREAD | YES
CL0163 | P06 | P06-WP043 | P06-A19b | 2026-08 | 122130.00 | WORKDAY_SPREAD | YES
CL0164 | P06 | P06-WP043 | P06-A20b | 2026-08 | 24426.00 | WORKDAY_SPREAD | YES
CL0164 | P06 | P06-WP043 | P06-A20b | 2026-09 | 97704.00 | WORKDAY_SPREAD | YES
CL0165 | P06 | P06-WP043 | P06-A21b | 2026-09 | 109917.00 | WORKDAY_SPREAD | YES
CL0165 | P06 | P06-WP043 | P06-A21b | 2026-10 | 12213.00 | WORKDAY_SPREAD | YES
CL0166 | P06 | P06-WP051 | P06-A17 | 2026-05 | 230000.00 | FINAL_GATE | YES
CL0167 | P06 | P06-WP051 | P06-A23 | 2026-10 | 207000.00 | WORKDAY_FALLBACK | YES
CL0167 | P06 | P06-WP051 | P06-A23 | 2026-11 | 138000.00 | WORKDAY_FALLBACK | YES
CL0168 | P06 | P06-WP051 | P06-A24 | 2026-11 | 115000.00 | WORKDAY_SPREAD | YES
CL0169 | P06 | P06-WP061 | P06-A25 | 2026-12 | 144900.00 | FINAL_GATE | YES
CL0170 | P06 | P06-WP062 | P06-A26 | 2026-12 | 62100.00 | FINAL_GATE | YES
CL0171 | P07 | P07-WP011 | P07-A1 | 2025-10 | 61500.00 | WORKDAY_SPREAD | YES
CL0172 | P07 | P07-WP012 | P07-A2 | 2025-10 | 49200.00 | WORKDAY_SPREAD | YES
CL0172 | P07 | P07-WP012 | P07-A2 | 2025-11 | 12300.00 | WORKDAY_SPREAD | YES
CL0173 | P07 | P07-WP021 | P07-A3 | 2025-11 | 116235.00 | WORKDAY_SPREAD | YES
CL0173 | P07 | P07-WP021 | P07-A3 | 2025-12 | 12915.00 | WORKDAY_SPREAD | YES
CL0174 | P07 | P07-WP022 | P07-A4 | 2025-12 | 95940.00 | WORKDAY_SPREAD | YES
CL0174 | P07 | P07-WP022 | P07-A4 | 2026-01 | 23985.00 | WORKDAY_SPREAD | YES
CL0175 | P07 | P07-WP022 | P07-A4b | 2026-01 | 119925.00 | WORKDAY_SPREAD | YES
CL0176 | P07 | P07-WP031 | P07-A5 | 2025-12 | 19133.58 | WORKDAY_SPREAD | YES
CL0176 | P07 | P07-WP031 | P07-A5 | 2026-01 | 28700.42 | WORKDAY_SPREAD | YES
CL0177 | P07 | P07-WP031 | P07-A5b | 2026-01 | 47833.00 | WORKDAY_SPREAD | YES
CL0178 | P07 | P07-WP031 | P07-A8 | 2026-02 | 9566.60 | PROCUREMENT_20_30_30_20 | YES
CL0178 | P07 | P07-WP031 | P07-A8 | 2026-03 | 38266.40 | PROCUREMENT_20_30_30_20 | YES
CL0179 | P07 | P07-WP032 | P07-A5c | 2026-01 | 39975.00 | WORKDAY_SPREAD | YES
CL0179 | P07 | P07-WP032 | P07-A5c | 2026-02 | 93275.00 | WORKDAY_SPREAD | YES
CL0180 | P07 | P07-WP032 | P07-A6 | 2026-02 | 39975.00 | WORKDAY_SPREAD | YES
CL0180 | P07 | P07-WP032 | P07-A6 | 2026-03 | 93275.00 | WORKDAY_SPREAD | YES
CL0181 | P07 | P07-WP041 | P07-A7 | 2026-02 | 133824.00 | WORKDAY_SPREAD | YES
CL0181 | P07 | P07-WP041 | P07-A7 | 2026-03 | 312256.00 | WORKDAY_SPREAD | YES
CL0182 | P07 | P07-WP041 | P07-A10 | 2026-03 | 446080.00 | WORKDAY_FALLBACK | YES
CL0183 | P07 | P07-WP041 | P07-A16 | 2026-08 | 892160.00 | FINAL_GATE | YES
CL0184 | P07 | P07-WP042 | P07-A11 | 2026-04 | 78064.00 | WORKDAY_FALLBACK | YES
CL0184 | P07 | P07-WP042 | P07-A11 | 2026-05 | 507416.00 | WORKDAY_FALLBACK | YES
CL0185 | P07 | P07-WP043 | P07-A9 | 2026-03 | 16728.00 | PROCUREMENT_20_30_30_20 | YES
CL0185 | P07 | P07-WP043 | P07-A9 | 2026-04 | 66912.00 | PROCUREMENT_20_30_30_20 | YES
CL0186 | P07 | P07-WP043 | P07-A12 | 2026-05 | 200736.00 | WORKDAY_FALLBACK | YES
CL0186 | P07 | P07-WP043 | P07-A12 | 2026-06 | 50184.00 | WORKDAY_FALLBACK | YES
CL0187 | P07 | P07-WP043 | P07-A13 | 2026-06 | 83640.00 | WORKDAY_SPREAD | YES
CL0188 | P07 | P07-WP051 | P07-A14 | 2026-06 | 191333.00 | FINAL_GATE | YES
CL0189 | P07 | P07-WP051 | P07-A15 | 2026-07 | 95667.00 | WORKDAY_SPREAD | YES
CL0190 | P07 | P07-WP061 | P07-A17 | 2026-08 | 79950.00 | FINAL_GATE | YES
CL0191 | P07 | P07-WP062 | P07-A18 | 2026-09 | 43050.00 | FINAL_GATE | YES
CL0192 | P08 | P08-WP011 | P08-A1 | 2025-12 | 62100.00 | WORKDAY_SPREAD | YES
CL0193 | P08 | P08-WP012 | P08-A2 | 2025-12 | 60720.00 | WORKDAY_SPREAD | YES
CL0193 | P08 | P08-WP012 | P08-A2 | 2026-01 | 15180.00 | WORKDAY_SPREAD | YES
CL0194 | P08 | P08-WP021 | P08-A3 | 2026-01 | 128800.00 | WORKDAY_SPREAD | YES
CL0195 | P08 | P08-WP022 | P08-A4 | 2026-02 | 89700.00 | WORKDAY_SPREAD | YES
CL0195 | P08 | P08-WP022 | P08-A4 | 2026-03 | 29900.00 | WORKDAY_SPREAD | YES
CL0196 | P08 | P08-WP022 | P08-A4b | 2026-03 | 119600.00 | WORKDAY_SPREAD | YES
CL0197 | P08 | P08-WP031 | P08-A5 | 2026-02 | 19626.65 | WORKDAY_SPREAD | YES
CL0197 | P08 | P08-WP031 | P08-A5 | 2026-03 | 39253.35 | WORKDAY_SPREAD | YES
CL0198 | P08 | P08-WP031 | P08-A5b | 2026-03 | 58880.00 | WORKDAY_SPREAD | YES
CL0199 | P08 | P08-WP031 | P08-A8 | 2026-04 | 11776.00 | PROCUREMENT_20_30_30_20 | YES
CL0199 | P08 | P08-WP031 | P08-A8 | 2026-05 | 47104.00 | PROCUREMENT_20_30_30_20 | YES
CL0200 | P08 | P08-WP032 | P08-A5c | 2026-03 | 37536.00 | WORKDAY_SPREAD | YES
CL0200 | P08 | P08-WP032 | P08-A5c | 2026-04 | 150144.00 | WORKDAY_SPREAD | YES
CL0201 | P08 | P08-WP032 | P08-A6 | 2026-04 | 75072.00 | WORKDAY_SPREAD | YES
CL0201 | P08 | P08-WP032 | P08-A6 | 2026-05 | 112608.00 | WORKDAY_SPREAD | YES
CL0202 | P08 | P08-WP041 | P08-A7 | 2026-01 | 68193.30 | WORKDAY_SPREAD | YES
CL0202 | P08 | P08-WP041 | P08-A7 | 2026-02 | 34096.70 | WORKDAY_SPREAD | YES
CL0203 | P08 | P08-WP041 | P08-A13 | 2026-04 | 27277.32 | WORKDAY_SPREAD | YES
CL0203 | P08 | P08-WP041 | P08-A13 | 2026-05 | 75012.68 | WORKDAY_SPREAD | YES
CL0204 | P08 | P08-WP041 | P08-A14 | 2026-04 | 40915.60 | WORKDAY_SPREAD | YES
CL0204 | P08 | P08-WP041 | P08-A14 | 2026-05 | 61373.40 | WORKDAY_SPREAD | YES
CL0205 | P08 | P08-WP041 | P08-A9 | 2026-06 | 81831.60 | PROCUREMENT_20_30_30_20 | YES
CL0205 | P08 | P08-WP041 | P08-A9 | 2026-07 | 122747.40 | PROCUREMENT_20_30_30_20 | YES
CL0205 | P08 | P08-WP041 | P08-A9 | 2026-08 | 204579.00 | PROCUREMENT_20_30_30_20 | YES
CL0206 | P08 | P08-WP041 | P08-A9fat | 2026-08 | 10228.90 | WORKDAY_SPREAD | YES
CL0206 | P08 | P08-WP041 | P08-A9fat | 2026-09 | 92060.10 | WORKDAY_SPREAD | YES
CL0207 | P08 | P08-WP041 | P08-A11 | 2026-09 | 409158.00 | PROCUREMENT_20_30_30_20 | YES
CL0208 | P08 | P08-WP041 | P08-A15 | 2026-09 | 122747.40 | WORKDAY_FALLBACK | YES
CL0208 | P08 | P08-WP041 | P08-A15 | 2026-10 | 286410.60 | WORKDAY_FALLBACK | YES
CL0209 | P08 | P08-WP041 | P08-A17 | 2026-10 | 102289.00 | WORKDAY_SPREAD | YES
CL0210 | P08 | P08-WP041 | P08-A21 | 2026-12 | 204579.00 | FINAL_GATE | YES
CL0211 | P08 | P08-WP042 | P08-A10 | 2026-06 | 144517.00 | PROCUREMENT_20_30_30_20 | YES
CL0211 | P08 | P08-WP042 | P08-A10 | 2026-07 | 86710.20 | PROCUREMENT_20_30_30_20 | YES
CL0211 | P08 | P08-WP042 | P08-A10 | 2026-08 | 57806.80 | PROCUREMENT_20_30_30_20 | YES
CL0212 | P08 | P08-WP042 | P08-A10fat | 2026-08 | 72258.00 | WORKDAY_SPREAD | YES
CL0213 | P08 | P08-WP042 | P08-A12 | 2026-08 | 289033.00 | PROCUREMENT_20_30_30_20 | YES
CL0214 | P08 | P08-WP042 | P08-A16 | 2026-09 | 216775.00 | WORKDAY_FALLBACK | YES
CL0215 | P08 | P08-WP051 | P08-A18 | 2026-11 | 138000.00 | FINAL_GATE | YES
CL0216 | P08 | P08-WP051 | P08-A19 | 2026-11 | 138000.00 | FINAL_GATE | YES
CL0217 | P08 | P08-WP051 | P08-A20 | 2026-11 | 138000.00 | FINAL_GATE | YES
CL0218 | P08 | P08-WP061 | P08-A22 | 2026-12 | 89700.00 | FINAL_GATE | YES
CL0219 | P08 | P08-WP062 | P08-A23 | 2027-01 | 48300.00 | FINAL_GATE | YES
CL0220 | P09 | P09-WP011 | P09-A1 | 2026-02 | 117000.00 | WORKDAY_SPREAD | YES
CL0221 | P09 | P09-WP012 | P09-A2 | 2026-02 | 58500.00 | WORKDAY_FALLBACK | YES
CL0221 | P09 | P09-WP012 | P09-A2 | 2026-03 | 58500.00 | WORKDAY_FALLBACK | YES
CL0222 | P09 | P09-WP021 | P09-A3a | 2026-03 | 106080.00 | WORKDAY_SPREAD | YES
CL0222 | P09 | P09-WP021 | P09-A3a | 2026-04 | 18720.00 | WORKDAY_SPREAD | YES
CL0223 | P09 | P09-WP021 | P09-A3 | 2026-04 | 118560.00 | WORKDAY_SPREAD | YES
CL0223 | P09 | P09-WP021 | P09-A3 | 2026-05 | 6240.00 | WORKDAY_SPREAD | YES
CL0224 | P09 | P09-WP022 | P09-A4 | 2026-05 | 56160.00 | WORKDAY_SPREAD | YES
CL0224 | P09 | P09-WP022 | P09-A4 | 2026-06 | 18720.00 | WORKDAY_SPREAD | YES
CL0225 | P09 | P09-WP022 | P09-A4b | 2026-06 | 42432.00 | WORKDAY_SPREAD | YES
CL0225 | P09 | P09-WP022 | P09-A4b | 2026-07 | 32448.00 | WORKDAY_SPREAD | YES
CL0226 | P09 | P09-WP022 | P09-A4c | 2026-06 | 31824.00 | WORKDAY_SPREAD | YES
CL0226 | P09 | P09-WP022 | P09-A4c | 2026-07 | 43056.00 | WORKDAY_SPREAD | YES
CL0227 | P09 | P09-WP022 | P09-A19 | 2026-12 | 149760.00 | FINAL_GATE | YES
CL0228 | P09 | P09-WP031 | P09-A5 | 2026-05 | 24266.65 | WORKDAY_SPREAD | YES
CL0228 | P09 | P09-WP031 | P09-A5 | 2026-06 | 48533.35 | WORKDAY_SPREAD | YES
CL0229 | P09 | P09-WP031 | P09-A5b | 2026-06 | 58239.96 | WORKDAY_SPREAD | YES
CL0229 | P09 | P09-WP031 | P09-A5b | 2026-07 | 14560.04 | WORKDAY_SPREAD | YES
CL0230 | P09 | P09-WP031 | P09-A10 | 2026-08 | 72800.00 | PROCUREMENT_20_30_30_20 | YES
CL0231 | P09 | P09-WP032 | P09-A5c | 2026-07 | 202800.00 | WORKDAY_SPREAD | YES
CL0232 | P09 | P09-WP032 | P09-A6 | 2026-08 | 202800.00 | WORKDAY_SPREAD | YES
CL0233 | P09 | P09-WP041 | P09-A7 | 2026-08 | 304869.00 | WORKDAY_SPREAD | YES
CL0234 | P09 | P09-WP041 | P09-A8 | 2026-08 | 304869.00 | WORKDAY_SPREAD | YES
CL0235 | P09 | P09-WP041 | P09-A9 | 2026-08 | 182921.40 | WORKDAY_FALLBACK | YES
CL0235 | P09 | P09-WP041 | P09-A9 | 2026-09 | 121947.60 | WORKDAY_FALLBACK | YES
CL0236 | P09 | P09-WP041 | P09-A13 | 2026-08 | 30486.90 | WORKDAY_FALLBACK | YES
CL0236 | P09 | P09-WP041 | P09-A13 | 2026-09 | 274382.10 | WORKDAY_FALLBACK | YES
CL0237 | P09 | P09-WP041 | P09-A14 | 2026-09 | 198164.85 | WORKDAY_SPREAD | YES
CL0237 | P09 | P09-WP041 | P09-A14 | 2026-10 | 106704.15 | WORKDAY_SPREAD | YES
CL0238 | P09 | P09-WP041 | P09-A12 | 2026-10 | 609737.00 | PROCUREMENT_20_30_30_20 | YES
CL0238 | P09 | P09-WP041 | P09-A12 | 2026-11 | 609737.00 | PROCUREMENT_20_30_30_20 | YES
CL0239 | P09 | P09-WP041 | P09-A15 | 2026-11 | 304868.00 | WORKDAY_SPREAD | YES
CL0240 | P09 | P09-WP041 | P09-A16 | 2026-11 | 91460.40 | WORKDAY_SPREAD | YES
CL0240 | P09 | P09-WP041 | P09-A16 | 2026-12 | 213407.60 | WORKDAY_SPREAD | YES
CL0241 | P09 | P09-WP041 | P09-A17 | 2026-11 | 91460.40 | WORKDAY_SPREAD | YES
CL0241 | P09 | P09-WP041 | P09-A17 | 2026-12 | 213407.60 | WORKDAY_SPREAD | YES
CL0242 | P09 | P09-WP041 | P09-A21 | 2027-02 | 609737.00 | FINAL_GATE | YES
CL0243 | P09 | P09-WP042 | P09-A11 | 2026-09 | 449280.00 | PROCUREMENT_20_30_30_20 | YES
CL0243 | P09 | P09-WP042 | P09-A11 | 2026-10 | 449280.00 | PROCUREMENT_20_30_30_20 | YES
CL0244 | P09 | P09-WP043 | P09-A20 | 2026-12 | 29952.00 | WORKDAY_FALLBACK | YES
CL0244 | P09 | P09-WP043 | P09-A20 | 2027-01 | 419328.00 | WORKDAY_FALLBACK | YES
CL0245 | P09 | P09-WP051 | P09-A18 | 2026-12 | 468000.00 | FINAL_GATE | YES
CL0246 | P09 | P09-WP061 | P09-A22 | 2027-02 | 152100.00 | FINAL_GATE | YES
CL0247 | P09 | P09-WP062 | P09-A23 | 2027-03 | 81900.00 | FINAL_GATE | YES
CL0248 | P10 | P10-WP011 | P10-A1 | 2026-04 | 66600.00 | WORKDAY_SPREAD | YES
CL0249 | P10 | P10-WP021 | P10-A4 | 2026-05 | 39960.00 | WORKDAY_SPREAD | YES
CL0249 | P10 | P10-WP021 | P10-A4 | 2026-06 | 226440.00 | WORKDAY_SPREAD | YES
CL0250 | P10 | P10-WP022 | P10-A3 | 2026-05 | 99900.00 | WORKDAY_SPREAD | YES
CL0251 | P10 | P10-WP022 | P10-A5 | 2026-06 | 99900.00 | WORKDAY_SPREAD | YES
CL0252 | P10 | P10-WP022 | P10-A6b | 2026-06 | 99900.00 | WORKDAY_SPREAD | YES
CL0253 | P10 | P10-WP022 | P10-A6 | 2026-06 | 24975.00 | WORKDAY_SPREAD | YES
CL0253 | P10 | P10-WP022 | P10-A6 | 2026-07 | 74925.00 | WORKDAY_SPREAD | YES
CL0254 | P10 | P10-WP031 | P10-A7 | 2026-07 | 60434.00 | WORKDAY_SPREAD | YES
CL0255 | P10 | P10-WP031 | P10-A7b | 2026-07 | 18129.90 | WORKDAY_SPREAD | YES
CL0255 | P10 | P10-WP031 | P10-A7b | 2026-08 | 42303.10 | WORKDAY_SPREAD | YES
CL0256 | P10 | P10-WP031 | P10-A9 | 2026-08 | 12086.60 | PROCUREMENT_20_30_30_20 | YES
CL0256 | P10 | P10-WP031 | P10-A9 | 2026-09 | 48346.40 | PROCUREMENT_20_30_30_20 | YES
CL0257 | P10 | P10-WP032 | P10-A7c | 2026-08 | 168350.00 | WORKDAY_SPREAD | YES
CL0258 | P10 | P10-WP032 | P10-A8 | 2026-08 | 67340.00 | WORKDAY_SPREAD | YES
CL0258 | P10 | P10-WP032 | P10-A8 | 2026-09 | 101010.00 | WORKDAY_SPREAD | YES
CL0259 | P10 | P10-WP041 | P10-IF-01 | 2026-07 | 114996.00 | WORKDAY_SPREAD | YES
CL0259 | P10 | P10-WP041 | P10-IF-01 | 2026-08 | 28749.00 | WORKDAY_SPREAD | YES
CL0260 | P10 | P10-WP041 | P10-A14 | 2026-08 | 57498.00 | WORKDAY_FALLBACK | YES
CL0260 | P10 | P10-WP041 | P10-A14 | 2026-09 | 316239.00 | WORKDAY_FALLBACK | YES
CL0260 | P10 | P10-WP041 | P10-A14 | 2026-10 | 57498.00 | WORKDAY_FALLBACK | YES
CL0261 | P10 | P10-WP042 | P10-A11 | 2026-08 | 58608.00 | PROCUREMENT_20_30_30_20 | YES
CL0261 | P10 | P10-WP042 | P10-A11 | 2026-09 | 234432.00 | PROCUREMENT_20_30_30_20 | YES
CL0262 | P10 | P10-WP042 | P10-A15 | 2026-08 | 35164.80 | WORKDAY_FALLBACK | YES
CL0262 | P10 | P10-WP042 | P10-A15 | 2026-09 | 184615.20 | WORKDAY_FALLBACK | YES
CL0263 | P10 | P10-WP043 | P10-A10 | 2026-09 | 24864.00 | PROCUREMENT_20_30_30_20 | YES
CL0263 | P10 | P10-WP043 | P10-A10 | 2026-10 | 99456.00 | PROCUREMENT_20_30_30_20 | YES
CL0264 | P10 | P10-WP043 | P10-A12 | 2026-11 | 99456.00 | PROCUREMENT_20_30_30_20 | YES
CL0264 | P10 | P10-WP043 | P10-A12 | 2026-12 | 24864.00 | PROCUREMENT_20_30_30_20 | YES
CL0265 | P10 | P10-WP043 | P10-A16 | 2026-12 | 99456.00 | PROCUREMENT_20_30_30_20 | YES
CL0265 | P10 | P10-WP043 | P10-A16 | 2027-01 | 24864.00 | PROCUREMENT_20_30_30_20 | YES
CL0266 | P10 | P10-WP043 | P10-A17 | 2027-01 | 74592.00 | WORKDAY_FALLBACK | YES
CL0266 | P10 | P10-WP043 | P10-A17 | 2027-02 | 18648.00 | WORKDAY_FALLBACK | YES
CL0267 | P10 | P10-WP051 | P10-A13 | 2026-12 | 41353.00 | FINAL_GATE | YES
CL0268 | P10 | P10-WP051 | P10-A18 | 2027-02 | 82706.00 | FINAL_GATE | YES
CL0269 | P10 | P10-WP051 | P10-A19 | 2027-03 | 82706.00 | FINAL_GATE | YES
CL0270 | P10 | P10-WP051 | P10-A20 | 2027-03 | 35839.18 | WORKDAY_SPREAD | YES
CL0270 | P10 | P10-WP051 | P10-A20 | 2027-04 | 5513.82 | WORKDAY_SPREAD | YES
CL0271 | P10 | P10-WP051 | P10-A21 | 2027-04 | 82706.00 | FINAL_GATE | YES
CL0272 | P10 | P10-WP051 | P10-A22 | 2027-04 | 20676.50 | WORKDAY_SPREAD | YES
CL0272 | P10 | P10-WP051 | P10-A22 | 2027-05 | 20676.50 | WORKDAY_SPREAD | YES
CL0273 | P10 | P10-WP051 | P10-A23 | 2027-05 | 82706.00 | FINAL_GATE | YES
CL0274 | P10 | P10-WP051 | P10-A24 | 2027-05 | 82706.00 | FINAL_GATE | YES
CL0275 | P10 | P10-WP051 | P10-A25 | 2027-06 | 82706.00 | FINAL_GATE | YES
CL0276 | P10 | P10-WP051 | P10-A27 | 2027-07 | 82705.00 | FINAL_GATE | YES
CL0277 | P10 | P10-WP061 | P10-A26 | 2027-07 | 77700.00 | FINAL_GATE | YES
CL0278 | P10 | P10-WP062 | P10-A28 | 2027-08 | 33300.00 | FINAL_GATE | YES
CL0279 | P11 | P11-WP011 | P11-A1 | 2025-04 | 76800.00 | WORKDAY_SPREAD | YES
CL0280 | P11 | P11-WP012 | P11-A2 | 2025-04 | 35840.00 | WORKDAY_SPREAD | YES
CL0280 | P11 | P11-WP012 | P11-A2 | 2025-05 | 15360.00 | WORKDAY_SPREAD | YES
CL0281 | P11 | P11-WP021 | P11-A3 | 2025-05 | 57600.00 | WORKDAY_SPREAD | YES
CL0282 | P11 | P11-WP022 | P11-A4 | 2025-06 | 67200.00 | WORKDAY_SPREAD | YES
CL0283 | P11 | P11-WP022 | P11-A8 | 2025-08 | 67200.00 | WORKDAY_SPREAD | YES
CL0284 | P11 | P11-WP031 | P11-A5 | 2025-06 | 33600.00 | WORKDAY_SPREAD | YES
CL0284 | P11 | P11-WP031 | P11-A5 | 2025-07 | 16800.00 | WORKDAY_SPREAD | YES
CL0285 | P11 | P11-WP031 | P11-A5b | 2025-07 | 50400.00 | WORKDAY_SPREAD | YES
CL0286 | P11 | P11-WP032 | P11-A5c | 2025-07 | 74880.00 | WORKDAY_SPREAD | YES
CL0286 | P11 | P11-WP032 | P11-A5c | 2025-08 | 18720.00 | WORKDAY_SPREAD | YES
CL0287 | P11 | P11-WP032 | P11-A6 | 2025-08 | 93600.00 | WORKDAY_SPREAD | YES
CL0288 | P11 | P11-WP041 | P11-A10 | 2025-08 | 89433.82 | WORKDAY_SPREAD | YES
CL0288 | P11 | P11-WP041 | P11-A10 | 2025-09 | 6388.18 | WORKDAY_SPREAD | YES
CL0289 | P11 | P11-WP041 | P11-A9 | 2025-08 | 191644.50 | PROCUREMENT_20_30_30_20 | YES
CL0289 | P11 | P11-WP041 | P11-A9 | 2025-09 | 191644.50 | PROCUREMENT_20_30_30_20 | YES
CL0290 | P11 | P11-WP041 | P11-AFIRST | 2025-09 | 287467.00 | WORKDAY_FALLBACK | YES
CL0291 | P11 | P11-WP041 | P11-B1inst | 2025-09 | 131755.47 | WORKDAY_FALLBACK | YES
CL0291 | P11 | P11-WP041 | P11-B1inst | 2025-10 | 275488.71 | WORKDAY_FALLBACK | YES
CL0291 | P11 | P11-WP041 | P11-B1inst | 2025-11 | 71866.82 | WORKDAY_FALLBACK | YES
CL0292 | P11 | P11-WP041 | P11-B2inst | 2025-10 | 107799.93 | WORKDAY_FALLBACK | YES
CL0292 | P11 | P11-WP041 | P11-B2inst | 2025-11 | 239555.40 | WORKDAY_FALLBACK | YES
CL0292 | P11 | P11-WP041 | P11-B2inst | 2025-12 | 131755.67 | WORKDAY_FALLBACK | YES
CL0293 | P11 | P11-WP043 | P11-B1rest | 2025-10 | 58800.00 | WORKDAY_FALLBACK | YES
CL0293 | P11 | P11-WP043 | P11-B1rest | 2025-11 | 84000.00 | WORKDAY_FALLBACK | YES
CL0293 | P11 | P11-WP043 | P11-B1rest | 2025-12 | 25200.00 | WORKDAY_FALLBACK | YES
CL0294 | P11 | P11-WP043 | P11-B2rest | 2025-11 | 37800.00 | WORKDAY_FALLBACK | YES
CL0294 | P11 | P11-WP043 | P11-B2rest | 2025-12 | 96600.00 | WORKDAY_FALLBACK | YES
CL0294 | P11 | P11-WP043 | P11-B2rest | 2026-01 | 33600.00 | WORKDAY_FALLBACK | YES
CL0295 | P11 | P11-WP051 | P11-A7 | 2025-09 | 64000.00 | FINAL_GATE | YES
CL0296 | P11 | P11-WP051 | P11-B1test | 2025-11 | 64000.00 | FINAL_GATE | YES
CL0297 | P11 | P11-WP051 | P11-B2test | 2025-12 | 64000.00 | FINAL_GATE | YES
CL0298 | P11 | P11-WP051 | P11-A11 | 2026-02 | 64000.00 | FINAL_GATE | YES
CL0299 | P11 | P11-WP061 | P11-B1gis | 2025-12 | 22400.00 | WORKDAY_SPREAD | YES
CL0300 | P11 | P11-WP061 | P11-B2gis | 2026-01 | 22400.00 | WORKDAY_SPREAD | YES
CL0301 | P11 | P11-WP061 | P11-A12 | 2026-02 | 22400.00 | FINAL_GATE | YES
CL0302 | P11 | P11-WP062 | P11-A13 | 2026-03 | 28800.00 | FINAL_GATE | YES
CL0303 | P12 | P12-WP011 | P12-Y1A1 | 2025-01 | 28560.00 | WORKDAY_SPREAD | YES
CL0304 | P12 | P12-WP011 | P12-Y1A2 | 2025-01 | 9996.00 | WORKDAY_SPREAD | YES
CL0304 | P12 | P12-WP011 | P12-Y1A2 | 2025-02 | 18564.00 | WORKDAY_SPREAD | YES
CL0305 | P12 | P12-WP011 | P12-Y2A1 | 2025-10 | 4896.00 | WORKDAY_SPREAD | YES
CL0305 | P12 | P12-WP011 | P12-Y2A1 | 2025-11 | 31824.00 | WORKDAY_SPREAD | YES
CL0306 | P12 | P12-WP011 | P12-Y2A2 | 2025-11 | 12852.00 | WORKDAY_SPREAD | YES
CL0306 | P12 | P12-WP011 | P12-Y2A2 | 2025-12 | 23868.00 | WORKDAY_SPREAD | YES
CL0307 | P12 | P12-WP011 | P12-Y3A1 | 2026-08 | 7344.00 | WORKDAY_SPREAD | YES
CL0307 | P12 | P12-WP011 | P12-Y3A1 | 2026-09 | 29376.00 | WORKDAY_SPREAD | YES
CL0308 | P12 | P12-WP011 | P12-Y3A2 | 2026-09 | 18360.00 | WORKDAY_SPREAD | YES
CL0308 | P12 | P12-WP011 | P12-Y3A2 | 2026-10 | 18360.00 | WORKDAY_SPREAD | YES
CL0309 | P12 | P12-WP021 | P12-Y1A3 | 2025-02 | 14994.00 | WORKDAY_FALLBACK | YES
CL0309 | P12 | P12-WP021 | P12-Y1A3 | 2025-03 | 27846.00 | WORKDAY_FALLBACK | YES
CL0310 | P12 | P12-WP021 | P12-Y1A4 | 2025-03 | 22848.00 | WORKDAY_FALLBACK | YES
CL0310 | P12 | P12-WP021 | P12-Y1A4 | 2025-04 | 19992.00 | WORKDAY_FALLBACK | YES
CL0311 | P12 | P12-WP021 | P12-Y2A3 | 2025-12 | 27540.00 | WORKDAY_FALLBACK | YES
CL0311 | P12 | P12-WP021 | P12-Y2A3 | 2026-01 | 27540.00 | WORKDAY_FALLBACK | YES
CL0312 | P12 | P12-WP021 | P12-Y2A4 | 2026-01 | 44064.00 | WORKDAY_FALLBACK | YES
CL0312 | P12 | P12-WP021 | P12-Y2A4 | 2026-02 | 11016.00 | WORKDAY_FALLBACK | YES
CL0313 | P12 | P12-WP021 | P12-Y3A3 | 2026-10 | 33048.00 | WORKDAY_FALLBACK | YES
CL0313 | P12 | P12-WP021 | P12-Y3A3 | 2026-11 | 22032.00 | WORKDAY_FALLBACK | YES
CL0314 | P12 | P12-WP021 | P12-Y3A4 | 2026-11 | 47736.00 | WORKDAY_FALLBACK | YES
CL0314 | P12 | P12-WP021 | P12-Y3A4 | 2026-12 | 7344.00 | WORKDAY_FALLBACK | YES
CL0315 | P12 | P12-WP031 | P12-Y1A5 | 2025-04 | 57120.00 | PROCUREMENT_20_30_30_20 | YES
CL0315 | P12 | P12-WP031 | P12-Y1A5 | 2025-05 | 57120.00 | PROCUREMENT_20_30_30_20 | YES
CL0316 | P12 | P12-WP031 | P12-Y2A5 | 2026-02 | 73440.00 | PROCUREMENT_20_30_30_20 | YES
CL0316 | P12 | P12-WP031 | P12-Y2A5 | 2026-03 | 73440.00 | PROCUREMENT_20_30_30_20 | YES
CL0317 | P12 | P12-WP031 | P12-Y3A5 | 2026-12 | 117504.00 | PROCUREMENT_20_30_30_20 | YES
CL0317 | P12 | P12-WP031 | P12-Y3A5 | 2027-01 | 29376.00 | PROCUREMENT_20_30_30_20 | YES
CL0318 | P12 | P12-WP041 | P12-Y1A6 | 2025-05 | 125892.48 | WORKDAY_FALLBACK | YES
CL0318 | P12 | P12-WP041 | P12-Y1A6 | 2025-06 | 220311.84 | WORKDAY_FALLBACK | YES
CL0318 | P12 | P12-WP041 | P12-Y1A6 | 2025-07 | 241293.92 | WORKDAY_FALLBACK | YES
CL0318 | P12 | P12-WP041 | P12-Y1A6 | 2025-08 | 220311.84 | WORKDAY_FALLBACK | YES
CL0318 | P12 | P12-WP041 | P12-Y1A6 | 2025-09 | 136383.92 | WORKDAY_FALLBACK | YES
CL0319 | P12 | P12-WP041 | P12-Y2A6 | 2026-03 | 188838.58 | WORKDAY_FALLBACK | YES
CL0319 | P12 | P12-WP041 | P12-Y2A6 | 2026-04 | 296746.34 | WORKDAY_FALLBACK | YES
CL0319 | P12 | P12-WP041 | P12-Y2A6 | 2026-05 | 283257.87 | WORKDAY_FALLBACK | YES
CL0319 | P12 | P12-WP041 | P12-Y2A6 | 2026-06 | 296746.34 | WORKDAY_FALLBACK | YES
CL0319 | P12 | P12-WP041 | P12-Y2A6 | 2026-07 | 148373.87 | WORKDAY_FALLBACK | YES
CL0320 | P12 | P12-WP041 | P12-Y3A6 | 2027-01 | 229303.99 | WORKDAY_FALLBACK | YES
CL0320 | P12 | P12-WP041 | P12-Y3A6 | 2027-02 | 269769.40 | WORKDAY_FALLBACK | YES
CL0320 | P12 | P12-WP041 | P12-Y3A6 | 2027-03 | 310234.81 | WORKDAY_FALLBACK | YES
CL0320 | P12 | P12-WP041 | P12-Y3A6 | 2027-04 | 296746.34 | WORKDAY_FALLBACK | YES
CL0320 | P12 | P12-WP041 | P12-Y3A6 | 2027-05 | 107908.46 | WORKDAY_FALLBACK | YES
CL0321 | P12 | P12-WP051 | P12-Y1A7 | 2025-10 | 57120.00 | FINAL_GATE | YES
CL0322 | P12 | P12-WP051 | P12-Y2A7 | 2026-08 | 73440.00 | FINAL_GATE | YES
CL0323 | P12 | P12-WP051 | P12-Y3A7 | 2027-06 | 73440.00 | FINAL_GATE | YES
CL0324 | P12 | P12-WP061 | P12-Y1A8 | 2025-10 | 28560.00 | FINAL_GATE | YES
CL0325 | P12 | P12-WP061 | P12-Y2A8 | 2026-08 | 36720.00 | FINAL_GATE | YES
CL0326 | P12 | P12-WP061 | P12-Y3A8 | 2027-06 | 36720.00 | FINAL_GATE | YES
CL0327 | P03 | P03-WP052 | P03-A28 | 2026-11 | 487200.00 | FINAL_GATE | YES
CL0328 | P03 | P03-WP053 | P03-A29 | 2026-09 | 121800.00 | FINAL_GATE | YES
CL0329 | P03 | P03-WP053 | P03-A30 | 2026-12 | 121800.00 | FINAL_GATE | YES
CL0330 | P05 | P05-WP043 | P05-A12c | 2025-12 | 105450.00 | FINAL_GATE | YES
CL0331 | P05 | P05-WP043 | P05-A13c | 2026-01 | 105450.00 | FINAL_GATE | YES
CL0332 | P05 | P05-WP043 | P05-A14c | 2026-02 | 105450.00 | FINAL_GATE | YES
CL0333 | P05 | P05-WP043 | P05-A15c | 2026-03 | 105450.00 | FINAL_GATE | YES
CL0334 | P10 | P10-WP012 | P10-A2 | 2026-05 | 81400.00 | FINAL_GATE | YES
CL0335 | P11 | P11-WP042 | P11-B1gis | 2025-12 | 89600.00 | FINAL_GATE | YES
CL0336 | P11 | P11-WP042 | P11-B2gis | 2026-01 | 89600.00 | FINAL_GATE | YES
CL0337 | P12 | P12-WP042 | P12-Y1A6 | 2025-05 | 18811.44 | WORKDAY_FALLBACK | YES
CL0337 | P12 | P12-WP042 | P12-Y1A6 | 2025-06 | 32920.02 | WORKDAY_FALLBACK | YES
CL0337 | P12 | P12-WP042 | P12-Y1A6 | 2025-07 | 36055.26 | WORKDAY_FALLBACK | YES
CL0337 | P12 | P12-WP042 | P12-Y1A6 | 2025-08 | 32920.02 | WORKDAY_FALLBACK | YES
CL0337 | P12 | P12-WP042 | P12-Y1A6 | 2025-09 | 20379.26 | WORKDAY_FALLBACK | YES
CL0338 | P12 | P12-WP042 | P12-Y2A6 | 2026-03 | 28217.28 | WORKDAY_FALLBACK | YES
CL0338 | P12 | P12-WP042 | P12-Y2A6 | 2026-04 | 44341.44 | WORKDAY_FALLBACK | YES
CL0338 | P12 | P12-WP042 | P12-Y2A6 | 2026-05 | 42325.92 | WORKDAY_FALLBACK | YES
CL0338 | P12 | P12-WP042 | P12-Y2A6 | 2026-06 | 44341.44 | WORKDAY_FALLBACK | YES
CL0338 | P12 | P12-WP042 | P12-Y2A6 | 2026-07 | 22170.92 | WORKDAY_FALLBACK | YES
CL0339 | P12 | P12-WP042 | P12-Y3A6 | 2027-01 | 34263.84 | WORKDAY_FALLBACK | YES
CL0339 | P12 | P12-WP042 | P12-Y3A6 | 2027-02 | 40310.40 | WORKDAY_FALLBACK | YES
CL0339 | P12 | P12-WP042 | P12-Y3A6 | 2027-03 | 46356.96 | WORKDAY_FALLBACK | YES
CL0339 | P12 | P12-WP042 | P12-Y3A6 | 2027-04 | 44341.44 | WORKDAY_FALLBACK | YES
CL0339 | P12 | P12-WP042 | P12-Y3A6 | 2027-05 | 16124.36 | WORKDAY_FALLBACK | YES
CL0340 | P04 | P04-WP051 | P04-A14 | 2026-03 | 132000.00 | FINAL_GATE | YES
CL0341 | P04 | P04-WP051 | P04-A15 | 2026-03 | 198000.00 | FINAL_GATE | YES
CL0342 | P08 | P08-WP043 | P08-A15 | 2026-10 | 179400.00 | FINAL_GATE | YES

## COST_PROJECT_MONTH
Reporting_Month | Project_ID | Monthly_PV_USD | Cumulative_PV_USD | Planned_Cash_USD | Actual_Cost_USD | Earned_Value_USD
2025-01 | P01 | 285455.00 | 285455.00
2025-01 | P02 | 0.00 | 0.00
2025-01 | P03 | 508515.00 | 508515.00
2025-01 | P04 | 0.00 | 0.00
2025-01 | P05 | 0.00 | 0.00
2025-01 | P06 | 0.00 | 0.00
2025-01 | P07 | 0.00 | 0.00
2025-01 | P08 | 0.00 | 0.00
2025-01 | P09 | 0.00 | 0.00
2025-01 | P10 | 0.00 | 0.00
2025-01 | P11 | 0.00 | 0.00
2025-01 | P12 | 38556.00 | 38556.00
2025-02 | P01 | 341621.00 | 627076.00
2025-02 | P02 | 745140.00 | 745140.00
2025-02 | P03 | 289681.00 | 798196.00
2025-02 | P04 | 0.00 | 0.00
2025-02 | P05 | 0.00 | 0.00
2025-02 | P06 | 0.00 | 0.00
2025-02 | P07 | 0.00 | 0.00
2025-02 | P08 | 0.00 | 0.00
2025-02 | P09 | 0.00 | 0.00
2025-02 | P10 | 0.00 | 0.00
2025-02 | P11 | 0.00 | 0.00
2025-02 | P12 | 33558.00 | 72114.00
2025-03 | P01 | 170323.38 | 797399.38
2025-03 | P02 | 269676.00 | 1014816.00
2025-03 | P03 | 153468.00 | 951664.00
2025-03 | P04 | 0.00 | 0.00
2025-03 | P05 | 189440.00 | 189440.00
2025-03 | P06 | 0.00 | 0.00
2025-03 | P07 | 0.00 | 0.00
2025-03 | P08 | 0.00 | 0.00
2025-03 | P09 | 0.00 | 0.00
2025-03 | P10 | 0.00 | 0.00
2025-03 | P11 | 0.00 | 0.00
2025-03 | P12 | 50694.00 | 122808.00
2025-04 | P01 | 232063.62 | 1029463.00
2025-04 | P02 | 327660.58 | 1342476.58
2025-04 | P03 | 282576.00 | 1234240.00
2025-04 | P04 | 0.00 | 0.00
2025-04 | P05 | 261960.00 | 451400.00
2025-04 | P06 | 0.00 | 0.00
2025-04 | P07 | 0.00 | 0.00
2025-04 | P08 | 0.00 | 0.00
2025-04 | P09 | 0.00 | 0.00
2025-04 | P10 | 0.00 | 0.00
2025-04 | P11 | 112640.00 | 112640.00
2025-04 | P12 | 77112.00 | 199920.00
2025-05 | P01 | 363093.56 | 1392556.56
2025-05 | P02 | 340963.42 | 1683440.00
2025-05 | P03 | 332108.00 | 1566348.00
2025-05 | P04 | 0.00 | 0.00
2025-05 | P05 | 284900.00 | 736300.00
2025-05 | P06 | 0.00 | 0.00
2025-05 | P07 | 0.00 | 0.00
2025-05 | P08 | 0.00 | 0.00
2025-05 | P09 | 0.00 | 0.00
2025-05 | P10 | 0.00 | 0.00
2025-05 | P11 | 72960.00 | 185600.00
2025-05 | P12 | 201823.92 | 401743.92
2025-06 | P01 | 730133.44 | 2122690.00
2025-06 | P02 | 1014992.00 | 2698432.00
2025-06 | P03 | 273779.28 | 1840127.28
2025-06 | P04 | 205425.00 | 205425.00
2025-06 | P05 | 302290.00 | 1038590.00
2025-06 | P06 | 0.00 | 0.00
2025-06 | P07 | 0.00 | 0.00
2025-06 | P08 | 0.00 | 0.00
2025-06 | P09 | 0.00 | 0.00
2025-06 | P10 | 0.00 | 0.00
2025-06 | P11 | 100800.00 | 286400.00
2025-06 | P12 | 253231.86 | 654975.78
2025-07 | P01 | 1939392.00 | 4062082.00
2025-07 | P02 | 792000.00 | 3490432.00
2025-07 | P03 | 408300.70 | 2248427.98
2025-07 | P04 | 94325.00 | 299750.00
2025-07 | P05 | 431280.10 | 1469870.10
2025-07 | P06 | 0.00 | 0.00
2025-07 | P07 | 0.00 | 0.00
2025-07 | P08 | 0.00 | 0.00
2025-07 | P09 | 0.00 | 0.00
2025-07 | P10 | 0.00 | 0.00
2025-07 | P11 | 142080.00 | 428480.00
2025-07 | P12 | 277349.18 | 932324.96
2025-08 | P01 | 575424.00 | 4637506.00
2025-08 | P02 | 842688.00 | 4333120.00
2025-08 | P03 | 456614.59 | 2705042.57
2025-08 | P04 | 94967.00 | 394717.00
2025-08 | P05 | 1395923.65 | 2865793.75
2025-08 | P06 | 150420.00 | 150420.00
2025-08 | P07 | 0.00 | 0.00
2025-08 | P08 | 0.00 | 0.00
2025-08 | P09 | 0.00 | 0.00
2025-08 | P10 | 0.00 | 0.00
2025-08 | P11 | 460598.32 | 889078.32
2025-08 | P12 | 253231.86 | 1185556.82
2025-09 | P01 | 575424.00 | 5212930.00
2025-09 | P02 | 266112.00 | 4599232.00
2025-09 | P03 | 856826.48 | 3561869.05
2025-09 | P04 | 252495.50 | 647212.50
2025-09 | P05 | 939560.81 | 3805354.56
2025-09 | P06 | 288765.00 | 439185.00
2025-09 | P07 | 0.00 | 0.00
2025-09 | P08 | 0.00 | 0.00
2025-09 | P09 | 0.00 | 0.00
2025-09 | P10 | 0.00 | 0.00
2025-09 | P11 | 681255.15 | 1570333.47
2025-09 | P12 | 156763.18 | 1342320.00
2025-10 | P01 | 1069966.00 | 6282896.00
2025-10 | P02 | 779328.00 | 5378560.00
2025-10 | P03 | 1086055.35 | 4647924.40
2025-10 | P04 | 182630.65 | 829843.15
2025-10 | P05 | 1487064.44 | 5292419.00
2025-10 | P06 | 161115.40 | 600300.40
2025-10 | P07 | 110700.00 | 110700.00
2025-10 | P08 | 0.00 | 0.00
2025-10 | P09 | 0.00 | 0.00
2025-10 | P10 | 0.00 | 0.00
2025-10 | P11 | 442088.64 | 2012422.11
2025-10 | P12 | 90576.00 | 1432896.00
2025-11 | P01 | 895104.00 | 7178000.00
2025-11 | P02 | 1985702.40 | 7364262.40
2025-11 | P03 | 816657.10 | 5464581.50
2025-11 | P04 | 557746.50 | 1387589.65
2025-11 | P05 | 1582531.00 | 6874950.00
2025-11 | P06 | 300495.60 | 900796.00
2025-11 | P07 | 128535.00 | 239235.00
2025-11 | P08 | 0.00 | 0.00
2025-11 | P09 | 0.00 | 0.00
2025-11 | P10 | 0.00 | 0.00
2025-11 | P11 | 497222.22 | 2509644.33
2025-11 | P12 | 44676.00 | 1477572.00
2025-12 | P01 | 222000.00 | 7400000.00
2025-12 | P02 | 263577.60 | 7627840.00
2025-12 | P03 | 1871540.00 | 7336121.50
2025-12 | P04 | 1036041.34 | 2423630.99
2025-12 | P05 | 1780659.68 | 8655609.68
2025-12 | P06 | 837717.34 | 1738513.34
2025-12 | P07 | 127988.58 | 367223.58
2025-12 | P08 | 122820.00 | 122820.00
2025-12 | P09 | 0.00 | 0.00
2025-12 | P10 | 0.00 | 0.00
2025-12 | P11 | 429555.67 | 2939200.00
2025-12 | P12 | 51408.00 | 1528980.00
2026-01 | P01 | 0.00 | 7400000.00
2026-01 | P02 | 528000.00 | 8155840.00
2026-01 | P03 | 426300.00 | 7762421.50
2026-01 | P04 | 846899.01 | 3270530.00
2026-01 | P05 | 1038292.52 | 9693902.20
2026-01 | P06 | 499657.82 | 2238171.16
2026-01 | P07 | 260418.42 | 627642.00
2026-01 | P08 | 212173.30 | 334993.30
2026-01 | P09 | 0.00 | 0.00
2026-01 | P10 | 0.00 | 0.00
2026-01 | P11 | 145600.00 | 3084800.00
2026-01 | P12 | 71604.00 | 1600584.00
2026-02 | P01 | 0.00 | 7400000.00
2026-02 | P02 | 644160.00 | 8800000.00
2026-02 | P03 | 2297840.50 | 10060262.00
2026-02 | P04 | 866571.00 | 4137101.00
2026-02 | P05 | 347732.80 | 10041635.00
2026-02 | P06 | 470976.94 | 2709148.10
2026-02 | P07 | 276640.60 | 904282.60
2026-02 | P08 | 143423.35 | 478416.65
2026-02 | P09 | 175500.00 | 175500.00
2026-02 | P10 | 0.00 | 0.00
2026-02 | P11 | 86400.00 | 3171200.00
2026-02 | P12 | 84456.00 | 1685040.00
2026-03 | P01 | 0.00 | 7400000.00
2026-03 | P02 | 0.00 | 8800000.00
2026-03 | P03 | 1414313.00 | 11474575.00
2026-03 | P04 | 1197899.00 | 5335000.00
2026-03 | P05 | 244200.00 | 10285835.00
2026-03 | P06 | 346948.90 | 3056097.00
2026-03 | P07 | 906605.40 | 1810888.00
2026-03 | P08 | 285169.35 | 763586.00
2026-03 | P09 | 164580.00 | 340080.00
2026-03 | P10 | 0.00 | 0.00
2026-03 | P11 | 28800.00 | 3200000.00
2026-03 | P12 | 290495.86 | 1975535.86
2026-04 | P01 | 0.00 | 7400000.00
2026-04 | P02 | 0.00 | 8800000.00
2026-04 | P03 | 1970452.96 | 13445027.96
2026-04 | P04 | 165000.00 | 5500000.00
2026-04 | P05 | 481165.00 | 10767000.00
2026-04 | P06 | 867301.30 | 3923398.30
2026-04 | P07 | 144976.00 | 1955864.00
2026-04 | P08 | 305184.92 | 1068770.92
2026-04 | P09 | 137280.00 | 477360.00
2026-04 | P10 | 66600.00 | 66600.00
2026-04 | P11 | 0.00 | 3200000.00
2026-04 | P12 | 341087.78 | 2316623.64
2026-05 | P01 | 0.00 | 7400000.00
2026-05 | P02 | 0.00 | 8800000.00
2026-05 | P03 | 1292580.37 | 14737608.33
2026-05 | P04 | 0.00 | 5500000.00
2026-05 | P05 | 333000.00 | 11100000.00
2026-05 | P06 | 353390.01 | 4276788.31
2026-05 | P07 | 708152.00 | 2664016.00
2026-05 | P08 | 296098.08 | 1364869.00
2026-05 | P09 | 86666.65 | 564026.65
2026-05 | P10 | 221260.00 | 287860.00
2026-05 | P11 | 0.00 | 3200000.00
2026-05 | P12 | 325583.79 | 2642207.43
2026-06 | P01 | 0.00 | 7400000.00
2026-06 | P02 | 0.00 | 8800000.00
2026-06 | P03 | 1650421.58 | 16388029.91
2026-06 | P04 | 0.00 | 5500000.00
2026-06 | P05 | 0.00 | 11100000.00
2026-06 | P06 | 292239.30 | 4569027.61
2026-06 | P07 | 325157.00 | 2989173.00
2026-06 | P08 | 226348.60 | 1591217.60
2026-06 | P09 | 199749.31 | 763775.96
2026-06 | P10 | 451215.00 | 739075.00
2026-06 | P11 | 0.00 | 3200000.00
2026-06 | P12 | 341087.78 | 2983295.21
2026-07 | P01 | 0.00 | 7400000.00
2026-07 | P02 | 0.00 | 8800000.00
2026-07 | P03 | 480284.59 | 16868314.50
2026-07 | P04 | 0.00 | 5500000.00
2026-07 | P05 | 0.00 | 11100000.00
2026-07 | P06 | 628678.27 | 5197705.88
2026-07 | P07 | 95667.00 | 3084840.00
2026-07 | P08 | 209457.60 | 1800675.20
2026-07 | P09 | 292864.04 | 1056640.00
2026-07 | P10 | 268484.90 | 1007559.90
2026-07 | P11 | 0.00 | 3200000.00
2026-07 | P12 | 170544.79 | 3153840.00
2026-08 | P01 | 0.00 | 7400000.00
2026-08 | P02 | 0.00 | 8800000.00
2026-08 | P03 | 499888.50 | 17368203.00
2026-08 | P04 | 0.00 | 5500000.00
2026-08 | P05 | 0.00 | 11100000.00
2026-08 | P06 | 575173.94 | 5772879.82
2026-08 | P07 | 972110.00 | 4056950.00
2026-08 | P08 | 633905.70 | 2434580.90
2026-08 | P09 | 1098746.30 | 2155386.30
2026-08 | P10 | 470099.50 | 1477659.40
2026-08 | P11 | 0.00 | 3200000.00
2026-08 | P12 | 117504.00 | 3271344.00
2026-09 | P01 | 0.00 | 7400000.00
2026-09 | P02 | 0.00 | 8800000.00
2026-09 | P03 | 991118.00 | 18359321.00
2026-09 | P04 | 0.00 | 5500000.00
2026-09 | P05 | 0.00 | 11100000.00
2026-09 | P06 | 334258.18 | 6107138.00
2026-09 | P07 | 43050.00 | 4100000.00
2026-09 | P08 | 840740.50 | 3275321.40
2026-09 | P09 | 1043774.55 | 3199160.85
2026-09 | P10 | 909506.60 | 2387166.00
2026-09 | P11 | 0.00 | 3200000.00
2026-09 | P12 | 47736.00 | 3319080.00
2026-10 | P01 | 0.00 | 7400000.00
2026-10 | P02 | 0.00 | 8800000.00
2026-10 | P03 | 446599.00 | 18805920.00
2026-10 | P04 | 0.00 | 5500000.00
2026-10 | P05 | 0.00 | 11100000.00
2026-10 | P06 | 332862.00 | 6440000.00
2026-10 | P07 | 0.00 | 4100000.00
2026-10 | P08 | 568099.60 | 3843421.00
2026-10 | P09 | 1165721.15 | 4364882.00
2026-10 | P10 | 156954.00 | 2544120.00
2026-10 | P11 | 0.00 | 3200000.00
2026-10 | P12 | 51408.00 | 3370488.00
2026-11 | P01 | 0.00 | 7400000.00
2026-11 | P02 | 0.00 | 8800000.00
2026-11 | P03 | 487200.00 | 19293120.00
2026-11 | P04 | 0.00 | 5500000.00
2026-11 | P05 | 0.00 | 11100000.00
2026-11 | P06 | 253000.00 | 6693000.00
2026-11 | P07 | 0.00 | 4100000.00
2026-11 | P08 | 414000.00 | 4257421.00
2026-11 | P09 | 1097525.80 | 5462407.80
2026-11 | P10 | 99456.00 | 2643576.00
2026-11 | P11 | 0.00 | 3200000.00
2026-11 | P12 | 69768.00 | 3440256.00
2026-12 | P01 | 0.00 | 7400000.00
2026-12 | P02 | 0.00 | 8800000.00
2026-12 | P03 | 824180.00 | 20117300.00
2026-12 | P04 | 0.00 | 5500000.00
2026-12 | P05 | 0.00 | 11100000.00
2026-12 | P06 | 207000.00 | 6900000.00
2026-12 | P07 | 0.00 | 4100000.00
2026-12 | P08 | 294279.00 | 4551700.00
2026-12 | P09 | 1074527.20 | 6536935.00
2026-12 | P10 | 165673.00 | 2809249.00
2026-12 | P11 | 0.00 | 3200000.00
2026-12 | P12 | 124848.00 | 3565104.00
2027-01 | P01 | 0.00 | 7400000.00
2027-01 | P02 | 0.00 | 8800000.00
2027-01 | P03 | 182700.00 | 20300000.00
2027-01 | P04 | 0.00 | 5500000.00
2027-01 | P05 | 0.00 | 11100000.00
2027-01 | P06 | 0.00 | 6900000.00
2027-01 | P07 | 0.00 | 4100000.00
2027-01 | P08 | 48300.00 | 4600000.00
2027-01 | P09 | 419328.00 | 6956263.00
2027-01 | P10 | 99456.00 | 2908705.00
2027-01 | P11 | 0.00 | 3200000.00
2027-01 | P12 | 292943.83 | 3858047.83
2027-02 | P01 | 0.00 | 7400000.00
2027-02 | P02 | 0.00 | 8800000.00
2027-02 | P03 | 0.00 | 20300000.00
2027-02 | P04 | 0.00 | 5500000.00
2027-02 | P05 | 0.00 | 11100000.00
2027-02 | P06 | 0.00 | 6900000.00
2027-02 | P07 | 0.00 | 4100000.00
2027-02 | P08 | 0.00 | 4600000.00
2027-02 | P09 | 761837.00 | 7718100.00
2027-02 | P10 | 101354.00 | 3010059.00
2027-02 | P11 | 0.00 | 3200000.00
2027-02 | P12 | 310079.80 | 4168127.63
2027-03 | P01 | 0.00 | 7400000.00
2027-03 | P02 | 0.00 | 8800000.00
2027-03 | P03 | 0.00 | 20300000.00
2027-03 | P04 | 0.00 | 5500000.00
2027-03 | P05 | 0.00 | 11100000.00
2027-03 | P06 | 0.00 | 6900000.00
2027-03 | P07 | 0.00 | 4100000.00
2027-03 | P08 | 0.00 | 4600000.00
2027-03 | P09 | 81900.00 | 7800000.00
2027-03 | P10 | 118545.18 | 3128604.18
2027-03 | P11 | 0.00 | 3200000.00
2027-03 | P12 | 356591.77 | 4524719.40
2027-04 | P01 | 0.00 | 7400000.00
2027-04 | P02 | 0.00 | 8800000.00
2027-04 | P03 | 0.00 | 20300000.00
2027-04 | P04 | 0.00 | 5500000.00
2027-04 | P05 | 0.00 | 11100000.00
2027-04 | P06 | 0.00 | 6900000.00
2027-04 | P07 | 0.00 | 4100000.00
2027-04 | P08 | 0.00 | 4600000.00
2027-04 | P09 | 0.00 | 7800000.00
2027-04 | P10 | 108896.32 | 3237500.50
2027-04 | P11 | 0.00 | 3200000.00
2027-04 | P12 | 341087.78 | 4865807.18
2027-05 | P01 | 0.00 | 7400000.00
2027-05 | P02 | 0.00 | 8800000.00
2027-05 | P03 | 0.00 | 20300000.00
2027-05 | P04 | 0.00 | 5500000.00
2027-05 | P05 | 0.00 | 11100000.00
2027-05 | P06 | 0.00 | 6900000.00
2027-05 | P07 | 0.00 | 4100000.00
2027-05 | P08 | 0.00 | 4600000.00
2027-05 | P09 | 0.00 | 7800000.00
2027-05 | P10 | 186088.50 | 3423589.00
2027-05 | P11 | 0.00 | 3200000.00
2027-05 | P12 | 124032.82 | 4989840.00
2027-06 | P01 | 0.00 | 7400000.00
2027-06 | P02 | 0.00 | 8800000.00
2027-06 | P03 | 0.00 | 20300000.00
2027-06 | P04 | 0.00 | 5500000.00
2027-06 | P05 | 0.00 | 11100000.00
2027-06 | P06 | 0.00 | 6900000.00
2027-06 | P07 | 0.00 | 4100000.00
2027-06 | P08 | 0.00 | 4600000.00
2027-06 | P09 | 0.00 | 7800000.00
2027-06 | P10 | 82706.00 | 3506295.00
2027-06 | P11 | 0.00 | 3200000.00
2027-06 | P12 | 110160.00 | 5100000.00
2027-07 | P01 | 0.00 | 7400000.00
2027-07 | P02 | 0.00 | 8800000.00
2027-07 | P03 | 0.00 | 20300000.00
2027-07 | P04 | 0.00 | 5500000.00
2027-07 | P05 | 0.00 | 11100000.00
2027-07 | P06 | 0.00 | 6900000.00
2027-07 | P07 | 0.00 | 4100000.00
2027-07 | P08 | 0.00 | 4600000.00
2027-07 | P09 | 0.00 | 7800000.00
2027-07 | P10 | 160405.00 | 3666700.00
2027-07 | P11 | 0.00 | 3200000.00
2027-07 | P12 | 0.00 | 5100000.00
2027-08 | P01 | 0.00 | 7400000.00
2027-08 | P02 | 0.00 | 8800000.00
2027-08 | P03 | 0.00 | 20300000.00
2027-08 | P04 | 0.00 | 5500000.00
2027-08 | P05 | 0.00 | 11100000.00
2027-08 | P06 | 0.00 | 6900000.00
2027-08 | P07 | 0.00 | 4100000.00
2027-08 | P08 | 0.00 | 4600000.00
2027-08 | P09 | 0.00 | 7800000.00
2027-08 | P10 | 33300.00 | 3700000.00
2027-08 | P11 | 0.00 | 3200000.00
2027-08 | P12 | 0.00 | 5100000.00
2027-09 | P01 | 0.00 | 7400000.00
2027-09 | P02 | 0.00 | 8800000.00
2027-09 | P03 | 0.00 | 20300000.00
2027-09 | P04 | 0.00 | 5500000.00
2027-09 | P05 | 0.00 | 11100000.00
2027-09 | P06 | 0.00 | 6900000.00
2027-09 | P07 | 0.00 | 4100000.00
2027-09 | P08 | 0.00 | 4600000.00
2027-09 | P09 | 0.00 | 7800000.00
2027-09 | P10 | 0.00 | 3700000.00
2027-09 | P11 | 0.00 | 3200000.00
2027-09 | P12 | 0.00 | 5100000.00
2027-10 | P01 | 0.00 | 7400000.00
2027-10 | P02 | 0.00 | 8800000.00
2027-10 | P03 | 0.00 | 20300000.00
2027-10 | P04 | 0.00 | 5500000.00
2027-10 | P05 | 0.00 | 11100000.00
2027-10 | P06 | 0.00 | 6900000.00
2027-10 | P07 | 0.00 | 4100000.00
2027-10 | P08 | 0.00 | 4600000.00
2027-10 | P09 | 0.00 | 7800000.00
2027-10 | P10 | 0.00 | 3700000.00
2027-10 | P11 | 0.00 | 3200000.00
2027-10 | P12 | 0.00 | 5100000.00
2027-11 | P01 | 0.00 | 7400000.00
2027-11 | P02 | 0.00 | 8800000.00
2027-11 | P03 | 0.00 | 20300000.00
2027-11 | P04 | 0.00 | 5500000.00
2027-11 | P05 | 0.00 | 11100000.00
2027-11 | P06 | 0.00 | 6900000.00
2027-11 | P07 | 0.00 | 4100000.00
2027-11 | P08 | 0.00 | 4600000.00
2027-11 | P09 | 0.00 | 7800000.00
2027-11 | P10 | 0.00 | 3700000.00
2027-11 | P11 | 0.00 | 3200000.00
2027-11 | P12 | 0.00 | 5100000.00
2027-12 | P01 | 0.00 | 7400000.00
2027-12 | P02 | 0.00 | 8800000.00
2027-12 | P03 | 0.00 | 20300000.00
2027-12 | P04 | 0.00 | 5500000.00
2027-12 | P05 | 0.00 | 11100000.00
2027-12 | P06 | 0.00 | 6900000.00
2027-12 | P07 | 0.00 | 4100000.00
2027-12 | P08 | 0.00 | 4600000.00
2027-12 | P09 | 0.00 | 7800000.00
2027-12 | P10 | 0.00 | 3700000.00
2027-12 | P11 | 0.00 | 3200000.00
2027-12 | P12 | 0.00 | 5100000.00

## COST_PROGRAM_MONTH
Reporting_Month | Program_Monthly_PV_USD | Program_Cumulative_PV_USD | Project_BAC_USD | Program_Contingency_USD | Authorized_Budget_USD
2025-01 | 832526.00 | 832526.00 | 88500000.00 | 7500000.00 | 96000000.00
2025-02 | 1410000.00 | 2242526.00 | 88500000.00 | 7500000.00 | 96000000.00
2025-03 | 833601.38 | 3076127.38 | 88500000.00 | 7500000.00 | 96000000.00
2025-04 | 1294012.20 | 4370139.58 | 88500000.00 | 7500000.00 | 96000000.00
2025-05 | 1595848.90 | 5965988.48 | 88500000.00 | 7500000.00 | 96000000.00
2025-06 | 2880651.58 | 8846640.06 | 88500000.00 | 7500000.00 | 96000000.00
2025-07 | 4084726.98 | 12931367.04 | 88500000.00 | 7500000.00 | 96000000.00
2025-08 | 4229867.42 | 17161234.46 | 88500000.00 | 7500000.00 | 96000000.00
2025-09 | 4017202.12 | 21178436.58 | 88500000.00 | 7500000.00 | 96000000.00
2025-10 | 5409524.48 | 26587961.06 | 88500000.00 | 7500000.00 | 96000000.00
2025-11 | 6808669.82 | 33396630.88 | 88500000.00 | 7500000.00 | 96000000.00
2025-12 | 6743308.21 | 40139939.09 | 88500000.00 | 7500000.00 | 96000000.00
2026-01 | 4028945.07 | 44168884.16 | 88500000.00 | 7500000.00 | 96000000.00
2026-02 | 5393701.19 | 49562585.35 | 88500000.00 | 7500000.00 | 96000000.00
2026-03 | 4879011.51 | 54441596.86 | 88500000.00 | 7500000.00 | 96000000.00
2026-04 | 4479047.96 | 58920644.82 | 88500000.00 | 7500000.00 | 96000000.00
2026-05 | 3616730.90 | 62537375.72 | 88500000.00 | 7500000.00 | 96000000.00
2026-06 | 3486218.57 | 66023594.29 | 88500000.00 | 7500000.00 | 96000000.00
2026-07 | 2145981.19 | 68169575.48 | 88500000.00 | 7500000.00 | 96000000.00
2026-08 | 4367427.94 | 72537003.42 | 88500000.00 | 7500000.00 | 96000000.00
2026-09 | 4210183.83 | 76747187.25 | 88500000.00 | 7500000.00 | 96000000.00
2026-10 | 2721643.75 | 79468831.00 | 88500000.00 | 7500000.00 | 96000000.00
2026-11 | 2420949.80 | 81889780.80 | 88500000.00 | 7500000.00 | 96000000.00
2026-12 | 2690507.20 | 84580288.00 | 88500000.00 | 7500000.00 | 96000000.00
2027-01 | 1042727.83 | 85623015.83 | 88500000.00 | 7500000.00 | 96000000.00
2027-02 | 1173270.80 | 86796286.63 | 88500000.00 | 7500000.00 | 96000000.00
2027-03 | 557036.95 | 87353323.58 | 88500000.00 | 7500000.00 | 96000000.00
2027-04 | 449984.10 | 87803307.68 | 88500000.00 | 7500000.00 | 96000000.00
2027-05 | 310121.32 | 88113429.00 | 88500000.00 | 7500000.00 | 96000000.00
2027-06 | 192866.00 | 88306295.00 | 88500000.00 | 7500000.00 | 96000000.00
2027-07 | 160405.00 | 88466700.00 | 88500000.00 | 7500000.00 | 96000000.00
2027-08 | 33300.00 | 88500000.00 | 88500000.00 | 7500000.00 | 96000000.00
2027-09 | 0.00 | 88500000.00 | 88500000.00 | 7500000.00 | 96000000.00
2027-10 | 0.00 | 88500000.00 | 88500000.00 | 7500000.00 | 96000000.00
2027-11 | 0.00 | 88500000.00 | 88500000.00 | 7500000.00 | 96000000.00
2027-12 | 0.00 | 88500000.00 | 88500000.00 | 7500000.00 | 96000000.00

## COST_ASSUMPTIONS
Category | Definition / Provenance
Approval | User approved Phase 3D cost ownership and Phase 3F recognition proxies for synthetic portfolio.
Project BAC | $88,500,000 across 12 projects; separate $7,500,000 contingency, authorized $96,000,000.
WBS | 72 control accounts and 141 work packages, 342 ownership lines across 328 tasks; zero additional milestone BAC.
Calendar | Inclusive scheduled Mon–Fri working days with no holiday exclusions.
Workday spread | Integer cents allocated evenly by eligible scheduled working date; last eligible date receives residual.
Procurement | 20/30/30/20 scheduled at synthetic within-activity workday percentile dates 20/50/80/100; date proxies do not assert vendor events.
Final gate | 100% planned at scheduled component activity finish; future EV requires distinct separately documented acceptance.
Quantity fallback | Workday spread used when independent planned quantity profile unavailable; synthetic baseline assumption.
P04 | WP051: $132,000 A14 functional readiness; $198,000 A15 acceptance; separate component recognition.
P08 | WP043 $179,400 A15 vendor-integrated fuel installation; synthetic vendor-scope assumption.
P12 | Annual 28%/36%/36% allocations; emergency-work portions explicitly within three annual execution tasks.
P08 outage | Approved schedule includes independent constrained outage event; not a procurement PV event.
Cash | Planned cash not generated: separate future model with payment terms.
EV/AC | No actual progress, invoices, commitments, EV or AC generated. Prior existing EVM sheet remains blank.
Version | Phase 3G synthetic baseline cost loading and 2025-01..2027-12 monthly PV. Schedule CPM frozen.

## COST_VERSION_LOG
Category | Definition / Provenance
Phase | 3G COST BASELINE
Approval | Approved Phase 3D allocation + Phase 3F proxy rules
Prior | Phase 3A through Phase 3F proposals kept separate
Schedule | Preserved approved 428 activity / 498 relationship CPM baseline
Financial scope | Project BAC 88.5M; contingency 7.5M
Date range | 2025-01 through 2027-12; no work invented after baseline finish

## COST_QA
QA Test | Result | Status
Project BAC from approved workbook (USD) | 88500000.00 | PASS
Cost ownership budget (USD) | 88500000.00 | PASS
Month PV through 2027-12 (USD) | 88500000.00 | PASS
Unallocated program contingency (USD) | 7500000.00 | EXCLUDED FROM PV
Total authorized (USD) | 96000000.00 | PASS
Control accounts | 72 | PASS
Work packages | 141 | PASS
Funded tasks | 328 | PASS
Cost-ownership lines | 342 | PASS
Schedule rows | 428 | UNCHANGED
Schedule relationships | 498 | UNCHANGED
Sparse detail project/line-month rows | 571 | PASS
Project reporting rows | 432 | PASS
Monthly program rows | 36 | PASS

## ACTUAL_PROGRESS
Cost_Ownership_Line_ID | Project_ID | Activity_ID | Funded_Cost_WP_ID | Component_BAC_USD | Baseline_Start | Baseline_Finish | Synthetic_Start | Synthetic_Finish_or_Gate | Recognition_Rule | Scenario_Status | Status_Date | Measured_Completion_Pct | Cumulative_EV_USD | Cumulative_AC_USD | Scenario_Assumption | Actual_Record_Provenance
CL0001 | P01 | P01-A1 | P01-WP011 | 122100.00 | 2025-01-02 | 2025-01-15 | 2025-01-02 | 2025-01-15 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 122100.00 | 122100.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0002 | P01 | P01-A2 | P01-WP012 | 99900.00 | 2025-01-16 | 2025-01-22 | 2025-01-16 | 2025-01-22 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 99900.00 | 99900.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0003 | P01 | P01-A3 | P01-WP021 | 181300.00 | 2025-01-23 | 2025-02-19 | 2025-01-23 | 2025-02-19 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 181300.00 | 181300.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0004 | P01 | P01-A4 | P01-WP022 | 84175.00 | 2025-03-06 | 2025-04-09 | 2025-03-06 | 2025-04-09 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 84175.00 | 84175.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0005 | P01 | P01-A4b | P01-WP022 | 84175.00 | 2025-04-10 | 2025-04-30 | 2025-04-10 | 2025-04-30 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 84175.00 | 84175.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0006 | P01 | P01-A12 | P01-WP022 | 168350.00 | 2025-10-14 | 2025-10-20 | 2025-10-14 | 2025-10-20 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 168350.00 | 168350.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0007 | P01 | P01-A7a | P01-WP031 | 69067.00 | 2025-05-15 | 2025-06-04 | 2025-05-15 | 2025-06-04 | PROCUREMENT_20_30_30_20 | CLOSED | 2026-03-31 | 100 | 69067.00 | 70448.34 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0008 | P01 | P01-A5 | P01-WP031 | 69067.00 | 2025-03-27 | 2025-04-16 | 2025-03-27 | 2025-04-16 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 69067.00 | 69067.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0009 | P01 | P01-A5b | P01-WP031 | 69066.00 | 2025-04-17 | 2025-04-30 | 2025-04-17 | 2025-04-30 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 69066.00 | 69066.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0010 | P01 | P01-A6 | P01-WP032 | 384800.00 | 2025-05-15 | 2025-06-04 | 2025-05-15 | 2025-06-04 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 384800.00 | 384800.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0011 | P01 | P01-A7b | P01-WP041 | 1278720.00 | 2025-06-05 | 2025-07-16 | 2025-06-05 | 2025-07-16 | PROCUREMENT_20_30_30_20 | CLOSED | 2026-03-31 | 100 | 1278720.00 | 1304294.40 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0012 | P01 | P01-A4u | P01-WP041 | 319680.00 | 2025-02-20 | 2025-03-05 | 2025-02-20 | 2025-03-05 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 319680.00 | 319680.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0013 | P01 | P01-A7c | P01-WP041 | 1278720.00 | 2025-07-17 | 2025-07-28 | 2025-07-17 | 2025-07-28 | PROCUREMENT_20_30_30_20 | CLOSED | 2026-03-31 | 100 | 1278720.00 | 1304294.40 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0014 | P01 | P01-A8 | P01-WP041 | 319680.00 | 2025-07-29 | 2025-09-29 | 2025-07-29 | 2025-09-29 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 319680.00 | 319680.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0015 | P01 | P01-A15 | P01-WP041 | 639360.00 | 2025-11-11 | 2025-11-24 | 2025-11-11 | 2025-11-24 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 639360.00 | 639360.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0016 | P01 | P01-A9 | P01-WP042 | 426240.00 | 2025-08-19 | 2025-09-08 | 2025-08-19 | 2025-09-08 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 426240.00 | 426240.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0017 | P01 | P01-A9b | P01-WP042 | 426240.00 | 2025-08-26 | 2025-09-08 | 2025-08-26 | 2025-09-08 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 426240.00 | 426240.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0018 | P01 | P01-A10 | P01-WP043 | 639360.00 | 2025-10-21 | 2025-11-10 | 2025-10-21 | 2025-11-10 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 639360.00 | 639360.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0019 | P01 | P01-A11 | P01-WP051 | 518000.00 | 2025-10-07 | 2025-10-13 | 2025-10-07 | 2025-10-13 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 518000.00 | 518000.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0020 | P01 | P01-A13 | P01-WP061 | 144300.00 | 2025-11-25 | 2025-12-08 | 2025-11-25 | 2025-12-08 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 144300.00 | 144300.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0021 | P01 | P01-A14 | P01-WP062 | 77700.00 | 2025-12-09 | 2025-12-29 | 2025-12-09 | 2025-12-29 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 77700.00 | 77700.00 | SYNTHETIC_SCENARIO_V1; Completed and accepted; post-completion invoices incur normal closeout adjustment. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0022 | P02 | P02-A1 | P02-WP011 | 132000.00 | 2025-02-03 | 2025-02-14 | 2025-02-03 | 2025-02-14 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 132000.00 | 145200.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0023 | P02 | P02-A2 | P02-WP012 | 132000.00 | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-21 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 132000.00 | 145200.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0024 | P02 | P02-A3 | P02-WP021 | 277200.00 | 2025-02-24 | 2025-03-21 | 2025-02-24 | 2025-03-21 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 277200.00 | 304920.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0025 | P02 | P02-A4 | P02-WP022 | 257400.00 | 2025-03-24 | 2025-04-25 | 2025-03-24 | 2025-04-25 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 257400.00 | 283140.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0026 | P02 | P02-A4b | P02-WP022 | 257400.00 | 2025-04-28 | 2025-05-23 | 2025-04-28 | 2025-05-23 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 257400.00 | 283140.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0027 | P02 | P02-A5 | P02-WP031 | 107800.00 | 2025-04-14 | 2025-05-02 | 2025-04-14 | 2025-05-02 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 107800.00 | 118580.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0028 | P02 | P02-A5b | P02-WP031 | 107800.00 | 2025-05-05 | 2025-05-16 | 2025-05-05 | 2025-05-16 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 107800.00 | 118580.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0029 | P02 | P02-A6 | P02-WP032 | 400400.00 | 2025-06-02 | 2025-06-13 | 2025-06-02 | 2025-06-13 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 400400.00 | 440440.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0030 | P02 | P02-A6b | P02-WP041 | 190080.00 | 2025-02-03 | 2025-02-21 | 2025-02-03 | 2025-02-21 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 190080.00 | 209088.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0031 | P02 | P02-A7a | P02-WP041 | 190080.00 | 2025-06-02 | 2025-06-27 | 2025-06-02 | 2025-06-27 | PROCUREMENT_20_30_30_20 | CLOSED | 2026-03-31 | 100 | 190080.00 | 212889.60 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0032 | P02 | P02-A8 | P02-WP041 | 190080.00 | 2025-06-16 | 2025-06-27 | 2025-06-16 | 2025-06-27 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 190080.00 | 209088.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0033 | P02 | P02-A7b | P02-WP041 | 760320.00 | 2025-06-30 | 2025-10-31 | 2025-06-30 | 2025-10-31 | PROCUREMENT_20_30_30_20 | CLOSED | 2026-03-31 | 100 | 760320.00 | 851558.40 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0034 | P02 | P02-A9 | P02-WP041 | 190080.00 | 2025-06-30 | 2025-07-18 | 2025-06-30 | 2025-07-18 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 190080.00 | 209088.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0035 | P02 | P02-A7c | P02-WP041 | 190080.00 | 2025-11-03 | 2025-11-14 | 2025-11-03 | 2025-11-14 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 190080.00 | 209088.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0036 | P02 | P02-A7d | P02-WP041 | 760320.00 | 2025-11-17 | 2025-11-26 | 2025-11-17 | 2025-11-26 | PROCUREMENT_20_30_30_20 | CLOSED | 2026-03-31 | 100 | 760320.00 | 851558.40 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0037 | P02 | P02-A10 | P02-WP041 | 190080.00 | 2025-11-27 | 2025-12-31 | 2025-11-27 | 2025-12-31 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 190080.00 | 209088.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0038 | P02 | P02-A15b | P02-WP041 | 380160.00 | 2026-01-22 | 2026-02-04 | 2026-01-22 | 2026-02-04 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 380160.00 | 418176.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0039 | P02 | P02-A11a | P02-WP042 | 221760.00 | 2025-06-02 | 2025-06-27 | 2025-06-02 | 2025-06-27 | PROCUREMENT_20_30_30_20 | CLOSED | 2026-03-31 | 100 | 221760.00 | 248371.20 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0040 | P02 | P02-A6c | P02-WP042 | 221760.00 | 2025-02-03 | 2025-02-21 | 2025-02-03 | 2025-02-21 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 221760.00 | 243936.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0041 | P02 | P02-A11b | P02-WP042 | 887040.00 | 2025-06-30 | 2025-10-17 | 2025-06-30 | 2025-10-17 | PROCUREMENT_20_30_30_20 | CLOSED | 2026-03-31 | 100 | 887040.00 | 993484.80 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0042 | P02 | P02-A11c | P02-WP042 | 221760.00 | 2025-10-20 | 2025-10-31 | 2025-10-20 | 2025-10-31 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 221760.00 | 243936.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0043 | P02 | P02-A11d | P02-WP042 | 887040.00 | 2025-11-03 | 2025-11-12 | 2025-11-03 | 2025-11-12 | PROCUREMENT_20_30_30_20 | CLOSED | 2026-03-31 | 100 | 887040.00 | 993484.80 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0044 | P02 | P02-A12 | P02-WP042 | 221760.00 | 2025-11-13 | 2025-12-10 | 2025-11-13 | 2025-12-10 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 221760.00 | 243936.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0045 | P02 | P02-A13 | P02-WP043 | 633600.00 | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-08-15 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 633600.00 | 696960.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0046 | P02 | P02-A14 | P02-WP051 | 264000.00 | 2026-01-01 | 2026-01-14 | 2026-01-01 | 2026-01-14 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 264000.00 | 290400.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0047 | P02 | P02-A15 | P02-WP051 | 264000.00 | 2026-01-15 | 2026-01-21 | 2026-01-15 | 2026-01-21 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 264000.00 | 290400.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0048 | P02 | P02-A16 | P02-WP061 | 171600.00 | 2026-01-22 | 2026-02-04 | 2026-01-22 | 2026-02-04 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 171600.00 | 188760.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0049 | P02 | P02-A17 | P02-WP062 | 92400.00 | 2026-02-05 | 2026-02-25 | 2026-02-05 | 2026-02-25 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 92400.00 | 101640.00 | SYNTHETIC_SCENARIO_V1; Completed; mechanical equipment experienced cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0050 | P03 | P03-A1 | P03-WP011 | 274050.00 | 2025-01-02 | 2025-01-22 | 2025-01-13 | 2025-01-31 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 274050.00 | 304195.50 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0051 | P03 | P03-A2 | P03-WP012 | 334950.00 | 2025-01-23 | 2025-02-05 | 2025-02-03 | 2025-02-14 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 334950.00 | 371794.50 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0052 | P03 | P03-A3 | P03-WP021 | 292320.00 | 2025-02-20 | 2025-04-16 | 2025-03-03 | 2025-04-25 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 292320.00 | 324475.20 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0053 | P03 | P03-A4 | P03-WP021 | 292320.00 | 2025-04-17 | 2025-05-07 | 2025-04-24 | 2025-05-14 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 292320.00 | 324475.20 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0054 | P03 | P03-A2b | P03-WP022 | 138040.00 | 2025-02-06 | 2025-02-19 | 2025-02-13 | 2025-02-26 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 138040.00 | 153224.40 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0055 | P03 | P03-A5 | P03-WP022 | 414120.00 | 2025-05-08 | 2025-06-18 | 2025-05-19 | 2025-06-27 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 414120.00 | 459673.20 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0056 | P03 | P03-A6 | P03-WP022 | 138040.00 | 2025-06-19 | 2025-07-09 | 2025-06-30 | 2025-07-18 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 138040.00 | 149083.20 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0057 | P03 | P03-A7 | P03-WP022 | 138040.00 | 2025-06-26 | 2025-07-23 | 2025-07-07 | 2025-08-01 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 138040.00 | 153224.40 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0058 | P03 | P03-A7b | P03-WP022 | 138040.00 | 2025-07-24 | 2025-09-03 | 2025-07-31 | 2025-09-10 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 138040.00 | 149083.20 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0059 | P03 | P03-A30 | P03-WP022 | 276080.00 | 2026-11-05 | 2026-12-02 | 2026-11-05 | 2026-12-11 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0060 | P03 | P03-A8 | P03-WP031 | 248675.00 | 2025-07-10 | 2025-08-06 | 2025-07-21 | 2025-08-15 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 248675.00 | 276029.25 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0061 | P03 | P03-A9 | P03-WP031 | 248675.00 | 2025-08-07 | 2025-08-27 | 2025-08-18 | 2025-09-05 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 248675.00 | 276029.25 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0062 | P03 | P03-A9b | P03-WP032 | 461825.00 | 2025-08-28 | 2025-09-17 | 2025-09-08 | 2025-09-26 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 461825.00 | 512625.75 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0063 | P03 | P03-A10 | P03-WP032 | 461825.00 | 2025-09-18 | 2025-10-15 | 2025-09-25 | 2025-10-22 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 461825.00 | 512625.75 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0064 | P03 | P03-A11 | P03-WP041 | 434659.00 | 2025-09-18 | 2025-10-15 | 2025-09-29 | 2025-10-24 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 434659.00 | 491164.67 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0065 | P03 | P03-A12 | P03-WP041 | 1738635.00 | 2025-10-16 | 2026-03-04 | 2025-10-27 | 2026-03-13 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 1738635.00 | 1912498.50 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0066 | P03 | P03-A13 | P03-WP041 | 434659.00 | 2026-03-05 | 2026-03-25 | 2026-03-16 | 2026-04-03 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 50 | 217329.50 | 249928.92 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0067 | P03 | P03-A14 | P03-WP041 | 1738635.00 | 2026-03-26 | 2026-04-08 | 2026-04-02 | 2026-04-15 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0068 | P03 | P03-A15 | P03-WP041 | 2173294.00 | 2026-04-09 | 2026-07-01 | 2026-04-09 | 2026-07-10 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0069 | P03 | P03-A29 | P03-WP041 | 869318.00 | 2026-09-10 | 2026-09-30 | 2026-09-10 | 2026-10-09 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0070 | P03 | P03-A16 | P03-WP042 | 355250.00 | 2025-09-18 | 2025-10-15 | 2025-09-29 | 2025-10-24 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 355250.00 | 390775.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0071 | P03 | P03-A17 | P03-WP042 | 1421000.00 | 2025-10-16 | 2026-02-04 | 2025-10-27 | 2026-02-13 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 1421000.00 | 1605730.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0072 | P03 | P03-A18 | P03-WP042 | 355250.00 | 2026-02-05 | 2026-02-18 | 2026-02-12 | 2026-02-25 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 355250.00 | 383670.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0073 | P03 | P03-A19 | P03-WP042 | 1421000.00 | 2026-02-19 | 2026-03-02 | 2026-02-26 | 2026-03-09 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 1421000.00 | 1563100.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0074 | P03 | P03-A20 | P03-WP042 | 1065750.00 | 2026-05-07 | 2026-07-08 | 2026-05-07 | 2026-07-17 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0075 | P03 | P03-A25 | P03-WP042 | 355250.00 | 2026-07-09 | 2026-08-05 | 2026-07-09 | 2026-08-18 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0076 | P03 | P03-A21 | P03-WP043 | 153942.00 | 2025-09-18 | 2025-10-08 | 2025-09-29 | 2025-10-17 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 153942.00 | 169336.20 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0077 | P03 | P03-A22 | P03-WP043 | 615767.00 | 2025-10-09 | 2025-12-17 | 2025-10-20 | 2025-12-26 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 615767.00 | 677343.70 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0078 | P03 | P03-A23 | P03-WP043 | 615766.00 | 2025-12-18 | 2025-12-29 | 2025-12-29 | 2026-01-07 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 615766.00 | 677342.60 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0079 | P03 | P03-A24 | P03-WP043 | 461825.00 | 2026-05-21 | 2026-06-24 | 2026-05-21 | 2026-07-03 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0080 | P03 | P03-A26 | P03-WP051 | 446601.00 | 2026-08-06 | 2026-08-26 | 2026-08-06 | 2026-09-04 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0081 | P03 | P03-A27 | P03-WP051 | 446599.00 | 2026-08-27 | 2026-10-07 | 2026-08-27 | 2026-10-16 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0082 | P03 | P03-A31 | P03-WP061 | 284200.00 | 2026-12-03 | 2026-12-23 | 2026-12-03 | 2027-01-01 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0083 | P03 | P03-A32 | P03-WP061 | 142100.00 | 2026-12-03 | 2026-12-30 | 2026-12-03 | 2027-01-12 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0084 | P03 | P03-A33 | P03-WP062 | 182700.00 | 2026-12-31 | 2027-01-27 | 2026-12-31 | 2027-02-03 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0085 | P04 | P04-A1 | P04-WP011 | 82500.00 | 2025-06-02 | 2025-06-13 | 2025-06-13 | 2025-06-26 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 82500.00 | 94875.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0086 | P04 | P04-A2 | P04-WP012 | 82500.00 | 2025-06-16 | 2025-06-20 | 2025-06-27 | 2025-07-03 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 82500.00 | 92400.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0087 | P04 | P04-A3 | P04-WP021 | 134750.00 | 2025-06-23 | 2025-07-18 | 2025-07-04 | 2025-07-31 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 134750.00 | 154962.50 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0088 | P04 | P04-A4 | P04-WP022 | 62563.00 | 2025-08-04 | 2025-09-05 | 2025-08-15 | 2025-09-18 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 62563.00 | 71947.45 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0089 | P04 | P04-A4b | P04-WP022 | 62562.00 | 2025-09-08 | 2025-09-26 | 2025-09-19 | 2025-10-09 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 62562.00 | 71946.30 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0090 | P04 | P04-A15 | P04-WP022 | 125125.00 | 2026-03-09 | 2026-03-13 | 2026-03-20 | 2026-03-26 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 125125.00 | 140140.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0091 | P04 | P04-A5 | P04-WP031 | 67375.00 | 2025-08-18 | 2025-09-05 | 2025-08-29 | 2025-09-18 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 67375.00 | 75460.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0092 | P04 | P04-A5b | P04-WP031 | 67375.00 | 2025-09-08 | 2025-09-19 | 2025-09-23 | 2025-10-06 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 67375.00 | 77481.25 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0093 | P04 | P04-A5c | P04-WP032 | 125125.00 | 2025-09-22 | 2025-10-03 | 2025-10-03 | 2025-10-16 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 125125.00 | 143893.75 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0094 | P04 | P04-A6 | P04-WP032 | 125125.00 | 2025-10-27 | 2025-11-07 | 2025-11-07 | 2025-11-20 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 125125.00 | 143893.75 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0095 | P04 | P04-A7 | P04-WP041 | 247592.00 | 2025-10-27 | 2025-11-14 | 2025-11-05 | 2025-11-25 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 247592.00 | 277303.04 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0096 | P04 | P04-A8 | P04-WP041 | 247592.00 | 2025-11-17 | 2025-11-21 | 2025-11-28 | 2025-12-04 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 247592.00 | 284730.80 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0097 | P04 | P04-A9 | P04-WP041 | 247592.00 | 2025-11-24 | 2025-12-12 | 2025-12-05 | 2025-12-25 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 247592.00 | 277303.04 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0098 | P04 | P04-A12 | P04-WP041 | 1237958.00 | 2026-01-19 | 2026-02-13 | 2026-01-28 | 2026-02-24 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 1237958.00 | 1386512.96 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0099 | P04 | P04-A13 | P04-WP041 | 247592.00 | 2026-02-16 | 2026-02-27 | 2026-02-27 | 2026-03-12 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 247592.00 | 277303.04 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0100 | P04 | P04-A14 | P04-WP041 | 247591.00 | 2026-03-02 | 2026-03-06 | 2026-03-13 | 2026-03-19 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 247591.00 | 277301.92 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0101 | P04 | P04-A16 | P04-WP041 | 495183.00 | 2026-03-16 | 2026-03-27 | 2026-03-27 | 2026-04-09 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0102 | P04 | P04-A10 | P04-WP042 | 814000.00 | 2025-12-15 | 2025-12-26 | 2025-12-30 | 2026-01-12 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 814000.00 | 911680.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0103 | P04 | P04-A11 | P04-WP043 | 284900.00 | 2025-12-29 | 2026-01-16 | 2026-01-07 | 2026-01-27 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 284900.00 | 319088.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0104 | P04 | P04-A17 | P04-WP061 | 107250.00 | 2026-03-30 | 2026-04-10 | 2026-04-10 | 2026-04-23 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0105 | P04 | P04-A18 | P04-WP062 | 57750.00 | 2026-04-06 | 2026-04-24 | 2026-04-06 | 2026-05-07 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0106 | P05 | P05-A1 | P05-WP011 | 96200.00 | 2025-03-03 | 2025-03-21 | 2025-03-18 | 2025-04-07 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 96200.00 | 110630.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0107 | P05 | P05-A8 | P05-WP011 | 192400.00 | 2025-08-04 | 2025-09-12 | 2025-08-19 | 2025-09-29 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 192400.00 | 227032.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0108 | P05 | P05-A2 | P05-WP012 | 155400.00 | 2025-03-24 | 2025-04-04 | 2025-04-08 | 2025-04-21 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 155400.00 | 178710.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0109 | P05 | P05-A3 | P05-WP021 | 199800.00 | 2025-04-07 | 2025-04-25 | 2025-04-22 | 2025-05-12 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 199800.00 | 235764.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0110 | P05 | P05-A4 | P05-WP022 | 155400.00 | 2025-05-05 | 2025-05-23 | 2025-05-20 | 2025-06-09 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 155400.00 | 183372.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0111 | P05 | P05-A4b | P05-WP022 | 155400.00 | 2025-05-26 | 2025-06-13 | 2025-06-10 | 2025-06-30 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 155400.00 | 178710.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0112 | P05 | P05-A10 | P05-WP022 | 155400.00 | 2025-07-14 | 2025-08-01 | 2025-07-29 | 2025-08-18 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 155400.00 | 183372.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0113 | P05 | P05-A5 | P05-WP031 | 116550.00 | 2025-05-19 | 2025-06-06 | 2025-06-03 | 2025-06-23 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 116550.00 | 137529.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0114 | P05 | P05-A5b | P05-WP031 | 116550.00 | 2025-06-09 | 2025-06-20 | 2025-06-24 | 2025-07-07 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 116550.00 | 134032.50 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0115 | P05 | P05-A5c | P05-WP032 | 72150.00 | 2025-06-23 | 2025-07-04 | 2025-07-08 | 2025-07-21 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 72150.00 | 82972.50 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0116 | P05 | P05-A11 | P05-WP032 | 288600.00 | 2025-07-14 | 2025-08-22 | 2025-07-29 | 2025-09-08 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 288600.00 | 337662.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0117 | P05 | P05-A6 | P05-WP032 | 72150.00 | 2025-07-14 | 2025-08-01 | 2025-07-29 | 2025-08-18 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 72150.00 | 85137.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0118 | P05 | P05-A7 | P05-WP041 | 240582.00 | 2025-07-14 | 2025-09-05 | 2025-07-25 | 2025-09-18 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 240582.00 | 283886.76 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0119 | P05 | P05-A9 | P05-WP041 | 240582.00 | 2025-07-28 | 2025-08-22 | 2025-08-12 | 2025-09-08 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 240582.00 | 276669.30 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0120 | P05 | P05-A12a | P05-WP041 | 1202911.00 | 2025-08-25 | 2025-11-07 | 2025-09-09 | 2025-11-24 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 1202911.00 | 1383347.65 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0121 | P05 | P05-AFIRST | P05-WP041 | 721747.00 | 2025-08-25 | 2025-08-26 | 2025-09-09 | 2025-09-10 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 721747.00 | 830009.05 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0122 | P05 | P05-A13a | P05-WP041 | 1202911.00 | 2025-09-22 | 2025-12-05 | 2025-10-07 | 2025-12-22 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 1202911.00 | 1383347.65 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0123 | P05 | P05-A14a | P05-WP041 | 1202911.00 | 2025-10-20 | 2026-01-02 | 2025-11-04 | 2026-01-19 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 1202911.00 | 1419434.98 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0124 | P05 | P05-A15a | P05-WP041 | 1202911.00 | 2025-11-17 | 2026-01-30 | 2025-12-02 | 2026-02-16 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 1202911.00 | 1383347.65 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0125 | P05 | P05-A16 | P05-WP041 | 481165.00 | 2026-03-16 | 2026-04-03 | 2026-03-31 | 2026-04-20 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0126 | P05 | P05-A12b | P05-WP042 | 379620.00 | 2025-09-15 | 2025-11-28 | 2025-09-30 | 2025-12-15 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 379620.00 | 447951.60 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0127 | P05 | P05-A13b | P05-WP042 | 379620.00 | 2025-10-13 | 2025-12-26 | 2025-10-28 | 2026-01-12 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 379620.00 | 436563.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0128 | P05 | P05-A14b | P05-WP042 | 379620.00 | 2025-11-10 | 2026-01-23 | 2025-11-25 | 2026-02-09 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 379620.00 | 436563.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0129 | P05 | P05-A15b | P05-WP042 | 379620.00 | 2025-12-08 | 2026-02-20 | 2025-12-23 | 2026-03-09 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 379620.00 | 436563.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0130 | P05 | P05-A12c | P05-WP051 | 138750.00 | 2025-12-01 | 2025-12-19 | 2025-12-12 | 2026-01-01 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 138750.00 | 159562.50 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0131 | P05 | P05-A13c | P05-WP051 | 138750.00 | 2025-12-29 | 2026-01-16 | 2026-01-13 | 2026-02-02 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 138750.00 | 163725.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0132 | P05 | P05-A14c | P05-WP051 | 138750.00 | 2026-01-26 | 2026-02-13 | 2026-02-06 | 2026-02-26 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 138750.00 | 159562.50 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0133 | P05 | P05-A15c | P05-WP051 | 138750.00 | 2026-02-23 | 2026-03-13 | 2026-03-10 | 2026-03-30 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 138750.00 | 156787.50 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0134 | P05 | P05-A17 | P05-WP061 | 249750.00 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-18 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0135 | P05 | P05-A18 | P05-WP062 | 83250.00 | 2026-04-20 | 2026-05-15 | 2026-04-20 | 2026-05-28 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0136 | P06 | P06-A1 | P06-WP011 | 75900.00 | 2025-08-01 | 2025-08-21 | 2025-08-13 | 2025-09-02 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 75900.00 | 81972.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0137 | P06 | P06-A10 | P06-WP011 | 75900.00 | 2025-12-12 | 2026-01-08 | 2025-12-22 | 2026-01-16 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 75900.00 | 81972.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0138 | P06 | P06-A2 | P06-WP012 | 124200.00 | 2025-08-22 | 2025-09-04 | 2025-09-03 | 2025-09-16 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 124200.00 | 134136.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0139 | P06 | P06-A3 | P06-WP021 | 265650.00 | 2025-09-05 | 2025-10-02 | 2025-09-17 | 2025-10-14 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 265650.00 | 286902.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0140 | P06 | P06-A4 | P06-WP022 | 123338.00 | 2025-10-10 | 2025-11-06 | 2025-10-22 | 2025-11-18 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 123338.00 | 136905.18 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0141 | P06 | P06-A4b | P06-WP022 | 123338.00 | 2025-11-07 | 2025-11-20 | 2025-11-19 | 2025-12-02 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 123338.00 | 133205.04 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0142 | P06 | P06-A7 | P06-WP022 | 123337.00 | 2025-12-12 | 2026-01-08 | 2025-12-24 | 2026-01-20 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 123337.00 | 133203.96 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0143 | P06 | P06-A8 | P06-WP022 | 123337.00 | 2025-12-12 | 2026-01-01 | 2025-12-24 | 2026-01-13 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 123337.00 | 133203.96 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0144 | P06 | P06-A5 | P06-WP031 | 89700.00 | 2025-10-24 | 2025-11-13 | 2025-11-05 | 2025-11-25 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 89700.00 | 96876.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0145 | P06 | P06-A5b | P06-WP031 | 89700.00 | 2025-11-14 | 2025-11-27 | 2025-11-26 | 2025-12-09 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 89700.00 | 99567.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0146 | P06 | P06-A11 | P06-WP031 | 89700.00 | 2025-12-12 | 2026-01-01 | 2025-12-24 | 2026-01-13 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 89700.00 | 101361.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0147 | P06 | P06-A5c | P06-WP032 | 89700.00 | 2025-11-28 | 2025-12-11 | 2025-12-10 | 2025-12-23 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 89700.00 | 96876.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0148 | P06 | P06-A6 | P06-WP032 | 89700.00 | 2025-12-12 | 2025-12-25 | 2025-12-24 | 2026-01-06 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 89700.00 | 96876.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0149 | P06 | P06-A12 | P06-WP032 | 358800.00 | 2026-01-02 | 2026-03-26 | 2026-01-14 | 2026-04-07 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 80 | 287040.00 | 317179.20 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0150 | P06 | P06-A13 | P06-WP032 | 89700.00 | 2026-03-27 | 2026-04-09 | 2026-04-08 | 2026-04-21 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0151 | P06 | P06-A15 | P06-WP041 | 340947.00 | 2025-12-12 | 2025-12-25 | 2025-12-26 | 2026-01-08 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 340947.00 | 368222.76 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0152 | P06 | P06-APILOTSTAGE | P06-WP041 | 454595.00 | 2026-04-10 | 2026-04-16 | 2026-04-10 | 2026-04-30 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0153 | P06 | P06-A16 | P06-WP041 | 340946.00 | 2026-04-17 | 2026-05-07 | 2026-04-17 | 2026-05-19 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0154 | P06 | P06-AFIRSTPILOT | P06-WP041 | 113649.00 | 2026-04-17 | 2026-04-20 | 2026-04-17 | 2026-04-30 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0155 | P06 | P06-A18a | P06-WP041 | 340946.00 | 2026-05-29 | 2026-07-16 | 2026-05-29 | 2026-07-28 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0156 | P06 | P06-A19a | P06-WP041 | 340946.00 | 2026-06-19 | 2026-08-06 | 2026-06-19 | 2026-08-18 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0157 | P06 | P06-A20a | P06-WP041 | 340946.00 | 2026-07-10 | 2026-08-27 | 2026-07-10 | 2026-09-08 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0158 | P06 | P06-A21a | P06-WP041 | 340946.00 | 2026-07-31 | 2026-09-17 | 2026-07-31 | 2026-10-01 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0159 | P06 | P06-A22 | P06-WP041 | 113649.00 | 2026-10-02 | 2026-10-22 | 2026-10-02 | 2026-11-03 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0160 | P06 | P06-A9 | P06-WP042 | 641183.00 | 2026-01-09 | 2026-02-19 | 2026-01-21 | 2026-03-03 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 641183.00 | 692477.64 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0161 | P06 | P06-A14 | P06-WP042 | 213727.00 | 2026-02-20 | 2026-03-19 | 2026-03-06 | 2026-04-02 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 90 | 192354.30 | 207742.64 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0162 | P06 | P06-A18b | P06-WP043 | 122130.00 | 2026-07-17 | 2026-07-30 | 2026-07-17 | 2026-08-11 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0163 | P06 | P06-A19b | P06-WP043 | 122130.00 | 2026-08-07 | 2026-08-20 | 2026-08-07 | 2026-09-01 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0164 | P06 | P06-A20b | P06-WP043 | 122130.00 | 2026-08-28 | 2026-09-10 | 2026-08-28 | 2026-09-22 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0165 | P06 | P06-A21b | P06-WP043 | 122130.00 | 2026-09-18 | 2026-10-01 | 2026-09-18 | 2026-10-13 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0166 | P06 | P06-A17 | P06-WP051 | 230000.00 | 2026-05-08 | 2026-05-28 | 2026-05-08 | 2026-06-09 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0167 | P06 | P06-A23 | P06-WP051 | 345000.00 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-13 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0168 | P06 | P06-A24 | P06-WP051 | 115000.00 | 2026-11-06 | 2026-11-19 | 2026-11-06 | 2026-12-01 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0169 | P06 | P06-A25 | P06-WP061 | 144900.00 | 2026-11-20 | 2026-12-03 | 2026-11-20 | 2026-12-15 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0170 | P06 | P06-A26 | P06-WP062 | 62100.00 | 2026-12-04 | 2026-12-24 | 2026-12-04 | 2027-01-05 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; AMI pilot staging experiencing integration delay and material premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0171 | P07 | P07-A1 | P07-WP011 | 61500.00 | 2025-10-01 | 2025-10-21 | 2025-09-26 | 2025-10-16 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 61500.00 | 59040.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0172 | P07 | P07-A2 | P07-WP012 | 61500.00 | 2025-10-22 | 2025-11-04 | 2025-10-17 | 2025-10-30 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 61500.00 | 60885.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0173 | P07 | P07-A3 | P07-WP021 | 129150.00 | 2025-11-05 | 2025-12-02 | 2025-10-31 | 2025-11-27 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 129150.00 | 127858.50 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0174 | P07 | P07-A4 | P07-WP022 | 119925.00 | 2025-12-10 | 2026-01-06 | 2025-12-05 | 2026-01-01 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 119925.00 | 115128.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0175 | P07 | P07-A4b | P07-WP022 | 119925.00 | 2026-01-07 | 2026-01-27 | 2025-12-31 | 2026-01-20 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 119925.00 | 115128.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0176 | P07 | P07-A5 | P07-WP031 | 47834.00 | 2025-12-24 | 2026-01-13 | 2025-12-19 | 2026-01-08 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 47834.00 | 45920.64 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0177 | P07 | P07-A5b | P07-WP031 | 47833.00 | 2026-01-14 | 2026-01-27 | 2026-01-07 | 2026-01-20 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 47833.00 | 47354.67 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0178 | P07 | P07-A8 | P07-WP031 | 47833.00 | 2026-02-25 | 2026-03-17 | 2026-02-20 | 2026-03-12 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 100 | 47833.00 | 46876.34 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0179 | P07 | P07-A5c | P07-WP032 | 133250.00 | 2026-01-28 | 2026-02-10 | 2026-01-23 | 2026-02-05 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 133250.00 | 127920.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0180 | P07 | P07-A6 | P07-WP032 | 133250.00 | 2026-02-25 | 2026-03-10 | 2026-02-20 | 2026-03-05 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 133250.00 | 125255.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0181 | P07 | P07-A7 | P07-WP041 | 446080.00 | 2026-02-25 | 2026-03-10 | 2026-02-20 | 2026-03-05 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 446080.00 | 428236.80 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0182 | P07 | P07-A10 | P07-WP041 | 446080.00 | 2026-03-11 | 2026-03-31 | 2026-03-06 | 2026-03-26 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 100 | 446080.00 | 428236.80 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0183 | P07 | P07-A16 | P07-WP041 | 892160.00 | 2026-07-22 | 2026-08-04 | 2026-07-22 | 2026-07-28 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0184 | P07 | P07-A11 | P07-WP042 | 585480.00 | 2026-04-29 | 2026-05-19 | 2026-04-29 | 2026-05-18 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0185 | P07 | P07-A9 | P07-WP043 | 83640.00 | 2026-03-18 | 2026-04-28 | 2026-03-11 | 2026-04-21 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 50 | 41820.00 | 41820.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0186 | P07 | P07-A12 | P07-WP043 | 250920.00 | 2026-05-20 | 2026-06-02 | 2026-05-20 | 2026-05-28 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0187 | P07 | P07-A13 | P07-WP043 | 83640.00 | 2026-06-03 | 2026-06-16 | 2026-06-03 | 2026-06-11 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0188 | P07 | P07-A14 | P07-WP051 | 191333.00 | 2026-06-17 | 2026-06-30 | 2026-06-17 | 2026-06-25 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0189 | P07 | P07-A15 | P07-WP051 | 95667.00 | 2026-07-01 | 2026-07-21 | 2026-07-01 | 2026-07-16 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0190 | P07 | P07-A17 | P07-WP061 | 79950.00 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-13 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0191 | P07 | P07-A18 | P07-WP062 | 43050.00 | 2026-08-12 | 2026-09-01 | 2026-08-12 | 2026-08-27 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; PRV procurement and installation advancing with favorable productivity. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0192 | P08 | P08-A1 | P08-WP011 | 62100.00 | 2025-12-01 | 2025-12-19 | 2025-12-15 | 2026-01-02 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 62100.00 | 67689.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0193 | P08 | P08-A2 | P08-WP012 | 75900.00 | 2025-12-22 | 2026-01-02 | 2026-01-07 | 2026-01-20 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 75900.00 | 82731.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0194 | P08 | P08-A3 | P08-WP021 | 128800.00 | 2026-01-05 | 2026-01-30 | 2026-01-19 | 2026-02-13 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 128800.00 | 140392.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0195 | P08 | P08-A4 | P08-WP022 | 119600.00 | 2026-02-09 | 2026-03-06 | 2026-02-23 | 2026-03-20 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 119600.00 | 130364.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0196 | P08 | P08-A4b | P08-WP022 | 119600.00 | 2026-03-09 | 2026-03-27 | 2026-03-23 | 2026-04-10 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 46 | 55016.00 | 58867.12 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0197 | P08 | P08-A5 | P08-WP031 | 58880.00 | 2026-02-23 | 2026-03-13 | 2026-03-09 | 2026-03-27 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 58880.00 | 65945.60 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0198 | P08 | P08-A5b | P08-WP031 | 58880.00 | 2026-03-16 | 2026-03-27 | 2026-03-30 | 2026-04-10 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 20 | 11776.00 | 12835.84 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0199 | P08 | P08-A8 | P08-WP031 | 58880.00 | 2026-04-27 | 2026-05-15 | 2026-04-27 | 2026-06-02 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0200 | P08 | P08-A5c | P08-WP032 | 187680.00 | 2026-03-30 | 2026-04-10 | 2026-04-13 | 2026-04-24 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0201 | P08 | P08-A6 | P08-WP032 | 187680.00 | 2026-04-27 | 2026-05-08 | 2026-04-27 | 2026-05-22 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0202 | P08 | P08-A7 | P08-WP041 | 102290.00 | 2026-01-19 | 2026-02-06 | 2026-02-02 | 2026-02-20 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 100 | 102290.00 | 111496.10 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0203 | P08 | P08-A13 | P08-WP041 | 102290.00 | 2026-04-27 | 2026-05-15 | 2026-04-27 | 2026-05-29 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0204 | P08 | P08-A14 | P08-WP041 | 102289.00 | 2026-04-27 | 2026-05-08 | 2026-04-27 | 2026-05-22 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0205 | P08 | P08-A9 | P08-WP041 | 409158.00 | 2026-05-18 | 2026-08-28 | 2026-05-18 | 2026-09-11 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0206 | P08 | P08-A9fat | P08-WP041 | 102289.00 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-25 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0207 | P08 | P08-A11 | P08-WP041 | 409158.00 | 2026-09-14 | 2026-09-25 | 2026-09-14 | 2026-10-09 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0208 | P08 | P08-A15 | P08-WP041 | 409158.00 | 2026-09-28 | 2026-10-09 | 2026-09-28 | 2026-10-23 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0209 | P08 | P08-A17 | P08-WP041 | 102289.00 | 2026-10-12 | 2026-10-23 | 2026-10-12 | 2026-11-06 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0210 | P08 | P08-A21 | P08-WP041 | 204579.00 | 2026-11-30 | 2026-12-11 | 2026-11-30 | 2026-12-25 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0211 | P08 | P08-A10 | P08-WP042 | 289034.00 | 2026-05-18 | 2026-08-07 | 2026-05-18 | 2026-08-21 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0212 | P08 | P08-A10fat | P08-WP042 | 72258.00 | 2026-08-10 | 2026-08-19 | 2026-08-10 | 2026-09-02 | WORKDAY_SPREAD | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0213 | P08 | P08-A12 | P08-WP042 | 289033.00 | 2026-08-20 | 2026-08-31 | 2026-08-20 | 2026-09-14 | PROCUREMENT_20_30_30_20 | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0214 | P08 | P08-A16 | P08-WP042 | 216775.00 | 2026-09-01 | 2026-09-21 | 2026-09-01 | 2026-10-05 | WORKDAY_FALLBACK | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0215 | P08 | P08-A18 | P08-WP051 | 138000.00 | 2026-10-26 | 2026-11-06 | 2026-10-26 | 2026-11-20 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0216 | P08 | P08-A19 | P08-WP051 | 138000.00 | 2026-11-09 | 2026-11-20 | 2026-11-09 | 2026-12-04 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0217 | P08 | P08-A20 | P08-WP051 | 138000.00 | 2026-11-23 | 2026-11-27 | 2026-11-23 | 2026-12-11 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0218 | P08 | P08-A22 | P08-WP061 | 89700.00 | 2026-12-14 | 2026-12-25 | 2026-12-14 | 2027-01-08 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0219 | P08 | P08-A23 | P08-WP062 | 48300.00 | 2026-12-21 | 2027-01-08 | 2026-12-21 | 2027-01-22 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0220 | P09 | P09-A1 | P09-WP011 | 117000.00 | 2026-02-02 | 2026-02-20 | 2026-02-06 | 2026-02-26 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 100 | 117000.00 | 120510.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0221 | P09 | P09-A2 | P09-WP012 | 117000.00 | 2026-02-23 | 2026-03-06 | 2026-02-25 | 2026-03-10 | WORKDAY_FALLBACK | EARLY | 2026-03-31 | 100 | 117000.00 | 120510.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0222 | P09 | P09-A3a | P09-WP021 | 124800.00 | 2026-03-09 | 2026-04-03 | 2026-03-13 | 2026-04-09 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 65 | 81120.00 | 83553.60 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0223 | P09 | P09-A3 | P09-WP021 | 124800.00 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-07 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0224 | P09 | P09-A4 | P09-WP022 | 74880.00 | 2026-05-11 | 2026-06-05 | 2026-05-11 | 2026-06-11 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0225 | P09 | P09-A4b | P09-WP022 | 74880.00 | 2026-06-08 | 2026-07-17 | 2026-06-08 | 2026-07-21 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0226 | P09 | P09-A4c | P09-WP022 | 74880.00 | 2026-06-08 | 2026-07-31 | 2026-06-08 | 2026-08-06 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0227 | P09 | P09-A19 | P09-WP022 | 149760.00 | 2026-12-24 | 2026-12-30 | 2026-12-24 | 2027-01-05 | FINAL_GATE | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0228 | P09 | P09-A5 | P09-WP031 | 72800.00 | 2026-05-25 | 2026-06-12 | 2026-05-25 | 2026-06-18 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0229 | P09 | P09-A5b | P09-WP031 | 72800.00 | 2026-06-15 | 2026-07-03 | 2026-06-15 | 2026-07-13 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0230 | P09 | P09-A10 | P09-WP031 | 72800.00 | 2026-08-03 | 2026-08-21 | 2026-08-03 | 2026-08-27 | PROCUREMENT_20_30_30_20 | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0231 | P09 | P09-A5c | P09-WP032 | 202800.00 | 2026-07-06 | 2026-07-17 | 2026-07-06 | 2026-07-23 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0232 | P09 | P09-A6 | P09-WP032 | 202800.00 | 2026-08-03 | 2026-08-28 | 2026-08-03 | 2026-09-01 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0233 | P09 | P09-A7 | P09-WP041 | 304869.00 | 2026-08-03 | 2026-08-21 | 2026-08-03 | 2026-08-27 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0234 | P09 | P09-A8 | P09-WP041 | 304869.00 | 2026-08-03 | 2026-08-21 | 2026-08-03 | 2026-08-27 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0235 | P09 | P09-A9 | P09-WP041 | 304869.00 | 2026-08-24 | 2026-09-04 | 2026-08-24 | 2026-09-08 | WORKDAY_FALLBACK | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0236 | P09 | P09-A13 | P09-WP041 | 304869.00 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-17 | WORKDAY_FALLBACK | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0237 | P09 | P09-A14 | P09-WP041 | 304869.00 | 2026-09-14 | 2026-10-09 | 2026-09-14 | 2026-10-15 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0238 | P09 | P09-A12 | P09-WP041 | 1219474.00 | 2026-10-26 | 2026-11-04 | 2026-10-26 | 2026-11-10 | PROCUREMENT_20_30_30_20 | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0239 | P09 | P09-A15 | P09-WP041 | 304868.00 | 2026-11-05 | 2026-11-25 | 2026-11-05 | 2026-12-01 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0240 | P09 | P09-A16 | P09-WP041 | 304868.00 | 2026-11-26 | 2026-12-09 | 2026-11-26 | 2026-12-15 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0241 | P09 | P09-A17 | P09-WP041 | 304868.00 | 2026-11-26 | 2026-12-09 | 2026-11-26 | 2026-12-15 | WORKDAY_SPREAD | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0242 | P09 | P09-A21 | P09-WP041 | 609737.00 | 2027-01-21 | 2027-02-03 | 2027-01-21 | 2027-02-09 | FINAL_GATE | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0243 | P09 | P09-A11 | P09-WP042 | 898560.00 | 2026-08-24 | 2026-10-23 | 2026-08-24 | 2026-10-29 | PROCUREMENT_20_30_30_20 | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0244 | P09 | P09-A20 | P09-WP043 | 449280.00 | 2026-12-31 | 2027-01-20 | 2026-12-31 | 2027-01-26 | WORKDAY_FALLBACK | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0245 | P09 | P09-A18 | P09-WP051 | 468000.00 | 2026-12-17 | 2026-12-23 | 2026-12-17 | 2026-12-29 | FINAL_GATE | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0246 | P09 | P09-A22 | P09-WP061 | 152100.00 | 2027-02-04 | 2027-02-17 | 2027-02-04 | 2027-02-19 | FINAL_GATE | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0247 | P09 | P09-A23 | P09-WP062 | 81900.00 | 2027-02-11 | 2027-03-03 | 2027-02-11 | 2027-03-09 | FINAL_GATE | EARLY | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Service line preconstruction progressing; no invented early field installations. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0248 | P10 | P10-A1 | P10-WP011 | 66600.00 | 2026-04-01 | 2026-04-21 | 2026-04-01 | 2026-04-21 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0249 | P10 | P10-A4 | P10-WP021 | 266400.00 | 2026-05-27 | 2026-06-23 | 2026-05-27 | 2026-06-23 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0250 | P10 | P10-A3 | P10-WP022 | 99900.00 | 2026-05-06 | 2026-05-26 | 2026-05-06 | 2026-05-26 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0251 | P10 | P10-A5 | P10-WP022 | 99900.00 | 2026-06-10 | 2026-06-30 | 2026-06-10 | 2026-06-30 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0252 | P10 | P10-A6b | P10-WP022 | 99900.00 | 2026-06-10 | 2026-06-30 | 2026-06-10 | 2026-06-30 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0253 | P10 | P10-A6 | P10-WP022 | 99900.00 | 2026-06-24 | 2026-07-21 | 2026-06-24 | 2026-07-21 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0254 | P10 | P10-A7 | P10-WP031 | 60434.00 | 2026-07-08 | 2026-07-28 | 2026-07-08 | 2026-07-28 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0255 | P10 | P10-A7b | P10-WP031 | 60433.00 | 2026-07-29 | 2026-08-11 | 2026-07-29 | 2026-08-11 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0256 | P10 | P10-A9 | P10-WP031 | 60433.00 | 2026-08-26 | 2026-09-15 | 2026-08-26 | 2026-09-15 | PROCUREMENT_20_30_30_20 | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0257 | P10 | P10-A7c | P10-WP032 | 168350.00 | 2026-08-12 | 2026-08-25 | 2026-08-12 | 2026-08-25 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0258 | P10 | P10-A8 | P10-WP032 | 168350.00 | 2026-08-26 | 2026-09-08 | 2026-08-26 | 2026-09-08 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0259 | P10 | P10-IF-01 | P10-WP041 | 143745.00 | 2026-07-22 | 2026-08-04 | 2026-07-22 | 2026-08-04 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0260 | P10 | P10-A14 | P10-WP041 | 431235.00 | 2026-08-26 | 2026-10-06 | 2026-08-26 | 2026-10-06 | WORKDAY_FALLBACK | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0261 | P10 | P10-A11 | P10-WP042 | 293040.00 | 2026-08-26 | 2026-09-15 | 2026-08-26 | 2026-09-15 | PROCUREMENT_20_30_30_20 | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0262 | P10 | P10-A15 | P10-WP042 | 219780.00 | 2026-08-26 | 2026-09-29 | 2026-08-26 | 2026-09-29 | WORKDAY_FALLBACK | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0263 | P10 | P10-A10 | P10-WP043 | 124320.00 | 2026-09-16 | 2026-10-27 | 2026-09-16 | 2026-10-27 | PROCUREMENT_20_30_30_20 | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0264 | P10 | P10-A12 | P10-WP043 | 124320.00 | 2026-10-28 | 2026-12-01 | 2026-10-28 | 2026-12-01 | PROCUREMENT_20_30_30_20 | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0265 | P10 | P10-A16 | P10-WP043 | 124320.00 | 2026-12-23 | 2027-01-01 | 2026-12-23 | 2027-01-01 | PROCUREMENT_20_30_30_20 | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0266 | P10 | P10-A17 | P10-WP043 | 93240.00 | 2027-01-04 | 2027-02-05 | 2027-01-04 | 2027-02-05 | WORKDAY_FALLBACK | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0267 | P10 | P10-A13 | P10-WP051 | 41353.00 | 2026-12-02 | 2026-12-22 | 2026-12-02 | 2026-12-22 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0268 | P10 | P10-A18 | P10-WP051 | 82706.00 | 2027-02-08 | 2027-02-26 | 2027-02-08 | 2027-02-26 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0269 | P10 | P10-A19 | P10-WP051 | 82706.00 | 2027-03-01 | 2027-03-12 | 2027-03-01 | 2027-03-12 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0270 | P10 | P10-A20 | P10-WP051 | 41353.00 | 2027-03-15 | 2027-04-02 | 2027-03-15 | 2027-04-02 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0271 | P10 | P10-A21 | P10-WP051 | 82706.00 | 2027-04-05 | 2027-04-23 | 2027-04-05 | 2027-04-23 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0272 | P10 | P10-A22 | P10-WP051 | 41353.00 | 2027-04-26 | 2027-05-07 | 2027-04-26 | 2027-05-07 | WORKDAY_SPREAD | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0273 | P10 | P10-A23 | P10-WP051 | 82706.00 | 2027-04-26 | 2027-05-07 | 2027-04-26 | 2027-05-07 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0274 | P10 | P10-A24 | P10-WP051 | 82706.00 | 2027-05-10 | 2027-05-28 | 2027-05-10 | 2027-05-28 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0275 | P10 | P10-A25 | P10-WP051 | 82706.00 | 2027-05-31 | 2027-06-18 | 2027-05-31 | 2027-06-18 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0276 | P10 | P10-A27 | P10-WP051 | 82705.00 | 2027-06-21 | 2027-07-02 | 2027-06-21 | 2027-07-02 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0277 | P10 | P10-A26 | P10-WP061 | 77700.00 | 2027-06-21 | 2027-07-09 | 2027-06-21 | 2027-07-09 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0278 | P10 | P10-A28 | P10-WP062 | 33300.00 | 2027-07-19 | 2027-08-06 | 2027-07-19 | 2027-08-06 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0279 | P11 | P11-A1 | P11-WP011 | 76800.00 | 2025-04-01 | 2025-04-21 | 2025-04-01 | 2025-04-21 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 76800.00 | 72960.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0280 | P11 | P11-A2 | P11-WP012 | 51200.00 | 2025-04-22 | 2025-05-05 | 2025-04-22 | 2025-05-05 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 51200.00 | 48640.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0281 | P11 | P11-A3 | P11-WP021 | 57600.00 | 2025-05-06 | 2025-05-26 | 2025-05-06 | 2025-05-26 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 57600.00 | 54720.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0282 | P11 | P11-A4 | P11-WP022 | 67200.00 | 2025-06-03 | 2025-06-23 | 2025-06-03 | 2025-06-23 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 67200.00 | 63840.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0283 | P11 | P11-A8 | P11-WP022 | 67200.00 | 2025-08-12 | 2025-08-25 | 2025-08-12 | 2025-08-25 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 67200.00 | 63840.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0284 | P11 | P11-A5 | P11-WP031 | 50400.00 | 2025-06-17 | 2025-07-07 | 2025-06-17 | 2025-07-07 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 50400.00 | 47880.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0285 | P11 | P11-A5b | P11-WP031 | 50400.00 | 2025-07-08 | 2025-07-21 | 2025-07-08 | 2025-07-21 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 50400.00 | 47880.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0286 | P11 | P11-A5c | P11-WP032 | 93600.00 | 2025-07-22 | 2025-08-04 | 2025-07-22 | 2025-08-04 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 93600.00 | 88920.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0287 | P11 | P11-A6 | P11-WP032 | 93600.00 | 2025-08-12 | 2025-08-25 | 2025-08-12 | 2025-08-25 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 93600.00 | 88920.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0288 | P11 | P11-A10 | P11-WP041 | 95822.00 | 2025-08-12 | 2025-09-01 | 2025-08-12 | 2025-09-01 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 95822.00 | 91030.90 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0289 | P11 | P11-A9 | P11-WP041 | 383289.00 | 2025-08-12 | 2025-09-15 | 2025-08-12 | 2025-09-15 | PROCUREMENT_20_30_30_20 | CLOSED | 2026-03-31 | 100 | 383289.00 | 371790.33 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0290 | P11 | P11-AFIRST | P11-WP041 | 287467.00 | 2025-09-16 | 2025-09-17 | 2025-09-16 | 2025-09-17 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 287467.00 | 273093.65 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0291 | P11 | P11-B1inst | P11-WP041 | 479111.00 | 2025-09-16 | 2025-11-10 | 2025-09-16 | 2025-11-10 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 479111.00 | 455155.45 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0292 | P11 | P11-B2inst | P11-WP041 | 479111.00 | 2025-10-21 | 2025-12-15 | 2025-10-21 | 2025-12-15 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 479111.00 | 455155.45 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0293 | P11 | P11-B1rest | P11-WP043 | 168000.00 | 2025-10-14 | 2025-12-08 | 2025-10-14 | 2025-12-08 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 168000.00 | 159600.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0294 | P11 | P11-B2rest | P11-WP043 | 168000.00 | 2025-11-18 | 2026-01-12 | 2025-11-18 | 2026-01-12 | WORKDAY_FALLBACK | CLOSED | 2026-03-31 | 100 | 168000.00 | 159600.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0295 | P11 | P11-A7 | P11-WP051 | 64000.00 | 2025-08-12 | 2025-09-01 | 2025-08-12 | 2025-09-01 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 64000.00 | 60800.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0296 | P11 | P11-B1test | P11-WP051 | 64000.00 | 2025-11-11 | 2025-11-24 | 2025-11-11 | 2025-11-24 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 64000.00 | 60800.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0297 | P11 | P11-B2test | P11-WP051 | 64000.00 | 2025-12-16 | 2025-12-29 | 2025-12-16 | 2025-12-29 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 64000.00 | 60800.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0298 | P11 | P11-A11 | P11-WP051 | 64000.00 | 2026-01-27 | 2026-02-09 | 2026-01-27 | 2026-02-09 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 64000.00 | 60800.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0299 | P11 | P11-B1gis | P11-WP061 | 22400.00 | 2025-12-09 | 2025-12-22 | 2025-12-09 | 2025-12-22 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 22400.00 | 21280.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0300 | P11 | P11-B2gis | P11-WP061 | 22400.00 | 2026-01-13 | 2026-01-26 | 2026-01-13 | 2026-01-26 | WORKDAY_SPREAD | CLOSED | 2026-03-31 | 100 | 22400.00 | 21280.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0301 | P11 | P11-A12 | P11-WP061 | 22400.00 | 2026-02-10 | 2026-02-23 | 2026-02-10 | 2026-02-23 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 22400.00 | 21280.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0302 | P11 | P11-A13 | P11-WP062 | 28800.00 | 2026-02-17 | 2026-03-09 | 2026-02-17 | 2026-03-09 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 28800.00 | 27360.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0303 | P12 | P12-Y1A1 | P12-WP011 | 28560.00 | 2025-01-02 | 2025-01-22 | 2025-01-09 | 2025-01-29 | WORKDAY_SPREAD | STANDING | 2026-03-31 | 100 | 28560.00 | 31130.40 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0304 | P12 | P12-Y1A2 | P12-WP011 | 28560.00 | 2025-01-23 | 2025-02-19 | 2025-01-30 | 2025-02-26 | WORKDAY_SPREAD | STANDING | 2026-03-31 | 100 | 28560.00 | 31130.40 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0305 | P12 | P12-Y2A1 | P12-WP011 | 36720.00 | 2025-10-30 | 2025-11-19 | 2025-11-04 | 2025-11-24 | WORKDAY_SPREAD | STANDING | 2026-03-31 | 100 | 36720.00 | 40024.80 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0306 | P12 | P12-Y2A2 | P12-WP011 | 36720.00 | 2025-11-20 | 2025-12-17 | 2025-12-01 | 2025-12-26 | WORKDAY_SPREAD | STANDING | 2026-03-31 | 100 | 36720.00 | 38923.20 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0307 | P12 | P12-Y3A1 | P12-WP011 | 36720.00 | 2026-08-27 | 2026-09-16 | 2026-08-27 | 2026-09-21 | WORKDAY_SPREAD | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0308 | P12 | P12-Y3A2 | P12-WP011 | 36720.00 | 2026-09-17 | 2026-10-14 | 2026-09-17 | 2026-10-21 | WORKDAY_SPREAD | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0309 | P12 | P12-Y1A3 | P12-WP021 | 42840.00 | 2025-02-20 | 2025-03-19 | 2025-02-27 | 2025-03-26 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 100 | 42840.00 | 46695.60 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0310 | P12 | P12-Y1A4 | P12-WP021 | 42840.00 | 2025-03-20 | 2025-04-09 | 2025-03-27 | 2025-04-16 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 100 | 42840.00 | 46695.60 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0311 | P12 | P12-Y2A3 | P12-WP021 | 55080.00 | 2025-12-18 | 2026-01-14 | 2025-12-25 | 2026-01-21 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 100 | 55080.00 | 58384.80 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0312 | P12 | P12-Y2A4 | P12-WP021 | 55080.00 | 2026-01-15 | 2026-02-04 | 2026-01-22 | 2026-02-11 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 100 | 55080.00 | 58384.80 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0313 | P12 | P12-Y3A3 | P12-WP021 | 55080.00 | 2026-10-15 | 2026-11-11 | 2026-10-15 | 2026-11-18 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0314 | P12 | P12-Y3A4 | P12-WP021 | 55080.00 | 2026-11-12 | 2026-12-02 | 2026-11-12 | 2026-12-09 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0315 | P12 | P12-Y1A5 | P12-WP031 | 114240.00 | 2025-04-10 | 2025-05-14 | 2025-04-15 | 2025-05-19 | PROCUREMENT_20_30_30_20 | STANDING | 2026-03-31 | 100 | 114240.00 | 123379.20 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0316 | P12 | P12-Y2A5 | P12-WP031 | 146880.00 | 2026-02-05 | 2026-03-11 | 2026-02-10 | 2026-03-16 | PROCUREMENT_20_30_30_20 | STANDING | 2026-03-31 | 100 | 146880.00 | 158630.40 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0317 | P12 | P12-Y3A5 | P12-WP031 | 146880.00 | 2026-12-03 | 2027-01-06 | 2026-12-03 | 2027-01-13 | PROCUREMENT_20_30_30_20 | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0318 | P12 | P12-Y1A6 | P12-WP041 | 944194.00 | 2025-05-15 | 2025-09-17 | 2025-05-22 | 2025-09-24 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 100 | 944194.00 | 1000845.64 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0319 | P12 | P12-Y2A6 | P12-WP041 | 1213963.00 | 2026-03-12 | 2026-07-15 | 2026-03-19 | 2026-07-22 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 10 | 121396.30 | 128680.07 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0320 | P12 | P12-Y3A6 | P12-WP041 | 1213963.00 | 2027-01-07 | 2027-05-12 | 2027-01-07 | 2027-05-19 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0321 | P12 | P12-Y1A7 | P12-WP051 | 57120.00 | 2025-09-18 | 2025-10-08 | 2025-09-25 | 2025-10-15 | FINAL_GATE | STANDING | 2026-03-31 | 100 | 57120.00 | 60547.20 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0322 | P12 | P12-Y2A7 | P12-WP051 | 73440.00 | 2026-07-16 | 2026-08-05 | 2026-07-16 | 2026-08-12 | FINAL_GATE | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0323 | P12 | P12-Y3A7 | P12-WP051 | 73440.00 | 2027-05-13 | 2027-06-02 | 2027-05-13 | 2027-06-09 | FINAL_GATE | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0324 | P12 | P12-Y1A8 | P12-WP061 | 28560.00 | 2025-10-09 | 2025-10-29 | 2025-10-16 | 2025-11-05 | FINAL_GATE | STANDING | 2026-03-31 | 100 | 28560.00 | 30273.60 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0325 | P12 | P12-Y2A8 | P12-WP061 | 36720.00 | 2026-08-06 | 2026-08-26 | 2026-08-06 | 2026-09-02 | FINAL_GATE | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0326 | P12 | P12-Y3A8 | P12-WP061 | 36720.00 | 2027-06-03 | 2027-06-23 | 2027-06-03 | 2027-06-30 | FINAL_GATE | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0327 | P03 | P03-A28 | P03-WP052 | 487200.00 | 2026-10-08 | 2026-11-04 | 2026-10-08 | 2026-11-13 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0328 | P03 | P03-A29 | P03-WP053 | 121800.00 | 2026-09-10 | 2026-09-30 | 2026-09-10 | 2026-10-09 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0329 | P03 | P03-A30 | P03-WP053 | 121800.00 | 2026-11-05 | 2026-12-02 | 2026-11-05 | 2026-12-11 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Treatment equipment approval and construction progressing with modest delivery delay. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0330 | P05 | P05-A12c | P05-WP043 | 105450.00 | 2025-12-01 | 2025-12-19 | 2025-12-16 | 2026-01-05 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 105450.00 | 124431.00 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0331 | P05 | P05-A13c | P05-WP043 | 105450.00 | 2025-12-29 | 2026-01-16 | 2026-01-15 | 2026-02-04 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 105450.00 | 121267.50 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0332 | P05 | P05-A14c | P05-WP043 | 105450.00 | 2026-01-26 | 2026-02-13 | 2026-02-10 | 2026-03-02 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 105450.00 | 121267.50 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0333 | P05 | P05-A15c | P05-WP043 | 105450.00 | 2026-02-23 | 2026-03-13 | 2026-03-10 | 2026-03-30 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 105450.00 | 121267.50 | SYNTHETIC_SCENARIO_V1; Four-zone field productivity below baseline. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0334 | P10 | P10-A2 | P10-WP012 | 81400.00 | 2026-04-22 | 2026-05-05 | 2026-04-22 | 2026-05-05 | FINAL_GATE | FUTURE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Not yet started at March 31 cutoff. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0335 | P11 | P11-B1gis | P11-WP042 | 89600.00 | 2025-12-09 | 2025-12-22 | 2025-12-09 | 2025-12-22 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 89600.00 | 85120.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0336 | P11 | P11-B2gis | P11-WP042 | 89600.00 | 2026-01-13 | 2026-01-26 | 2026-01-13 | 2026-01-26 | FINAL_GATE | CLOSED | 2026-03-31 | 100 | 89600.00 | 85120.00 | SYNTHETIC_SCENARIO_V1; Valve program completed; productivity savings. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0337 | P12 | P12-Y1A6 | P12-WP042 | 141086.00 | 2025-05-15 | 2025-09-17 | 2025-05-20 | 2025-09-22 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 100 | 141086.00 | 149551.16 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0338 | P12 | P12-Y2A6 | P12-WP042 | 181397.00 | 2026-03-12 | 2026-07-15 | 2026-03-17 | 2026-07-20 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 12 | 21767.64 | 23073.69 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0339 | P12 | P12-Y3A6 | P12-WP042 | 181397.00 | 2027-01-07 | 2027-05-12 | 2027-01-07 | 2027-05-19 | WORKDAY_FALLBACK | STANDING | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Year 1 and early Year 2 work orders with mixed emergency response throughput. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0340 | P04 | P04-A14 | P04-WP051 | 132000.00 | 2026-03-02 | 2026-03-06 | 2026-03-13 | 2026-03-19 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 132000.00 | 147840.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0341 | P04 | P04-A15 | P04-WP051 | 198000.00 | 2026-03-09 | 2026-03-13 | 2026-03-20 | 2026-03-26 | FINAL_GATE | ACTIVE | 2026-03-31 | 100 | 198000.00 | 221760.00 | SYNTHETIC_SCENARIO_V1; Tank rehabilitation has inspection/quality rework and cost pressure. | SIMULATED_NOT_EXTERNAL_EVIDENCE
CL0342 | P08 | P08-A15 | P08-WP043 | 179400.00 | 2026-09-28 | 2026-10-09 | 2026-09-28 | 2026-10-23 | FINAL_GATE | ACTIVE | 2026-03-31 | 0 | 0.00 | 0.00 | SYNTHETIC_SCENARIO_V1; Generator manufacturing/installation has vendor delay and procurement premium. | SIMULATED_NOT_EXTERNAL_EVIDENCE

## ACTUAL_EVIDENCE
Evidence_ID | Cost_Ownership_Line_ID | Project_ID | Activity_ID | Reporting_Month | Evidence_Date | Measurement_Method | Evidence_Type | Incremental_Earned_Pct | Cumulative_Completion_Pct | Accepted_Quantity_Units | Quantity_Basis | Earned_Value_USD | Source
EVID-CL0001-2025-01 | CL0001 | P01 | P01-A1 | 2025-01 | 2025-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 122100.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0002-2025-01 | CL0002 | P01 | P01-A2 | 2025-01 | 2025-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 99900.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0003-2025-01 | CL0003 | P01 | P01-A3 | 2025-01 | 2025-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 35 | 35 |  |  | 63455.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0003-2025-02 | CL0003 | P01 | P01-A3 | 2025-02 | 2025-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 65 | 100 |  |  | 117845.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0004-2025-03 | CL0004 | P01 | P01-A4 | 2025-03 | 2025-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 72 | 72 |  |  | 60606.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0004-2025-04 | CL0004 | P01 | P01-A4 | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 28 | 100 |  |  | 23569.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0005-2025-04 | CL0005 | P01 | P01-A4b | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 84175.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0006-2025-10 | CL0006 | P01 | P01-A12 | 2025-10 | 2025-10-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 168350.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0007-2025-05 | CL0007 | P01 | P01-A7a | 2025-05 | 2025-05-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 80 | 80 |  |  | 55253.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0007-2025-06 | CL0007 | P01 | P01-A7a | 2025-06 | 2025-06-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 100 |  |  | 13813.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0008-2025-03 | CL0008 | P01 | P01-A5 | 2025-03 | 2025-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 20 | 20 |  |  | 13813.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0008-2025-04 | CL0008 | P01 | P01-A5 | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 80 | 100 |  |  | 55253.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0009-2025-04 | CL0009 | P01 | P01-A5b | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 69066.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0010-2025-05 | CL0010 | P01 | P01-A6 | 2025-05 | 2025-05-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 80 | 80 |  |  | 307840.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0010-2025-06 | CL0010 | P01 | P01-A6 | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 20 | 100 |  |  | 76960.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0011-2025-06 | CL0011 | P01 | P01-A7b | 2025-06 | 2025-06-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 50 |  |  | 639360.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0011-2025-07 | CL0011 | P01 | P01-A7b | 2025-07 | 2025-07-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 100 |  |  | 639360.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0012-2025-02 | CL0012 | P01 | P01-A4u | 2025-02 | 2025-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 70 | 70 |  |  | 223776.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0012-2025-03 | CL0012 | P01 | P01-A4u | 2025-03 | 2025-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 30 | 100 |  |  | 95904.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0013-2025-07 | CL0013 | P01 | P01-A7c | 2025-07 | 2025-07-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 100 | 100 |  |  | 1278720.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0014-2025-07 | CL0014 | P01 | P01-A8 | 2025-07 | 2025-07-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 6 | 6 | 6 | SYNTHETIC 100-unit progress index; not a field measurement | 19180.80 | SYNTHETIC_SCENARIO_V1
EVID-CL0014-2025-08 | CL0014 | P01 | P01-A8 | 2025-08 | 2025-08-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 47 | 53 | 53 | SYNTHETIC 100-unit progress index; not a field measurement | 150249.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0014-2025-09 | CL0014 | P01 | P01-A8 | 2025-09 | 2025-09-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 47 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 150249.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0015-2025-11 | CL0015 | P01 | P01-A15 | 2025-11 | 2025-11-30 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 639360.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0016-2025-08 | CL0016 | P01 | P01-A9 | 2025-08 | 2025-08-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 60 | 60 | 60 | SYNTHETIC 100-unit progress index; not a field measurement | 255744.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0016-2025-09 | CL0016 | P01 | P01-A9 | 2025-09 | 2025-09-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 40 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 170496.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0017-2025-08 | CL0017 | P01 | P01-A9b | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 40 |  |  | 170496.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0017-2025-09 | CL0017 | P01 | P01-A9b | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 100 |  |  | 255744.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0018-2025-10 | CL0018 | P01 | P01-A10 | 2025-10 | 2025-10-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 60 | 60 | 60 | SYNTHETIC 100-unit progress index; not a field measurement | 383616.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0018-2025-11 | CL0018 | P01 | P01-A10 | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 40 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 255744.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0019-2025-10 | CL0019 | P01 | P01-A11 | 2025-10 | 2025-10-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 518000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0020-2025-12 | CL0020 | P01 | P01-A13 | 2025-12 | 2025-12-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 144300.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0021-2025-12 | CL0021 | P01 | P01-A14 | 2025-12 | 2025-12-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 77700.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0022-2025-02 | CL0022 | P02 | P02-A1 | 2025-02 | 2025-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 132000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0023-2025-02 | CL0023 | P02 | P02-A2 | 2025-02 | 2025-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 132000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0024-2025-02 | CL0024 | P02 | P02-A3 | 2025-02 | 2025-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 25 | 25 |  |  | 69300.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0024-2025-03 | CL0024 | P02 | P02-A3 | 2025-03 | 2025-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 75 | 100 |  |  | 207900.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0025-2025-03 | CL0025 | P02 | P02-A4 | 2025-03 | 2025-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 24 | 24 |  |  | 61776.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0025-2025-04 | CL0025 | P02 | P02-A4 | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 76 | 100 |  |  | 195624.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0026-2025-04 | CL0026 | P02 | P02-A4b | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 15 | 15 |  |  | 38610.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0026-2025-05 | CL0026 | P02 | P02-A4b | 2025-05 | 2025-05-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 85 | 100 |  |  | 218790.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0027-2025-04 | CL0027 | P02 | P02-A5 | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 86 | 86 |  |  | 92708.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0027-2025-05 | CL0027 | P02 | P02-A5 | 2025-05 | 2025-05-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 14 | 100 |  |  | 15092.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0028-2025-05 | CL0028 | P02 | P02-A5b | 2025-05 | 2025-05-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 107800.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0029-2025-06 | CL0029 | P02 | P02-A6 | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 400400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0030-2025-02 | CL0030 | P02 | P02-A6b | 2025-02 | 2025-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 190080.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0031-2025-06 | CL0031 | P02 | P02-A7a | 2025-06 | 2025-06-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 100 | 100 |  |  | 190080.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0032-2025-06 | CL0032 | P02 | P02-A8 | 2025-06 | 2025-06-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 100 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 190080.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0033-2025-07 | CL0033 | P02 | P02-A7b | 2025-07 | 2025-07-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 20 |  |  | 152064.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0033-2025-08 | CL0033 | P02 | P02-A7b | 2025-08 | 2025-08-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 30 | 50 |  |  | 228096.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0033-2025-10 | CL0033 | P02 | P02-A7b | 2025-10 | 2025-10-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 100 |  |  | 380160.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0034-2025-06 | CL0034 | P02 | P02-A9 | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 6 | 6 |  |  | 11404.80 | SYNTHETIC_SCENARIO_V1
EVID-CL0034-2025-07 | CL0034 | P02 | P02-A9 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 94 | 100 |  |  | 178675.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0035-2025-11 | CL0035 | P02 | P02-A7c | 2025-11 | 2025-11-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 190080.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0036-2025-11 | CL0036 | P02 | P02-A7d | 2025-11 | 2025-11-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 100 | 100 |  |  | 760320.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0037-2025-11 | CL0037 | P02 | P02-A10 | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 8 | 8 | 8 | SYNTHETIC 100-unit progress index; not a field measurement | 15206.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0037-2025-12 | CL0037 | P02 | P02-A10 | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 92 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 174873.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0038-2026-02 | CL0038 | P02 | P02-A15b | 2026-02 | 2026-02-28 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 380160.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0039-2025-06 | CL0039 | P02 | P02-A11a | 2025-06 | 2025-06-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 100 | 100 |  |  | 221760.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0040-2025-02 | CL0040 | P02 | P02-A6c | 2025-02 | 2025-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 221760.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0041-2025-07 | CL0041 | P02 | P02-A11b | 2025-07 | 2025-07-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 20 |  |  | 177408.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0041-2025-08 | CL0041 | P02 | P02-A11b | 2025-08 | 2025-08-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 30 | 50 |  |  | 266112.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0041-2025-09 | CL0041 | P02 | P02-A11b | 2025-09 | 2025-09-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 30 | 80 |  |  | 266112.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0041-2025-10 | CL0041 | P02 | P02-A11b | 2025-10 | 2025-10-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 100 |  |  | 177408.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0042-2025-10 | CL0042 | P02 | P02-A11c | 2025-10 | 2025-10-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 221760.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0043-2025-11 | CL0043 | P02 | P02-A11d | 2025-11 | 2025-11-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 100 | 100 |  |  | 887040.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0044-2025-11 | CL0044 | P02 | P02-A12 | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 60 | 60 | 60 | SYNTHETIC 100-unit progress index; not a field measurement | 133056.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0044-2025-12 | CL0044 | P02 | P02-A12 | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 40 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 88704.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0045-2025-07 | CL0045 | P02 | P02-A13 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 45 | 45 |  |  | 285120.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0045-2025-08 | CL0045 | P02 | P02-A13 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 55 | 100 |  |  | 348480.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0046-2026-01 | CL0046 | P02 | P02-A14 | 2026-01 | 2026-01-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 264000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0047-2026-01 | CL0047 | P02 | P02-A15 | 2026-01 | 2026-01-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 264000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0048-2026-02 | CL0048 | P02 | P02-A16 | 2026-02 | 2026-02-28 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 171600.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0049-2026-02 | CL0049 | P02 | P02-A17 | 2026-02 | 2026-02-28 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 92400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0050-2025-01 | CL0050 | P03 | P03-A1 | 2025-01 | 2025-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 274050.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0051-2025-02 | CL0051 | P03 | P03-A2 | 2025-02 | 2025-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 334950.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0052-2025-03 | CL0052 | P03 | P03-A3 | 2025-03 | 2025-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 52 | 52 |  |  | 152006.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0052-2025-04 | CL0052 | P03 | P03-A3 | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 48 | 100 |  |  | 140313.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0053-2025-04 | CL0053 | P03 | P03-A4 | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 33 | 33 |  |  | 96465.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0053-2025-05 | CL0053 | P03 | P03-A4 | 2025-05 | 2025-05-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 67 | 100 |  |  | 195854.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0054-2025-02 | CL0054 | P03 | P03-A2b | 2025-02 | 2025-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 138040.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0055-2025-05 | CL0055 | P03 | P03-A5 | 2025-05 | 2025-05-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 33 | 33 | 33 | SYNTHETIC 100-unit progress index; not a field measurement | 136659.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0055-2025-06 | CL0055 | P03 | P03-A5 | 2025-06 | 2025-06-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 67 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 277460.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0056-2025-06 | CL0056 | P03 | P03-A6 | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 6 | 6 |  |  | 8282.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0056-2025-07 | CL0056 | P03 | P03-A6 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 94 | 100 |  |  | 129757.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0057-2025-07 | CL0057 | P03 | P03-A7 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 95 | 95 |  |  | 131138.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0057-2025-08 | CL0057 | P03 | P03-A7 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 5 | 100 |  |  | 6902.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0058-2025-07 | CL0058 | P03 | P03-A7b | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 3 | 3 |  |  | 4141.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0058-2025-08 | CL0058 | P03 | P03-A7b | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 70 | 73 |  |  | 96628.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0058-2025-09 | CL0058 | P03 | P03-A7b | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 27 | 100 |  |  | 37270.80 | SYNTHETIC_SCENARIO_V1
EVID-CL0060-2025-07 | CL0060 | P03 | P03-A8 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 45 | 45 |  |  | 111903.75 | SYNTHETIC_SCENARIO_V1
EVID-CL0060-2025-08 | CL0060 | P03 | P03-A8 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 55 | 100 |  |  | 136771.25 | SYNTHETIC_SCENARIO_V1
EVID-CL0061-2025-08 | CL0061 | P03 | P03-A9 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 66 | 66 |  |  | 164125.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0061-2025-09 | CL0061 | P03 | P03-A9 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 34 | 100 |  |  | 84549.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0062-2025-09 | CL0062 | P03 | P03-A9b | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 461825.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0063-2025-09 | CL0063 | P03 | P03-A10 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 20 | 20 |  |  | 92365.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0063-2025-10 | CL0063 | P03 | P03-A10 | 2025-10 | 2025-10-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 80 | 100 |  |  | 369460.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0064-2025-10 | CL0064 | P03 | P03-A11 | 2025-10 | 2025-10-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 100 | 100 |  |  | 434659.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0065-2025-11 | CL0065 | P03 | P03-A12 | 2025-11 | 2025-11-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 20 |  |  | 347727.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0065-2026-01 | CL0065 | P03 | P03-A12 | 2026-01 | 2026-01-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 30 | 50 |  |  | 521590.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0065-2026-02 | CL0065 | P03 | P03-A12 | 2026-02 | 2026-02-28 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 30 | 80 |  |  | 521590.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0065-2026-03 | CL0065 | P03 | P03-A12 | 2026-03 | 2026-03-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 100 |  |  | 347727.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0066-2026-03 | CL0066 | P03 | P03-A13 | 2026-03 | 2026-03-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 50 |  |  | 217329.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0070-2025-10 | CL0070 | P03 | P03-A16 | 2025-10 | 2025-10-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 100 | 100 |  |  | 355250.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0071-2025-11 | CL0071 | P03 | P03-A17 | 2025-11 | 2025-11-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 20 |  |  | 284200.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0071-2025-12 | CL0071 | P03 | P03-A17 | 2025-12 | 2025-12-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 30 | 50 |  |  | 426300.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0071-2026-01 | CL0071 | P03 | P03-A17 | 2026-01 | 2026-01-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 30 | 80 |  |  | 426300.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0071-2026-02 | CL0071 | P03 | P03-A17 | 2026-02 | 2026-02-28 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 100 |  |  | 284200.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0072-2026-02 | CL0072 | P03 | P03-A18 | 2026-02 | 2026-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 355250.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0073-2026-03 | CL0073 | P03 | P03-A19 | 2026-03 | 2026-03-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 100 | 100 |  |  | 1421000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0076-2025-10 | CL0076 | P03 | P03-A21 | 2025-10 | 2025-10-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 100 | 100 |  |  | 153942.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0077-2025-11 | CL0077 | P03 | P03-A22 | 2025-11 | 2025-11-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 50 |  |  | 307883.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0077-2025-12 | CL0077 | P03 | P03-A22 | 2025-12 | 2025-12-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 100 |  |  | 307883.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0078-2026-01 | CL0078 | P03 | P03-A23 | 2026-01 | 2026-01-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 100 | 100 |  |  | 615766.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0085-2025-06 | CL0085 | P04 | P04-A1 | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 82500.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0086-2025-06 | CL0086 | P04 | P04-A2 | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 40 |  |  | 33000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0086-2025-07 | CL0086 | P04 | P04-A2 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 100 |  |  | 49500.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0087-2025-07 | CL0087 | P04 | P04-A3 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 134750.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0088-2025-08 | CL0088 | P04 | P04-A4 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 44 | 44 |  |  | 27527.72 | SYNTHETIC_SCENARIO_V1
EVID-CL0088-2025-09 | CL0088 | P04 | P04-A4 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 56 | 100 |  |  | 35035.28 | SYNTHETIC_SCENARIO_V1
EVID-CL0089-2025-09 | CL0089 | P04 | P04-A4b | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 53 | 53 |  |  | 33157.86 | SYNTHETIC_SCENARIO_V1
EVID-CL0089-2025-10 | CL0089 | P04 | P04-A4b | 2025-10 | 2025-10-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 47 | 100 |  |  | 29404.14 | SYNTHETIC_SCENARIO_V1
EVID-CL0090-2026-03 | CL0090 | P04 | P04-A15 | 2026-03 | 2026-03-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 125125.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0091-2025-08 | CL0091 | P04 | P04-A5 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 6 | 6 |  |  | 4042.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0091-2025-09 | CL0091 | P04 | P04-A5 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 94 | 100 |  |  | 63332.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0092-2025-09 | CL0092 | P04 | P04-A5b | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 60 |  |  | 40425.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0092-2025-10 | CL0092 | P04 | P04-A5b | 2025-10 | 2025-10-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 100 |  |  | 26950.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0093-2025-10 | CL0093 | P04 | P04-A5c | 2025-10 | 2025-10-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 125125.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0094-2025-11 | CL0094 | P04 | P04-A6 | 2025-11 | 2025-11-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 125125.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0095-2025-11 | CL0095 | P04 | P04-A7 | 2025-11 | 2025-11-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 247592.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0096-2025-11 | CL0096 | P04 | P04-A8 | 2025-11 | 2025-11-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 20 | 20 |  |  | 49518.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0096-2025-12 | CL0096 | P04 | P04-A8 | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 80 | 100 |  |  | 198073.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0097-2025-12 | CL0097 | P04 | P04-A9 | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 247592.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0098-2026-01 | CL0098 | P04 | P04-A12 | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 15 | 15 | 15 | SYNTHETIC 100-unit progress index; not a field measurement | 185693.70 | SYNTHETIC_SCENARIO_V1
EVID-CL0098-2026-02 | CL0098 | P04 | P04-A12 | 2026-02 | 2026-02-28 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 85 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 1052264.30 | SYNTHETIC_SCENARIO_V1
EVID-CL0099-2026-02 | CL0099 | P04 | P04-A13 | 2026-02 | 2026-02-28 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 10 | 10 | 10 | SYNTHETIC 100-unit progress index; not a field measurement | 24759.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0099-2026-03 | CL0099 | P04 | P04-A13 | 2026-03 | 2026-03-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 90 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 222832.80 | SYNTHETIC_SCENARIO_V1
EVID-CL0100-2026-03 | CL0100 | P04 | P04-A14 | 2026-03 | 2026-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 247591.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0102-2025-12 | CL0102 | P04 | P04-A10 | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 20 | 20 | 20 | SYNTHETIC 100-unit progress index; not a field measurement | 162800.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0102-2026-01 | CL0102 | P04 | P04-A10 | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 80 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 651200.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0103-2026-01 | CL0103 | P04 | P04-A11 | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 100 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 284900.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0106-2025-03 | CL0106 | P05 | P05-A1 | 2025-03 | 2025-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 66 | 66 |  |  | 63492.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0106-2025-04 | CL0106 | P05 | P05-A1 | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 34 | 100 |  |  | 32708.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0107-2025-09 | CL0107 | P05 | P05-A8 | 2025-09 | 2025-09-30 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 192400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0108-2025-04 | CL0108 | P05 | P05-A2 | 2025-04 | 2025-04-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 100 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 155400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0109-2025-04 | CL0109 | P05 | P05-A3 | 2025-04 | 2025-04-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 46 | 46 | 46 | SYNTHETIC 100-unit progress index; not a field measurement | 91908.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0109-2025-05 | CL0109 | P05 | P05-A3 | 2025-05 | 2025-05-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 54 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 107892.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0110-2025-05 | CL0110 | P05 | P05-A4 | 2025-05 | 2025-05-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 60 |  |  | 93240.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0110-2025-06 | CL0110 | P05 | P05-A4 | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 100 |  |  | 62160.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0111-2025-06 | CL0111 | P05 | P05-A4b | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 155400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0112-2025-07 | CL0112 | P05 | P05-A10 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 20 | 20 |  |  | 31080.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0112-2025-08 | CL0112 | P05 | P05-A10 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 80 | 100 |  |  | 124320.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0113-2025-06 | CL0113 | P05 | P05-A5 | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 116550.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0114-2025-06 | CL0114 | P05 | P05-A5b | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 50 | 50 |  |  | 58275.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0114-2025-07 | CL0114 | P05 | P05-A5b | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 50 | 100 |  |  | 58275.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0115-2025-07 | CL0115 | P05 | P05-A5c | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 72150.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0116-2025-08 | CL0116 | P05 | P05-A11 | 2025-08 | 2025-08-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 80 | 80 |  |  | 230880.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0116-2025-09 | CL0116 | P05 | P05-A11 | 2025-09 | 2025-09-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 100 |  |  | 57720.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0117-2025-07 | CL0117 | P05 | P05-A6 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 20 | 20 |  |  | 14430.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0117-2025-08 | CL0117 | P05 | P05-A6 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 80 | 100 |  |  | 57720.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0118-2025-07 | CL0118 | P05 | P05-A7 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 12 | 12 |  |  | 28869.84 | SYNTHETIC_SCENARIO_V1
EVID-CL0118-2025-08 | CL0118 | P05 | P05-A7 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 53 | 65 |  |  | 127508.46 | SYNTHETIC_SCENARIO_V1
EVID-CL0118-2025-09 | CL0118 | P05 | P05-A7 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 35 | 100 |  |  | 84203.70 | SYNTHETIC_SCENARIO_V1
EVID-CL0119-2025-08 | CL0119 | P05 | P05-A9 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 70 | 70 |  |  | 168407.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0119-2025-09 | CL0119 | P05 | P05-A9 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 30 | 100 |  |  | 72174.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0120-2025-09 | CL0120 | P05 | P05-A12a | 2025-09 | 2025-09-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 29 | 29 | 29 | SYNTHETIC 100-unit progress index; not a field measurement | 348844.19 | SYNTHETIC_SCENARIO_V1
EVID-CL0120-2025-10 | CL0120 | P05 | P05-A12a | 2025-10 | 2025-10-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 41 | 70 | 70 | SYNTHETIC 100-unit progress index; not a field measurement | 493193.51 | SYNTHETIC_SCENARIO_V1
EVID-CL0120-2025-11 | CL0120 | P05 | P05-A12a | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 30 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 360873.30 | SYNTHETIC_SCENARIO_V1
EVID-CL0121-2025-09 | CL0121 | P05 | P05-AFIRST | 2025-09 | 2025-09-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 100 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 721747.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0122-2025-10 | CL0122 | P05 | P05-A13a | 2025-10 | 2025-10-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 34 | 34 | 34 | SYNTHETIC 100-unit progress index; not a field measurement | 408989.74 | SYNTHETIC_SCENARIO_V1
EVID-CL0122-2025-11 | CL0122 | P05 | P05-A13a | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 36 | 70 | 70 | SYNTHETIC 100-unit progress index; not a field measurement | 433047.96 | SYNTHETIC_SCENARIO_V1
EVID-CL0122-2025-12 | CL0122 | P05 | P05-A13a | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 30 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 360873.30 | SYNTHETIC_SCENARIO_V1
EVID-CL0123-2025-11 | CL0123 | P05 | P05-A14a | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 34 | 34 | 34 | SYNTHETIC 100-unit progress index; not a field measurement | 408989.74 | SYNTHETIC_SCENARIO_V1
EVID-CL0123-2025-12 | CL0123 | P05 | P05-A14a | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 42 | 76 | 76 | SYNTHETIC 100-unit progress index; not a field measurement | 505222.62 | SYNTHETIC_SCENARIO_V1
EVID-CL0123-2026-01 | CL0123 | P05 | P05-A14a | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 24 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 288698.64 | SYNTHETIC_SCENARIO_V1
EVID-CL0124-2025-12 | CL0124 | P05 | P05-A15a | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 40 | 40 | 40 | SYNTHETIC 100-unit progress index; not a field measurement | 481164.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0124-2026-01 | CL0124 | P05 | P05-A15a | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 40 | 80 | 80 | SYNTHETIC 100-unit progress index; not a field measurement | 481164.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0124-2026-02 | CL0124 | P05 | P05-A15a | 2026-02 | 2026-02-28 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 20 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 240582.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0126-2025-09 | CL0126 | P05 | P05-A12b | 2025-09 | 2025-09-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 1 | 1 | 1 | SYNTHETIC 100-unit progress index; not a field measurement | 3796.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0126-2025-10 | CL0126 | P05 | P05-A12b | 2025-10 | 2025-10-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 42 | 43 | 43 | SYNTHETIC 100-unit progress index; not a field measurement | 159440.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0126-2025-11 | CL0126 | P05 | P05-A12b | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 37 | 80 | 80 | SYNTHETIC 100-unit progress index; not a field measurement | 140459.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0126-2025-12 | CL0126 | P05 | P05-A12b | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 20 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 75924.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0127-2025-10 | CL0127 | P05 | P05-A13b | 2025-10 | 2025-10-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 7 | 7 | 7 | SYNTHETIC 100-unit progress index; not a field measurement | 26573.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0127-2025-11 | CL0127 | P05 | P05-A13b | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 36 | 43 | 43 | SYNTHETIC 100-unit progress index; not a field measurement | 136663.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0127-2025-12 | CL0127 | P05 | P05-A13b | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 42 | 85 | 85 | SYNTHETIC 100-unit progress index; not a field measurement | 159440.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0127-2026-01 | CL0127 | P05 | P05-A13b | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 15 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 56943.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0128-2025-11 | CL0128 | P05 | P05-A14b | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 7 | 7 | 7 | SYNTHETIC 100-unit progress index; not a field measurement | 26573.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0128-2025-12 | CL0128 | P05 | P05-A14b | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 42 | 49 | 49 | SYNTHETIC 100-unit progress index; not a field measurement | 159440.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0128-2026-01 | CL0128 | P05 | P05-A14b | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 40 | 89 | 89 | SYNTHETIC 100-unit progress index; not a field measurement | 151848.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0128-2026-02 | CL0128 | P05 | P05-A14b | 2026-02 | 2026-02-28 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 11 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 41758.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0129-2025-12 | CL0129 | P05 | P05-A15b | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 12 | 12 | 12 | SYNTHETIC 100-unit progress index; not a field measurement | 45554.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0129-2026-01 | CL0129 | P05 | P05-A15b | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 40 | 52 | 52 | SYNTHETIC 100-unit progress index; not a field measurement | 151848.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0129-2026-02 | CL0129 | P05 | P05-A15b | 2026-02 | 2026-02-28 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 37 | 89 | 89 | SYNTHETIC 100-unit progress index; not a field measurement | 140459.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0129-2026-03 | CL0129 | P05 | P05-A15b | 2026-03 | 2026-03-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 11 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 41758.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0130-2026-01 | CL0130 | P05 | P05-A12c | 2026-01 | 2026-01-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 138750.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0131-2026-02 | CL0131 | P05 | P05-A13c | 2026-02 | 2026-02-28 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 138750.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0132-2026-02 | CL0132 | P05 | P05-A14c | 2026-02 | 2026-02-28 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 138750.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0133-2026-03 | CL0133 | P05 | P05-A15c | 2026-03 | 2026-03-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 138750.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0136-2025-08 | CL0136 | P06 | P06-A1 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 86 | 86 |  |  | 65274.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0136-2025-09 | CL0136 | P06 | P06-A1 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 14 | 100 |  |  | 10626.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0137-2025-12 | CL0137 | P06 | P06-A10 | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 40 |  |  | 30360.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0137-2026-01 | CL0137 | P06 | P06-A10 | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 100 |  |  | 45540.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0138-2025-09 | CL0138 | P06 | P06-A2 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 124200.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0139-2025-09 | CL0139 | P06 | P06-A3 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 50 | 50 |  |  | 132825.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0139-2025-10 | CL0139 | P06 | P06-A3 | 2025-10 | 2025-10-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 50 | 100 |  |  | 132825.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0140-2025-10 | CL0140 | P06 | P06-A4 | 2025-10 | 2025-10-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 40 |  |  | 49335.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0140-2025-11 | CL0140 | P06 | P06-A4 | 2025-11 | 2025-11-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 100 |  |  | 74002.80 | SYNTHETIC_SCENARIO_V1
EVID-CL0141-2025-11 | CL0141 | P06 | P06-A4b | 2025-11 | 2025-11-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 80 | 80 |  |  | 98670.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0141-2025-12 | CL0141 | P06 | P06-A4b | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 20 | 100 |  |  | 24667.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0142-2025-12 | CL0142 | P06 | P06-A7 | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 30 | 30 |  |  | 37001.10 | SYNTHETIC_SCENARIO_V1
EVID-CL0142-2026-01 | CL0142 | P06 | P06-A7 | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 70 | 100 |  |  | 86335.90 | SYNTHETIC_SCENARIO_V1
EVID-CL0143-2025-12 | CL0143 | P06 | P06-A8 | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 40 |  |  | 49334.80 | SYNTHETIC_SCENARIO_V1
EVID-CL0143-2026-01 | CL0143 | P06 | P06-A8 | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 100 |  |  | 74002.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0144-2025-11 | CL0144 | P06 | P06-A5 | 2025-11 | 2025-11-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 89700.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0145-2025-11 | CL0145 | P06 | P06-A5b | 2025-11 | 2025-11-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 30 | 30 |  |  | 26910.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0145-2025-12 | CL0145 | P06 | P06-A5b | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 70 | 100 |  |  | 62790.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0146-2025-12 | CL0146 | P06 | P06-A11 | 2025-12 | 2025-12-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 20 |  |  | 17940.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0146-2026-01 | CL0146 | P06 | P06-A11 | 2026-01 | 2026-01-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 80 | 100 |  |  | 71760.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0147-2025-12 | CL0147 | P06 | P06-A5c | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 89700.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0148-2025-12 | CL0148 | P06 | P06-A6 | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 60 |  |  | 53820.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0148-2026-01 | CL0148 | P06 | P06-A6 | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 100 |  |  | 35880.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0149-2026-01 | CL0149 | P06 | P06-A12 | 2026-01 | 2026-01-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 20 |  |  | 71760.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0149-2026-02 | CL0149 | P06 | P06-A12 | 2026-02 | 2026-02-28 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 30 | 50 |  |  | 107640.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0149-2026-03 | CL0149 | P06 | P06-A12 | 2026-03 | 2026-03-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 30 | 80 |  |  | 107640.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0151-2025-12 | CL0151 | P06 | P06-A15 | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 40 | 40 | 40 | SYNTHETIC 100-unit progress index; not a field measurement | 136378.80 | SYNTHETIC_SCENARIO_V1
EVID-CL0151-2026-01 | CL0151 | P06 | P06-A15 | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 60 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 204568.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0160-2026-01 | CL0160 | P06 | P06-A9 | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 26 | 26 | 26 | SYNTHETIC 100-unit progress index; not a field measurement | 166707.58 | SYNTHETIC_SCENARIO_V1
EVID-CL0160-2026-02 | CL0160 | P06 | P06-A9 | 2026-02 | 2026-02-28 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 67 | 93 | 93 | SYNTHETIC 100-unit progress index; not a field measurement | 429592.61 | SYNTHETIC_SCENARIO_V1
EVID-CL0160-2026-03 | CL0160 | P06 | P06-A9 | 2026-03 | 2026-03-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 7 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 44882.81 | SYNTHETIC_SCENARIO_V1
EVID-CL0161-2026-03 | CL0161 | P06 | P06-A14 | 2026-03 | 2026-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 90 | 90 |  |  | 192354.30 | SYNTHETIC_SCENARIO_V1
EVID-CL0171-2025-09 | CL0171 | P07 | P07-A1 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 20 | 20 |  |  | 12300.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0171-2025-10 | CL0171 | P07 | P07-A1 | 2025-10 | 2025-10-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 80 | 100 |  |  | 49200.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0172-2025-10 | CL0172 | P07 | P07-A2 | 2025-10 | 2025-10-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 61500.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0173-2025-10 | CL0173 | P07 | P07-A3 | 2025-10 | 2025-10-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 5 | 5 |  |  | 6457.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0173-2025-11 | CL0173 | P07 | P07-A3 | 2025-11 | 2025-11-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 95 | 100 |  |  | 122692.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0174-2025-12 | CL0174 | P07 | P07-A4 | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 95 | 95 |  |  | 113928.75 | SYNTHETIC_SCENARIO_V1
EVID-CL0174-2026-01 | CL0174 | P07 | P07-A4 | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 5 | 100 |  |  | 5996.25 | SYNTHETIC_SCENARIO_V1
EVID-CL0175-2025-12 | CL0175 | P07 | P07-A4b | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 6 | 6 |  |  | 7195.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0175-2026-01 | CL0175 | P07 | P07-A4b | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 94 | 100 |  |  | 112729.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0176-2025-12 | CL0176 | P07 | P07-A5 | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 60 |  |  | 28700.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0176-2026-01 | CL0176 | P07 | P07-A5 | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 100 |  |  | 19133.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0177-2026-01 | CL0177 | P07 | P07-A5b | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 47833.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0178-2026-02 | CL0178 | P07 | P07-A8 | 2026-02 | 2026-02-28 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 20 |  |  | 9566.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0178-2026-03 | CL0178 | P07 | P07-A8 | 2026-03 | 2026-03-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 80 | 100 |  |  | 38266.40 | SYNTHETIC_SCENARIO_V1
EVID-CL0179-2026-01 | CL0179 | P07 | P07-A5c | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 60 |  |  | 79950.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0179-2026-02 | CL0179 | P07 | P07-A5c | 2026-02 | 2026-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 100 |  |  | 53300.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0180-2026-02 | CL0180 | P07 | P07-A6 | 2026-02 | 2026-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 60 |  |  | 79950.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0180-2026-03 | CL0180 | P07 | P07-A6 | 2026-03 | 2026-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 100 |  |  | 53300.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0181-2026-02 | CL0181 | P07 | P07-A7 | 2026-02 | 2026-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 60 | 60 |  |  | 267648.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0181-2026-03 | CL0181 | P07 | P07-A7 | 2026-03 | 2026-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 40 | 100 |  |  | 178432.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0182-2026-03 | CL0182 | P07 | P07-A10 | 2026-03 | 2026-03-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 100 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 446080.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0185-2026-03 | CL0185 | P07 | P07-A9 | 2026-03 | 2026-03-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 50 |  |  | 41820.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0192-2025-12 | CL0192 | P08 | P08-A1 | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 86 | 86 |  |  | 53406.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0192-2026-01 | CL0192 | P08 | P08-A1 | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 14 | 100 |  |  | 8694.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0193-2026-01 | CL0193 | P08 | P08-A2 | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 75900.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0194-2026-01 | CL0194 | P08 | P08-A3 | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 50 | 50 |  |  | 64400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0194-2026-02 | CL0194 | P08 | P08-A3 | 2026-02 | 2026-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 50 | 100 |  |  | 64400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0195-2026-02 | CL0195 | P08 | P08-A4 | 2026-02 | 2026-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 25 | 25 |  |  | 29900.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0195-2026-03 | CL0195 | P08 | P08-A4 | 2026-03 | 2026-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 75 | 100 |  |  | 89700.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0196-2026-03 | CL0196 | P08 | P08-A4b | 2026-03 | 2026-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 46 | 46 |  |  | 55016.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0197-2026-03 | CL0197 | P08 | P08-A5 | 2026-03 | 2026-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 58880.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0198-2026-03 | CL0198 | P08 | P08-A5b | 2026-03 | 2026-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 20 | 20 |  |  | 11776.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0202-2026-02 | CL0202 | P08 | P08-A7 | 2026-02 | 2026-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 102290.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0220-2026-02 | CL0220 | P09 | P09-A1 | 2026-02 | 2026-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 117000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0221-2026-02 | CL0221 | P09 | P09-A2 | 2026-02 | 2026-02-28 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 30 | 30 | 30 | SYNTHETIC 100-unit progress index; not a field measurement | 35100.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0221-2026-03 | CL0221 | P09 | P09-A2 | 2026-03 | 2026-03-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 70 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 81900.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0222-2026-03 | CL0222 | P09 | P09-A3a | 2026-03 | 2026-03-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 65 | 65 |  |  | 81120.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0279-2025-04 | CL0279 | P11 | P11-A1 | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 76800.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0280-2025-04 | CL0280 | P11 | P11-A2 | 2025-04 | 2025-04-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 70 | 70 |  |  | 35840.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0280-2025-05 | CL0280 | P11 | P11-A2 | 2025-05 | 2025-05-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 30 | 100 |  |  | 15360.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0281-2025-05 | CL0281 | P11 | P11-A3 | 2025-05 | 2025-05-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 57600.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0282-2025-06 | CL0282 | P11 | P11-A4 | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 67200.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0283-2025-08 | CL0283 | P11 | P11-A8 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 67200.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0284-2025-06 | CL0284 | P11 | P11-A5 | 2025-06 | 2025-06-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 66 | 66 |  |  | 33264.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0284-2025-07 | CL0284 | P11 | P11-A5 | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 34 | 100 |  |  | 17136.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0285-2025-07 | CL0285 | P11 | P11-A5b | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 50400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0286-2025-07 | CL0286 | P11 | P11-A5c | 2025-07 | 2025-07-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 80 | 80 |  |  | 74880.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0286-2025-08 | CL0286 | P11 | P11-A5c | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 20 | 100 |  |  | 18720.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0287-2025-08 | CL0287 | P11 | P11-A6 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 93600.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0288-2025-08 | CL0288 | P11 | P11-A10 | 2025-08 | 2025-08-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 93 | 93 |  |  | 89114.46 | SYNTHETIC_SCENARIO_V1
EVID-CL0288-2025-09 | CL0288 | P11 | P11-A10 | 2025-09 | 2025-09-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 7 | 100 |  |  | 6707.54 | SYNTHETIC_SCENARIO_V1
EVID-CL0289-2025-08 | CL0289 | P11 | P11-A9 | 2025-08 | 2025-08-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 50 |  |  | 191644.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0289-2025-09 | CL0289 | P11 | P11-A9 | 2025-09 | 2025-09-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 100 |  |  | 191644.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0290-2025-09 | CL0290 | P11 | P11-AFIRST | 2025-09 | 2025-09-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 100 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 287467.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0291-2025-09 | CL0291 | P11 | P11-B1inst | 2025-09 | 2025-09-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 27 | 27 | 27 | SYNTHETIC 100-unit progress index; not a field measurement | 129359.97 | SYNTHETIC_SCENARIO_V1
EVID-CL0291-2025-10 | CL0291 | P11 | P11-B1inst | 2025-10 | 2025-10-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 58 | 85 | 85 | SYNTHETIC 100-unit progress index; not a field measurement | 277884.38 | SYNTHETIC_SCENARIO_V1
EVID-CL0291-2025-11 | CL0291 | P11 | P11-B1inst | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 15 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 71866.65 | SYNTHETIC_SCENARIO_V1
EVID-CL0292-2025-10 | CL0292 | P11 | P11-B2inst | 2025-10 | 2025-10-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 22 | 22 | 22 | SYNTHETIC 100-unit progress index; not a field measurement | 105404.42 | SYNTHETIC_SCENARIO_V1
EVID-CL0292-2025-11 | CL0292 | P11 | P11-B2inst | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 50 | 72 | 72 | SYNTHETIC 100-unit progress index; not a field measurement | 239555.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0292-2025-12 | CL0292 | P11 | P11-B2inst | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 28 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 134151.08 | SYNTHETIC_SCENARIO_V1
EVID-CL0293-2025-10 | CL0293 | P11 | P11-B1rest | 2025-10 | 2025-10-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 35 | 35 | 35 | SYNTHETIC 100-unit progress index; not a field measurement | 58800.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0293-2025-11 | CL0293 | P11 | P11-B1rest | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 50 | 85 | 85 | SYNTHETIC 100-unit progress index; not a field measurement | 84000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0293-2025-12 | CL0293 | P11 | P11-B1rest | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 15 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 25200.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0294-2025-11 | CL0294 | P11 | P11-B2rest | 2025-11 | 2025-11-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 22 | 22 | 22 | SYNTHETIC 100-unit progress index; not a field measurement | 36960.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0294-2025-12 | CL0294 | P11 | P11-B2rest | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 58 | 80 | 80 | SYNTHETIC 100-unit progress index; not a field measurement | 97440.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0294-2026-01 | CL0294 | P11 | P11-B2rest | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 20 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 33600.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0295-2025-09 | CL0295 | P11 | P11-A7 | 2025-09 | 2025-09-30 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 64000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0296-2025-11 | CL0296 | P11 | P11-B1test | 2025-11 | 2025-11-30 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 64000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0297-2025-12 | CL0297 | P11 | P11-B2test | 2025-12 | 2025-12-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 64000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0298-2026-02 | CL0298 | P11 | P11-A11 | 2026-02 | 2026-02-28 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 64000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0299-2025-12 | CL0299 | P11 | P11-B1gis | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 22400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0300-2026-01 | CL0300 | P11 | P11-B2gis | 2026-01 | 2026-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 22400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0301-2026-02 | CL0301 | P11 | P11-A12 | 2026-02 | 2026-02-28 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 22400.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0302-2026-03 | CL0302 | P11 | P11-A13 | 2026-03 | 2026-03-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 28800.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0303-2025-01 | CL0303 | P12 | P12-Y1A1 | 2025-01 | 2025-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 28560.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0304-2025-01 | CL0304 | P12 | P12-Y1A2 | 2025-01 | 2025-01-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 10 | 10 |  |  | 2856.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0304-2025-02 | CL0304 | P12 | P12-Y1A2 | 2025-02 | 2025-02-28 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 90 | 100 |  |  | 25704.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0305-2025-11 | CL0305 | P12 | P12-Y2A1 | 2025-11 | 2025-11-30 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 36720.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0306-2025-12 | CL0306 | P12 | P12-Y2A2 | 2025-12 | 2025-12-31 | WORKDAY_SPREAD | SYNTHETIC_ENGINEER_PROGRESS_ASSESSMENT | 100 | 100 |  |  | 36720.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0309-2025-02 | CL0309 | P12 | P12-Y1A3 | 2025-02 | 2025-02-28 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 10 | 10 | 10 | SYNTHETIC 100-unit progress index; not a field measurement | 4284.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0309-2025-03 | CL0309 | P12 | P12-Y1A3 | 2025-03 | 2025-03-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 90 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 38556.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0310-2025-03 | CL0310 | P12 | P12-Y1A4 | 2025-03 | 2025-03-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 20 | 20 | 20 | SYNTHETIC 100-unit progress index; not a field measurement | 8568.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0310-2025-04 | CL0310 | P12 | P12-Y1A4 | 2025-04 | 2025-04-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 80 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 34272.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0311-2025-12 | CL0311 | P12 | P12-Y2A3 | 2025-12 | 2025-12-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 25 | 25 | 25 | SYNTHETIC 100-unit progress index; not a field measurement | 13770.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0311-2026-01 | CL0311 | P12 | P12-Y2A3 | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 75 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 41310.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0312-2026-01 | CL0312 | P12 | P12-Y2A4 | 2026-01 | 2026-01-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 46 | 46 | 46 | SYNTHETIC 100-unit progress index; not a field measurement | 25336.80 | SYNTHETIC_SCENARIO_V1
EVID-CL0312-2026-02 | CL0312 | P12 | P12-Y2A4 | 2026-02 | 2026-02-28 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 54 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 29743.20 | SYNTHETIC_SCENARIO_V1
EVID-CL0315-2025-04 | CL0315 | P12 | P12-Y1A5 | 2025-04 | 2025-04-30 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 20 | 20 |  |  | 22848.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0315-2025-05 | CL0315 | P12 | P12-Y1A5 | 2025-05 | 2025-05-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 80 | 100 |  |  | 91392.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0316-2026-02 | CL0316 | P12 | P12-Y2A5 | 2026-02 | 2026-02-28 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 50 |  |  | 73440.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0316-2026-03 | CL0316 | P12 | P12-Y2A5 | 2026-03 | 2026-03-31 | PROCUREMENT_20_30_30_20 | SYNTHETIC_PROCUREMENT_STAGE_LOG | 50 | 100 |  |  | 73440.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0318-2025-05 | CL0318 | P12 | P12-Y1A6 | 2025-05 | 2025-05-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 7 | 7 | 7 | SYNTHETIC 100-unit progress index; not a field measurement | 66093.58 | SYNTHETIC_SCENARIO_V1
EVID-CL0318-2025-06 | CL0318 | P12 | P12-Y1A6 | 2025-06 | 2025-06-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 24 | 31 | 31 | SYNTHETIC 100-unit progress index; not a field measurement | 226606.56 | SYNTHETIC_SCENARIO_V1
EVID-CL0318-2025-07 | CL0318 | P12 | P12-Y1A6 | 2025-07 | 2025-07-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 25 | 56 | 56 | SYNTHETIC 100-unit progress index; not a field measurement | 236048.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0318-2025-08 | CL0318 | P12 | P12-Y1A6 | 2025-08 | 2025-08-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 24 | 80 | 80 | SYNTHETIC 100-unit progress index; not a field measurement | 226606.56 | SYNTHETIC_SCENARIO_V1
EVID-CL0318-2025-09 | CL0318 | P12 | P12-Y1A6 | 2025-09 | 2025-09-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 20 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 188838.80 | SYNTHETIC_SCENARIO_V1
EVID-CL0319-2026-03 | CL0319 | P12 | P12-Y2A6 | 2026-03 | 2026-03-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 10 | 10 | 10 | SYNTHETIC 100-unit progress index; not a field measurement | 121396.30 | SYNTHETIC_SCENARIO_V1
EVID-CL0321-2025-10 | CL0321 | P12 | P12-Y1A7 | 2025-10 | 2025-10-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 57120.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0324-2025-11 | CL0324 | P12 | P12-Y1A8 | 2025-11 | 2025-11-30 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 28560.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0330-2026-01 | CL0330 | P05 | P05-A12c | 2026-01 | 2026-01-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 105450.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0331-2026-02 | CL0331 | P05 | P05-A13c | 2026-02 | 2026-02-28 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 105450.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0332-2026-03 | CL0332 | P05 | P05-A14c | 2026-03 | 2026-03-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 105450.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0333-2026-03 | CL0333 | P05 | P05-A15c | 2026-03 | 2026-03-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 105450.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0335-2025-12 | CL0335 | P11 | P11-B1gis | 2025-12 | 2025-12-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 89600.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0336-2026-01 | CL0336 | P11 | P11-B2gis | 2026-01 | 2026-01-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 89600.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0337-2025-05 | CL0337 | P12 | P12-Y1A6 | 2025-05 | 2025-05-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 10 | 10 | 10 | SYNTHETIC 100-unit progress index; not a field measurement | 14108.60 | SYNTHETIC_SCENARIO_V1
EVID-CL0337-2025-06 | CL0337 | P12 | P12-Y1A6 | 2025-06 | 2025-06-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 23 | 33 | 33 | SYNTHETIC 100-unit progress index; not a field measurement | 32449.78 | SYNTHETIC_SCENARIO_V1
EVID-CL0337-2025-07 | CL0337 | P12 | P12-Y1A6 | 2025-07 | 2025-07-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 25 | 58 | 58 | SYNTHETIC 100-unit progress index; not a field measurement | 35271.50 | SYNTHETIC_SCENARIO_V1
EVID-CL0337-2025-08 | CL0337 | P12 | P12-Y1A6 | 2025-08 | 2025-08-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 24 | 82 | 82 | SYNTHETIC 100-unit progress index; not a field measurement | 33860.64 | SYNTHETIC_SCENARIO_V1
EVID-CL0337-2025-09 | CL0337 | P12 | P12-Y1A6 | 2025-09 | 2025-09-30 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 18 | 100 | 100 | SYNTHETIC 100-unit progress index; not a field measurement | 25395.48 | SYNTHETIC_SCENARIO_V1
EVID-CL0338-2026-03 | CL0338 | P12 | P12-Y2A6 | 2026-03 | 2026-03-31 | WORKDAY_FALLBACK | SYNTHETIC_QUANTITY_ACCEPTANCE_100_UNITS | 12 | 12 | 12 | SYNTHETIC 100-unit progress index; not a field measurement | 21767.64 | SYNTHETIC_SCENARIO_V1
EVID-CL0340-2026-03 | CL0340 | P04 | P04-A14 | 2026-03 | 2026-03-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 132000.00 | SYNTHETIC_SCENARIO_V1
EVID-CL0341-2026-03 | CL0341 | P04 | P04-A15 | 2026-03 | 2026-03-31 | FINAL_GATE | SYNTHETIC_ACCEPTANCE_RECORD | 100 | 100 |  |  | 198000.00 | SYNTHETIC_SCENARIO_V1

## ACTUAL_COST_LEDGER
Cost_Entry_ID | Cost_Ownership_Line_ID | Project_ID | Activity_ID | Incurred_Date | Reporting_Month | Cost_Category | Incurred_Cost_USD | Transaction_Description | Source
AC-CL0001-2025-01 | CL0001 | P01 | P01-A1 | 2025-01-31 | 2025-01 | ENGINEERING_OR_FIELD | 122100.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0002-2025-01 | CL0002 | P01 | P01-A2 | 2025-01-31 | 2025-01 | ENGINEERING_OR_FIELD | 99900.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0003-2025-01 | CL0003 | P01 | P01-A3 | 2025-01-31 | 2025-01 | ENGINEERING_OR_FIELD | 63455.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0003-2025-02 | CL0003 | P01 | P01-A3 | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 117845.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0004-2025-03 | CL0004 | P01 | P01-A4 | 2025-03-31 | 2025-03 | ENGINEERING_OR_FIELD | 60606.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0004-2025-04 | CL0004 | P01 | P01-A4 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 23569.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0005-2025-04 | CL0005 | P01 | P01-A4b | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 84175.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0006-2025-10 | CL0006 | P01 | P01-A12 | 2025-10-31 | 2025-10 | TESTING_ACCEPTANCE | 168350.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0007-2025-05 | CL0007 | P01 | P01-A7a | 2025-05-31 | 2025-05 | PROCUREMENT | 56634.94 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0007-2025-06 | CL0007 | P01 | P01-A7a | 2025-06-30 | 2025-06 | PROCUREMENT | 13813.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0008-2025-03 | CL0008 | P01 | P01-A5 | 2025-03-31 | 2025-03 | ENGINEERING_OR_FIELD | 13813.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0008-2025-04 | CL0008 | P01 | P01-A5 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 55253.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0009-2025-04 | CL0009 | P01 | P01-A5b | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 69066.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0010-2025-05 | CL0010 | P01 | P01-A6 | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 307840.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0010-2025-06 | CL0010 | P01 | P01-A6 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 76960.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0011-2025-06 | CL0011 | P01 | P01-A7b | 2025-06-30 | 2025-06 | PROCUREMENT | 664934.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0011-2025-07 | CL0011 | P01 | P01-A7b | 2025-07-31 | 2025-07 | PROCUREMENT | 639360.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0012-2025-02 | CL0012 | P01 | P01-A4u | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 223776.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0012-2025-03 | CL0012 | P01 | P01-A4u | 2025-03-31 | 2025-03 | ENGINEERING_OR_FIELD | 95904.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0013-2025-07 | CL0013 | P01 | P01-A7c | 2025-07-31 | 2025-07 | PROCUREMENT | 1304294.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0014-2025-07 | CL0014 | P01 | P01-A8 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 19180.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0014-2025-08 | CL0014 | P01 | P01-A8 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 150249.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0014-2025-09 | CL0014 | P01 | P01-A8 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 150249.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0015-2025-11 | CL0015 | P01 | P01-A15 | 2025-11-30 | 2025-11 | TESTING_ACCEPTANCE | 639360.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0016-2025-08 | CL0016 | P01 | P01-A9 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 255744.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0016-2025-09 | CL0016 | P01 | P01-A9 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 170496.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0017-2025-08 | CL0017 | P01 | P01-A9b | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 170496.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0017-2025-09 | CL0017 | P01 | P01-A9b | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 255744.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0018-2025-10 | CL0018 | P01 | P01-A10 | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 383616.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0018-2025-11 | CL0018 | P01 | P01-A10 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 255744.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0019-2025-10 | CL0019 | P01 | P01-A11 | 2025-10-31 | 2025-10 | TESTING_ACCEPTANCE | 518000.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0020-2025-12 | CL0020 | P01 | P01-A13 | 2025-12-31 | 2025-12 | TESTING_ACCEPTANCE | 144300.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0021-2025-12 | CL0021 | P01 | P01-A14 | 2025-12-31 | 2025-12 | TESTING_ACCEPTANCE | 77700.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0022-2025-02 | CL0022 | P02 | P02-A1 | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 145200.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0023-2025-02 | CL0023 | P02 | P02-A2 | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 145200.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0024-2025-02 | CL0024 | P02 | P02-A3 | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 76230.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0024-2025-03 | CL0024 | P02 | P02-A3 | 2025-03-31 | 2025-03 | ENGINEERING_OR_FIELD | 228690.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0025-2025-03 | CL0025 | P02 | P02-A4 | 2025-03-31 | 2025-03 | ENGINEERING_OR_FIELD | 67953.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0025-2025-04 | CL0025 | P02 | P02-A4 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 215186.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0026-2025-04 | CL0026 | P02 | P02-A4b | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 42471.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0026-2025-05 | CL0026 | P02 | P02-A4b | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 240669.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0027-2025-04 | CL0027 | P02 | P02-A5 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 101978.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0027-2025-05 | CL0027 | P02 | P02-A5 | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 16601.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0028-2025-05 | CL0028 | P02 | P02-A5b | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 118580.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0029-2025-06 | CL0029 | P02 | P02-A6 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 440440.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0030-2025-02 | CL0030 | P02 | P02-A6b | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 209088.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0031-2025-06 | CL0031 | P02 | P02-A7a | 2025-06-30 | 2025-06 | PROCUREMENT | 212889.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0032-2025-06 | CL0032 | P02 | P02-A8 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 209088.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0033-2025-06 | CL0033 | P02 | P02-A7b | 2025-06-30 | 2025-06 | PROCUREMENT | 15206.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0033-2025-07 | CL0033 | P02 | P02-A7b | 2025-07-31 | 2025-07 | PROCUREMENT | 167270.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0033-2025-08 | CL0033 | P02 | P02-A7b | 2025-08-31 | 2025-08 | PROCUREMENT | 250905.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0033-2025-10 | CL0033 | P02 | P02-A7b | 2025-10-31 | 2025-10 | PROCUREMENT | 418176.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0034-2025-06 | CL0034 | P02 | P02-A9 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 12545.28 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0034-2025-07 | CL0034 | P02 | P02-A9 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 196542.72 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0035-2025-11 | CL0035 | P02 | P02-A7c | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 209088.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0036-2025-11 | CL0036 | P02 | P02-A7d | 2025-11-30 | 2025-11 | PROCUREMENT | 851558.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0037-2025-11 | CL0037 | P02 | P02-A10 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 16727.04 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0037-2025-12 | CL0037 | P02 | P02-A10 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 192360.96 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0038-2026-02 | CL0038 | P02 | P02-A15b | 2026-02-28 | 2026-02 | TESTING_ACCEPTANCE | 418176.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0039-2025-06 | CL0039 | P02 | P02-A11a | 2025-06-30 | 2025-06 | PROCUREMENT | 248371.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0040-2025-02 | CL0040 | P02 | P02-A6c | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 243936.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0041-2025-06 | CL0041 | P02 | P02-A11b | 2025-06-30 | 2025-06 | PROCUREMENT | 17740.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0041-2025-07 | CL0041 | P02 | P02-A11b | 2025-07-31 | 2025-07 | PROCUREMENT | 195148.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0041-2025-08 | CL0041 | P02 | P02-A11b | 2025-08-31 | 2025-08 | PROCUREMENT | 292723.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0041-2025-09 | CL0041 | P02 | P02-A11b | 2025-09-30 | 2025-09 | PROCUREMENT | 292723.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0041-2025-10 | CL0041 | P02 | P02-A11b | 2025-10-31 | 2025-10 | PROCUREMENT | 195148.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0042-2025-10 | CL0042 | P02 | P02-A11c | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 243936.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0043-2025-11 | CL0043 | P02 | P02-A11d | 2025-11-30 | 2025-11 | PROCUREMENT | 993484.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0044-2025-11 | CL0044 | P02 | P02-A12 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 146361.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0044-2025-12 | CL0044 | P02 | P02-A12 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 97574.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0045-2025-07 | CL0045 | P02 | P02-A13 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 313632.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0045-2025-08 | CL0045 | P02 | P02-A13 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 383328.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0046-2026-01 | CL0046 | P02 | P02-A14 | 2026-01-31 | 2026-01 | TESTING_ACCEPTANCE | 290400.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0047-2026-01 | CL0047 | P02 | P02-A15 | 2026-01-31 | 2026-01 | TESTING_ACCEPTANCE | 290400.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0048-2026-02 | CL0048 | P02 | P02-A16 | 2026-02-28 | 2026-02 | TESTING_ACCEPTANCE | 188760.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0049-2026-02 | CL0049 | P02 | P02-A17 | 2026-02-28 | 2026-02 | TESTING_ACCEPTANCE | 101640.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0050-2025-01 | CL0050 | P03 | P03-A1 | 2025-01-31 | 2025-01 | ENGINEERING_OR_FIELD | 295974.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0050-2025-02 | CL0050 | P03 | P03-A1 | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 8221.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0051-2025-02 | CL0051 | P03 | P03-A2 | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 361746.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0051-2025-03 | CL0051 | P03 | P03-A2 | 2025-03-31 | 2025-03 | ENGINEERING_OR_FIELD | 10048.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0052-2025-03 | CL0052 | P03 | P03-A3 | 2025-03-31 | 2025-03 | ENGINEERING_OR_FIELD | 168727.10 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0052-2025-04 | CL0052 | P03 | P03-A3 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 146978.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0052-2025-11 | CL0052 | P03 | P03-A3 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 8769.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0053-2025-04 | CL0053 | P03 | P03-A4 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 104182.84 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0053-2025-05 | CL0053 | P03 | P03-A4 | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 211522.76 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0053-2025-06 | CL0053 | P03 | P03-A4 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 8769.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0054-2025-02 | CL0054 | P03 | P03-A2b | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 149083.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0054-2025-10 | CL0054 | P03 | P03-A2b | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 4141.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0055-2025-05 | CL0055 | P03 | P03-A5 | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 147592.36 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0055-2025-06 | CL0055 | P03 | P03-A5 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 312080.84 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0056-2025-06 | CL0056 | P03 | P03-A6 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 9193.46 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0056-2025-07 | CL0056 | P03 | P03-A6 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 139889.74 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0057-2025-07 | CL0057 | P03 | P03-A7 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 141629.04 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0057-2025-08 | CL0057 | P03 | P03-A7 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 7454.16 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0057-2025-11 | CL0057 | P03 | P03-A7 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 4141.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0058-2025-07 | CL0058 | P03 | P03-A7b | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 4472.49 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0058-2025-08 | CL0058 | P03 | P03-A7b | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 104358.24 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0058-2025-09 | CL0058 | P03 | P03-A7b | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 40252.47 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0060-2025-07 | CL0060 | P03 | P03-A8 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 120856.05 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0060-2025-08 | CL0060 | P03 | P03-A8 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 147712.95 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0060-2026-02 | CL0060 | P03 | P03-A8 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 7460.25 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0061-2025-08 | CL0061 | P03 | P03-A9 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 177255.54 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0061-2025-09 | CL0061 | P03 | P03-A9 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 91313.46 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0061-2026-02 | CL0061 | P03 | P03-A9 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 7460.25 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0062-2025-09 | CL0062 | P03 | P03-A9b | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 498771.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0062-2026-01 | CL0062 | P03 | P03-A9b | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 13854.75 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0063-2025-09 | CL0063 | P03 | P03-A10 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 99754.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0063-2025-10 | CL0063 | P03 | P03-A10 | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 412871.55 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0064-2025-09 | CL0064 | P03 | P03-A11 | 2025-09-30 | 2025-09 | PROCUREMENT | 8693.18 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0064-2025-10 | CL0064 | P03 | P03-A11 | 2025-10-31 | 2025-10 | PROCUREMENT | 469431.72 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0064-2025-12 | CL0064 | P03 | P03-A11 | 2025-12-31 | 2025-12 | PROCUREMENT | 13039.77 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0065-2025-10 | CL0065 | P03 | P03-A12 | 2025-10-31 | 2025-10 | PROCUREMENT | 34772.70 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0065-2025-11 | CL0065 | P03 | P03-A12 | 2025-11-30 | 2025-11 | PROCUREMENT | 375545.16 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0065-2026-01 | CL0065 | P03 | P03-A12 | 2026-01-31 | 2026-01 | PROCUREMENT | 563317.74 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0065-2026-02 | CL0065 | P03 | P03-A12 | 2026-02-28 | 2026-02 | PROCUREMENT | 563317.74 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0065-2026-03 | CL0065 | P03 | P03-A12 | 2026-03-31 | 2026-03 | PROCUREMENT | 375545.16 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0066-2026-03 | CL0066 | P03 | P03-A13 | 2026-03-31 | 2026-03 | PROCUREMENT | 249928.92 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0070-2025-09 | CL0070 | P03 | P03-A16 | 2025-09-30 | 2025-09 | PROCUREMENT | 7105.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0070-2025-10 | CL0070 | P03 | P03-A16 | 2025-10-31 | 2025-10 | PROCUREMENT | 383670.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0071-2025-10 | CL0071 | P03 | P03-A17 | 2025-10-31 | 2025-10 | PROCUREMENT | 28420.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0071-2025-11 | CL0071 | P03 | P03-A17 | 2025-11-30 | 2025-11 | PROCUREMENT | 315462.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0071-2025-12 | CL0071 | P03 | P03-A17 | 2025-12-31 | 2025-12 | PROCUREMENT | 451878.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0071-2026-01 | CL0071 | P03 | P03-A17 | 2026-01-31 | 2026-01 | PROCUREMENT | 460404.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0071-2026-02 | CL0071 | P03 | P03-A17 | 2026-02-28 | 2026-02 | PROCUREMENT | 349566.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0072-2026-02 | CL0072 | P03 | P03-A18 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 383670.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0073-2026-02 | CL0073 | P03 | P03-A19 | 2026-02-28 | 2026-02 | PROCUREMENT | 28420.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0073-2026-03 | CL0073 | P03 | P03-A19 | 2026-03-31 | 2026-03 | PROCUREMENT | 1534680.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0076-2025-09 | CL0076 | P03 | P03-A21 | 2025-09-30 | 2025-09 | PROCUREMENT | 3078.84 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0076-2025-10 | CL0076 | P03 | P03-A21 | 2025-10-31 | 2025-10 | PROCUREMENT | 166257.36 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0077-2025-10 | CL0077 | P03 | P03-A22 | 2025-10-31 | 2025-10 | PROCUREMENT | 12315.34 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0077-2025-11 | CL0077 | P03 | P03-A22 | 2025-11-30 | 2025-11 | PROCUREMENT | 332514.18 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0077-2025-12 | CL0077 | P03 | P03-A22 | 2025-12-31 | 2025-12 | PROCUREMENT | 332514.18 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0078-2025-12 | CL0078 | P03 | P03-A23 | 2025-12-31 | 2025-12 | PROCUREMENT | 12315.32 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0078-2026-01 | CL0078 | P03 | P03-A23 | 2026-01-31 | 2026-01 | PROCUREMENT | 665027.28 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0085-2025-06 | CL0085 | P04 | P04-A1 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 92400.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0085-2025-09 | CL0085 | P04 | P04-A1 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 2475.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0086-2025-06 | CL0086 | P04 | P04-A2 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 36960.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0086-2025-07 | CL0086 | P04 | P04-A2 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 55440.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0087-2025-07 | CL0087 | P04 | P04-A3 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 154962.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0088-2025-08 | CL0088 | P04 | P04-A4 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 31656.87 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0088-2025-09 | CL0088 | P04 | P04-A4 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 40290.58 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0089-2025-09 | CL0089 | P04 | P04-A4b | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 37136.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0089-2025-10 | CL0089 | P04 | P04-A4b | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 32932.64 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0089-2025-11 | CL0089 | P04 | P04-A4b | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 1876.86 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0090-2026-03 | CL0090 | P04 | P04-A15 | 2026-03-31 | 2026-03 | TESTING_ACCEPTANCE | 140140.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0091-2025-08 | CL0091 | P04 | P04-A5 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 4648.87 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0091-2025-09 | CL0091 | P04 | P04-A5 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 70811.13 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0092-2025-09 | CL0092 | P04 | P04-A5b | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 45276.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0092-2025-10 | CL0092 | P04 | P04-A5b | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 30184.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0092-2026-01 | CL0092 | P04 | P04-A5b | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 2021.25 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0093-2025-10 | CL0093 | P04 | P04-A5c | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 140140.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0093-2025-12 | CL0093 | P04 | P04-A5c | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 3753.75 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0094-2025-11 | CL0094 | P04 | P04-A6 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 143893.75 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0095-2025-11 | CL0095 | P04 | P04-A7 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 277303.04 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0096-2025-11 | CL0096 | P04 | P04-A8 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 55460.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0096-2025-12 | CL0096 | P04 | P04-A8 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 221842.44 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0096-2026-03 | CL0096 | P04 | P04-A8 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 7427.76 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0097-2025-12 | CL0097 | P04 | P04-A9 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 277303.04 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0098-2026-01 | CL0098 | P04 | P04-A12 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 213547.75 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0098-2026-02 | CL0098 | P04 | P04-A12 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 1172965.21 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0099-2026-02 | CL0099 | P04 | P04-A13 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 27730.30 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0099-2026-03 | CL0099 | P04 | P04-A13 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 249572.74 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0100-2026-03 | CL0100 | P04 | P04-A14 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 277301.92 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0102-2025-12 | CL0102 | P04 | P04-A10 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 182336.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0102-2026-01 | CL0102 | P04 | P04-A10 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 729344.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0103-2026-01 | CL0103 | P04 | P04-A11 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 319088.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0106-2025-03 | CL0106 | P05 | P05-A1 | 2025-03-31 | 2025-03 | ENGINEERING_OR_FIELD | 71745.96 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0106-2025-04 | CL0106 | P05 | P05-A1 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 38884.04 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0107-2025-09 | CL0107 | P05 | P05-A8 | 2025-09-30 | 2025-09 | TESTING_ACCEPTANCE | 221260.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0107-2025-12 | CL0107 | P05 | P05-A8 | 2025-12-31 | 2025-12 | TESTING_ACCEPTANCE | 5772.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0108-2025-04 | CL0108 | P05 | P05-A2 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 178710.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0109-2025-04 | CL0109 | P05 | P05-A3 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 105694.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0109-2025-05 | CL0109 | P05 | P05-A3 | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 124075.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0109-2025-08 | CL0109 | P05 | P05-A3 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 5994.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0110-2025-05 | CL0110 | P05 | P05-A4 | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 107226.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0110-2025-06 | CL0110 | P05 | P05-A4 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 71484.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0110-2025-11 | CL0110 | P05 | P05-A4 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 4662.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0111-2025-06 | CL0111 | P05 | P05-A4b | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 178710.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0112-2025-07 | CL0112 | P05 | P05-A10 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 35742.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0112-2025-08 | CL0112 | P05 | P05-A10 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 142968.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0112-2026-02 | CL0112 | P05 | P05-A10 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 4662.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0113-2025-06 | CL0113 | P05 | P05-A5 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 134032.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0113-2026-02 | CL0113 | P05 | P05-A5 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 3496.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0114-2025-06 | CL0114 | P05 | P05-A5b | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 67016.25 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0114-2025-07 | CL0114 | P05 | P05-A5b | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 67016.25 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0115-2025-07 | CL0115 | P05 | P05-A5c | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 82972.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0116-2025-07 | CL0116 | P05 | P05-A11 | 2025-07-31 | 2025-07 | PROCUREMENT | 5772.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0116-2025-08 | CL0116 | P05 | P05-A11 | 2025-08-31 | 2025-08 | PROCUREMENT | 265512.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0116-2025-09 | CL0116 | P05 | P05-A11 | 2025-09-30 | 2025-09 | PROCUREMENT | 66378.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0117-2025-07 | CL0117 | P05 | P05-A6 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 17027.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0117-2025-08 | CL0117 | P05 | P05-A6 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 65945.10 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0117-2026-01 | CL0117 | P05 | P05-A6 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 2164.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0118-2025-07 | CL0118 | P05 | P05-A7 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 33200.31 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0118-2025-08 | CL0118 | P05 | P05-A7 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 146634.73 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0118-2025-09 | CL0118 | P05 | P05-A7 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 96834.26 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0118-2025-10 | CL0118 | P05 | P05-A7 | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 7217.46 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0119-2025-08 | CL0119 | P05 | P05-A9 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 193668.51 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0119-2025-09 | CL0119 | P05 | P05-A9 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 83000.79 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0120-2025-09 | CL0120 | P05 | P05-A12a | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 401170.81 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0120-2025-10 | CL0120 | P05 | P05-A12a | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 567172.54 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0120-2025-11 | CL0120 | P05 | P05-A12a | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 415004.30 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0121-2025-09 | CL0121 | P05 | P05-AFIRST | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 830009.05 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0122-2025-10 | CL0122 | P05 | P05-A13a | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 470338.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0122-2025-11 | CL0122 | P05 | P05-A13a | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 498005.15 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0122-2025-12 | CL0122 | P05 | P05-A13a | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 415004.30 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0123-2025-11 | CL0123 | P05 | P05-A14a | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 470338.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0123-2025-12 | CL0123 | P05 | P05-A14a | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 581006.01 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0123-2026-01 | CL0123 | P05 | P05-A14a | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 368090.77 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0124-2025-12 | CL0124 | P05 | P05-A15a | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 553339.06 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0124-2026-01 | CL0124 | P05 | P05-A15a | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 553339.06 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0124-2026-02 | CL0124 | P05 | P05-A15a | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 276669.53 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0126-2025-09 | CL0126 | P05 | P05-A12b | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 4479.51 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0126-2025-10 | CL0126 | P05 | P05-A12b | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 183242.58 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0126-2025-11 | CL0126 | P05 | P05-A12b | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 161528.31 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0126-2025-12 | CL0126 | P05 | P05-A12b | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 87312.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0126-2026-01 | CL0126 | P05 | P05-A12b | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 11388.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0127-2025-10 | CL0127 | P05 | P05-A13b | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 30559.41 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0127-2025-11 | CL0127 | P05 | P05-A13b | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 157162.68 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0127-2025-12 | CL0127 | P05 | P05-A13b | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 183356.46 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0127-2026-01 | CL0127 | P05 | P05-A13b | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 65484.45 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0128-2025-11 | CL0128 | P05 | P05-A14b | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 30559.41 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0128-2025-12 | CL0128 | P05 | P05-A14b | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 183356.46 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0128-2026-01 | CL0128 | P05 | P05-A14b | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 174625.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0128-2026-02 | CL0128 | P05 | P05-A14b | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 48021.93 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0129-2025-12 | CL0129 | P05 | P05-A15b | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 52387.56 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0129-2026-01 | CL0129 | P05 | P05-A15b | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 174625.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0129-2026-02 | CL0129 | P05 | P05-A15b | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 161528.31 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0129-2026-03 | CL0129 | P05 | P05-A15b | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 48021.93 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0130-2026-01 | CL0130 | P05 | P05-A12c | 2026-01-31 | 2026-01 | TESTING_ACCEPTANCE | 159562.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0131-2026-02 | CL0131 | P05 | P05-A13c | 2026-02-28 | 2026-02 | TESTING_ACCEPTANCE | 159562.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0131-2026-03 | CL0131 | P05 | P05-A13c | 2026-03-31 | 2026-03 | TESTING_ACCEPTANCE | 4162.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0132-2026-02 | CL0132 | P05 | P05-A14c | 2026-02-28 | 2026-02 | TESTING_ACCEPTANCE | 159562.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0133-2026-03 | CL0133 | P05 | P05-A15c | 2026-03-31 | 2026-03 | TESTING_ACCEPTANCE | 156787.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0136-2025-08 | CL0136 | P06 | P06-A1 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 70495.92 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0136-2025-09 | CL0136 | P06 | P06-A1 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 11476.08 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0137-2025-12 | CL0137 | P06 | P06-A10 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 32788.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0137-2026-01 | CL0137 | P06 | P06-A10 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 49183.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0138-2025-09 | CL0138 | P06 | P06-A2 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 134136.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0139-2025-09 | CL0139 | P06 | P06-A3 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 143451.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0139-2025-10 | CL0139 | P06 | P06-A3 | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 143451.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0140-2025-10 | CL0140 | P06 | P06-A4 | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 52295.31 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0140-2025-11 | CL0140 | P06 | P06-A4 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 84609.87 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0141-2025-11 | CL0141 | P06 | P06-A4b | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 109524.14 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0141-2025-12 | CL0141 | P06 | P06-A4b | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 23680.90 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0142-2025-12 | CL0142 | P06 | P06-A7 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 39961.18 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0142-2026-01 | CL0142 | P06 | P06-A7 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 93242.78 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0143-2025-12 | CL0143 | P06 | P06-A8 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 53281.58 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0143-2026-01 | CL0143 | P06 | P06-A8 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 79922.38 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0144-2025-11 | CL0144 | P06 | P06-A5 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 96876.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0145-2025-11 | CL0145 | P06 | P06-A5b | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 28524.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0145-2025-12 | CL0145 | P06 | P06-A5b | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 68351.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0145-2026-01 | CL0145 | P06 | P06-A5b | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 2691.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0146-2025-12 | CL0146 | P06 | P06-A11 | 2025-12-31 | 2025-12 | PROCUREMENT | 21169.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0146-2026-01 | CL0146 | P06 | P06-A11 | 2026-01-31 | 2026-01 | PROCUREMENT | 77500.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0146-2026-03 | CL0146 | P06 | P06-A11 | 2026-03-31 | 2026-03 | PROCUREMENT | 2691.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0147-2025-12 | CL0147 | P06 | P06-A5c | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 96876.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0148-2025-12 | CL0148 | P06 | P06-A6 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 57049.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0148-2026-01 | CL0148 | P06 | P06-A6 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 39826.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0149-2026-01 | CL0149 | P06 | P06-A12 | 2026-01-31 | 2026-01 | PROCUREMENT | 84676.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0149-2026-02 | CL0149 | P06 | P06-A12 | 2026-02-28 | 2026-02 | PROCUREMENT | 112663.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0149-2026-03 | CL0149 | P06 | P06-A12 | 2026-03-31 | 2026-03 | PROCUREMENT | 119839.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0151-2025-12 | CL0151 | P06 | P06-A15 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 151380.46 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0151-2026-01 | CL0151 | P06 | P06-A15 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 216842.30 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0160-2026-01 | CL0160 | P06 | P06-A9 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 180044.18 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0160-2026-02 | CL0160 | P06 | P06-A9 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 463960.02 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0160-2026-03 | CL0160 | P06 | P06-A9 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 48473.44 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0161-2026-03 | CL0161 | P06 | P06-A14 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 207742.64 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0171-2025-09 | CL0171 | P07 | P07-A1 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 12177.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0171-2025-10 | CL0171 | P07 | P07-A1 | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 46863.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0172-2025-10 | CL0172 | P07 | P07-A2 | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 59040.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0172-2025-12 | CL0172 | P07 | P07-A2 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 1845.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0173-2025-10 | CL0173 | P07 | P07-A3 | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 6199.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0173-2025-11 | CL0173 | P07 | P07-A3 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 117784.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0173-2026-03 | CL0173 | P07 | P07-A3 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 3874.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0174-2025-12 | CL0174 | P07 | P07-A4 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 109371.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0174-2026-01 | CL0174 | P07 | P07-A4 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 5756.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0175-2025-12 | CL0175 | P07 | P07-A4b | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 6907.68 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0175-2026-01 | CL0175 | P07 | P07-A4b | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 108220.32 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0176-2025-12 | CL0176 | P07 | P07-A5 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 27552.38 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0176-2026-01 | CL0176 | P07 | P07-A5 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 18368.26 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0177-2026-01 | CL0177 | P07 | P07-A5b | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 45919.68 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0177-2026-03 | CL0177 | P07 | P07-A5b | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 1434.99 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0178-2026-02 | CL0178 | P07 | P07-A8 | 2026-02-28 | 2026-02 | PROCUREMENT | 10140.59 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0178-2026-03 | CL0178 | P07 | P07-A8 | 2026-03-31 | 2026-03 | PROCUREMENT | 36735.75 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0179-2026-01 | CL0179 | P07 | P07-A5c | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 76752.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0179-2026-02 | CL0179 | P07 | P07-A5c | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 51168.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0180-2026-02 | CL0180 | P07 | P07-A6 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 76752.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0180-2026-03 | CL0180 | P07 | P07-A6 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 48503.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0181-2026-02 | CL0181 | P07 | P07-A7 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 256942.08 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0181-2026-03 | CL0181 | P07 | P07-A7 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 171294.72 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0182-2026-03 | CL0182 | P07 | P07-A10 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 428236.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0185-2026-03 | CL0185 | P07 | P07-A9 | 2026-03-31 | 2026-03 | PROCUREMENT | 41820.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0192-2025-12 | CL0192 | P08 | P08-A1 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 58212.54 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0192-2026-01 | CL0192 | P08 | P08-A1 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 9476.46 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0193-2026-01 | CL0193 | P08 | P08-A2 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 82731.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0194-2026-01 | CL0194 | P08 | P08-A3 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 70196.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0194-2026-02 | CL0194 | P08 | P08-A3 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 70196.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0195-2026-02 | CL0195 | P08 | P08-A4 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 32591.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0195-2026-03 | CL0195 | P08 | P08-A4 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 97773.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0196-2026-03 | CL0196 | P08 | P08-A4b | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 58867.12 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0197-2026-03 | CL0197 | P08 | P08-A5 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 65945.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0198-2026-03 | CL0198 | P08 | P08-A5b | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 12835.84 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0202-2026-02 | CL0202 | P08 | P08-A7 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 111496.10 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0220-2026-02 | CL0220 | P09 | P09-A1 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 120510.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0221-2026-02 | CL0221 | P09 | P09-A2 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 36153.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0221-2026-03 | CL0221 | P09 | P09-A2 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 84357.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0222-2026-03 | CL0222 | P09 | P09-A3a | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 83553.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0279-2025-04 | CL0279 | P11 | P11-A1 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 72960.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0280-2025-04 | CL0280 | P11 | P11-A2 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 34048.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0280-2025-05 | CL0280 | P11 | P11-A2 | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 14592.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0281-2025-05 | CL0281 | P11 | P11-A3 | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 54720.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0282-2025-06 | CL0282 | P11 | P11-A4 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 63840.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0283-2025-08 | CL0283 | P11 | P11-A8 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 63840.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0284-2025-06 | CL0284 | P11 | P11-A5 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 31600.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0284-2025-07 | CL0284 | P11 | P11-A5 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 16279.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0285-2025-07 | CL0285 | P11 | P11-A5b | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 47880.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0286-2025-07 | CL0286 | P11 | P11-A5c | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 71136.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0286-2025-08 | CL0286 | P11 | P11-A5c | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 17784.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0287-2025-08 | CL0287 | P11 | P11-A6 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 88920.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0288-2025-08 | CL0288 | P11 | P11-A10 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 84658.73 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0288-2025-09 | CL0288 | P11 | P11-A10 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 6372.17 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0289-2025-08 | CL0289 | P11 | P11-A9 | 2025-08-31 | 2025-08 | PROCUREMENT | 189728.05 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0289-2025-09 | CL0289 | P11 | P11-A9 | 2025-09-30 | 2025-09 | PROCUREMENT | 182062.28 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0290-2025-09 | CL0290 | P11 | P11-AFIRST | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 273093.65 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0291-2025-09 | CL0291 | P11 | P11-B1inst | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 122891.97 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0291-2025-10 | CL0291 | P11 | P11-B1inst | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 255845.27 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0291-2025-11 | CL0291 | P11 | P11-B1inst | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 76418.21 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0292-2025-10 | CL0292 | P11 | P11-B2inst | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 100134.19 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0292-2025-11 | CL0292 | P11 | P11-B2inst | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 227577.73 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0292-2025-12 | CL0292 | P11 | P11-B2inst | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 127443.53 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0293-2025-10 | CL0293 | P11 | P11-B1rest | 2025-10-31 | 2025-10 | ENGINEERING_OR_FIELD | 54684.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0293-2025-11 | CL0293 | P11 | P11-B1rest | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 80976.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0293-2025-12 | CL0293 | P11 | P11-B1rest | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 23940.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0294-2025-11 | CL0294 | P11 | P11-B2rest | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 35112.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0294-2025-12 | CL0294 | P11 | P11-B2rest | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 96600.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0294-2026-01 | CL0294 | P11 | P11-B2rest | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 27888.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0295-2025-09 | CL0295 | P11 | P11-A7 | 2025-09-30 | 2025-09 | TESTING_ACCEPTANCE | 60800.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0296-2025-11 | CL0296 | P11 | P11-B1test | 2025-11-30 | 2025-11 | TESTING_ACCEPTANCE | 60800.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0297-2025-12 | CL0297 | P11 | P11-B2test | 2025-12-31 | 2025-12 | TESTING_ACCEPTANCE | 60800.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0298-2026-02 | CL0298 | P11 | P11-A11 | 2026-02-28 | 2026-02 | TESTING_ACCEPTANCE | 60800.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0299-2025-12 | CL0299 | P11 | P11-B1gis | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 21280.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0300-2026-01 | CL0300 | P11 | P11-B2gis | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 21280.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0301-2026-02 | CL0301 | P11 | P11-A12 | 2026-02-28 | 2026-02 | TESTING_ACCEPTANCE | 21280.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0302-2026-03 | CL0302 | P11 | P11-A13 | 2026-03-31 | 2026-03 | TESTING_ACCEPTANCE | 27360.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0303-2025-01 | CL0303 | P12 | P12-Y1A1 | 2025-01-31 | 2025-01 | ENGINEERING_OR_FIELD | 29702.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0303-2025-02 | CL0303 | P12 | P12-Y1A1 | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 571.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0303-2025-06 | CL0303 | P12 | P12-Y1A1 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 856.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0304-2025-01 | CL0304 | P12 | P12-Y1A2 | 2025-01-31 | 2025-01 | ENGINEERING_OR_FIELD | 3027.36 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0304-2025-02 | CL0304 | P12 | P12-Y1A2 | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 27246.24 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0304-2025-04 | CL0304 | P12 | P12-Y1A2 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 856.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0305-2025-11 | CL0305 | P12 | P12-Y2A1 | 2025-11-30 | 2025-11 | ENGINEERING_OR_FIELD | 38923.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0305-2026-01 | CL0305 | P12 | P12-Y2A1 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 1101.60 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0306-2025-12 | CL0306 | P12 | P12-Y2A2 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 38923.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0309-2025-02 | CL0309 | P12 | P12-Y1A3 | 2025-02-28 | 2025-02 | ENGINEERING_OR_FIELD | 4541.04 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0309-2025-03 | CL0309 | P12 | P12-Y1A3 | 2025-03-31 | 2025-03 | ENGINEERING_OR_FIELD | 40869.36 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0309-2025-07 | CL0309 | P12 | P12-Y1A3 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 1285.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0310-2025-03 | CL0310 | P12 | P12-Y1A4 | 2025-03-31 | 2025-03 | ENGINEERING_OR_FIELD | 9082.08 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0310-2025-04 | CL0310 | P12 | P12-Y1A4 | 2025-04-30 | 2025-04 | ENGINEERING_OR_FIELD | 36328.32 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0310-2025-07 | CL0310 | P12 | P12-Y1A4 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 1285.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0311-2025-12 | CL0311 | P12 | P12-Y2A3 | 2025-12-31 | 2025-12 | ENGINEERING_OR_FIELD | 14320.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0311-2026-01 | CL0311 | P12 | P12-Y2A3 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 44064.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0312-2026-01 | CL0312 | P12 | P12-Y2A4 | 2026-01-31 | 2026-01 | ENGINEERING_OR_FIELD | 26857.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0312-2026-02 | CL0312 | P12 | P12-Y2A4 | 2026-02-28 | 2026-02 | ENGINEERING_OR_FIELD | 31527.80 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0315-2025-04 | CL0315 | P12 | P12-Y1A5 | 2025-04-30 | 2025-04 | PROCUREMENT | 26503.68 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0315-2025-05 | CL0315 | P12 | P12-Y1A5 | 2025-05-31 | 2025-05 | PROCUREMENT | 96875.52 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0316-2026-02 | CL0316 | P12 | P12-Y2A5 | 2026-02-28 | 2026-02 | PROCUREMENT | 80784.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0316-2026-03 | CL0316 | P12 | P12-Y2A5 | 2026-03-31 | 2026-03 | PROCUREMENT | 77846.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0318-2025-05 | CL0318 | P12 | P12-Y1A6 | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 70059.19 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0318-2025-06 | CL0318 | P12 | P12-Y1A6 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 240202.95 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0318-2025-07 | CL0318 | P12 | P12-Y1A6 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 250211.41 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0318-2025-08 | CL0318 | P12 | P12-Y1A6 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 240202.96 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0318-2025-09 | CL0318 | P12 | P12-Y1A6 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 200169.13 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0319-2026-03 | CL0319 | P12 | P12-Y2A6 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 128680.07 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0321-2025-10 | CL0321 | P12 | P12-Y1A7 | 2025-10-31 | 2025-10 | TESTING_ACCEPTANCE | 60547.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0324-2025-11 | CL0324 | P12 | P12-Y1A8 | 2025-11-30 | 2025-11 | TESTING_ACCEPTANCE | 29702.40 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0324-2025-12 | CL0324 | P12 | P12-Y1A8 | 2025-12-31 | 2025-12 | TESTING_ACCEPTANCE | 571.20 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0330-2026-01 | CL0330 | P05 | P05-A12c | 2026-01-31 | 2026-01 | TESTING_ACCEPTANCE | 121267.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0330-2026-02 | CL0330 | P05 | P05-A12c | 2026-02-28 | 2026-02 | TESTING_ACCEPTANCE | 3163.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0331-2026-02 | CL0331 | P05 | P05-A13c | 2026-02-28 | 2026-02 | TESTING_ACCEPTANCE | 121267.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0332-2026-03 | CL0332 | P05 | P05-A14c | 2026-03-31 | 2026-03 | TESTING_ACCEPTANCE | 121267.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0333-2026-03 | CL0333 | P05 | P05-A15c | 2026-03-31 | 2026-03 | TESTING_ACCEPTANCE | 121267.50 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0335-2025-12 | CL0335 | P11 | P11-B1gis | 2025-12-31 | 2025-12 | TESTING_ACCEPTANCE | 85120.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0336-2026-01 | CL0336 | P11 | P11-B2gis | 2026-01-31 | 2026-01 | TESTING_ACCEPTANCE | 85120.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0337-2025-05 | CL0337 | P12 | P12-Y1A6 | 2025-05-31 | 2025-05 | ENGINEERING_OR_FIELD | 14955.11 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0337-2025-06 | CL0337 | P12 | P12-Y1A6 | 2025-06-30 | 2025-06 | ENGINEERING_OR_FIELD | 34396.77 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0337-2025-07 | CL0337 | P12 | P12-Y1A6 | 2025-07-31 | 2025-07 | ENGINEERING_OR_FIELD | 37387.79 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0337-2025-08 | CL0337 | P12 | P12-Y1A6 | 2025-08-31 | 2025-08 | ENGINEERING_OR_FIELD | 35892.28 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0337-2025-09 | CL0337 | P12 | P12-Y1A6 | 2025-09-30 | 2025-09 | ENGINEERING_OR_FIELD | 26919.21 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0338-2026-03 | CL0338 | P12 | P12-Y2A6 | 2026-03-31 | 2026-03 | ENGINEERING_OR_FIELD | 23073.69 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0340-2026-03 | CL0340 | P04 | P04-A14 | 2026-03-31 | 2026-03 | TESTING_ACCEPTANCE | 147840.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1
AC-CL0341-2026-03 | CL0341 | P04 | P04-A15 | 2026-03-31 | 2026-03 | TESTING_ACCEPTANCE | 221760.00 | Synthetic work-performed cost incurrence incl. scenario cost pressure; not paid invoice | SYNTHETIC_SCENARIO_V1

## COMMITMENT_REGISTER
Commitment_ID | Cost_Ownership_Line_ID | Project_ID | Activity_ID | Commitment_Date | Commitment_Type | Authorized_Commitment_USD | Cumulative_AC_At_Cutoff_USD | Unincurred_Commitment_USD | Source
PO-CL0007 | CL0007 | P01 | P01-A7a | 2025-05-15 | SYNTHETIC_PURCHASE_ORDER | 73901.69 | 70448.34 | 3453.35 | SYNTHETIC_SCENARIO_V1
PO-CL0011 | CL0011 | P01 | P01-A7b | 2025-06-05 | SYNTHETIC_PURCHASE_ORDER | 1393804.80 | 1304294.40 | 89510.40 | SYNTHETIC_SCENARIO_V1
PO-CL0013 | CL0013 | P01 | P01-A7c | 2025-07-17 | SYNTHETIC_PURCHASE_ORDER | 1317081.60 | 1304294.40 | 12787.20 | SYNTHETIC_SCENARIO_V1
PO-CL0031 | CL0031 | P02 | P02-A7a | 2025-06-02 | SYNTHETIC_PURCHASE_ORDER | 207187.20 | 212889.60 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0033 | CL0033 | P02 | P02-A7b | 2025-06-30 | SYNTHETIC_PURCHASE_ORDER | 821145.60 | 851558.40 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0036 | CL0036 | P02 | P02-A7d | 2025-11-17 | SYNTHETIC_PURCHASE_ORDER | 790732.80 | 851558.40 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0039 | CL0039 | P02 | P02-A11a | 2025-06-02 | SYNTHETIC_PURCHASE_ORDER | 230630.40 | 248371.20 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0041 | CL0041 | P02 | P02-A11b | 2025-06-30 | SYNTHETIC_PURCHASE_ORDER | 975744.00 | 993484.80 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0043 | CL0043 | P02 | P02-A11d | 2025-11-03 | SYNTHETIC_PURCHASE_ORDER | 949132.80 | 993484.80 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0064 | CL0064 | P03 | P03-A11 | 2025-09-18 | SYNTHETIC_PURCHASE_ORDER | 452045.36 | 491164.67 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0065 | CL0065 | P03 | P03-A12 | 2025-10-16 | SYNTHETIC_PURCHASE_ORDER | 1877725.80 | 1912498.50 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0066 | CL0066 | P03 | P03-A13 | 2026-03-05 | SYNTHETIC_PURCHASE_ORDER | 469431.72 | 249928.92 | 219502.80 | SYNTHETIC_SCENARIO_V1
PO-CL0067 | CL0067 | P03 | P03-A14 | 2026-03-26 | SYNTHETIC_PURCHASE_ORDER | 1929884.85 | 0.00 | 1929884.85 | SYNTHETIC_SCENARIO_V1
PO-CL0070 | CL0070 | P03 | P03-A16 | 2025-09-18 | SYNTHETIC_PURCHASE_ORDER | 373012.50 | 390775.00 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0071 | CL0071 | P03 | P03-A17 | 2025-10-16 | SYNTHETIC_PURCHASE_ORDER | 1534680.00 | 1605730.00 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0073 | CL0073 | P03 | P03-A19 | 2026-02-19 | SYNTHETIC_PURCHASE_ORDER | 1548890.00 | 1563100.00 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0076 | CL0076 | P03 | P03-A21 | 2025-09-18 | SYNTHETIC_PURCHASE_ORDER | 164717.94 | 169336.20 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0077 | CL0077 | P03 | P03-A22 | 2025-10-09 | SYNTHETIC_PURCHASE_ORDER | 640397.68 | 677343.70 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0078 | CL0078 | P03 | P03-A23 | 2025-12-18 | SYNTHETIC_PURCHASE_ORDER | 683500.26 | 677342.60 | 6157.66 | SYNTHETIC_SCENARIO_V1
PO-CL0116 | CL0116 | P05 | P05-A11 | 2025-07-14 | SYNTHETIC_PURCHASE_ORDER | 320346.00 | 337662.00 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0146 | CL0146 | P06 | P06-A11 | 2025-12-12 | SYNTHETIC_PURCHASE_ORDER | 99567.00 | 101361.00 | 0.00 | SYNTHETIC_SCENARIO_V1
PO-CL0149 | CL0149 | P06 | P06-A12 | 2026-01-02 | SYNTHETIC_PURCHASE_ORDER | 373152.00 | 317179.20 | 55972.80 | SYNTHETIC_SCENARIO_V1
PO-CL0150 | CL0150 | P06 | P06-A13 | 2026-03-27 | SYNTHETIC_PURCHASE_ORDER | 97773.00 | 0.00 | 97773.00 | SYNTHETIC_SCENARIO_V1
PO-CL0178 | CL0178 | P07 | P07-A8 | 2026-02-25 | SYNTHETIC_PURCHASE_ORDER | 50702.98 | 46876.34 | 3826.64 | SYNTHETIC_SCENARIO_V1
PO-CL0185 | CL0185 | P07 | P07-A9 | 2026-03-18 | SYNTHETIC_PURCHASE_ORDER | 92840.40 | 41820.00 | 51020.40 | SYNTHETIC_SCENARIO_V1
PO-CL0289 | CL0289 | P11 | P11-A9 | 2025-08-12 | SYNTHETIC_PURCHASE_ORDER | 413952.12 | 371790.33 | 42161.79 | SYNTHETIC_SCENARIO_V1
PO-CL0315 | CL0315 | P12 | P12-Y1A5 | 2025-04-10 | SYNTHETIC_PURCHASE_ORDER | 126806.40 | 123379.20 | 3427.20 | SYNTHETIC_SCENARIO_V1
PO-CL0316 | CL0316 | P12 | P12-Y2A5 | 2026-02-05 | SYNTHETIC_PURCHASE_ORDER | 151286.40 | 158630.40 | 0.00 | SYNTHETIC_SCENARIO_V1

## EVM_PROJECT_MONTH
Reporting_Month | Project_ID | Baseline_Monthly_PV_USD | Baseline_Cumulative_PV_USD | Scenario_Monthly_EV_USD | Scenario_Cumulative_EV_USD | Scenario_Monthly_AC_USD | Scenario_Cumulative_AC_USD | Status
2025-01 | P01 | 285455.00 | 285455.00 | 285455.00 | 285455.00 | 285455.00 | 285455.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P02 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P03 | 508515.00 | 508515.00 | 274050.00 | 274050.00 | 295974.00 | 295974.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P04 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P05 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P06 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P07 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P11 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-01 | P12 | 38556.00 | 38556.00 | 31416.00 | 31416.00 | 32729.76 | 32729.76 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P01 | 341621.00 | 627076.00 | 341621.00 | 627076.00 | 341621.00 | 627076.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P02 | 745140.00 | 745140.00 | 745140.00 | 745140.00 | 819654.00 | 819654.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P03 | 289681.00 | 798196.00 | 472990.00 | 747040.00 | 519050.70 | 815024.70 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P04 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P05 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P06 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P07 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P11 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-02 | P12 | 33558.00 | 72114.00 | 29988.00 | 61404.00 | 32358.48 | 65088.24 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P01 | 170323.38 | 797399.38 | 170323.40 | 797399.40 | 170323.40 | 797399.40 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P02 | 269676.00 | 1014816.00 | 269676.00 | 1014816.00 | 296643.60 | 1116297.60 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P03 | 153468.00 | 951664.00 | 152006.40 | 899046.40 | 178775.60 | 993800.30 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P04 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P05 | 189440.00 | 189440.00 | 63492.00 | 63492.00 | 71745.96 | 71745.96 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P06 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P07 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P11 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-03 | P12 | 50694.00 | 122808.00 | 47124.00 | 108528.00 | 49951.44 | 115039.68 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P01 | 232063.62 | 1029463.00 | 232063.60 | 1029463.00 | 232063.60 | 1029463.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P02 | 327660.58 | 1342476.58 | 326942.00 | 1341758.00 | 359636.20 | 1475933.80 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P03 | 282576.00 | 1234240.00 | 236779.20 | 1135825.60 | 251161.34 | 1244961.64 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P04 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P05 | 261960.00 | 451400.00 | 280016.00 | 343508.00 | 323288.24 | 395034.20 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P06 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P07 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P11 | 112640.00 | 112640.00 | 112640.00 | 112640.00 | 107008.00 | 107008.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-04 | P12 | 77112.00 | 199920.00 | 57120.00 | 165648.00 | 63688.80 | 178728.48 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P01 | 363093.56 | 1392556.56 | 363093.60 | 1392556.60 | 364474.94 | 1393937.94 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P02 | 340963.42 | 1683440.00 | 341682.00 | 1683440.00 | 375850.20 | 1851784.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P03 | 332108.00 | 1566348.00 | 332514.00 | 1468339.60 | 359115.12 | 1604076.76 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P04 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P05 | 284900.00 | 736300.00 | 201132.00 | 544640.00 | 231301.80 | 626336.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P06 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P07 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P11 | 72960.00 | 185600.00 | 72960.00 | 185600.00 | 69312.00 | 176320.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-05 | P12 | 201823.92 | 401743.92 | 171594.18 | 337242.18 | 181889.82 | 360618.30 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P01 | 730133.44 | 2122690.00 | 730133.40 | 2122690.00 | 755707.80 | 2149645.74 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P02 | 1014992.00 | 2698432.00 | 1013724.80 | 2697164.80 | 1156281.28 | 3008065.28 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P03 | 273779.28 | 1840127.28 | 285742.80 | 1754082.40 | 330043.90 | 1934120.66 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P04 | 205425.00 | 205425.00 | 115500.00 | 115500.00 | 129360.00 | 129360.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P05 | 302290.00 | 1038590.00 | 392385.00 | 937025.00 | 451242.75 | 1077578.75 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P06 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P07 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P11 | 100800.00 | 286400.00 | 100464.00 | 286064.00 | 95440.80 | 271760.80 | SYNTHETIC_ACTUALS_CUTOFF
2025-06 | P12 | 253231.86 | 654975.78 | 259056.34 | 596298.52 | 275456.52 | 636074.82 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P01 | 1939392.00 | 4062082.00 | 1937260.80 | 4059950.80 | 1962835.20 | 4112480.94 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P02 | 792000.00 | 3490432.00 | 793267.20 | 3490432.00 | 872593.92 | 3880659.20 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P03 | 408300.70 | 2248427.98 | 376940.55 | 2131022.95 | 406847.32 | 2340967.98 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P04 | 94325.00 | 299750.00 | 184250.00 | 299750.00 | 210402.50 | 339762.50 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P05 | 431280.10 | 1469870.10 | 204804.84 | 1141829.84 | 241730.46 | 1319309.21 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P06 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P07 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P11 | 142080.00 | 428480.00 | 142416.00 | 428480.00 | 135295.20 | 407056.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-07 | P12 | 277349.18 | 932324.96 | 271320.00 | 867618.52 | 290169.60 | 926244.42 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P01 | 575424.00 | 4637506.00 | 576489.60 | 4636440.40 | 576489.60 | 4688970.54 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P02 | 842688.00 | 4333120.00 | 842688.00 | 4333120.00 | 926956.80 | 4807616.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P03 | 456614.59 | 2705042.57 | 404426.75 | 2535449.70 | 436780.89 | 2777748.87 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P04 | 94967.00 | 394717.00 | 31570.22 | 331320.22 | 36305.74 | 376068.24 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P05 | 1395923.65 | 2865793.75 | 708835.86 | 1850665.70 | 820722.34 | 2140031.55 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P06 | 150420.00 | 150420.00 | 65274.00 | 65274.00 | 70495.92 | 70495.92 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P07 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P11 | 460598.32 | 889078.32 | 460278.96 | 888758.96 | 444930.78 | 851986.78 | SYNTHETIC_ACTUALS_CUTOFF
2025-08 | P12 | 253231.86 | 1185556.82 | 260467.20 | 1128085.72 | 276095.24 | 1202339.66 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P01 | 575424.00 | 5212930.00 | 576489.60 | 5212930.00 | 576489.60 | 5265460.14 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P02 | 266112.00 | 4599232.00 | 266112.00 | 4599232.00 | 292723.20 | 5100339.20 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P03 | 856826.48 | 3561869.05 | 676010.30 | 3211460.00 | 748968.15 | 3526717.02 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P04 | 252495.50 | 647212.50 | 171950.64 | 503270.86 | 195989.51 | 572057.75 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P05 | 939560.81 | 3805354.56 | 1480885.69 | 3331551.39 | 1703132.42 | 3843163.97 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P06 | 288765.00 | 439185.00 | 267651.00 | 332925.00 | 289063.08 | 359559.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P07 | 0.00 | 0.00 | 12300.00 | 12300.00 | 12177.00 | 12177.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P11 | 681255.15 | 1570333.47 | 679179.01 | 1567937.97 | 645220.07 | 1497206.85 | SYNTHETIC_ACTUALS_CUTOFF
2025-09 | P12 | 156763.18 | 1342320.00 | 214234.28 | 1342320.00 | 227088.34 | 1429428.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P01 | 1069966.00 | 6282896.00 | 1069966.00 | 6282896.00 | 1069966.00 | 6335426.14 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P02 | 779328.00 | 5378560.00 | 779328.00 | 5378560.00 | 857260.80 | 5957600.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P03 | 1086055.35 | 4647924.40 | 1313311.00 | 4524771.00 | 1511879.87 | 5038596.89 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P04 | 182630.65 | 829843.15 | 181479.14 | 684750.00 | 203256.64 | 775314.39 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P05 | 1487064.44 | 5292419.00 | 1088197.05 | 4419748.44 | 1258530.19 | 5101694.16 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P06 | 161115.40 | 600300.40 | 182160.20 | 515085.20 | 195746.31 | 555305.31 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P07 | 110700.00 | 110700.00 | 117157.50 | 129457.50 | 112102.20 | 124279.20 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P11 | 442088.64 | 2012422.11 | 442088.80 | 2010026.77 | 410663.46 | 1907870.31 | SYNTHETIC_ACTUALS_CUTOFF
2025-10 | P12 | 90576.00 | 1432896.00 | 57120.00 | 1399440.00 | 60547.20 | 1489975.20 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P01 | 895104.00 | 7178000.00 | 895104.00 | 7178000.00 | 895104.00 | 7230530.14 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P02 | 1985702.40 | 7364262.40 | 1985702.40 | 7364262.40 | 2217219.84 | 8174819.84 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P03 | 816657.10 | 5464581.50 | 939810.50 | 5464581.50 | 1036432.14 | 6075029.03 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P04 | 557746.50 | 1387589.65 | 422235.40 | 1106985.40 | 478534.25 | 1253848.64 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P05 | 1582531.00 | 6874950.00 | 1506607.00 | 5926355.44 | 1737260.05 | 6838954.21 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P06 | 300495.60 | 900796.00 | 289283.20 | 804368.40 | 319534.61 | 874839.92 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P07 | 128535.00 | 239235.00 | 122692.50 | 252150.00 | 117784.80 | 242064.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P08 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P11 | 497222.22 | 2509644.33 | 496382.15 | 2506408.92 | 480883.94 | 2388754.25 | SYNTHETIC_ACTUALS_CUTOFF
2025-11 | P12 | 44676.00 | 1477572.00 | 65280.00 | 1464720.00 | 68625.60 | 1558600.80 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P01 | 222000.00 | 7400000.00 | 222000.00 | 7400000.00 | 222000.00 | 7452530.14 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P02 | 263577.60 | 7627840.00 | 263577.60 | 7627840.00 | 289935.36 | 8464755.20 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P03 | 1871540.00 | 7336121.50 | 734183.50 | 6198765.00 | 809747.27 | 6884776.30 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P04 | 1036041.34 | 2423630.99 | 608465.60 | 1715451.00 | 685235.23 | 1939083.87 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P05 | 1780659.68 | 8655609.68 | 1787619.52 | 7713974.96 | 2061534.45 | 8900488.66 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P06 | 837717.34 | 1738513.34 | 501992.30 | 1306360.70 | 544538.72 | 1419378.64 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P07 | 127988.58 | 367223.58 | 149824.65 | 401974.65 | 145676.66 | 387740.66 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P08 | 122820.00 | 122820.00 | 53406.00 | 53406.00 | 58212.54 | 58212.54 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P11 | 429555.67 | 2939200.00 | 432791.08 | 2939200.00 | 415183.53 | 2803937.78 | SYNTHETIC_ACTUALS_CUTOFF
2025-12 | P12 | 51408.00 | 1528980.00 | 50490.00 | 1515210.00 | 53815.20 | 1612416.00 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P01 | 0.00 | 7400000.00 | 0.00 | 7400000.00 | 0.00 | 7452530.14 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P02 | 528000.00 | 8155840.00 | 528000.00 | 8155840.00 | 580800.00 | 9045555.20 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P03 | 426300.00 | 7762421.50 | 1563656.50 | 7762421.50 | 1702603.77 | 8587380.07 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P04 | 846899.01 | 3270530.00 | 1121793.70 | 2837244.70 | 1264001.00 | 3203084.87 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P05 | 1038292.52 | 9693902.20 | 1374702.04 | 9088677.00 | 1630547.78 | 10531036.44 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P06 | 499657.82 | 2238171.16 | 756553.88 | 2062914.58 | 823930.24 | 2243308.88 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P07 | 260418.42 | 627642.00 | 265642.35 | 667617.00 | 255016.66 | 642757.32 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P08 | 212173.30 | 334993.30 | 148994.00 | 202400.00 | 162403.46 | 220616.00 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P09 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P11 | 145600.00 | 3084800.00 | 145600.00 | 3084800.00 | 134288.00 | 2938225.78 | SYNTHETIC_ACTUALS_CUTOFF
2026-01 | P12 | 71604.00 | 1600584.00 | 66646.80 | 1581856.80 | 72022.60 | 1684438.60 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P01 | 0.00 | 7400000.00 | 0.00 | 7400000.00 | 0.00 | 7452530.14 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P02 | 644160.00 | 8800000.00 | 644160.00 | 8800000.00 | 708576.00 | 9754131.20 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P03 | 2297840.50 | 10060262.00 | 1161040.50 | 8923462.00 | 1339894.24 | 9927274.31 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P04 | 866571.00 | 4137101.00 | 1077023.50 | 3914268.20 | 1200695.51 | 4403780.38 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P05 | 347732.80 | 10041635.00 | 805749.80 | 9894426.80 | 937934.27 | 11468970.71 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P06 | 470976.94 | 2709148.10 | 537232.61 | 2600147.19 | 576623.22 | 2819932.10 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P07 | 276640.60 | 904282.60 | 410464.60 | 1078081.60 | 395002.67 | 1037759.99 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P08 | 143423.35 | 478416.65 | 196590.00 | 398990.00 | 214283.10 | 434899.10 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P09 | 175500.00 | 175500.00 | 152100.00 | 152100.00 | 156663.00 | 156663.00 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P11 | 86400.00 | 3171200.00 | 86400.00 | 3171200.00 | 82080.00 | 3020305.78 | SYNTHETIC_ACTUALS_CUTOFF
2026-02 | P12 | 84456.00 | 1685040.00 | 103183.20 | 1685040.00 | 112311.80 | 1796750.40 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P01 | 0.00 | 7400000.00 | 0.00 | 7400000.00 | 0.00 | 7452530.14 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P02 | 0.00 | 8800000.00 | 0.00 | 8800000.00 | 0.00 | 9754131.20 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P03 | 1414313.00 | 11474575.00 | 1986056.50 | 10909518.50 | 2160154.08 | 12087428.39 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P04 | 1197899.00 | 5335000.00 | 925548.80 | 4839817.00 | 1044042.42 | 5447822.80 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P05 | 244200.00 | 10285835.00 | 391408.20 | 10285835.00 | 451506.93 | 11920477.64 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P06 | 346948.90 | 3056097.00 | 344877.11 | 2945024.30 | 378746.28 | 3198678.38 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P07 | 906605.40 | 1810888.00 | 757898.40 | 1835980.00 | 731899.76 | 1769659.75 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P08 | 285169.35 | 763586.00 | 215372.00 | 614362.00 | 235421.56 | 670320.66 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P09 | 164580.00 | 340080.00 | 163020.00 | 315120.00 | 167910.60 | 324573.60 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P11 | 28800.00 | 3200000.00 | 28800.00 | 3200000.00 | 27360.00 | 3047665.78 | SYNTHETIC_ACTUALS_CUTOFF
2026-03 | P12 | 290495.86 | 1975535.86 | 216603.94 | 1901643.94 | 229600.16 | 2026350.56 | SYNTHETIC_ACTUALS_CUTOFF
2026-04 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P03 | 1970452.96 | 13445027.96 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P04 | 165000.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P05 | 481165.00 | 10767000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P06 | 867301.30 | 3923398.30 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P07 | 144976.00 | 1955864.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P08 | 305184.92 | 1068770.92 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P09 | 137280.00 | 477360.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P10 | 66600.00 | 66600.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-04 | P12 | 341087.78 | 2316623.64 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P03 | 1292580.37 | 14737608.33 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P05 | 333000.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P06 | 353390.01 | 4276788.31 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P07 | 708152.00 | 2664016.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P08 | 296098.08 | 1364869.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P09 | 86666.65 | 564026.65 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P10 | 221260.00 | 287860.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-05 | P12 | 325583.79 | 2642207.43 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P03 | 1650421.58 | 16388029.91 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P06 | 292239.30 | 4569027.61 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P07 | 325157.00 | 2989173.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P08 | 226348.60 | 1591217.60 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P09 | 199749.31 | 763775.96 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P10 | 451215.00 | 739075.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-06 | P12 | 341087.78 | 2983295.21 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P03 | 480284.59 | 16868314.50 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P06 | 628678.27 | 5197705.88 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P07 | 95667.00 | 3084840.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P08 | 209457.60 | 1800675.20 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P09 | 292864.04 | 1056640.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P10 | 268484.90 | 1007559.90 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-07 | P12 | 170544.79 | 3153840.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P03 | 499888.50 | 17368203.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P06 | 575173.94 | 5772879.82 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P07 | 972110.00 | 4056950.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P08 | 633905.70 | 2434580.90 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P09 | 1098746.30 | 2155386.30 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P10 | 470099.50 | 1477659.40 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-08 | P12 | 117504.00 | 3271344.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P03 | 991118.00 | 18359321.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P06 | 334258.18 | 6107138.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P07 | 43050.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P08 | 840740.50 | 3275321.40 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P09 | 1043774.55 | 3199160.85 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P10 | 909506.60 | 2387166.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-09 | P12 | 47736.00 | 3319080.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P03 | 446599.00 | 18805920.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P06 | 332862.00 | 6440000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P08 | 568099.60 | 3843421.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P09 | 1165721.15 | 4364882.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P10 | 156954.00 | 2544120.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-10 | P12 | 51408.00 | 3370488.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P03 | 487200.00 | 19293120.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P06 | 253000.00 | 6693000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P08 | 414000.00 | 4257421.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P09 | 1097525.80 | 5462407.80 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P10 | 99456.00 | 2643576.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-11 | P12 | 69768.00 | 3440256.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P03 | 824180.00 | 20117300.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P06 | 207000.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P08 | 294279.00 | 4551700.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P09 | 1074527.20 | 6536935.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P10 | 165673.00 | 2809249.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2026-12 | P12 | 124848.00 | 3565104.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P03 | 182700.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P08 | 48300.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P09 | 419328.00 | 6956263.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P10 | 99456.00 | 2908705.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-01 | P12 | 292943.83 | 3858047.83 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P09 | 761837.00 | 7718100.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P10 | 101354.00 | 3010059.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-02 | P12 | 310079.80 | 4168127.63 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P09 | 81900.00 | 7800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P10 | 118545.18 | 3128604.18 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-03 | P12 | 356591.77 | 4524719.40 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P09 | 0.00 | 7800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P10 | 108896.32 | 3237500.50 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-04 | P12 | 341087.78 | 4865807.18 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P09 | 0.00 | 7800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P10 | 186088.50 | 3423589.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-05 | P12 | 124032.82 | 4989840.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P09 | 0.00 | 7800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P10 | 82706.00 | 3506295.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-06 | P12 | 110160.00 | 5100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P09 | 0.00 | 7800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P10 | 160405.00 | 3666700.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-07 | P12 | 0.00 | 5100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P09 | 0.00 | 7800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P10 | 33300.00 | 3700000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-08 | P12 | 0.00 | 5100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P09 | 0.00 | 7800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P10 | 0.00 | 3700000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-09 | P12 | 0.00 | 5100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P09 | 0.00 | 7800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P10 | 0.00 | 3700000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-10 | P12 | 0.00 | 5100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P09 | 0.00 | 7800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P10 | 0.00 | 3700000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-11 | P12 | 0.00 | 5100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P01 | 0.00 | 7400000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P02 | 0.00 | 8800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P03 | 0.00 | 20300000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P04 | 0.00 | 5500000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P05 | 0.00 | 11100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P06 | 0.00 | 6900000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P07 | 0.00 | 4100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P08 | 0.00 | 4600000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P09 | 0.00 | 7800000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P10 | 0.00 | 3700000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P11 | 0.00 | 3200000.00 |  |  |  |  | FUTURE_BASELINE_ONLY
2027-12 | P12 | 0.00 | 5100000.00 |  |  |  |  | FUTURE_BASELINE_ONLY

## EVM_PROGRAM_MONTH
Reporting_Month | Monthly_PV_USD | Monthly_EV_USD | Monthly_AC_USD | Cumulative_PV_USD | Cumulative_EV_USD | Cumulative_AC_USD | Status
2025-01 | 832526.00 | 590921.00 | 614158.76 | 832526.00 | 590921.00 | 614158.76 | SYNTHETIC_SCENARIO_V1
2025-02 | 1410000.00 | 1589739.00 | 1712684.18 | 2242526.00 | 2180660.00 | 2326842.94 | SYNTHETIC_SCENARIO_V1
2025-03 | 833601.38 | 702621.80 | 767440.00 | 3076127.38 | 2883281.80 | 3094282.94 | SYNTHETIC_SCENARIO_V1
2025-04 | 1294012.20 | 1245560.80 | 1336846.18 | 4370139.58 | 4128842.60 | 4431129.12 | SYNTHETIC_SCENARIO_V1
2025-05 | 1595848.90 | 1482975.78 | 1581943.88 | 5965988.48 | 5611818.38 | 6013073.00 | SYNTHETIC_SCENARIO_V1
2025-06 | 2880651.58 | 2897006.34 | 3193533.05 | 8846640.06 | 8508824.72 | 9206606.05 | SYNTHETIC_SCENARIO_V1
2025-07 | 4084726.98 | 3910259.39 | 4119874.20 | 12931367.04 | 12419084.11 | 13326480.25 | SYNTHETIC_SCENARIO_V1
2025-08 | 4229867.42 | 3350030.59 | 3588777.31 | 17161234.46 | 15769114.70 | 16915257.56 | SYNTHETIC_SCENARIO_V1
2025-09 | 4017202.12 | 4344812.52 | 4690851.37 | 21178436.58 | 20113927.22 | 21606108.93 | SYNTHETIC_SCENARIO_V1
2025-10 | 5409524.48 | 5230807.69 | 5679952.67 | 26587961.06 | 25344734.91 | 27286061.60 | SYNTHETIC_SCENARIO_V1
2025-11 | 6808669.82 | 6723097.15 | 7351379.23 | 33396630.88 | 32067832.06 | 34637440.83 | SYNTHETIC_SCENARIO_V1
2025-12 | 6743308.21 | 4804350.25 | 5285878.96 | 40139939.09 | 36872182.31 | 39923319.79 | SYNTHETIC_SCENARIO_V1
2026-01 | 4028945.07 | 5971589.27 | 6625613.51 | 44168884.16 | 42843771.58 | 46548933.30 | SYNTHETIC_SCENARIO_V1
2026-02 | 5393701.19 | 5173944.21 | 5724063.81 | 49562585.35 | 48017715.79 | 52272997.11 | SYNTHETIC_SCENARIO_V1
2026-03 | 4879011.51 | 5029584.95 | 5426641.79 | 54441596.86 | 53047300.74 | 57699638.90 | SYNTHETIC_SCENARIO_V1

## EVM_SCENARIOS
Project_ID | Scenario_Type | Scope_Description | Synthetic_Workday_Shift | Synthetic_Actual_Cost_Factor_Pct
P01 | CLOSED | Completed and accepted; post-completion invoices incur normal closeout adjustment. | 0 | 100
P02 | CLOSED | Completed; mechanical equipment experienced cost pressure. | 0 | 110
P03 | ACTIVE | Treatment equipment approval and construction progressing with modest delivery delay. | 7 | 108
P04 | ACTIVE | Tank rehabilitation has inspection/quality rework and cost pressure. | 9 | 112
P05 | ACTIVE | Four-zone field productivity below baseline. | 11 | 115
P06 | ACTIVE | AMI pilot staging experiencing integration delay and material premium. | 8 | 108
P07 | ACTIVE | PRV procurement and installation advancing with favorable productivity. | -3 | 96
P08 | ACTIVE | Generator manufacturing/installation has vendor delay and procurement premium. | 10 | 109
P09 | EARLY | Service line preconstruction progressing; no invented early field installations. | 4 | 103
P10 | FUTURE | Not yet started at March 31 cutoff. | 0 | 100
P11 | CLOSED | Valve program completed; productivity savings. | 0 | 95
P12 | STANDING | Year 1 and early Year 2 work orders with mixed emergency response throughput. | 5 | 106

## EVM_QA
QA_Test | Result | Status
Source component BAC | 88500000.00 | PASS
Baseline PV all 36 months | 88500000.00 | PASS
Program authorized contingency | 7500000.00 | EXCLUDED
Ownership lines | 342 | PASS
Unique evidence IDs | 343 | PASS
Unique cost entry IDs | 391 | PASS
Evidence EV vs snapshot | 0.00 | PASS
Cost ledger vs snapshot | 0.00 | PASS
PV baseline unchanged | 432 | PASS
All source schedule rows | 428 | UNCHANGED
All source relationships | 498 | UNCHANGED
Future actuals | 0 | PASS
Fully completed projects EV= BAC | True | PASS
EV cap and component progress | True | PASS
Program EAC sum project EAC | 95434737.44 | PASS