## 00_README
HWSD_Project_Controls_Model.xlsx
Source-of-truth project-controls workbook for the HWSD Municipal Water Capital Improvement Program (simulated).
Project BAC total (P01-P12): $88,500,000 ¦ Program contingency reserve: $7,500,000
Total program authorization: $96,000,000 ¦ 12 projects ¦ 36-month program (Jan 2025 - Dec 2027)
Status date (all PV/EV/AC/schedule status is measured as of this date): March 31, 2026 (Month 15 of 36)
IMPORTANT: For all Earned Value Management calculations (Phase 4), 'program BAC' means the
$88,500,000 project BAC total, NOT the $96,000,000 total authorization. The $7,500,000
contingency reserve is unallocated and only enters the model through an approved change
(07_CHANGES tab), at which point it is drawn down and the receiving project's BAC increases.
Build status: Phase 1 complete (01_PROJECTS). All other tabs are structural shells only —
column headers are final, but data has not yet been entered. Each phase of the build populates
the next tab(s). See the repository README for the full phase sequence.
Conventions used throughout this workbook:
- Blue font = hardcoded input. Black font = formula. Do not hand-edit formula cells.
- All dollar figures are in whole USD.
- project_id is the join key across every sheet in this workbook and every CSV in /02_data.
- This workbook is the controlled source of truth. Power BI and Python read from exports
of this workbook or from /02_data/processed — they do not maintain independent copies of
baseline data.
All program, project, cost, schedule, risk, and vendor data in this workbook is synthetic
and created for portfolio demonstration purposes only.

## 01_PROJECTS
Project Master List
One row per project. project_id is the join key used across every other sheet and CSV in this repository.
project_id | project_name | category | project_manager | bac | pct_of_project_bac_total | planned_start | planned_finish | planned_duration_months | status_as_of_status_date
P01 | Downtown 12-inch Water Main Replacement | Distribution | Maria Chen | 7400000 | 8.362% | 2025-01-01 | 2026-02-01 | 13 | Substantially Complete
P02 | Northside Pump Station Rehabilitation | Pumping | David Okafor | 8800000 | 9.944% | 2025-02-01 | 2026-09-01 | 19 | In Construction
P03 | Central Water Treatment Plant Process Upgrade | Treatment | Sarah Whitfield | 20300000 | 22.94% | 2025-01-01 | 2027-09-01 | 32 | In Construction
P04 | Hilltop Storage Tank Rehabilitation | Storage | James Patel | 5500000 | 6.215% | 2025-06-01 | 2026-04-01 | 10 | In Construction
P05 | Lead Service Line Replacement - Phase 1 | Distribution / Public Health | Maria Chen | 11100000 | 12.54% | 2025-03-01 | 2026-12-01 | 21 | In Construction
P06 | AMI / Smart Meter Modernization | Metering / Digital | Angela Torres | 6900000 | 7.797% | 2025-08-01 | 2026-10-01 | 14 | In Construction
P07 | East Zone Pressure Management Improvements | Distribution | Robert Kim | 4100000 | 4.633% | 2025-10-01 | 2026-06-01 | 8 | In Construction
P08 | Emergency Generator & Electrical Resiliency | Resiliency | Robert Kim | 4600000 | 5.198% | 2025-12-01 | 2027-02-01 | 14 | Design / Early Construction
P09 | River Crossing Main Rehabilitation | Distribution | David Okafor | 7800000 | 8.814% | 2026-02-01 | 2027-04-01 | 14 | Mobilization / Early Construction
P10 | SCADA Controls Modernization | Digital / Controls | Angela Torres | 3700000 | 4.181% | 2026-04-01 | 2027-03-01 | 11 | Planning / Not Started
P11 | Valve Replacement & Isolation Program | Distribution | James Patel | 3200000 | 3.616% | 2025-04-01 | 2026-08-01 | 16 | In Construction
P12 | Programwide Small Capital & Emergency Response Improvements | Small Capital & Emergency Response | Program Controls Office | 5100000 | 5.763% | 2025-01-01 | 2027-12-01 | 35 | Ongoing / As-Needed
| PROJECT BAC TOTAL (P01-P12) |  |  | 88500000
| Program Contingency Reserve (not a project; held at program level) |  |  | 7500000
| TOTAL PROGRAM AUTHORIZATION |  |  | 96000000
QA checks: | OK - Project BAC total = $88.5M
OK - Total program authorization = $96.0M
Note: | P12 (Programwide Small Capital & Emergency Response Improvements) is real, planned, scoped standing capital work with its own BAC, included in the $88.5M project total above. It is NOT the program contingency reserve. Truly unplanned/unscoped changes draw from the $7.5M program contingency reserve via an approved change request (07_CHANGES), not from P12.
Formulas:
planned_duration_months = DATEDIF([planned_start],[planned_finish],"m")

## 02_WBS
Work Breakdown Structure
Level 3 = Control Account (receives its own allocated BAC/PV/EV/AC in Phase 4; project BAC rolls up from its control accounts). Level 4 = Work Package (schedule activities in Phase 2 will attach here). Standard_Lifecycle_Phase maps every control account - including P12's differently-worded phases - back to one of six portfolio-wide categories for Power BI rollups.
WBS_Code | WBS_Level | Project_ID | Project_Name | Control_Account_ID | Control_Account_Name | Work_Package_ID | Work_Package_Name | Standard_Lifecycle_Phase | Responsible_Role | Description
1.01.1 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Downtown 12-inch Water Main Replacement: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.01.1.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning | P01-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Downtown 12-inch Water Main Replacement.
1.01.1.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning | P01-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Downtown 12-inch Water Main Replacement.
1.01.2 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Downtown 12-inch Water Main Replacement: develop and finalize engineering design to support procurement and construction.
1.01.2.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design | P01-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Downtown 12-inch Water Main Replacement.
1.01.2.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design | P01-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Downtown 12-inch Water Main Replacement.
1.01.3 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Downtown 12-inch Water Main Replacement: solicit, award, and execute construction and/or equipment contracts.
1.01.3.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement | P01-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Downtown 12-inch Water Main Replacement.
1.01.3.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement | P01-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Downtown 12-inch Water Main Replacement.
1.01.4 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Downtown 12-inch Water Main Replacement: execute physical construction, installation, or implementation work.
1.01.4.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP041 | Pipe Installation & Jointing | Construction | Construction Manager / Contractor | Excavate, lay, and joint new 12-inch ductile iron water main along the downtown corridor route.
1.01.4.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP042 | Valve & Hydrant Tie-Ins | Construction | Construction Manager / Contractor | Install new isolation valves and fire hydrant connections and tie into the existing distribution system.
1.01.4.3 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP043 | Pavement & Surface Restoration | Construction | Construction Manager / Contractor | Backfill, compact, and restore pavement, sidewalks, and surface features disturbed by construction.
1.01.5 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Downtown 12-inch Water Main Replacement: test, start up, and verify system performance prior to acceptance.
1.01.5.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA05 | Testing & Commissioning | P01-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Downtown 12-inch Water Main Replacement.
1.01.6 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Downtown 12-inch Water Main Replacement: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.01.6.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout | P01-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Downtown 12-inch Water Main Replacement.
1.01.6.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout | P01-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Downtown 12-inch Water Main Replacement.
1.02.1 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Northside Pump Station Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.02.1.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning | P02-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Northside Pump Station Rehabilitation.
1.02.1.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning | P02-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Northside Pump Station Rehabilitation.
1.02.2 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Northside Pump Station Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.02.2.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design | P02-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Northside Pump Station Rehabilitation.
1.02.2.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design | P02-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Northside Pump Station Rehabilitation.
1.02.3 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Northside Pump Station Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.02.3.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement | P02-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Northside Pump Station Rehabilitation.
1.02.3.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement | P02-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Northside Pump Station Rehabilitation.
1.02.4 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Northside Pump Station Rehabilitation: execute physical construction, installation, or implementation work.
1.02.4.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP041 | Pump & Motor Replacement | Construction | Construction Manager / Contractor | Remove existing pumps and motors and install new high-efficiency units per design.
1.02.4.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP042 | Electrical Switchgear Upgrade | Construction | Construction Manager / Contractor | Replace station switchgear, VFDs, and associated electrical distribution equipment.
1.02.4.3 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP043 | Wetwell Structural Rehabilitation | Construction | Construction Manager / Contractor | Repair and recoat wetwell concrete structure and associated access hardware.
1.02.5 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Northside Pump Station Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.02.5.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA05 | Testing & Commissioning | P02-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Northside Pump Station Rehabilitation.
1.02.6 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Northside Pump Station Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.02.6.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout | P02-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Northside Pump Station Rehabilitation.
1.02.6.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout | P02-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Northside Pump Station Rehabilitation.
1.03.1 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Central Water Treatment Plant Process Upgrade: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.03.1.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning | P03-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Central Water Treatment Plant Process Upgrade.
1.03.1.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning | P03-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Central Water Treatment Plant Process Upgrade.
1.03.2 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Central Water Treatment Plant Process Upgrade: develop and finalize engineering design to support procurement and construction.
1.03.2.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design | P03-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Central Water Treatment Plant Process Upgrade.
1.03.2.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design | P03-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Central Water Treatment Plant Process Upgrade.
1.03.3 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Central Water Treatment Plant Process Upgrade: solicit, award, and execute construction and/or equipment contracts.
1.03.3.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement | P03-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Central Water Treatment Plant Process Upgrade.
1.03.3.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement | P03-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Central Water Treatment Plant Process Upgrade.
1.03.4 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Central Water Treatment Plant Process Upgrade: execute physical construction, installation, or implementation work.
1.03.4.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP041 | Process Mechanical Installation | Construction | Construction Manager / Contractor | Install new process mechanical equipment (clarifiers, filters, pumps) per the treatment process design.
1.03.4.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP042 | Electrical & Instrumentation Installation | Construction | Construction Manager / Contractor | Install new electrical distribution, control panels, and process instrumentation.
1.03.4.3 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP043 | Chemical Feed System Installation | Construction | Construction Manager / Contractor | Install new chemical storage, feed pumps, and containment for treatment process chemicals.
1.03.5 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Central Water Treatment Plant Process Upgrade: test, start up, and verify system performance prior to acceptance.
1.03.5.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP051 | Process Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform sequential process startup and functional testing of new mechanical and electrical systems.
1.03.5.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP052 | Performance / Acceptance Testing | Testing & Commissioning | Commissioning Lead | Conduct performance testing against design criteria and regulatory treatment standards.
1.03.5.3 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP053 | Regulatory Sign-off & SCADA Integration Checkout | Testing & Commissioning | Commissioning Lead | Coordinate state regulatory sign-off and verify full SCADA integration prior to substantial completion.
1.03.6 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Central Water Treatment Plant Process Upgrade: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.03.6.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout | P03-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Central Water Treatment Plant Process Upgrade.
1.03.6.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout | P03-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Central Water Treatment Plant Process Upgrade.
1.04.1 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Hilltop Storage Tank Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.04.1.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning | P04-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Hilltop Storage Tank Rehabilitation.
1.04.1.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning | P04-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Hilltop Storage Tank Rehabilitation.
1.04.2 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Hilltop Storage Tank Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.04.2.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design | P04-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Hilltop Storage Tank Rehabilitation.
1.04.2.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design | P04-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Hilltop Storage Tank Rehabilitation.
1.04.3 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Hilltop Storage Tank Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.04.3.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement | P04-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Hilltop Storage Tank Rehabilitation.
1.04.3.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement | P04-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Hilltop Storage Tank Rehabilitation.
1.04.4 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Hilltop Storage Tank Rehabilitation: execute physical construction, installation, or implementation work.
1.04.4.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP041 | Tank Interior/Exterior Coating | Construction | Construction Manager / Contractor | Prepare surfaces and apply new interior and exterior protective coating systems to the storage tank.
1.04.4.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP042 | Structural Steel Repairs | Construction | Construction Manager / Contractor | Repair or replace corroded structural steel members identified during inspection.
1.04.4.3 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP043 | Cathodic Protection System Installation | Construction | Construction Manager / Contractor | Install a new impressed-current cathodic protection system to mitigate future corrosion.
1.04.5 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Hilltop Storage Tank Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.04.5.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA05 | Testing & Commissioning | P04-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Hilltop Storage Tank Rehabilitation.
1.04.6 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Hilltop Storage Tank Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.04.6.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout | P04-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Hilltop Storage Tank Rehabilitation.
1.04.6.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout | P04-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Hilltop Storage Tank Rehabilitation.
1.05.1 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Lead Service Line Replacement - Phase 1: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.05.1.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning | P05-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Lead Service Line Replacement - Phase 1.
1.05.1.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning | P05-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Lead Service Line Replacement - Phase 1.
1.05.2 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Lead Service Line Replacement - Phase 1: develop and finalize engineering design to support procurement and construction.
1.05.2.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design | P05-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Lead Service Line Replacement - Phase 1.
1.05.2.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design | P05-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Lead Service Line Replacement - Phase 1.
1.05.3 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Lead Service Line Replacement - Phase 1: solicit, award, and execute construction and/or equipment contracts.
1.05.3.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement | P05-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Lead Service Line Replacement - Phase 1.
1.05.3.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement | P05-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Lead Service Line Replacement - Phase 1.
1.05.4 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Lead Service Line Replacement - Phase 1: execute physical construction, installation, or implementation work.
1.05.4.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP041 | Service Line Excavation & Replacement | Construction | Construction Manager / Contractor | Excavate and replace individual lead service lines with new copper or approved alternative piping.
1.05.4.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP042 | Property Restoration | Construction | Construction Manager / Contractor | Restore landscaping, driveways, and other surface features disturbed at each service address.
1.05.4.3 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP043 | Water Quality Sampling & Verification | Construction | Construction Manager / Contractor | Collect and analyze post-replacement water samples to verify compliance with lead action levels.
1.05.5 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Lead Service Line Replacement - Phase 1: test, start up, and verify system performance prior to acceptance.
1.05.5.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA05 | Testing & Commissioning | P05-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Lead Service Line Replacement - Phase 1.
1.05.6 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Lead Service Line Replacement - Phase 1: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.05.6.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout | P05-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Lead Service Line Replacement - Phase 1.
1.05.6.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout | P05-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Lead Service Line Replacement - Phase 1.
1.06.1 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for AMI / Smart Meter Modernization: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.06.1.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning | P06-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for AMI / Smart Meter Modernization.
1.06.1.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning | P06-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for AMI / Smart Meter Modernization.
1.06.2 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for AMI / Smart Meter Modernization: develop and finalize engineering design to support procurement and construction.
1.06.2.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design | P06-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for AMI / Smart Meter Modernization.
1.06.2.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design | P06-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for AMI / Smart Meter Modernization.
1.06.3 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for AMI / Smart Meter Modernization: solicit, award, and execute construction and/or equipment contracts.
1.06.3.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement | P06-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for AMI / Smart Meter Modernization.
1.06.3.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement | P06-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for AMI / Smart Meter Modernization.
1.06.4 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for AMI / Smart Meter Modernization: execute physical construction, installation, or implementation work.
1.06.4.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP041 | Meter Deployment & Installation | Construction | Construction Manager / Contractor | Remove existing meters and install new AMI-compatible meters at customer premises.
1.06.4.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP042 | Head-End System Integration | Construction | Construction Manager / Contractor | Install and configure the head-end data collection system and network gateways.
1.06.4.3 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP043 | Customer Data Migration & Validation | Construction | Construction Manager / Contractor | Migrate existing customer account and consumption data into the new metering platform and validate accuracy.
1.06.5 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for AMI / Smart Meter Modernization: test, start up, and verify system performance prior to acceptance.
1.06.5.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA05 | Testing & Commissioning | P06-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for AMI / Smart Meter Modernization.
1.06.6 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for AMI / Smart Meter Modernization: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.06.6.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout | P06-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for AMI / Smart Meter Modernization.
1.06.6.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout | P06-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for AMI / Smart Meter Modernization.
1.07.1 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for East Zone Pressure Management Improvements: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.07.1.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning | P07-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for East Zone Pressure Management Improvements.
1.07.1.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning | P07-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for East Zone Pressure Management Improvements.
1.07.2 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for East Zone Pressure Management Improvements: develop and finalize engineering design to support procurement and construction.
1.07.2.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design | P07-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for East Zone Pressure Management Improvements.
1.07.2.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design | P07-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for East Zone Pressure Management Improvements.
1.07.3 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for East Zone Pressure Management Improvements: solicit, award, and execute construction and/or equipment contracts.
1.07.3.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement | P07-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for East Zone Pressure Management Improvements.
1.07.3.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement | P07-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for East Zone Pressure Management Improvements.
1.07.4 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for East Zone Pressure Management Improvements: execute physical construction, installation, or implementation work.
1.07.4.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP041 | PRV Station Installation | Construction | Construction Manager / Contractor | Construct new pressure-reducing valve vaults and install PRV equipment at designated zone boundaries.
1.07.4.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP042 | Zone Isolation Valve Installation | Construction | Construction Manager / Contractor | Install new isolation valves to establish discrete pressure zone boundaries.
1.07.4.3 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP043 | Pressure Monitoring Instrumentation | Construction | Construction Manager / Contractor | Install remote pressure monitoring sensors and telemetry at key system locations.
1.07.5 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for East Zone Pressure Management Improvements: test, start up, and verify system performance prior to acceptance.
1.07.5.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA05 | Testing & Commissioning | P07-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for East Zone Pressure Management Improvements.
1.07.6 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for East Zone Pressure Management Improvements: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.07.6.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout | P07-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for East Zone Pressure Management Improvements.
1.07.6.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout | P07-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for East Zone Pressure Management Improvements.
1.08.1 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Emergency Generator & Electrical Resiliency: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.08.1.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning | P08-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Emergency Generator & Electrical Resiliency.
1.08.1.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning | P08-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Emergency Generator & Electrical Resiliency.
1.08.2 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Emergency Generator & Electrical Resiliency: develop and finalize engineering design to support procurement and construction.
1.08.2.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design | P08-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Emergency Generator & Electrical Resiliency.
1.08.2.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design | P08-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Emergency Generator & Electrical Resiliency.
1.08.3 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Emergency Generator & Electrical Resiliency: solicit, award, and execute construction and/or equipment contracts.
1.08.3.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement | P08-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Emergency Generator & Electrical Resiliency.
1.08.3.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement | P08-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Emergency Generator & Electrical Resiliency.
1.08.4 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Emergency Generator & Electrical Resiliency: execute physical construction, installation, or implementation work.
1.08.4.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP041 | Generator Installation | Construction | Construction Manager / Contractor | Install new standby generator units and associated foundations/enclosures at each site.
1.08.4.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP042 | Automatic Transfer Switch Installation | Construction | Construction Manager / Contractor | Install automatic transfer switches and integrate with existing electrical distribution.
1.08.4.3 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP043 | Fuel Storage System Installation | Construction | Construction Manager / Contractor | Install fuel storage tanks and supply piping per code requirements.
1.08.5 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Emergency Generator & Electrical Resiliency: test, start up, and verify system performance prior to acceptance.
1.08.5.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA05 | Testing & Commissioning | P08-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Emergency Generator & Electrical Resiliency.
1.08.6 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Emergency Generator & Electrical Resiliency: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.08.6.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout | P08-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Emergency Generator & Electrical Resiliency.
1.08.6.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout | P08-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Emergency Generator & Electrical Resiliency.
1.09.1 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for River Crossing Main Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.09.1.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning | P09-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for River Crossing Main Rehabilitation.
1.09.1.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning | P09-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for River Crossing Main Rehabilitation.
1.09.2 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for River Crossing Main Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.09.2.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design | P09-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for River Crossing Main Rehabilitation.
1.09.2.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design | P09-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for River Crossing Main Rehabilitation.
1.09.3 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for River Crossing Main Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.09.3.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement | P09-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for River Crossing Main Rehabilitation.
1.09.3.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement | P09-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for River Crossing Main Rehabilitation.
1.09.4 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for River Crossing Main Rehabilitation: execute physical construction, installation, or implementation work.
1.09.4.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP041 | Directional Drilling / Crossing Installation | Construction | Construction Manager / Contractor | Perform horizontal directional drilling to install new main beneath the river crossing.
1.09.4.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP042 | Pipe Fusion & Pressure Testing | Construction | Construction Manager / Contractor | Fuse HDPE pipe segments and perform hydrostatic pressure testing of the completed crossing.
1.09.4.3 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP043 | Riverbank Restoration | Construction | Construction Manager / Contractor | Restore riverbank grading, erosion control, and vegetation at entry/exit pit locations.
1.09.5 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for River Crossing Main Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.09.5.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA05 | Testing & Commissioning | P09-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for River Crossing Main Rehabilitation.
1.09.6 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for River Crossing Main Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.09.6.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout | P09-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for River Crossing Main Rehabilitation.
1.09.6.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout | P09-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for River Crossing Main Rehabilitation.
1.10.1 | 3 | P10 | SCADA Controls Modernization | P10-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for SCADA Controls Modernization: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.10.1.1 | 4 | P10 | SCADA Controls Modernization | P10-CA01 | Planning | P10-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for SCADA Controls Modernization.
1.10.1.2 | 4 | P10 | SCADA Controls Modernization | P10-CA01 | Planning | P10-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for SCADA Controls Modernization.
1.10.2 | 3 | P10 | SCADA Controls Modernization | P10-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for SCADA Controls Modernization: develop and finalize engineering design to support procurement and construction.
1.10.2.1 | 4 | P10 | SCADA Controls Modernization | P10-CA02 | Design | P10-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for SCADA Controls Modernization.
1.10.2.2 | 4 | P10 | SCADA Controls Modernization | P10-CA02 | Design | P10-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for SCADA Controls Modernization.
1.10.3 | 3 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for SCADA Controls Modernization: solicit, award, and execute construction and/or equipment contracts.
1.10.3.1 | 4 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement | P10-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for SCADA Controls Modernization.
1.10.3.2 | 4 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement | P10-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for SCADA Controls Modernization.
1.10.4 | 3 | P10 | SCADA Controls Modernization | P10-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for SCADA Controls Modernization: execute physical construction, installation, or implementation work.
1.10.4.1 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP041 | PLC Programming & Configuration | Construction | Construction Manager / Contractor | Develop and configure PLC logic for affected pump stations and treatment facilities.
1.10.4.2 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP042 | HMI Development | Construction | Construction Manager / Contractor | Develop human-machine interface screens and alarm configurations for operator use.
1.10.4.3 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP043 | Network & Communications Infrastructure | Construction | Construction Manager / Contractor | Install and configure the SCADA communications network linking field sites to the control center.
1.10.5 | 3 | P10 | SCADA Controls Modernization | P10-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for SCADA Controls Modernization: test, start up, and verify system performance prior to acceptance.
1.10.5.1 | 4 | P10 | SCADA Controls Modernization | P10-CA05 | Testing & Commissioning | P10-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for SCADA Controls Modernization.
1.10.6 | 3 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for SCADA Controls Modernization: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.10.6.1 | 4 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout | P10-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for SCADA Controls Modernization.
1.10.6.2 | 4 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout | P10-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for SCADA Controls Modernization.
1.11.1 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Valve Replacement & Isolation Program: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.11.1.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning | P11-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Valve Replacement & Isolation Program.
1.11.1.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning | P11-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Valve Replacement & Isolation Program.
1.11.2 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Valve Replacement & Isolation Program: develop and finalize engineering design to support procurement and construction.
1.11.2.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design | P11-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Valve Replacement & Isolation Program.
1.11.2.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design | P11-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Valve Replacement & Isolation Program.
1.11.3 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Valve Replacement & Isolation Program: solicit, award, and execute construction and/or equipment contracts.
1.11.3.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement | P11-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Valve Replacement & Isolation Program.
1.11.3.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement | P11-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Valve Replacement & Isolation Program.
1.11.4 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Valve Replacement & Isolation Program: execute physical construction, installation, or implementation work.
1.11.4.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP041 | Isolation Valve Installation | Construction | Construction Manager / Contractor | Install new isolation valves at designated locations across the distribution system.
1.11.4.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP042 | Distribution System Mapping Update | Construction | Construction Manager / Contractor | Update GIS and system mapping records to reflect newly installed valve locations and status.
1.11.4.3 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP043 | Site Restoration | Construction | Construction Manager / Contractor | Restore pavement and surface conditions at each valve installation location.
1.11.5 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Valve Replacement & Isolation Program: test, start up, and verify system performance prior to acceptance.
1.11.5.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA05 | Testing & Commissioning | P11-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Valve Replacement & Isolation Program.
1.11.6 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Valve Replacement & Isolation Program: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.11.6.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout | P11-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Valve Replacement & Isolation Program.
1.11.6.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout | P11-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Valve Replacement & Isolation Program.
1.12.1 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA01 | Planning & Prioritization |  |  | Planning | Program Controls Office | Planning & Prioritization phase for Programwide Small Capital & Emergency Response Improvements: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.12.1.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA01 | Planning & Prioritization | P12-WP011 | Work Order Intake & Prioritization | Planning | Program Controls Office | Intake, screen, and prioritize candidate small-capital and emergency work orders across the program.
1.12.2 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA02 | Design / Scope Development |  |  | Design | Program Controls Office | Design / Scope Development phase for Programwide Small Capital & Emergency Response Improvements: develop and finalize engineering design to support procurement and construction.
1.12.2.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA02 | Design / Scope Development | P12-WP021 | Field Scoping & Estimate | Design | Program Controls Office | Develop field scope and cost estimate for prioritized work orders.
1.12.3 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Programwide Small Capital & Emergency Response Improvements: solicit, award, and execute construction and/or equipment contracts.
1.12.3.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA03 | Procurement | P12-WP031 | Contractor / Materials Procurement | Procurement | Procurement & Contracts Lead | Procure contractor task-order support and/or materials for prioritized work orders.
1.12.4 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution |  |  | Construction | Field Operations / Contractor | Execution phase for Programwide Small Capital & Emergency Response Improvements: perform planned small-capital repairs and prioritized emergency-response work.
1.12.4.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution | P12-WP041 | Small Capital Repair Execution | Construction | Field Operations / Contractor | Execute planned, prioritized small-capital repair work orders across the distribution system.
1.12.4.2 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution | P12-WP042 | Emergency Response Work Execution | Construction | Field Operations / Contractor | Execute unplanned emergency repair work orders as they are identified and prioritized.
1.12.5 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA05 | Verification / Acceptance |  |  | Testing & Commissioning | Program Controls Office | Verification / Acceptance phase for Programwide Small Capital & Emergency Response Improvements: confirm completed work meets specification before closing the work order.
1.12.5.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA05 | Verification / Acceptance | P12-WP051 | Work Order Acceptance & Sign-off | Testing & Commissioning | Program Controls Office | Confirm completed work orders meet specification and obtain sign-off.
1.12.6 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA06 | Closeout |  |  | Closeout | Program Controls Office | Closeout phase for Programwide Small Capital & Emergency Response Improvements: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.12.6.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA06 | Closeout | P12-WP061 | Documentation & Work Order Closeout | Closeout | Program Controls Office | Finalize work order documentation and close out completed small-capital/emergency work orders.

## 03_SCHEDULE
Schedule
Not yet populated - built in Phase 2 (Baseline Schedule).
activity_id | project_id | activity_name | wbs_code | baseline_start | baseline_finish | forecast_start | forecast_finish | actual_start | actual_finish | duration_days | predecessor | percent_complete | is_milestone | critical_flag

## 04_MONTHLY_COSTS
Monthly Costs
Not yet populated - built in Phase 3 (Monthly Cost Model). Baseline monthly spend per project must sum to that project's BAC.
month | project_id | baseline_monthly | baseline_cumulative | actual_monthly | actual_cumulative | committed_cost | forecast_remaining | forecast_at_completion

## 05_EVM
Evm
Not yet populated - built in Phase 4 (Earned Value Management), calculated as of the status date (Mar 31, 2026).
project_id | bac | pv | ev | ac | cv | sv | cpi | spi | eac | etc | vac | rag_status

## 06_RISKS
Risks
Not yet populated - built in Phase 5 (Risk Register). 25-40 risks planned across the program.
risk_id | project_id | risk_category | risk_statement | probability_score | impact_score | inherent_score | owner | response_strategy | mitigation | residual_probability | residual_impact | residual_score | status

## 07_CHANGES
Changes
Not yet populated - built in Phase 6 (Change Control), including the featured $600K / six-week contractor change scenario.
change_id | project_id | change_description | cause | requested_date | approval_status | cost_impact | schedule_impact_days | contingency_drawdown | approved_by

## 08_RESOURCES
Resources
Not yet populated - built in Phase 7 (Staffing / Resource Plan).
month | project_id | role | planned_fte | notes

## 09_VENDORS
Vendors
Not yet populated - built in Phase 7 (Contractor / Vendor Tracker).
vendor_id | vendor_name | role | project_id | contract_value | status | performance_notes

## 10_MILESTONES
Milestones
Not yet populated - built in Phase 8 (Milestone Tracker). 35-50 milestones planned across the program.
milestone_id | project_id | milestone_name | baseline_date | forecast_date | actual_date | variance_days | status

## 11_KPI_THRESHOLDS
Kpi Thresholds
Not yet populated - built in Phase 4, alongside EVM. Defines RAG (Red/Amber/Green) status logic. These are project assumptions, not industry-mandated values.
kpi | green_threshold | amber_threshold | red_threshold

## 12_DASHBOARD_DATA
Dashboard Data
Not yet populated - built in Phase 9 (Power BI Prep). Flattened export tables consumed by the Power BI dashboard.
table_name | description | refreshed_from