## 00_README
HWSD_Project_Controls_Model.xlsx
Source-of-truth project-controls workbook for the HWSD Municipal Water Capital Improvement Program (simulated).
Project BAC total (P01-P12): $88,500,000 ¦ Program contingency reserve: $7,500,000
Total program authorization: $96,000,000 ¦ 12 projects ¦ 36-month program (Jan 2025 - Dec 2027)
Status date (all PV/EV/AC/schedule status is measured as of this date): March 31, 2026 (Month 15 of 36)
IMPORTANT: For all Earned Value Management calculations (Phase 4), 'program BAC' means the
$88,500,000 project BAC total, NOT the $96,000,000 total authorization. The $7,500,000
contingency reserve is unallocated and only enters the model through an approved change
(07_CHANGES tab), at which point it is drawn down and the receiving project's BAC increases.
Build status: Phase 1 complete (01_PROJECTS). All other tabs are structural shells only —
column headers are final, but data has not yet been entered. Each phase of the build populates
the next tab(s). See the repository README for the full phase sequence.
Conventions used throughout this workbook:
- Blue font = hardcoded input. Black font = formula. Do not hand-edit formula cells.
- All dollar figures are in whole USD.
- project_id is the join key across every sheet in this workbook and every CSV in /02_data.
- This workbook is the controlled source of truth. Power BI and Python read from exports
of this workbook or from /02_data/processed — they do not maintain independent copies of
baseline data.
All program, project, cost, schedule, risk, and vendor data in this workbook is synthetic
and created for portfolio demonstration purposes only.
BASELINE CONTROL — SYNTHETIC RECOVERY APPROVED
03_SCHEDULE: 428 activity/milestone rows; 03_SCHEDULE_RELATIONSHIPS: 498 dependency records.
Schedule CPM complete: 428 activities and milestones; 498 dependency records; all twelve approved project finishes unchanged.
Five user-approved synthetic NTP release holds were inserted and retained in the relationship CSV.
Critical / near-critical criteria: 0bd / 1–5bd total float under per-project finish anchors. See CPM_SUMMARY and CPM_METHOD.
P08-MOUTAGE is independently fixed on 2026-05-22; its zero float is constraint-driven and not evidence of the governing construction path.
Project BAC $88.5M, reserve $7.5M, authorized total $96M unchanged.

## 01_PROJECTS
Project Master List
One row per project. project_id is the join key used across every other sheet and CSV in this repository.
project_id | project_name | category | project_manager | bac | pct_of_project_bac_total | planned_start | planned_finish | planned_duration_months | status_as_of_status_date
P01 | Downtown 12-inch Water Main Replacement | Distribution | Maria Chen | 7400000 | 8.362% | 2025-01-02 | 2025-12-29 | 11.9 | Substantially Complete
P02 | Northside Pump Station Rehabilitation | Pumping | David Okafor | 8800000 | 9.944% | 2025-02-03 | 2026-02-25 | 12.7 | In Construction
P03 | Central Water Treatment Plant Process Upgrade | Treatment | Sarah Whitfield | 20300000 | 22.94% | 2025-01-02 | 2027-01-27 | 24.8 | In Construction
P04 | Hilltop Storage Tank Rehabilitation | Storage | James Patel | 5500000 | 6.215% | 2025-06-02 | 2026-04-24 | 10.7 | In Construction
P05 | Lead Service Line Replacement - Phase 1 | Distribution / Public Health | Maria Chen | 11100000 | 12.54% | 2025-03-03 | 2026-05-15 | 14.4 | In Construction
P06 | AMI / Smart Meter Modernization | Metering / Digital | Angela Torres | 6900000 | 7.797% | 2025-08-01 | 2026-12-24 | 16.8 | In Construction
P07 | East Zone Pressure Management Improvements | Distribution | Robert Kim | 4100000 | 4.633% | 2025-10-01 | 2026-09-01 | 11 | In Construction
P08 | Emergency Generator & Electrical Resiliency | Resiliency | Robert Kim | 4600000 | 5.198% | 2025-12-01 | 2027-01-08 | 13.2 | Design / Early Construction
P09 | River Crossing Main Rehabilitation | Distribution | David Okafor | 7800000 | 8.814% | 2026-02-02 | 2027-03-03 | 12.9 | Mobilization / Early Construction
P10 | SCADA Controls Modernization | Digital / Controls | Angela Torres | 3700000 | 4.181% | 2026-04-01 | 2027-08-06 | 16.2 | Planning / Not Started
P11 | Valve Replacement & Isolation Program | Distribution | James Patel | 3200000 | 3.616% | 2025-04-01 | 2026-03-09 | 11.2 | In Construction
P12 | Programwide Small Capital & Emergency Response Improvements | Small Capital & Emergency Response | Program Controls Office | 5100000 | 5.763% | 2025-01-02 | 2027-06-23 | 29.6 | Ongoing / As-Needed
| PROJECT BAC TOTAL (P01-P12) |  |  | 88500000
| Program Contingency Reserve (not a project; held at program level) |  |  | 7500000
| TOTAL PROGRAM AUTHORIZATION |  |  | 96000000
QA checks: | OK - Project BAC total = $88.5M
OK - Total program authorization = $96.0M
Note: | P12 (Programwide Small Capital & Emergency Response Improvements) is real, planned, scoped standing capital work with its own BAC, included in the $88.5M project total above. It is NOT the program contingency reserve. Truly unplanned/unscoped changes draw from the $7.5M program contingency reserve via an approved change request (07_CHANGES), not from P12.

## 02_WBS
Work Breakdown Structure
Level 3 = Control Account (receives its own allocated BAC/PV/EV/AC in Phase 4; project BAC rolls up from its control accounts). Level 4 = Work Package (schedule activities in Phase 2 will attach here). Standard_Lifecycle_Phase maps every control account - including P12's differently-worded phases - back to one of six portfolio-wide categories for Power BI rollups.
WBS_Code | WBS_Level | Project_ID | Project_Name | Control_Account_ID | Control_Account_Name | Work_Package_ID | Work_Package_Name | Standard_Lifecycle_Phase | Responsible_Role | Description
1.01.1 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Downtown 12-inch Water Main Replacement: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.01.1.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning | P01-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Downtown 12-inch Water Main Replacement.
1.01.1.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA01 | Planning | P01-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Downtown 12-inch Water Main Replacement.
1.01.2 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Downtown 12-inch Water Main Replacement: develop and finalize engineering design to support procurement and construction.
1.01.2.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design | P01-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Downtown 12-inch Water Main Replacement.
1.01.2.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA02 | Design | P01-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Downtown 12-inch Water Main Replacement.
1.01.3 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Downtown 12-inch Water Main Replacement: solicit, award, and execute construction and/or equipment contracts.
1.01.3.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement | P01-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Downtown 12-inch Water Main Replacement.
1.01.3.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA03 | Procurement | P01-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Downtown 12-inch Water Main Replacement.
1.01.4 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Downtown 12-inch Water Main Replacement: execute physical construction, installation, or implementation work.
1.01.4.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP041 | Pipe Installation & Jointing | Construction | Construction Manager / Contractor | Excavate, lay, and joint new 12-inch ductile iron water main along the downtown corridor route.
1.01.4.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP042 | Valve & Hydrant Tie-Ins | Construction | Construction Manager / Contractor | Install new isolation valves and fire hydrant connections and tie into the existing distribution system.
1.01.4.3 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA04 | Construction | P01-WP043 | Pavement & Surface Restoration | Construction | Construction Manager / Contractor | Backfill, compact, and restore pavement, sidewalks, and surface features disturbed by construction.
1.01.5 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Downtown 12-inch Water Main Replacement: test, start up, and verify system performance prior to acceptance.
1.01.5.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA05 | Testing & Commissioning | P01-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Downtown 12-inch Water Main Replacement.
1.01.6 | 3 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Downtown 12-inch Water Main Replacement: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.01.6.1 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout | P01-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Downtown 12-inch Water Main Replacement.
1.01.6.2 | 4 | P01 | Downtown 12-inch Water Main Replacement | P01-CA06 | Closeout | P01-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Downtown 12-inch Water Main Replacement.
1.02.1 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Northside Pump Station Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.02.1.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning | P02-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Northside Pump Station Rehabilitation.
1.02.1.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA01 | Planning | P02-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Northside Pump Station Rehabilitation.
1.02.2 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Northside Pump Station Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.02.2.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design | P02-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Northside Pump Station Rehabilitation.
1.02.2.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA02 | Design | P02-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Northside Pump Station Rehabilitation.
1.02.3 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Northside Pump Station Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.02.3.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement | P02-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Northside Pump Station Rehabilitation.
1.02.3.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA03 | Procurement | P02-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Northside Pump Station Rehabilitation.
1.02.4 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Northside Pump Station Rehabilitation: execute physical construction, installation, or implementation work.
1.02.4.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP041 | Pump & Motor Replacement | Construction | Construction Manager / Contractor | Remove existing pumps and motors and install new high-efficiency units per design.
1.02.4.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP042 | Electrical Switchgear Upgrade | Construction | Construction Manager / Contractor | Replace station switchgear, VFDs, and associated electrical distribution equipment.
1.02.4.3 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA04 | Construction | P02-WP043 | Wetwell Structural Rehabilitation | Construction | Construction Manager / Contractor | Repair and recoat wetwell concrete structure and associated access hardware.
1.02.5 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Northside Pump Station Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.02.5.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA05 | Testing & Commissioning | P02-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Northside Pump Station Rehabilitation.
1.02.6 | 3 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Northside Pump Station Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.02.6.1 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout | P02-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Northside Pump Station Rehabilitation.
1.02.6.2 | 4 | P02 | Northside Pump Station Rehabilitation | P02-CA06 | Closeout | P02-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Northside Pump Station Rehabilitation.
1.03.1 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Central Water Treatment Plant Process Upgrade: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.03.1.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning | P03-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Central Water Treatment Plant Process Upgrade.
1.03.1.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA01 | Planning | P03-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Central Water Treatment Plant Process Upgrade.
1.03.2 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Central Water Treatment Plant Process Upgrade: develop and finalize engineering design to support procurement and construction.
1.03.2.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design | P03-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Central Water Treatment Plant Process Upgrade.
1.03.2.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA02 | Design | P03-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Central Water Treatment Plant Process Upgrade.
1.03.3 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Central Water Treatment Plant Process Upgrade: solicit, award, and execute construction and/or equipment contracts.
1.03.3.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement | P03-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Central Water Treatment Plant Process Upgrade.
1.03.3.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA03 | Procurement | P03-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Central Water Treatment Plant Process Upgrade.
1.03.4 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Central Water Treatment Plant Process Upgrade: execute physical construction, installation, or implementation work.
1.03.4.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP041 | Process Mechanical Installation | Construction | Construction Manager / Contractor | Install new process mechanical equipment (clarifiers, filters, pumps) per the treatment process design.
1.03.4.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP042 | Electrical & Instrumentation Installation | Construction | Construction Manager / Contractor | Install new electrical distribution, control panels, and process instrumentation.
1.03.4.3 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA04 | Construction | P03-WP043 | Chemical Feed System Installation | Construction | Construction Manager / Contractor | Install new chemical storage, feed pumps, and containment for treatment process chemicals.
1.03.5 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Central Water Treatment Plant Process Upgrade: test, start up, and verify system performance prior to acceptance.
1.03.5.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP051 | Process Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform sequential process startup and functional testing of new mechanical and electrical systems.
1.03.5.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP052 | Performance / Acceptance Testing | Testing & Commissioning | Commissioning Lead | Conduct performance testing against design criteria and regulatory treatment standards.
1.03.5.3 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA05 | Testing & Commissioning | P03-WP053 | Regulatory Sign-off & SCADA Integration Checkout | Testing & Commissioning | Commissioning Lead | Coordinate state regulatory sign-off and verify full SCADA integration prior to substantial completion.
1.03.6 | 3 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Central Water Treatment Plant Process Upgrade: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.03.6.1 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout | P03-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Central Water Treatment Plant Process Upgrade.
1.03.6.2 | 4 | P03 | Central Water Treatment Plant Process Upgrade | P03-CA06 | Closeout | P03-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Central Water Treatment Plant Process Upgrade.
1.04.1 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Hilltop Storage Tank Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.04.1.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning | P04-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Hilltop Storage Tank Rehabilitation.
1.04.1.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA01 | Planning | P04-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Hilltop Storage Tank Rehabilitation.
1.04.2 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Hilltop Storage Tank Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.04.2.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design | P04-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Hilltop Storage Tank Rehabilitation.
1.04.2.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA02 | Design | P04-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Hilltop Storage Tank Rehabilitation.
1.04.3 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Hilltop Storage Tank Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.04.3.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement | P04-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Hilltop Storage Tank Rehabilitation.
1.04.3.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA03 | Procurement | P04-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Hilltop Storage Tank Rehabilitation.
1.04.4 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Hilltop Storage Tank Rehabilitation: execute physical construction, installation, or implementation work.
1.04.4.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP041 | Tank Interior/Exterior Coating | Construction | Construction Manager / Contractor | Prepare surfaces and apply new interior and exterior protective coating systems to the storage tank.
1.04.4.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP042 | Structural Steel Repairs | Construction | Construction Manager / Contractor | Repair or replace corroded structural steel members identified during inspection.
1.04.4.3 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA04 | Construction | P04-WP043 | Cathodic Protection System Installation | Construction | Construction Manager / Contractor | Install a new impressed-current cathodic protection system to mitigate future corrosion.
1.04.5 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Hilltop Storage Tank Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.04.5.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA05 | Testing & Commissioning | P04-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Hilltop Storage Tank Rehabilitation.
1.04.6 | 3 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Hilltop Storage Tank Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.04.6.1 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout | P04-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Hilltop Storage Tank Rehabilitation.
1.04.6.2 | 4 | P04 | Hilltop Storage Tank Rehabilitation | P04-CA06 | Closeout | P04-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Hilltop Storage Tank Rehabilitation.
1.05.1 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Lead Service Line Replacement - Phase 1: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.05.1.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning | P05-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Lead Service Line Replacement - Phase 1.
1.05.1.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA01 | Planning | P05-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Lead Service Line Replacement - Phase 1.
1.05.2 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Lead Service Line Replacement - Phase 1: develop and finalize engineering design to support procurement and construction.
1.05.2.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design | P05-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Lead Service Line Replacement - Phase 1.
1.05.2.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA02 | Design | P05-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Lead Service Line Replacement - Phase 1.
1.05.3 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Lead Service Line Replacement - Phase 1: solicit, award, and execute construction and/or equipment contracts.
1.05.3.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement | P05-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Lead Service Line Replacement - Phase 1.
1.05.3.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA03 | Procurement | P05-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Lead Service Line Replacement - Phase 1.
1.05.4 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Lead Service Line Replacement - Phase 1: execute physical construction, installation, or implementation work.
1.05.4.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP041 | Service Line Excavation & Replacement | Construction | Construction Manager / Contractor | Excavate and replace individual lead service lines with new copper or approved alternative piping.
1.05.4.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP042 | Property Restoration | Construction | Construction Manager / Contractor | Restore landscaping, driveways, and other surface features disturbed at each service address.
1.05.4.3 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA04 | Construction | P05-WP043 | Water Quality Sampling & Verification | Construction | Construction Manager / Contractor | Collect and analyze post-replacement water samples to verify compliance with lead action levels.
1.05.5 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Lead Service Line Replacement - Phase 1: test, start up, and verify system performance prior to acceptance.
1.05.5.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA05 | Testing & Commissioning | P05-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Lead Service Line Replacement - Phase 1.
1.05.6 | 3 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Lead Service Line Replacement - Phase 1: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.05.6.1 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout | P05-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Lead Service Line Replacement - Phase 1.
1.05.6.2 | 4 | P05 | Lead Service Line Replacement - Phase 1 | P05-CA06 | Closeout | P05-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Lead Service Line Replacement - Phase 1.
1.06.1 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for AMI / Smart Meter Modernization: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.06.1.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning | P06-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for AMI / Smart Meter Modernization.
1.06.1.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA01 | Planning | P06-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for AMI / Smart Meter Modernization.
1.06.2 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for AMI / Smart Meter Modernization: develop and finalize engineering design to support procurement and construction.
1.06.2.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design | P06-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for AMI / Smart Meter Modernization.
1.06.2.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA02 | Design | P06-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for AMI / Smart Meter Modernization.
1.06.3 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for AMI / Smart Meter Modernization: solicit, award, and execute construction and/or equipment contracts.
1.06.3.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement | P06-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for AMI / Smart Meter Modernization.
1.06.3.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA03 | Procurement | P06-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for AMI / Smart Meter Modernization.
1.06.4 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for AMI / Smart Meter Modernization: execute physical construction, installation, or implementation work.
1.06.4.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP041 | Meter Deployment & Installation | Construction | Construction Manager / Contractor | Remove existing meters and install new AMI-compatible meters at customer premises.
1.06.4.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP042 | Head-End System Integration | Construction | Construction Manager / Contractor | Install and configure the head-end data collection system and network gateways.
1.06.4.3 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA04 | Construction | P06-WP043 | Customer Data Migration & Validation | Construction | Construction Manager / Contractor | Migrate existing customer account and consumption data into the new metering platform and validate accuracy.
1.06.5 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for AMI / Smart Meter Modernization: test, start up, and verify system performance prior to acceptance.
1.06.5.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA05 | Testing & Commissioning | P06-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for AMI / Smart Meter Modernization.
1.06.6 | 3 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for AMI / Smart Meter Modernization: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.06.6.1 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout | P06-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for AMI / Smart Meter Modernization.
1.06.6.2 | 4 | P06 | AMI / Smart Meter Modernization | P06-CA06 | Closeout | P06-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for AMI / Smart Meter Modernization.
1.07.1 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for East Zone Pressure Management Improvements: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.07.1.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning | P07-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for East Zone Pressure Management Improvements.
1.07.1.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA01 | Planning | P07-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for East Zone Pressure Management Improvements.
1.07.2 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for East Zone Pressure Management Improvements: develop and finalize engineering design to support procurement and construction.
1.07.2.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design | P07-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for East Zone Pressure Management Improvements.
1.07.2.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA02 | Design | P07-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for East Zone Pressure Management Improvements.
1.07.3 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for East Zone Pressure Management Improvements: solicit, award, and execute construction and/or equipment contracts.
1.07.3.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement | P07-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for East Zone Pressure Management Improvements.
1.07.3.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA03 | Procurement | P07-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for East Zone Pressure Management Improvements.
1.07.4 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for East Zone Pressure Management Improvements: execute physical construction, installation, or implementation work.
1.07.4.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP041 | PRV Station Installation | Construction | Construction Manager / Contractor | Construct new pressure-reducing valve vaults and install PRV equipment at designated zone boundaries.
1.07.4.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP042 | Zone Isolation Valve Installation | Construction | Construction Manager / Contractor | Install new isolation valves to establish discrete pressure zone boundaries.
1.07.4.3 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA04 | Construction | P07-WP043 | Pressure Monitoring Instrumentation | Construction | Construction Manager / Contractor | Install remote pressure monitoring sensors and telemetry at key system locations.
1.07.5 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for East Zone Pressure Management Improvements: test, start up, and verify system performance prior to acceptance.
1.07.5.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA05 | Testing & Commissioning | P07-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for East Zone Pressure Management Improvements.
1.07.6 | 3 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for East Zone Pressure Management Improvements: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.07.6.1 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout | P07-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for East Zone Pressure Management Improvements.
1.07.6.2 | 4 | P07 | East Zone Pressure Management Improvements | P07-CA06 | Closeout | P07-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for East Zone Pressure Management Improvements.
1.08.1 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Emergency Generator & Electrical Resiliency: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.08.1.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning | P08-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Emergency Generator & Electrical Resiliency.
1.08.1.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA01 | Planning | P08-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Emergency Generator & Electrical Resiliency.
1.08.2 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Emergency Generator & Electrical Resiliency: develop and finalize engineering design to support procurement and construction.
1.08.2.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design | P08-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Emergency Generator & Electrical Resiliency.
1.08.2.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA02 | Design | P08-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Emergency Generator & Electrical Resiliency.
1.08.3 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Emergency Generator & Electrical Resiliency: solicit, award, and execute construction and/or equipment contracts.
1.08.3.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement | P08-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Emergency Generator & Electrical Resiliency.
1.08.3.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA03 | Procurement | P08-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Emergency Generator & Electrical Resiliency.
1.08.4 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Emergency Generator & Electrical Resiliency: execute physical construction, installation, or implementation work.
1.08.4.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP041 | Generator Installation | Construction | Construction Manager / Contractor | Install new standby generator units and associated foundations/enclosures at each site.
1.08.4.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP042 | Automatic Transfer Switch Installation | Construction | Construction Manager / Contractor | Install automatic transfer switches and integrate with existing electrical distribution.
1.08.4.3 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA04 | Construction | P08-WP043 | Fuel Storage System Installation | Construction | Construction Manager / Contractor | Install fuel storage tanks and supply piping per code requirements.
1.08.5 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Emergency Generator & Electrical Resiliency: test, start up, and verify system performance prior to acceptance.
1.08.5.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA05 | Testing & Commissioning | P08-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Emergency Generator & Electrical Resiliency.
1.08.6 | 3 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Emergency Generator & Electrical Resiliency: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.08.6.1 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout | P08-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Emergency Generator & Electrical Resiliency.
1.08.6.2 | 4 | P08 | Emergency Generator & Electrical Resiliency | P08-CA06 | Closeout | P08-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Emergency Generator & Electrical Resiliency.
1.09.1 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for River Crossing Main Rehabilitation: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.09.1.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning | P09-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for River Crossing Main Rehabilitation.
1.09.1.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA01 | Planning | P09-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for River Crossing Main Rehabilitation.
1.09.2 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for River Crossing Main Rehabilitation: develop and finalize engineering design to support procurement and construction.
1.09.2.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design | P09-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for River Crossing Main Rehabilitation.
1.09.2.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA02 | Design | P09-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for River Crossing Main Rehabilitation.
1.09.3 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for River Crossing Main Rehabilitation: solicit, award, and execute construction and/or equipment contracts.
1.09.3.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement | P09-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for River Crossing Main Rehabilitation.
1.09.3.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA03 | Procurement | P09-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for River Crossing Main Rehabilitation.
1.09.4 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for River Crossing Main Rehabilitation: execute physical construction, installation, or implementation work.
1.09.4.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP041 | Directional Drilling / Crossing Installation | Construction | Construction Manager / Contractor | Perform horizontal directional drilling to install new main beneath the river crossing.
1.09.4.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP042 | Pipe Fusion & Pressure Testing | Construction | Construction Manager / Contractor | Fuse HDPE pipe segments and perform hydrostatic pressure testing of the completed crossing.
1.09.4.3 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA04 | Construction | P09-WP043 | Riverbank Restoration | Construction | Construction Manager / Contractor | Restore riverbank grading, erosion control, and vegetation at entry/exit pit locations.
1.09.5 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for River Crossing Main Rehabilitation: test, start up, and verify system performance prior to acceptance.
1.09.5.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA05 | Testing & Commissioning | P09-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for River Crossing Main Rehabilitation.
1.09.6 | 3 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for River Crossing Main Rehabilitation: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.09.6.1 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout | P09-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for River Crossing Main Rehabilitation.
1.09.6.2 | 4 | P09 | River Crossing Main Rehabilitation | P09-CA06 | Closeout | P09-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for River Crossing Main Rehabilitation.
1.10.1 | 3 | P10 | SCADA Controls Modernization | P10-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for SCADA Controls Modernization: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.10.1.1 | 4 | P10 | SCADA Controls Modernization | P10-CA01 | Planning | P10-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for SCADA Controls Modernization.
1.10.1.2 | 4 | P10 | SCADA Controls Modernization | P10-CA01 | Planning | P10-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for SCADA Controls Modernization.
1.10.2 | 3 | P10 | SCADA Controls Modernization | P10-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for SCADA Controls Modernization: develop and finalize engineering design to support procurement and construction.
1.10.2.1 | 4 | P10 | SCADA Controls Modernization | P10-CA02 | Design | P10-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for SCADA Controls Modernization.
1.10.2.2 | 4 | P10 | SCADA Controls Modernization | P10-CA02 | Design | P10-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for SCADA Controls Modernization.
1.10.3 | 3 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for SCADA Controls Modernization: solicit, award, and execute construction and/or equipment contracts.
1.10.3.1 | 4 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement | P10-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for SCADA Controls Modernization.
1.10.3.2 | 4 | P10 | SCADA Controls Modernization | P10-CA03 | Procurement | P10-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for SCADA Controls Modernization.
1.10.4 | 3 | P10 | SCADA Controls Modernization | P10-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for SCADA Controls Modernization: execute physical construction, installation, or implementation work.
1.10.4.1 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP041 | PLC Programming & Configuration | Construction | Construction Manager / Contractor | Develop and configure PLC logic for affected pump stations and treatment facilities.
1.10.4.2 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP042 | HMI Development | Construction | Construction Manager / Contractor | Develop human-machine interface screens and alarm configurations for operator use.
1.10.4.3 | 4 | P10 | SCADA Controls Modernization | P10-CA04 | Construction | P10-WP043 | Network & Communications Infrastructure | Construction | Construction Manager / Contractor | Install and configure the SCADA communications network linking field sites to the control center.
1.10.5 | 3 | P10 | SCADA Controls Modernization | P10-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for SCADA Controls Modernization: test, start up, and verify system performance prior to acceptance.
1.10.5.1 | 4 | P10 | SCADA Controls Modernization | P10-CA05 | Testing & Commissioning | P10-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for SCADA Controls Modernization.
1.10.6 | 3 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for SCADA Controls Modernization: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.10.6.1 | 4 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout | P10-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for SCADA Controls Modernization.
1.10.6.2 | 4 | P10 | SCADA Controls Modernization | P10-CA06 | Closeout | P10-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for SCADA Controls Modernization.
1.11.1 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning |  |  | Planning | Program Controls / Planning Lead | Planning phase for Valve Replacement & Isolation Program: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.11.1.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning | P11-WP011 | Needs Assessment | Planning | Program Controls / Planning Lead | Confirm the justification, condition assessment, and need for Valve Replacement & Isolation Program.
1.11.1.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA01 | Planning | P11-WP012 | Project Definition | Planning | Program Controls / Planning Lead | Finalize scope boundaries, success criteria, and program alignment for Valve Replacement & Isolation Program.
1.11.2 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design |  |  | Design | Design Engineer (Consultant) | Design phase for Valve Replacement & Isolation Program: develop and finalize engineering design to support procurement and construction.
1.11.2.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design | P11-WP021 | Preliminary Design (30%) | Design | Design Engineer (Consultant) | Develop preliminary (~30%) design concepts and basis of design for Valve Replacement & Isolation Program.
1.11.2.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA02 | Design | P11-WP022 | Final Design (100%) | Design | Design Engineer (Consultant) | Complete final (100%) design documents and specifications for Valve Replacement & Isolation Program.
1.11.3 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Valve Replacement & Isolation Program: solicit, award, and execute construction and/or equipment contracts.
1.11.3.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement | P11-WP031 | Bid Package & Solicitation | Procurement | Procurement & Contracts Lead | Prepare bid documents and solicit contractor/vendor proposals for Valve Replacement & Isolation Program.
1.11.3.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA03 | Procurement | P11-WP032 | Award & Mobilization | Procurement | Procurement & Contracts Lead | Award the contract and mobilize the contractor/vendor for Valve Replacement & Isolation Program.
1.11.4 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction |  |  | Construction | Construction Manager / Contractor | Construction phase for Valve Replacement & Isolation Program: execute physical construction, installation, or implementation work.
1.11.4.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP041 | Isolation Valve Installation | Construction | Construction Manager / Contractor | Install new isolation valves at designated locations across the distribution system.
1.11.4.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP042 | Distribution System Mapping Update | Construction | Construction Manager / Contractor | Update GIS and system mapping records to reflect newly installed valve locations and status.
1.11.4.3 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA04 | Construction | P11-WP043 | Site Restoration | Construction | Construction Manager / Contractor | Restore pavement and surface conditions at each valve installation location.
1.11.5 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA05 | Testing & Commissioning |  |  | Testing & Commissioning | Commissioning Lead | Testing & Commissioning phase for Valve Replacement & Isolation Program: test, start up, and verify system performance prior to acceptance.
1.11.5.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA05 | Testing & Commissioning | P11-WP051 | Startup & Functional Testing | Testing & Commissioning | Commissioning Lead | Perform startup and functional testing of completed work for Valve Replacement & Isolation Program.
1.11.6 | 3 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout |  |  | Closeout | Project Manager | Closeout phase for Valve Replacement & Isolation Program: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.11.6.1 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout | P11-WP061 | Documentation & Turnover | Closeout | Project Manager | Compile as-built documentation and turn over the completed asset to operations for Valve Replacement & Isolation Program.
1.11.6.2 | 4 | P11 | Valve Replacement & Isolation Program | P11-CA06 | Closeout | P11-WP062 | Financial Closeout | Closeout | Project Manager | Reconcile final costs, close out contracts, and complete financial closeout for Valve Replacement & Isolation Program.
1.12.1 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA01 | Planning & Prioritization |  |  | Planning | Program Controls Office | Planning & Prioritization phase for Programwide Small Capital & Emergency Response Improvements: confirm scope, budget, and regulatory requirements, and align with the overall program schedule.
1.12.1.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA01 | Planning & Prioritization | P12-WP011 | Work Order Intake & Prioritization | Planning | Program Controls Office | Intake, screen, and prioritize candidate small-capital and emergency work orders across the program.
1.12.2 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA02 | Design / Scope Development |  |  | Design | Program Controls Office | Design / Scope Development phase for Programwide Small Capital & Emergency Response Improvements: develop and finalize engineering design to support procurement and construction.
1.12.2.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA02 | Design / Scope Development | P12-WP021 | Field Scoping & Estimate | Design | Program Controls Office | Develop field scope and cost estimate for prioritized work orders.
1.12.3 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA03 | Procurement |  |  | Procurement | Procurement & Contracts Lead | Procurement phase for Programwide Small Capital & Emergency Response Improvements: solicit, award, and execute construction and/or equipment contracts.
1.12.3.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA03 | Procurement | P12-WP031 | Contractor / Materials Procurement | Procurement | Procurement & Contracts Lead | Procure contractor task-order support and/or materials for prioritized work orders.
1.12.4 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution |  |  | Construction | Field Operations / Contractor | Execution phase for Programwide Small Capital & Emergency Response Improvements: perform planned small-capital repairs and prioritized emergency-response work.
1.12.4.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution | P12-WP041 | Small Capital Repair Execution | Construction | Field Operations / Contractor | Execute planned, prioritized small-capital repair work orders across the distribution system.
1.12.4.2 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA04 | Execution | P12-WP042 | Emergency Response Work Execution | Construction | Field Operations / Contractor | Execute unplanned emergency repair work orders as they are identified and prioritized.
1.12.5 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA05 | Verification / Acceptance |  |  | Testing & Commissioning | Program Controls Office | Verification / Acceptance phase for Programwide Small Capital & Emergency Response Improvements: confirm completed work meets specification before closing the work order.
1.12.5.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA05 | Verification / Acceptance | P12-WP051 | Work Order Acceptance & Sign-off | Testing & Commissioning | Program Controls Office | Confirm completed work orders meet specification and obtain sign-off.
1.12.6 | 3 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA06 | Closeout |  |  | Closeout | Program Controls Office | Closeout phase for Programwide Small Capital & Emergency Response Improvements: complete punch-list items, finalize documentation, and transfer the asset to operations.
1.12.6.1 | 4 | P12 | Programwide Small Capital & Emergency Response Improvements | P12-CA06 | Closeout | P12-WP061 | Documentation & Work Order Closeout | Closeout | Program Controls Office | Finalize work order documentation and close out completed small-capital/emergency work orders.

## 03_SCHEDULE
Schedule
Approved HWSD synthetic recovery baseline — CPM calculated with per-project finish anchors, cross-project interfaces, 5 approved release holds and a source-explicit fixed-date P08 outage milestone.
activity_id | project_id | activity_name | wbs_code | baseline_start | baseline_finish | forecast_start | forecast_finish | actual_start | actual_finish | duration_days | predecessor | percent_complete | is_milestone | critical_flag | control_account_id | work_package_id | activity_type | assumption_basis | recovery_status | early_start | early_finish | late_start | late_finish | total_float_days
P01-A1 | P01 | Conduct Needs Assessment | 1.01.1.1 | 2025-01-02 | 2025-01-15 |  |  |  |  | 10 |  |  | FALSE | TRUE | P01-CA01 | P01-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-01-02 | 2025-01-15 | 2025-01-02 | 2025-01-15 | 0
P01-A6 | P01 | Contractor Mobilization | 1.01.3.2 | 2025-05-15 | 2025-06-04 |  |  |  |  | 15 | P01-M2 |  | FALSE | FALSE | P01-CA03 | P01-WP032 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-15 | 2025-06-04 | 2025-07-08 | 2025-07-28 | 38
P01-A7a | P01 | Pipe / Valve / Hydrant Submittal Review | 1.01.3.1 | 2025-05-15 | 2025-06-04 |  |  |  |  | 15 | P01-M2 |  | FALSE | TRUE | P01-CA03 | P01-WP031 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-15 | 2025-06-04 | 2025-05-15 | 2025-06-04 | 0
P01-A2 | P01 | Finalize Project Definition & Scope | 1.01.1.2 | 2025-01-16 | 2025-01-22 |  |  |  |  | 5 | P01-A1 |  | FALSE | TRUE | P01-CA01 | P01-WP012 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-01-16 | 2025-01-22 | 2025-01-16 | 2025-01-22 | 0
P01-A3 | P01 | Develop Preliminary Design | 1.01.2.1 | 2025-01-23 | 2025-02-19 |  |  |  |  | 20 | P01-A2 |  | FALSE | TRUE | P01-CA02 | P01-WP021 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-01-23 | 2025-02-19 | 2025-01-23 | 2025-02-19 | 0
P01-A7b | P01 | Pipe Fabrication | 1.01.4.1 | 2025-06-05 | 2025-07-16 |  |  |  |  | 30 | P01-A7a |  | FALSE | TRUE | P01-CA04 | P01-WP041 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-05 | 2025-07-16 | 2025-06-05 | 2025-07-16 | 0
P01-A4u | P01 | Utility Coordination & Locate Requests | 1.01.4.1 | 2025-02-20 | 2025-03-05 |  |  |  |  | 10 | P01-A3 |  | FALSE | FALSE | P01-CA04 | P01-WP041 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 10 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-20 | 2025-03-05 | 2025-07-15 | 2025-07-28 | 103
P01-A4 | P01 | Complete Final Design | 1.01.2.2 | 2025-03-06 | 2025-04-09 |  |  |  |  | 25 | P01-A3 |  | FALSE | TRUE | P01-CA02 | P01-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-03-06 | 2025-04-09 | 2025-03-06 | 2025-04-09 | 0
P01-A7c | P01 | Delivery & Receiving Inspection | 1.01.4.1 | 2025-07-17 | 2025-07-28 |  |  |  |  | 8 | P01-A7b |  | FALSE | TRUE | P01-CA04 | P01-WP041 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-17 | 2025-07-28 | 2025-07-17 | 2025-07-28 | 0
P01-A8 | P01 | Install & Joint Water Main Pipe | 1.01.4.1 | 2025-07-29 | 2025-09-29 |  |  |  |  | 45 | P01-A6, P01-A7c, P01-A4u |  | FALSE | TRUE | P01-CA04 | P01-WP041 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-29 | 2025-09-29 | 2025-07-29 | 2025-09-29 | 0
P01-A5 | P01 | Prepare & Advertise Bid Package | 1.01.3.1 | 2025-03-27 | 2025-04-16 |  |  |  |  | 15 | P01-A4 |  | FALSE | TRUE | P01-CA03 | P01-WP031 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-03-27 | 2025-04-16 | 2025-03-27 | 2025-04-16 | 0
P01-A9 | P01 | Install Valves & Hydrant Tie-Ins | 1.01.4.2 | 2025-08-19 | 2025-09-08 |  |  |  |  | 15 | P01-A8 |  | FALSE | FALSE | P01-CA04 | P01-WP042 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-19 | 2025-09-08 | 2025-09-16 | 2025-10-06 | 20
P01-A4b | P01 | Regulatory Plan Review & Approval | 1.01.2.2 | 2025-04-10 | 2025-04-30 |  |  |  |  | 15 | P01-A4 |  | FALSE | FALSE | P01-CA02 | P01-WP022 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 15 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-10 | 2025-04-30 | 2025-04-24 | 2025-05-14 | 10
P01-M1 | P01 | Design Complete | 1.01.2.2 | 2025-04-09 | 2025-04-09 |  |  |  |  | 0 | P01-A4 |  | TRUE | FALSE | P01-CA02 | P01-WP022 | Milestone | Approved standard milestone; exact milestone date reconstructed from final network | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-09 | 2025-04-09 | 2025-12-29 | 2025-12-29 | 188
P01-A9b | P01 | Shutdown Planning & Operations Coordination | 1.01.4.2 | 2025-08-26 | 2025-09-08 |  |  |  |  | 10 | P01-A8 |  | FALSE | FALSE | P01-CA04 | P01-WP042 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 10 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-26 | 2025-09-08 | 2025-09-23 | 2025-10-06 | 20
P01-A5b | P01 | Bid Evaluation, Selection & Award Recommendation | 1.01.3.1 | 2025-04-17 | 2025-04-30 |  |  |  |  | 10 | P01-A5 |  | FALSE | TRUE | P01-CA03 | P01-WP031 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-17 | 2025-04-30 | 2025-04-17 | 2025-04-30 | 0
P01-M2 | P01 | Contract Award / NTP | 1.01.3.2 | 2025-05-14 | 2025-05-14 |  |  |  |  | 0 | P01-A5b, P01-A4b |  | TRUE | TRUE | P01-CA03 | P01-WP032 | Milestone | Approved standard milestone; exact milestone date reconstructed from final network | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 0
P01-A11 | P01 | Pressure Testing & Disinfection | 1.01.5.1 | 2025-10-07 | 2025-10-13 |  |  |  |  | 5 | P01-A8, P01-A9, P01-A9b |  | FALSE | TRUE | P01-CA05 | P01-WP051 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-07 | 2025-10-13 | 2025-10-07 | 2025-10-13 | 0
P01-A12 | P01 | Bacteriological Sampling & Regulatory Clearance | 1.01.2.2 | 2025-10-14 | 2025-10-20 |  |  |  |  | 5 | P01-A11 |  | FALSE | TRUE | P01-CA02 | P01-WP022 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-14 | 2025-10-20 | 2025-10-14 | 2025-10-20 | 0
P01-A10 | P01 | Pavement & Surface Restoration | 1.01.4.3 | 2025-10-21 | 2025-11-10 |  |  |  |  | 15 | P01-A12 |  | FALSE | TRUE | P01-CA04 | P01-WP043 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-21 | 2025-11-10 | 2025-10-21 | 2025-11-10 | 0
P01-A13 | P01 | Documentation & Turnover | 1.01.6.1 | 2025-11-25 | 2025-12-08 |  |  |  |  | 10 | P01-M3 |  | FALSE | TRUE | P01-CA06 | P01-WP061 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered ¦ PROPOSED AFTER SUBSTANTIAL COMPLETION: final turnover -> financial closeout -> final completion (not original-source recovered) | 2025-11-25 | 2025-12-08 | 2025-11-25 | 2025-12-08 | 0
P01-A14 | P01 | Financial Closeout | 1.01.6.2 | 2025-12-09 | 2025-12-29 |  |  |  |  | 15 | P01-A13, P01-A15 |  | FALSE | TRUE | P01-CA06 | P01-WP062 | Task | Approved P01 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered ¦ PROPOSED AFTER SUBSTANTIAL COMPLETION: final turnover -> financial closeout -> final completion (not original-source recovered) | 2025-12-09 | 2025-12-29 | 2025-12-09 | 2025-12-29 | 0
P01-A15 | P01 | Final Inspection & Punch List | 1.01.4.1 | 2025-11-11 | 2025-11-24 |  |  |  |  | 10 | P01-A10 |  | FALSE | TRUE | P01-CA04 | P01-WP041 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 10 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-11 | 2025-11-24 | 2025-11-11 | 2025-11-24 | 0
P01-M3 | P01 | Substantial Completion | 1.01.5.1 | 2025-11-24 | 2025-11-24 |  |  |  |  | 0 | P01-A15 |  | TRUE | TRUE | P01-CA05 | P01-WP051 | Milestone | Approved standard milestone; exact milestone date reconstructed from final network | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 0
P01-M4 | P01 | Final Completion | 1.01.4.1 | 2025-12-29 | 2025-12-29 |  |  |  |  | 0 | P01-A14 |  | TRUE | TRUE | P01-CA04 | P01-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit validated finish date ¦ Scenario dates calculated from reconstructed logic, not source recovered ¦ PROPOSED AFTER SUBSTANTIAL COMPLETION: final turnover -> financial closeout -> final completion (not original-source recovered) | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 0
P02-A1 | P02 | Conduct Needs Assessment | 1.02.1.1 | 2025-02-03 | 2025-02-14 |  |  |  |  | 10 |  |  | FALSE | TRUE | P02-CA01 | P02-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-03 | 2025-02-14 | 2025-02-03 | 2025-02-14 | 0
P02-A11a | P02 | Switchgear/VFD Submittal & Shop Drawing Review | 1.02.4.2 | 2025-06-02 | 2025-06-27 |  |  |  |  | 20 | P02-M2 |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | Synthetic reconstruction from approved audit standard | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-02 | 2025-06-27 | 2025-06-23 | 2025-07-18 | 15
P02-A6 | P02 | Contractor Mobilization | 1.02.3.2 | 2025-06-02 | 2025-06-13 |  |  |  |  | 10 | P02-M2 |  | FALSE | FALSE | P02-CA03 | P02-WP032 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-02 | 2025-06-13 | 2025-10-09 | 2025-10-22 | 93
P02-A6b | P02 | Bypass Planning & Operations Coordination | 1.02.4.1 | 2025-02-03 | 2025-02-21 |  |  |  |  | 15 |  |  | FALSE | FALSE | P02-CA04 | P02-WP041 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 15 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-03 | 2025-02-21 | 2025-10-02 | 2025-10-22 | 173
P02-A6c | P02 | Electric Utility Coordination | 1.02.4.2 | 2025-02-03 | 2025-02-21 |  |  |  |  | 15 |  |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 15 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-03 | 2025-02-21 | 2025-11-13 | 2025-12-03 | 203
P02-A7a | P02 | Pump/Motor Submittal & Shop Drawing Review | 1.02.4.1 | 2025-06-02 | 2025-06-27 |  |  |  |  | 20 | P02-M2 |  | FALSE | TRUE | P02-CA04 | P02-WP041 | Task | Synthetic reconstruction from approved audit standard | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-02 | 2025-06-27 | 2025-06-02 | 2025-06-27 | 0
P02-A2 | P02 | Finalize Project Definition & Scope | 1.02.1.2 | 2025-02-17 | 2025-02-21 |  |  |  |  | 5 | P02-A1 |  | FALSE | TRUE | P02-CA01 | P02-WP012 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-21 | 0
P02-A3 | P02 | Develop Preliminary Design | 1.02.2.1 | 2025-02-24 | 2025-03-21 |  |  |  |  | 20 | P02-A2 |  | FALSE | TRUE | P02-CA02 | P02-WP021 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-24 | 2025-03-21 | 2025-02-24 | 2025-03-21 | 0
P02-A8 | P02 | Install Temporary Bypass Pumping | 1.02.4.1 | 2025-06-16 | 2025-06-27 |  |  |  |  | 10 | P02-A6, P02-A6b |  | FALSE | FALSE | P02-CA04 | P02-WP041 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-16 | 2025-06-27 | 2025-10-23 | 2025-11-05 | 93
P02-A11b | P02 | Switchgear/VFD Fabrication | 1.02.4.2 | 2025-06-30 | 2025-10-17 |  |  |  |  | 80 | P02-A11a |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | Approved equipment-realistic scenario | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-30 | 2025-10-17 | 2025-07-21 | 2025-11-07 | 15
P02-A7b | P02 | Pump/Motor Fabrication | 1.02.4.1 | 2025-06-30 | 2025-10-31 |  |  |  |  | 90 | P02-A7a |  | FALSE | TRUE | P02-CA04 | P02-WP041 | Task | Approved equipment-realistic scenario | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-30 | 2025-10-31 | 2025-06-30 | 2025-10-31 | 0
P02-A9 | P02 | Demolition & Removal | 1.02.4.1 | 2025-06-30 | 2025-07-18 |  |  |  |  | 15 | P02-A8 |  | FALSE | FALSE | P02-CA04 | P02-WP041 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-30 | 2025-07-18 | 2025-11-06 | 2025-11-26 | 93
P02-M3 | P02 | Bypass Operational | 1.02.4.1 | 2025-06-27 | 2025-06-27 |  |  |  |  | 0 | P02-A8 |  | TRUE | FALSE | P02-CA04 | P02-WP041 | Milestone | Approved P02 milestone | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-27 | 2025-06-27 | 2026-02-25 | 2026-02-25 | 173
P02-A4 | P02 | Complete Final Design | 1.02.2.2 | 2025-03-24 | 2025-04-25 |  |  |  |  | 25 | P02-A3 |  | FALSE | TRUE | P02-CA02 | P02-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-03-24 | 2025-04-25 | 2025-03-24 | 2025-04-25 | 0
P02-A13 | P02 | Wetwell Structural Rehabilitation | 1.02.4.3 | 2025-07-21 | 2025-08-15 |  |  |  |  | 20 | P02-A9 |  | FALSE | FALSE | P02-CA04 | P02-WP043 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-21 | 2025-08-15 | 2025-12-04 | 2025-12-31 | 98
P02-A5 | P02 | Prepare & Advertise Bid Package | 1.02.3.1 | 2025-04-14 | 2025-05-02 |  |  |  |  | 15 | P02-A4 |  | FALSE | TRUE | P02-CA03 | P02-WP031 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-14 | 2025-05-02 | 2025-04-14 | 2025-05-02 | 0
P02-A4b | P02 | Regulatory Plan Review & Approval | 1.02.2.2 | 2025-04-28 | 2025-05-23 |  |  |  |  | 20 | P02-A4 |  | FALSE | FALSE | P02-CA02 | P02-WP022 | Task | PROVISIONAL SYNTHETIC (user approved for planning only); exact original audit duration unavailable; retained 20 business days | USER-APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE RECOVERED ¦ APPROVED PROVISIONAL SYNTHETIC DURATION; NOT SOURCE-RECOVERED; DATE/NETWORK NOT BASELINE-APPROVED ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-28 | 2025-05-23 | 2025-05-05 | 2025-05-30 | 5
P02-M1 | P02 | Design Complete | 1.02.2.2 | 2025-04-25 | 2025-04-25 |  |  |  |  | 0 | P02-A4 |  | TRUE | FALSE | P02-CA02 | P02-WP022 | Milestone | Approved P02 milestone | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-25 | 2025-04-25 | 2026-02-25 | 2026-02-25 | 218
P02-A5b | P02 | Bid Evaluation, Selection & Award Recommendation | 1.02.3.1 | 2025-05-05 | 2025-05-16 |  |  |  |  | 10 | P02-A5 |  | FALSE | TRUE | P02-CA03 | P02-WP031 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-05 | 2025-05-16 | 2025-05-05 | 2025-05-16 | 0
P02-M2 | P02 | Contract Award / NTP | 1.02.3.2 | 2025-05-30 | 2025-05-30 |  |  |  |  | 0 | P02-A5b, P02-A4b |  | TRUE | TRUE | P02-CA03 | P02-WP032 | Milestone | Approved P02 milestone | UNRESOLVED: milestone depends on reconstructed P01/P02 network; exact approved date not recoverable from available source ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 0
P02-A11c | P02 | FAT — Switchgear/VFDs | 1.02.4.2 | 2025-10-20 | 2025-10-31 |  |  |  |  | 10 | P02-A11b |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-20 | 2025-10-31 | 2025-11-10 | 2025-11-21 | 15
P02-A11d | P02 | Delivery & Receiving — Switchgear/VFDs | 1.02.4.2 | 2025-11-03 | 2025-11-12 |  |  |  |  | 8 | P02-A11c |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-03 | 2025-11-12 | 2025-11-24 | 2025-12-03 | 15
P02-A7c | P02 | FAT — Pumps & Motors | 1.02.4.1 | 2025-11-03 | 2025-11-14 |  |  |  |  | 10 | P02-A7b |  | FALSE | TRUE | P02-CA04 | P02-WP041 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-03 | 2025-11-14 | 2025-11-03 | 2025-11-14 | 0
P02-A12 | P02 | Install Switchgear / VFDs | 1.02.4.2 | 2025-11-13 | 2025-12-10 |  |  |  |  | 20 | P02-A9, P02-A11d, P02-A6c |  | FALSE | FALSE | P02-CA04 | P02-WP042 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-13 | 2025-12-10 | 2025-12-04 | 2025-12-31 | 15
P02-A7d | P02 | Delivery & Receiving — Pumps & Motors | 1.02.4.1 | 2025-11-17 | 2025-11-26 |  |  |  |  | 8 | P02-A7c |  | FALSE | TRUE | P02-CA04 | P02-WP041 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-17 | 2025-11-26 | 2025-11-17 | 2025-11-26 | 0
P02-A10 | P02 | Install New Pumps & Motors | 1.02.4.1 | 2025-11-27 | 2025-12-31 |  |  |  |  | 25 | P02-A9, P02-A7d |  | FALSE | TRUE | P02-CA04 | P02-WP041 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-27 | 2025-12-31 | 2025-11-27 | 2025-12-31 | 0
P02-A14 | P02 | Startup & Functional Testing | 1.02.5.1 | 2026-01-01 | 2026-01-14 |  |  |  |  | 10 | P02-A10, P02-A12, P02-A13 |  | FALSE | TRUE | P02-CA05 | P02-WP051 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-01 | 2026-01-14 | 2026-01-01 | 2026-01-14 | 0
P02-A15 | P02 | Bypass Deactivation / Cutover | 1.02.5.1 | 2026-01-15 | 2026-01-21 |  |  |  |  | 5 | P02-A14 |  | FALSE | TRUE | P02-CA05 | P02-WP051 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-15 | 2026-01-21 | 2026-01-15 | 2026-01-21 | 0
P02-A15b | P02 | Final Inspection & Punch List | 1.02.4.1 | 2026-01-22 | 2026-02-04 |  |  |  |  | 10 | P02-A15 |  | FALSE | FALSE | P02-CA04 | P02-WP041 | Task | Approved realism audit | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-22 | 2026-02-04 | 2026-02-12 | 2026-02-25 | 15
P02-A16 | P02 | Documentation & Turnover | 1.02.6.1 | 2026-01-22 | 2026-02-04 |  |  |  |  | 10 | P02-A15 |  | FALSE | TRUE | P02-CA06 | P02-WP061 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-22 | 2026-02-04 | 2026-01-22 | 2026-02-04 | 0
P02-A17 | P02 | Financial Closeout | 1.02.6.2 | 2026-02-05 | 2026-02-25 |  |  |  |  | 15 | P02-A16, P02-A15b |  | FALSE | TRUE | P02-CA06 | P02-WP062 | Task | Approved P02 schedule | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-05 | 2026-02-25 | 2026-02-05 | 2026-02-25 | 0
P02-M4 | P02 | Substantial Completion | 1.02.5.1 | 2026-02-04 | 2026-02-04 |  |  |  |  | 0 | P02-A15b |  | TRUE | FALSE | P02-CA05 | P02-WP051 | Milestone | Approved P02 milestone; renamed in recovered export to avoid collision with existing final milestone ID | ID normalized to documented original P02 M4 Substantial Completion; provisional milestone date remains unverified ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-04 | 2026-02-04 | 2026-02-25 | 2026-02-25 | 15
P02-M5 | P02 | Final Completion | 1.02.4.1 | 2026-02-25 | 2026-02-25 |  |  |  |  | 0 | P02-A17 |  | TRUE | TRUE | P02-CA04 | P02-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit validated finish date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 0
P03-A1 | P03 | Conduct Needs Assessment | 1.03.1.1 | 2025-01-02 | 2025-01-22 |  |  |  |  | 15 |  |  | FALSE | TRUE | P03-CA01 | P03-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-01-02 | 2025-01-22 | 2025-01-02 | 2025-01-22 | 0
P03-A2 | P03 | Finalize Project Definition & Scope | 1.03.1.2 | 2025-01-23 | 2025-02-05 |  |  |  |  | 10 | P03-A1 |  | FALSE | TRUE | P03-CA01 | P03-WP012 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-01-23 | 2025-02-05 | 2025-01-23 | 2025-02-05 | 0
P03-A2b | P03 | Regulatory Pre-Design Coordination | 1.03.2.2 | 2025-02-06 | 2025-02-19 |  |  |  |  | 10 | P03-A2 |  | FALSE | TRUE | P03-CA02 | P03-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-06 | 2025-02-19 | 2025-02-06 | 2025-02-19 | 0
P03-A3 | P03 | Preliminary Design (30%) | 1.03.2.1 | 2025-02-20 | 2025-04-16 |  |  |  |  | 40 | P03-A2b |  | FALSE | TRUE | P03-CA02 | P03-WP021 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-02-20 | 2025-04-16 | 2025-02-20 | 2025-04-16 | 0
P03-A4 | P03 | Design Review Gate 1 (30% review & comment resolution) | 1.03.2.1 | 2025-04-17 | 2025-05-07 |  |  |  |  | 15 | P03-A3 |  | FALSE | TRUE | P03-CA02 | P03-WP021 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-04-17 | 2025-05-07 | 2025-04-17 | 2025-05-07 | 0
P03-A5 | P03 | 60%/90% Design Development | 1.03.2.2 | 2025-05-08 | 2025-06-18 |  |  |  |  | 30 | P03-A4 |  | FALSE | TRUE | P03-CA02 | P03-WP022 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-05-08 | 2025-06-18 | 2025-05-08 | 2025-06-18 | 0
P03-A6 | P03 | Design Review Gate 2 (90% review & comment resolution) | 1.03.2.2 | 2025-06-19 | 2025-07-09 |  |  |  |  | 15 | P03-A5 |  | FALSE | TRUE | P03-CA02 | P03-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-19 | 2025-07-09 | 2025-06-19 | 2025-07-09 | 0
P03-A7 | P03 | Final Design (100%) | 1.03.2.2 | 2025-06-26 | 2025-07-23 |  |  |  |  | 20 | P03-A6 |  | FALSE | TRUE | P03-CA02 | P03-WP022 | Task | Synthetic, industry-informed | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-06-26 | 2025-07-23 | 2025-06-26 | 2025-07-23 | 0
P03-I-P03-01 | P03 | Controls / I/O Design Freeze | 1.03.4.2 | 2025-07-23 | 2025-07-23 |  |  |  |  | 0 | P03-M1 |  | TRUE | FALSE | P03-CA04 | P03-WP042 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-23 | 2025-07-23 | 2027-01-27 | 2027-01-27 | 395
P03-M1 | P03 | Design Complete | 1.03.4.1 | 2025-07-23 | 2025-07-23 |  |  |  |  | 0 | P03-A7 |  | TRUE | FALSE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-23 | 2025-07-23 | 2027-01-27 | 2027-01-27 | 395
P03-A8 | P03 | Prepare & Advertise Bid Package | 1.03.3.1 | 2025-07-10 | 2025-08-06 |  |  |  |  | 20 | P03-A7 |  | FALSE | TRUE | P03-CA03 | P03-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-10 | 2025-08-06 | 2025-07-10 | 2025-08-06 | 0
P03-A7b | P03 | Regulatory Plan Review & Approval | 1.03.2.2 | 2025-07-24 | 2025-09-03 |  |  |  |  | 30 | P03-A7 |  | FALSE | FALSE | P03-CA02 | P03-WP022 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-07-24 | 2025-09-03 | 2025-08-07 | 2025-09-17 | 10
P03-A9 | P03 | Bid Evaluation, Selection & Award Recommendation | 1.03.3.1 | 2025-08-07 | 2025-08-27 |  |  |  |  | 15 | P03-A8 |  | FALSE | TRUE | P03-CA03 | P03-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-07 | 2025-08-27 | 2025-08-07 | 2025-08-27 | 0
P03-A9b | P03 | Governing Body Award Approval | 1.03.3.2 | 2025-08-28 | 2025-09-17 |  |  |  |  | 15 | P03-A9 |  | FALSE | TRUE | P03-CA03 | P03-WP032 | Task | Approved P03 v2 explicit replacement for +15bd lag | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-28 | 2025-09-17 | 2025-08-28 | 2025-09-17 | 0
P03-M2 | P03 | Contract Award / NTP | 1.03.4.1 | 2025-09-17 | 2025-09-17 |  |  |  |  | 0 | P03-A9b, P03-A7b |  | TRUE | TRUE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 0
P03-A10 | P03 | Contractor Mobilization | 1.03.3.2 | 2025-09-18 | 2025-10-15 |  |  |  |  | 20 | P03-M2 |  | FALSE | FALSE | P03-CA03 | P03-WP032 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-18 | 2025-10-15 | 2026-12-31 | 2027-01-27 | 335
P03-A11 | P03 | Process Equipment Submittal & Shop Drawing Review | 1.03.4.1 | 2025-09-18 | 2025-10-15 |  |  |  |  | 20 | P03-M2 |  | FALSE | TRUE | P03-CA04 | P03-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-18 | 2025-10-15 | 2025-09-18 | 2025-10-15 | 0
P03-A16 | P03 | Electrical/I&C Submittal & Shop Drawing Review | 1.03.4.2 | 2025-09-18 | 2025-10-15 |  |  |  |  | 20 | P03-M2 |  | FALSE | FALSE | P03-CA04 | P03-WP042 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-18 | 2025-10-15 | 2025-11-24 | 2025-12-19 | 47
P03-A21 | P03 | Chemical Feed Equipment Submittal & Review | 1.03.4.3 | 2025-09-18 | 2025-10-08 |  |  |  |  | 15 | P03-M2 |  | FALSE | FALSE | P03-CA04 | P03-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-18 | 2025-10-08 | 2026-03-23 | 2026-04-10 | 132
P03-A22 | P03 | Chemical Feed Equipment Fabrication | 1.03.4.3 | 2025-10-09 | 2025-12-17 |  |  |  |  | 50 | P03-A21 |  | FALSE | FALSE | P03-CA04 | P03-WP043 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-09 | 2025-12-17 | 2026-04-13 | 2026-06-19 | 132
P03-I-P03-02 | P03 | Approved Point List Available | 1.03.4.1 | 2025-10-15 | 2025-10-15 |  |  |  |  | 0 | P03-A16 |  | TRUE | FALSE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-15 | 2025-10-15 | 2026-11-17 | 2026-11-17 | 284
P03-A12 | P03 | Process Equipment Fabrication | 1.03.4.1 | 2025-10-16 | 2026-03-04 |  |  |  |  | 100 | P03-A11 |  | FALSE | TRUE | P03-CA04 | P03-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-16 | 2026-03-04 | 2025-10-16 | 2026-03-04 | 0
P03-A17 | P03 | Electrical Switchgear & Instrumentation Fabrication | 1.03.4.2 | 2025-10-16 | 2026-02-04 |  |  |  |  | 80 | P03-A16 |  | FALSE | FALSE | P03-CA04 | P03-WP042 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-16 | 2026-02-04 | 2025-12-22 | 2026-04-10 | 47
P03-A23 | P03 | Delivery & Receiving Inspection — Chemical Feed | 1.03.4.3 | 2025-12-18 | 2025-12-29 |  |  |  |  | 8 | P03-A22 |  | FALSE | FALSE | P03-CA04 | P03-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-18 | 2025-12-29 | 2026-06-22 | 2026-07-01 | 132
P03-A18 | P03 | FAT — Electrical/I&C | 1.03.4.2 | 2026-02-05 | 2026-02-18 |  |  |  |  | 10 | P03-A17 |  | FALSE | FALSE | P03-CA04 | P03-WP042 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-05 | 2026-02-18 | 2026-04-13 | 2026-04-24 | 47
P03-A19 | P03 | Delivery & Receiving Inspection — Electrical/I&C | 1.03.4.2 | 2026-02-19 | 2026-03-02 |  |  |  |  | 8 | P03-A18 |  | FALSE | FALSE | P03-CA04 | P03-WP042 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-19 | 2026-03-02 | 2026-04-27 | 2026-05-06 | 47
P03-A13 | P03 | FAT — Process Equipment | 1.03.4.1 | 2026-03-05 | 2026-03-25 |  |  |  |  | 15 | P03-A12 |  | FALSE | TRUE | P03-CA04 | P03-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-03-05 | 2026-03-25 | 2026-03-05 | 2026-03-25 | 0
P03-A14 | P03 | Delivery & Receiving Inspection — Process Equipment | 1.03.4.1 | 2026-03-26 | 2026-04-08 |  |  |  |  | 10 | P03-A13 |  | FALSE | TRUE | P03-CA04 | P03-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-03-26 | 2026-04-08 | 2026-03-26 | 2026-04-08 | 0
P03-M5 | P03 | Major Process Equipment Delivered | 1.03.4.1 | 2026-04-08 | 2026-04-08 |  |  |  |  | 0 | P03-A14 |  | TRUE | FALSE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-08 | 2026-04-08 | 2027-01-27 | 2027-01-27 | 210
P03-A15 | P03 | Process Mechanical Installation | 1.03.4.1 | 2026-04-09 | 2026-07-01 |  |  |  |  | 60 | P03-A14 |  | FALSE | TRUE | P03-CA04 | P03-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-09 | 2026-07-01 | 2026-04-09 | 2026-07-01 | 0
P03-A20 | P03 | Electrical & Instrumentation Installation | 1.03.4.2 | 2026-05-07 | 2026-07-08 |  |  |  |  | 45 | P03-A15, P03-A19 |  | FALSE | TRUE | P03-CA04 | P03-WP042 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-07 | 2026-07-08 | 2026-05-07 | 2026-07-08 | 0
P03-A24 | P03 | Chemical Feed System Installation | 1.03.4.3 | 2026-05-21 | 2026-06-24 |  |  |  |  | 25 | P03-A15, P03-A23 |  | FALSE | FALSE | P03-CA04 | P03-WP043 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-21 | 2026-06-24 | 2026-07-02 | 2026-08-05 | 30
P03-A25 | P03 | Electrical & Controls Integration | 1.03.4.2 | 2026-07-09 | 2026-08-05 |  |  |  |  | 20 | P03-A15, P03-A20 |  | FALSE | TRUE | P03-CA04 | P03-WP042 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-09 | 2026-08-05 | 2026-07-09 | 2026-08-05 | 0
P03-A26 | P03 | Pre-Startup Inspection & Punch List | 1.03.5.1 | 2026-08-06 | 2026-08-26 |  |  |  |  | 15 | P03-A15, P03-A25, P03-A24 |  | FALSE | TRUE | P03-CA05 | P03-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-06 | 2026-08-26 | 2026-08-06 | 2026-08-26 | 0
P03-I-P03-03 | P03 | Controls Installation Ready for Integration | 1.03.4.2 | 2026-08-26 | 2026-08-26 |  |  |  |  | 0 | P03-M6 |  | TRUE | FALSE | P03-CA04 | P03-WP042 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-08-26 | 2027-01-27 | 2027-01-27 | 110
P03-M6 | P03 | Installation Complete / Ready for Startup | 1.03.5.1 | 2026-08-26 | 2026-08-26 |  |  |  |  | 0 | P03-A26 |  | TRUE | FALSE | P03-CA05 | P03-WP051 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-08-26 | 2027-01-27 | 2027-01-27 | 110
P03-A27 | P03 | Process Startup & Functional Testing | 1.03.5.1 | 2026-08-27 | 2026-10-07 |  |  |  |  | 30 | P03-A26 |  | FALSE | TRUE | P03-CA05 | P03-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-27 | 2026-10-07 | 2026-08-27 | 2026-10-07 | 0
P03-A29 | P03 | SCADA Integration Checkout | 1.03.4.1 | 2026-09-10 | 2026-09-30 |  |  |  |  | 15 | P03-A27 |  | FALSE | FALSE | P03-CA04 | P03-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-09-10 | 2026-09-30 | 2026-10-15 | 2026-11-04 | 25
P03-M7 | P03 | Process Startup Complete | 1.03.5.1 | 2026-10-07 | 2026-10-07 |  |  |  |  | 0 | P03-A27 |  | TRUE | FALSE | P03-CA05 | P03-WP051 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-07 | 2026-10-07 | 2027-01-27 | 2027-01-27 | 80
P03-A28 | P03 | Performance / Acceptance Testing | 1.03.5.1 | 2026-10-08 | 2026-11-04 |  |  |  |  | 20 | P03-A27 |  | FALSE | TRUE | P03-CA05 | P03-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-08 | 2026-11-04 | 2026-10-08 | 2026-11-04 | 0
P03-M8 | P03 | Performance Testing Complete | 1.03.5.1 | 2026-11-04 | 2026-11-04 |  |  |  |  | 0 | P03-A28 |  | TRUE | FALSE | P03-CA05 | P03-WP051 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-04 | 2026-11-04 | 2027-01-27 | 2027-01-27 | 60
P03-A30 | P03 | Regulatory Acceptance / Final Inspection | 1.03.2.2 | 2026-11-05 | 2026-12-02 |  |  |  |  | 20 | P03-A28, P03-A29 |  | FALSE | TRUE | P03-CA02 | P03-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-05 | 2026-12-02 | 2026-11-05 | 2026-12-02 | 0
P03-M3 | P03 | Substantial Completion | 1.03.4.1 | 2026-12-02 | 2026-12-02 |  |  |  |  | 0 | P03-A30 |  | TRUE | FALSE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-02 | 2026-12-02 | 2027-01-27 | 2027-01-27 | 40
P03-M9 | P03 | Regulatory Acceptance | 1.03.2.2 | 2026-12-02 | 2026-12-02 |  |  |  |  | 0 | P03-A30 |  | TRUE | FALSE | P03-CA02 | P03-WP022 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-02 | 2026-12-02 | 2027-01-27 | 2027-01-27 | 40
P03-A31 | P03 | Final Inspection & Punch List (closeout) | 1.03.6.1 | 2026-12-03 | 2026-12-23 |  |  |  |  | 15 | P03-A30 |  | FALSE | FALSE | P03-CA06 | P03-WP061 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-03 | 2026-12-23 | 2027-01-07 | 2027-01-27 | 25
P03-A32 | P03 | Documentation & Turnover | 1.03.6.1 | 2026-12-03 | 2026-12-30 |  |  |  |  | 20 | P03-A30 |  | FALSE | TRUE | P03-CA06 | P03-WP061 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-03 | 2026-12-30 | 2026-12-03 | 2026-12-30 | 0
P03-A33 | P03 | Financial Closeout | 1.03.6.2 | 2026-12-31 | 2027-01-27 |  |  |  |  | 20 | P03-A32, P03-A31 |  | FALSE | TRUE | P03-CA06 | P03-WP062 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-31 | 2027-01-27 | 2026-12-31 | 2027-01-27 | 0
P03-M4 | P03 | Final Completion | 1.03.4.1 | 2027-01-27 | 2027-01-27 |  |  |  |  | 0 | P03-A33 |  | TRUE | TRUE | P03-CA04 | P03-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-01-27 | 2027-01-27 | 2027-01-27 | 2027-01-27 | 0
P04-A1 | P04 | Conduct Needs Assessment | 1.04.1.1 | 2025-06-02 | 2025-06-13 |  |  |  |  | 10 |  |  | FALSE | TRUE | P04-CA01 | P04-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-02 | 2025-06-13 | 2025-06-02 | 2025-06-13 | 0
P04-A2 | P04 | Finalize Project Definition & Scope | 1.04.1.2 | 2025-06-16 | 2025-06-20 |  |  |  |  | 5 | P04-A1 |  | FALSE | TRUE | P04-CA01 | P04-WP012 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-16 | 2025-06-20 | 2025-06-16 | 2025-06-20 | 0
P04-A3 | P04 | Preliminary Design (30%) | 1.04.2.1 | 2025-06-23 | 2025-07-18 |  |  |  |  | 20 | P04-A2 |  | FALSE | TRUE | P04-CA02 | P04-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-23 | 2025-07-18 | 2025-06-23 | 2025-07-18 | 0
P04-A4 | P04 | Final Design (100%) | 1.04.2.2 | 2025-08-04 | 2025-09-05 |  |  |  |  | 25 | P04-A3 |  | FALSE | TRUE | P04-CA02 | P04-WP022 | Task | Synthetic, industry-informed; +10bd review lag in logic | Source-derived / reconstructed network | 2025-08-04 | 2025-09-05 | 2025-08-04 | 2025-09-05 | 0
P04-A5 | P04 | Prepare & Advertise Bid Package | 1.04.3.1 | 2025-08-18 | 2025-09-05 |  |  |  |  | 15 | P04-A4 |  | FALSE | TRUE | P04-CA03 | P04-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-08-18 | 2025-09-05 | 2025-08-18 | 2025-09-05 | 0
P04-M1 | P04 | Design Complete | 1.04.4.1 | 2025-09-05 | 2025-09-05 |  |  |  |  | 0 | P04-A4 |  | TRUE | FALSE | P04-CA04 | P04-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-09-05 | 2025-09-05 | 2026-04-24 | 2026-04-24 | 165
P04-A4b | P04 | Regulatory Plan Review & Approval | 1.04.2.2 | 2025-09-08 | 2025-09-26 |  |  |  |  | 15 | P04-A4 |  | FALSE | FALSE | P04-CA02 | P04-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2025-09-08 | 2025-09-26 | 2025-10-06 | 2025-10-24 | 20
P04-A5b | P04 | Bid Evaluation, Selection & Award Recommendation | 1.04.3.1 | 2025-09-08 | 2025-09-19 |  |  |  |  | 10 | P04-A5 |  | FALSE | TRUE | P04-CA03 | P04-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-09-08 | 2025-09-19 | 2025-09-08 | 2025-09-19 | 0
P04-A5c | P04 | Governing Body Award Approval | 1.04.3.2 | 2025-09-22 | 2025-10-03 |  |  |  |  | 10 | P04-A5b |  | FALSE | TRUE | P04-CA03 | P04-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | 0
P04-M2 | P04 | Contract Award / NTP | 1.04.4.1 | 2025-10-24 | 2025-10-24 |  |  |  |  | 0 | P04-A5c, P04-A4b |  | TRUE | TRUE | P04-CA04 | P04-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 0
P04-A6 | P04 | Contractor Mobilization | 1.04.3.2 | 2025-10-27 | 2025-11-07 |  |  |  |  | 10 | P04-M2 |  | FALSE | FALSE | P04-CA03 | P04-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-27 | 2025-11-07 | 2025-11-03 | 2025-11-14 | 5
P04-A7 | P04 | Tank Shutdown & Dewatering Planning | 1.04.4.1 | 2025-10-27 | 2025-11-14 |  |  |  |  | 15 | P04-M2 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-27 | 2025-11-14 | 2025-10-27 | 2025-11-14 | 0
P04-A8 | P04 | Take Tank Offline & Dewater | 1.04.4.1 | 2025-11-17 | 2025-11-21 |  |  |  |  | 5 | P04-A6, P04-A7 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2025-11-17 | 2025-11-21 | 2025-11-17 | 2025-11-21 | 0
P04-A9 | P04 | Interior/Exterior Surface Preparation (abrasive blasting) | 1.04.4.1 | 2025-11-24 | 2025-12-12 |  |  |  |  | 15 | P04-A8 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2025-11-24 | 2025-12-12 | 2025-11-24 | 2025-12-12 | 0
P04-A10 | P04 | Structural Steel Repairs | 1.04.4.2 | 2025-12-15 | 2025-12-26 |  |  |  |  | 10 | P04-A9 |  | FALSE | TRUE | P04-CA04 | P04-WP042 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-15 | 2025-12-26 | 2025-12-15 | 2025-12-26 | 0
P04-A11 | P04 | Cathodic Protection System Installation | 1.04.4.3 | 2025-12-29 | 2026-01-16 |  |  |  |  | 15 | P04-A10 |  | FALSE | TRUE | P04-CA04 | P04-WP043 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-29 | 2026-01-16 | 2025-12-29 | 2026-01-16 | 0
P04-A12 | P04 | Interior/Exterior Coating Application | 1.04.4.1 | 2026-01-19 | 2026-02-13 |  |  |  |  | 20 | P04-A11 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network | 2026-01-19 | 2026-02-13 | 2026-01-19 | 2026-02-13 | 0
P04-A13 | P04 | Coating Cure Time | 1.04.4.1 | 2026-02-16 | 2026-02-27 |  |  |  |  | 10 | P04-A12 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-02-16 | 2026-02-27 | 2026-02-16 | 2026-02-27 | 0
P04-A14 | P04 | Refill & Disinfection | 1.04.4.1 | 2026-03-02 | 2026-03-06 |  |  |  |  | 5 | P04-A13 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-02 | 2026-03-06 | 2026-03-02 | 2026-03-06 | 0
P04-A15 | P04 | Bacteriological Sampling & Regulatory Clearance | 1.04.2.2 | 2026-03-09 | 2026-03-13 |  |  |  |  | 5 | P04-A14 |  | FALSE | TRUE | P04-CA02 | P04-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 0
P04-M5 | P04 | Major Process Equipment Delivered | 1.04.4.1 | 2026-03-13 | 2026-03-13 |  |  |  |  | 0 | P04-A15 |  | TRUE | FALSE | P04-CA04 | P04-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-03-13 | 2026-03-13 | 2026-04-24 | 2026-04-24 | 30
P04-A16 | P04 | Final Inspection & Punch List | 1.04.4.1 | 2026-03-16 | 2026-03-27 |  |  |  |  | 10 | P04-A15 |  | FALSE | TRUE | P04-CA04 | P04-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-16 | 2026-03-27 | 2026-03-16 | 2026-03-27 | 0
P04-M3 | P04 | Substantial Completion | 1.04.4.1 | 2026-03-27 | 2026-03-27 |  |  |  |  | 0 | P04-A16 |  | TRUE | FALSE | P04-CA04 | P04-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-03-27 | 2026-03-27 | 2026-04-24 | 2026-04-24 | 20
P04-A17 | P04 | Documentation & Turnover | 1.04.6.1 | 2026-03-30 | 2026-04-10 |  |  |  |  | 10 | P04-A16 |  | FALSE | TRUE | P04-CA06 | P04-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-30 | 2026-04-10 | 2026-03-30 | 2026-04-10 | 0
P04-A18 | P04 | Financial Closeout | 1.04.6.2 | 2026-04-06 | 2026-04-24 |  |  |  |  | 15 | P04-A17, P04-A16 |  | FALSE | TRUE | P04-CA06 | P04-WP062 | Task | Project-type realism | Recovered from approved P04 M3/M4 dates + SS+5 closeout overlap | 2026-04-06 | 2026-04-24 | 2026-04-06 | 2026-04-24 | 0
P04-M4 | P04 | Final Completion | 1.04.4.1 | 2026-04-24 | 2026-04-24 |  |  |  |  | 0 | P04-A18 |  | TRUE | TRUE | P04-CA04 | P04-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 0
P05-A1 | P05 | Lead Service Line Inventory Review & Prioritization | 1.05.1.1 | 2025-03-03 | 2025-03-21 |  |  |  |  | 15 |  |  | FALSE | TRUE | P05-CA01 | P05-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-03-03 | 2025-03-21 | 2025-03-03 | 2025-03-21 | 0
P05-A2 | P05 | Project Definition & Zone/Batch Plan Development | 1.05.1.2 | 2025-03-24 | 2025-04-04 |  |  |  |  | 10 | P05-A1 |  | FALSE | TRUE | P05-CA01 | P05-WP012 | Task | Project-type realism | Source-derived / reconstructed network | 2025-03-24 | 2025-04-04 | 2025-03-24 | 2025-04-04 | 0
P05-A3 | P05 | Preliminary Design — Typical Replacement Details & Specs (30%) | 1.05.2.1 | 2025-04-07 | 2025-04-25 |  |  |  |  | 15 | P05-A2 |  | FALSE | TRUE | P05-CA02 | P05-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2025-04-07 | 2025-04-25 | 2025-04-07 | 2025-04-25 | 0
P05-A4 | P05 | Final Design — Standard Specs & Bid Documents (100%) | 1.05.2.2 | 2025-05-05 | 2025-05-23 |  |  |  |  | 15 | P05-A3 |  | FALSE | TRUE | P05-CA02 | P05-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network | 2025-05-05 | 2025-05-23 | 2025-05-05 | 2025-05-23 | 0
P05-A5 | P05 | Bid Advertisement | 1.05.3.1 | 2025-05-19 | 2025-06-06 |  |  |  |  | 15 | P05-A4 |  | FALSE | TRUE | P05-CA03 | P05-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-05-19 | 2025-06-06 | 2025-05-19 | 2025-06-06 | 0
P05-M1 | P05 | Design Complete | 1.05.4.1 | 2025-05-23 | 2025-05-23 |  |  |  |  | 0 | P05-A4 |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-05-23 | 2025-05-23 | 2026-05-15 | 2026-05-15 | 255
P05-A4b | P05 | Regulatory Plan Review & Approval | 1.05.2.2 | 2025-05-26 | 2025-06-13 |  |  |  |  | 15 | P05-A4 |  | FALSE | FALSE | P05-CA02 | P05-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2025-05-26 | 2025-06-13 | 2025-06-23 | 2025-07-11 | 20
P05-A5b | P05 | Evaluation & Award Recommendation | 1.05.3.1 | 2025-06-09 | 2025-06-20 |  |  |  |  | 10 | P05-A5 |  | FALSE | TRUE | P05-CA03 | P05-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-09 | 2025-06-20 | 2025-06-09 | 2025-06-20 | 0
P05-A5c | P05 | Governing Body Approval | 1.05.3.2 | 2025-06-23 | 2025-07-04 |  |  |  |  | 10 | P05-A5b |  | FALSE | TRUE | P05-CA03 | P05-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-23 | 2025-07-04 | 2025-06-23 | 2025-07-04 | 0
P05-M2 | P05 | Contract Award / NTP | 1.05.4.1 | 2025-07-11 | 2025-07-11 |  |  |  |  | 0 | P05-A5c, P05-A4b |  | TRUE | TRUE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-07-11 | 0
P05-A10 | P05 | Street Opening / Right-of-Way Permitting (program-wide) | 1.05.2.2 | 2025-07-14 | 2025-08-01 |  |  |  |  | 15 | P05-M2 |  | FALSE | FALSE | P05-CA02 | P05-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2025-07-14 | 2025-08-01 | 2025-08-04 | 2025-08-22 | 15
P05-A11 | P05 | Material Procurement — Copper Tubing & Fittings | 1.05.3.2 | 2025-07-14 | 2025-08-22 |  |  |  |  | 30 | P05-M2 |  | FALSE | TRUE | P05-CA03 | P05-WP032 | Task | Synthetic, industry-informed | Semantic WBS mapping corrected: bulk material procurement belongs in Procurement, not Construction | 2025-07-14 | 2025-08-22 | 2025-07-14 | 2025-08-22 | 0
P05-A6 | P05 | Contractor Mobilization (multi-crew) | 1.05.3.2 | 2025-07-14 | 2025-08-01 |  |  |  |  | 15 | P05-M2 |  | FALSE | FALSE | P05-CA03 | P05-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-07-14 | 2025-08-01 | 2025-08-04 | 2025-08-22 | 15
P05-A7 | P05 | Customer/Property Outreach Campaign (program-wide) | 1.05.4.1 | 2025-07-14 | 2025-09-05 |  |  |  |  | 40 | P05-M2 |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network | 2025-07-14 | 2025-09-05 | 2025-07-14 | 2025-09-05 | 0
P05-A9 | P05 | Access/Consent Coordination & Scheduling | 1.05.4.1 | 2025-07-28 | 2025-08-22 |  |  |  |  | 20 | P05-A7 |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-07-28 | 2025-08-22 | 2025-07-28 | 2025-08-22 | 0
P05-A8 | P05 | Property Eligibility & Service Line Material Verification | 1.05.1.1 | 2025-08-04 | 2025-09-12 |  |  |  |  | 30 | P05-A7 |  | FALSE | FALSE | P05-CA01 | P05-WP011 | Task | Project-type realism | Semantic WBS mapping corrected: eligibility/material verification is pre-field inventory/assessment work | 2025-08-04 | 2025-09-12 | 2026-04-06 | 2026-05-15 | 175
P05-A12a | P05 | Zone A Field Replacement | 1.05.4.1 | 2025-08-25 | 2025-11-07 |  |  |  |  | 55 | P05-A6, P05-A9, P05-A10, P05-A11 |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Synthetic, industry-informed | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-08-25 | 2025-11-07 | 2025-08-25 | 2025-11-07 | 0
P05-AFIRST | P05 | Complete First Service Line Replacement | 1.05.4.1 | 2025-08-25 | 2025-08-26 |  |  |  |  | 2 | P05-A12a |  | FALSE | FALSE | P05-CA04 | P05-WP041 | Task | Approved P05 v2 explicit completed-scope activity | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-08-25 | 2025-08-26 | 2026-05-14 | 2026-05-15 | 188
P05-MFIRST | P05 | MFIRST | 1.05.4.1 | 2025-08-26 | 2025-08-26 |  |  |  |  | 0 | P05-AFIRST |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-08-26 | 2025-08-26 | 2026-05-15 | 2026-05-15 | 188
P05-A12b | P05 | Zone A Property Restoration | 1.05.4.2 | 2025-09-15 | 2025-11-28 |  |  |  |  | 55 | P05-A12a |  | FALSE | FALSE | P05-CA04 | P05-WP042 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-09-15 | 2025-11-28 | 2025-12-08 | 2026-02-20 | 60
P05-A13a | P05 | Zone B Field Replacement | 1.05.4.1 | 2025-09-22 | 2025-12-05 |  |  |  |  | 55 | P05-A12a |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Synthetic, industry-informed | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-09-22 | 2025-12-05 | 2025-09-22 | 2025-12-05 | 0
P05-A13b | P05 | Zone B Property Restoration | 1.05.4.2 | 2025-10-13 | 2025-12-26 |  |  |  |  | 55 | P05-A13a |  | FALSE | FALSE | P05-CA04 | P05-WP042 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-10-13 | 2025-12-26 | 2025-12-08 | 2026-02-20 | 40
P05-A14a | P05 | Zone C Field Replacement | 1.05.4.1 | 2025-10-20 | 2026-01-02 |  |  |  |  | 55 | P05-A13a |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Synthetic, industry-informed | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-10-20 | 2026-01-02 | 2025-10-20 | 2026-01-02 | 0
P05-M25 | P05 | M25 | 1.05.4.1 | 2025-11-07 | 2025-11-07 |  |  |  |  | 0 | P05-A12a |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-11-07 | 2025-11-07 | 2026-05-15 | 2026-05-15 | 135
P05-A14b | P05 | Zone C Property Restoration | 1.05.4.2 | 2025-11-10 | 2026-01-23 |  |  |  |  | 55 | P05-A14a |  | FALSE | FALSE | P05-CA04 | P05-WP042 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-11-10 | 2026-01-23 | 2025-12-08 | 2026-02-20 | 20
P05-A15a | P05 | Zone D Field Replacement | 1.05.4.1 | 2025-11-17 | 2026-01-30 |  |  |  |  | 55 | P05-A14a |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Synthetic, industry-informed | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-11-17 | 2026-01-30 | 2025-11-17 | 2026-01-30 | 0
P05-A12c | P05 | Zone A Water Quality Sampling & Customer Notification | 1.05.5.1 | 2025-12-01 | 2025-12-19 |  |  |  |  | 15 | P05-A12b |  | FALSE | FALSE | P05-CA05 | P05-WP051 | Task | Project-type realism; remapped to Testing & Commissioning | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-12-01 | 2025-12-19 | 2026-02-23 | 2026-03-13 | 60
P05-M50 | P05 | M50 | 1.05.4.1 | 2025-12-05 | 2025-12-05 |  |  |  |  | 0 | P05-A13a |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-12-05 | 2025-12-05 | 2026-05-15 | 2026-05-15 | 115
P05-A15b | P05 | Zone D Property Restoration | 1.05.4.2 | 2025-12-08 | 2026-02-20 |  |  |  |  | 55 | P05-A15a |  | FALSE | TRUE | P05-CA04 | P05-WP042 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-12-08 | 2026-02-20 | 2025-12-08 | 2026-02-20 | 0
P05-A13c | P05 | Zone B Water Quality Sampling & Customer Notification | 1.05.5.1 | 2025-12-29 | 2026-01-16 |  |  |  |  | 15 | P05-A13b |  | FALSE | FALSE | P05-CA05 | P05-WP051 | Task | Project-type realism; remapped to Testing & Commissioning | Recovered by reconciliation to approved P05 milestone dates and published durations | 2025-12-29 | 2026-01-16 | 2026-02-23 | 2026-03-13 | 40
P05-M75 | P05 | M75 | 1.05.4.1 | 2026-01-02 | 2026-01-02 |  |  |  |  | 0 | P05-A14a |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-01-02 | 2026-01-02 | 2026-05-15 | 2026-05-15 | 95
P05-A14c | P05 | Zone C Water Quality Sampling & Customer Notification | 1.05.5.1 | 2026-01-26 | 2026-02-13 |  |  |  |  | 15 | P05-A14b |  | FALSE | FALSE | P05-CA05 | P05-WP051 | Task | Project-type realism; remapped to Testing & Commissioning | Recovered by reconciliation to approved P05 milestone dates and published durations | 2026-01-26 | 2026-02-13 | 2026-02-23 | 2026-03-13 | 20
P05-MTARGET | P05 | MTARGET | 1.05.4.1 | 2026-01-30 | 2026-01-30 |  |  |  |  | 0 | P05-A15a |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-01-30 | 2026-01-30 | 2026-05-15 | 2026-05-15 | 75
P05-A15c | P05 | Zone D Water Quality Sampling & Customer Notification | 1.05.5.1 | 2026-02-23 | 2026-03-13 |  |  |  |  | 15 | P05-A15b |  | FALSE | TRUE | P05-CA05 | P05-WP051 | Task | Project-type realism; remapped to Testing & Commissioning | Recovered by reconciliation to approved P05 milestone dates and published durations | 2026-02-23 | 2026-03-13 | 2026-02-23 | 2026-03-13 | 0
P05-A16 | P05 | Final Program Inspection & Punch List | 1.05.4.1 | 2026-03-16 | 2026-04-03 |  |  |  |  | 15 | P05-A12c, P05-A13c, P05-A14c, P05-A15c |  | FALSE | TRUE | P05-CA04 | P05-WP041 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | 0
P05-M3 | P05 | Substantial Completion | 1.05.4.1 | 2026-04-03 | 2026-04-03 |  |  |  |  | 0 | P05-A16 |  | TRUE | FALSE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-04-03 | 2026-04-03 | 2026-05-15 | 2026-05-15 | 30
P05-A17 | P05 | GIS & Service Line Inventory Records Update / Documentation & Turnover | 1.05.6.1 | 2026-04-06 | 2026-05-01 |  |  |  |  | 20 | P05-A16 |  | FALSE | TRUE | P05-CA06 | P05-WP061 | Task | Project-type realism | Semantic WBS mapping corrected: documentation/GIS turnover belongs in Closeout | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | 0
P05-A18 | P05 | Financial Closeout | 1.05.6.2 | 2026-04-20 | 2026-05-15 |  |  |  |  | 20 | P05-A17 |  | FALSE | TRUE | P05-CA06 | P05-WP062 | Task | Project-type realism | Recovered by reconciliation to approved P05 milestone dates and published durations | 2026-04-20 | 2026-05-15 | 2026-04-20 | 2026-05-15 | 0
P05-M4 | P05 | Final Completion | 1.05.4.1 | 2026-05-15 | 2026-05-15 |  |  |  |  | 0 | P05-A18 |  | TRUE | TRUE | P05-CA04 | P05-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 0
P06-A1 | P06 | Needs Assessment | 1.06.1.1 | 2025-08-01 | 2025-08-21 |  |  |  |  | 15 |  |  | FALSE | TRUE | P06-CA01 | P06-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-01 | 2025-08-21 | 2025-08-01 | 2025-08-21 | 0
P06-A2 | P06 | Project Definition | 1.06.1.2 | 2025-08-22 | 2025-09-04 |  |  |  |  | 10 | P06-A1 |  | FALSE | TRUE | P06-CA01 | P06-WP012 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-08-22 | 2025-09-04 | 2025-08-22 | 2025-09-04 | 0
P06-A3 | P06 | Preliminary Design | 1.06.2.1 | 2025-09-05 | 2025-10-02 |  |  |  |  | 20 | P06-A2 |  | FALSE | TRUE | P06-CA02 | P06-WP021 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-09-05 | 2025-10-02 | 2025-09-05 | 2025-10-02 | 0
P06-A4 | P06 | Final Design | 1.06.2.2 | 2025-10-10 | 2025-11-06 |  |  |  |  | 20 | P06-A3 |  | FALSE | TRUE | P06-CA02 | P06-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-10 | 2025-11-06 | 2025-10-10 | 2025-11-06 | 0
P06-A5 | P06 | Bid Advertisement | 1.06.3.1 | 2025-10-24 | 2025-11-13 |  |  |  |  | 15 | P06-A4 |  | FALSE | TRUE | P06-CA03 | P06-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-10-24 | 2025-11-13 | 2025-10-24 | 2025-11-13 | 0
P06-M1 | P06 | Design Complete | 1.06.4.1 | 2025-11-06 | 2025-11-06 |  |  |  |  | 0 | P06-A4 |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-06 | 2025-11-06 | 2026-12-24 | 2026-12-24 | 295
P06-A4b | P06 | Regulatory Plan Review & Approval | 1.06.2.2 | 2025-11-07 | 2025-11-20 |  |  |  |  | 10 | P06-A4 |  | FALSE | FALSE | P06-CA02 | P06-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-07 | 2025-11-20 | 2025-11-28 | 2025-12-11 | 15
P06-A5b | P06 | Evaluation & Award | 1.06.3.1 | 2025-11-14 | 2025-11-27 |  |  |  |  | 10 | P06-A5 |  | FALSE | TRUE | P06-CA03 | P06-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-14 | 2025-11-27 | 2025-11-14 | 2025-11-27 | 0
P06-A5c | P06 | Governing Body Approval | 1.06.3.2 | 2025-11-28 | 2025-12-11 |  |  |  |  | 10 | P06-A5b |  | FALSE | TRUE | P06-CA03 | P06-WP032 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-11-28 | 2025-12-11 | 2025-11-28 | 2025-12-11 | 0
P06-M2 | P06 | Contract Award / NTP | 1.06.4.1 | 2025-12-11 | 2025-12-11 |  |  |  |  | 0 | P06-A5c, P06-A4b |  | TRUE | TRUE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-11 | 2025-12-11 | 2025-12-11 | 2025-12-11 | 0
P06-A10 | P06 | Meter/Endpoint Inventory & Route Planning | 1.06.1.1 | 2025-12-12 | 2026-01-08 |  |  |  |  | 20 | P06-M2 |  | FALSE | FALSE | P06-CA01 | P06-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2026-01-08 | 2026-11-27 | 2026-12-24 | 250
P06-A11 | P06 | Meter/Endpoint Submittal Review | 1.06.3.1 | 2025-12-12 | 2026-01-01 |  |  |  |  | 15 | P06-M2 |  | FALSE | TRUE | P06-CA03 | P06-WP031 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2026-01-01 | 2025-12-12 | 2026-01-01 | 0
P06-A15 | P06 | Pilot Deployment Planning & Customer Selection | 1.06.4.1 | 2025-12-12 | 2025-12-25 |  |  |  |  | 10 | P06-M2 |  | FALSE | FALSE | P06-CA04 | P06-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2025-12-25 | 2026-04-03 | 2026-04-16 | 80
P06-A6 | P06 | Contractor Mobilization | 1.06.3.2 | 2025-12-12 | 2025-12-25 |  |  |  |  | 10 | P06-M2 |  | FALSE | FALSE | P06-CA03 | P06-WP032 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2025-12-25 | 2026-04-03 | 2026-04-16 | 80
P06-A7 | P06 | Communications/Network Design | 1.06.2.2 | 2025-12-12 | 2026-01-08 |  |  |  |  | 20 | P06-M2 |  | FALSE | FALSE | P06-CA02 | P06-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2026-01-08 | 2026-01-09 | 2026-02-05 | 20
P06-A8 | P06 | Cybersecurity & IT Coordination | 1.06.2.2 | 2025-12-12 | 2026-01-01 |  |  |  |  | 15 | P06-M2 |  | FALSE | FALSE | P06-CA02 | P06-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2025-12-12 | 2026-01-01 | 2026-02-27 | 2026-03-19 | 55
P06-A12 | P06 | Meter/Endpoint Fabrication | 1.06.3.2 | 2026-01-02 | 2026-03-26 |  |  |  |  | 60 | P06-A11 |  | FALSE | TRUE | P06-CA03 | P06-WP032 | Task | Synthetic, industry-informed | Semantic WBS mapping corrected: meter/endpoint fabrication is procurement ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-02 | 2026-03-26 | 2026-01-02 | 2026-03-26 | 0
P06-A9 | P06 | Head-End / Meter Data Management System Configuration | 1.06.4.2 | 2026-01-09 | 2026-02-19 |  |  |  |  | 30 | P06-A7 |  | FALSE | FALSE | P06-CA04 | P06-WP042 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-01-09 | 2026-02-19 | 2026-02-06 | 2026-03-19 | 20
P06-A14 | P06 | System Integration — head-end / MDM / billing | 1.06.4.2 | 2026-02-20 | 2026-03-19 |  |  |  |  | 20 | P06-A9, P06-A8 |  | FALSE | FALSE | P06-CA04 | P06-WP042 | Task | Project-type realism | Semantic WBS mapping corrected: head-end/MDM/billing integration maps to Head-End System Integration ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-02-20 | 2026-03-19 | 2026-03-20 | 2026-04-16 | 20
P06-A13 | P06 | Meter/Endpoint Delivery | 1.06.3.2 | 2026-03-27 | 2026-04-09 |  |  |  |  | 10 | P06-A12 |  | FALSE | TRUE | P06-CA03 | P06-WP032 | Task | Synthetic, industry-informed | Semantic WBS mapping corrected: meter/endpoint delivery is procurement ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-03-27 | 2026-04-09 | 2026-03-27 | 2026-04-09 | 0
P06-APILOTSTAGE | P06 | Pilot Equipment Staging & Configuration | 1.06.4.1 | 2026-04-10 | 2026-04-16 |  |  |  |  | 5 | P06-A13 |  | FALSE | TRUE | P06-CA04 | P06-WP041 | Task | Approved P06 v2 added prerequisite | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-10 | 2026-04-16 | 2026-04-10 | 2026-04-16 | 0
P06-A16 | P06 | Pilot Deployment | 1.06.4.1 | 2026-04-17 | 2026-05-07 |  |  |  |  | 15 | P06-A14, P06-A15, P06-APILOTSTAGE, P06-A8, P06-A6, P06-MPILOTREADY |  | FALSE | TRUE | P06-CA04 | P06-WP041 | Task | Synthetic, industry-informed | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-17 | 2026-05-07 | 2026-04-17 | 2026-05-07 | 0
P06-AFIRSTPILOT | P06 | Install First Pilot Endpoints | 1.06.4.1 | 2026-04-17 | 2026-04-20 |  |  |  |  | 2 | P06-A16 |  | FALSE | FALSE | P06-CA04 | P06-WP041 | Task | Approved P06 v2 explicit completed-scope activity | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-17 | 2026-04-20 | 2026-12-23 | 2026-12-24 | 178
P06-MFIRSTPILOT | P06 | First Pilot Endpoints Live | 1.06.5.1 | 2026-04-20 | 2026-04-20 |  |  |  |  | 0 | P06-AFIRSTPILOT |  | TRUE | FALSE | P06-CA05 | P06-WP051 | Milestone | Approved P06 v2 completed-scope milestone | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-20 | 2026-04-20 | 2026-12-24 | 2026-12-24 | 178
P06-MSYSINT | P06 | MSYSINT | 1.06.4.2 | 2026-03-19 | 2026-03-19 |  |  |  |  | 0 | P06-A14 |  | TRUE | FALSE | P06-CA04 | P06-WP042 | Milestone | Approved milestone / interface milestone | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-03-19 | 2026-03-19 | 2026-04-16 | 2026-04-16 | 20
P06-A17 | P06 | Pilot Validation | 1.06.5.1 | 2026-05-08 | 2026-05-28 |  |  |  |  | 15 | P06-A16 |  | FALSE | TRUE | P06-CA05 | P06-WP051 | Task | Project-type realism | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-08 | 2026-05-28 | 2026-05-08 | 2026-05-28 | 0
P06-A18a | P06 | Field Deployment Wave 1 | 1.06.4.1 | 2026-05-29 | 2026-07-16 |  |  |  |  | 35 | P06-A17 |  | FALSE | FALSE | P06-CA04 | P06-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-29 | 2026-07-16 | 2026-07-31 | 2026-09-17 | 45
P06-MPILOTREADY | P06 | Pilot Ready | 1.06.5.1 | 2026-04-16 | 2026-04-16 |  |  |  |  | 0 | P06-MSYSINT, P06-A15, P06-APILOTSTAGE, P06-A8, P06-A6 |  | TRUE | TRUE | P06-CA05 | P06-WP051 | Milestone | Approved P06 v2 corrected pre-deployment gate | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 0
P06-A19a | P06 | Field Deployment Wave 2 | 1.06.4.1 | 2026-06-19 | 2026-08-06 |  |  |  |  | 35 | P06-A17 |  | FALSE | FALSE | P06-CA04 | P06-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-06-19 | 2026-08-06 | 2026-07-31 | 2026-09-17 | 30
P06-MPILOTDONE | P06 | MPILOTDONE | 1.06.4.1 | 2026-05-28 | 2026-05-28 |  |  |  |  | 0 | P06-A17 |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-28 | 2026-05-28 | 2026-12-24 | 2026-12-24 | 150
P06-A20a | P06 | Field Deployment Wave 3 | 1.06.4.1 | 2026-07-10 | 2026-08-27 |  |  |  |  | 35 | P06-A17 |  | FALSE | FALSE | P06-CA04 | P06-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-10 | 2026-08-27 | 2026-07-31 | 2026-09-17 | 15
P06-A18b | P06 | Wave 1 Data Migration / Account Reconciliation | 1.06.4.3 | 2026-07-17 | 2026-07-30 |  |  |  |  | 10 | P06-A18a |  | FALSE | FALSE | P06-CA04 | P06-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-17 | 2026-07-30 | 2026-09-18 | 2026-10-01 | 45
P06-A21a | P06 | Field Deployment Wave 4 | 1.06.4.1 | 2026-07-31 | 2026-09-17 |  |  |  |  | 35 | P06-A17 |  | FALSE | TRUE | P06-CA04 | P06-WP041 | Task | Synthetic, industry-informed | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-31 | 2026-09-17 | 2026-07-31 | 2026-09-17 | 0
P06-A19b | P06 | Wave 2 Data Migration / Account Reconciliation | 1.06.4.3 | 2026-08-07 | 2026-08-20 |  |  |  |  | 10 | P06-A19a |  | FALSE | FALSE | P06-CA04 | P06-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-07 | 2026-08-20 | 2026-09-18 | 2026-10-01 | 30
P06-M25 | P06 | M25 | 1.06.4.1 | 2026-07-16 | 2026-07-16 |  |  |  |  | 0 | P06-A18a |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-16 | 2026-07-16 | 2026-12-24 | 2026-12-24 | 115
P06-A20b | P06 | Wave 3 Data Migration / Account Reconciliation | 1.06.4.3 | 2026-08-28 | 2026-09-10 |  |  |  |  | 10 | P06-A20a |  | FALSE | FALSE | P06-CA04 | P06-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-28 | 2026-09-10 | 2026-09-18 | 2026-10-01 | 15
P06-M50 | P06 | M50 | 1.06.4.1 | 2026-08-06 | 2026-08-06 |  |  |  |  | 0 | P06-A19a |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-06 | 2026-08-06 | 2026-12-24 | 2026-12-24 | 100
P06-A21b | P06 | Wave 4 Data Migration / Account Reconciliation | 1.06.4.3 | 2026-09-18 | 2026-10-01 |  |  |  |  | 10 | P06-A21a |  | FALSE | TRUE | P06-CA04 | P06-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-09-18 | 2026-10-01 | 2026-09-18 | 2026-10-01 | 0
P06-M75 | P06 | M75 | 1.06.4.1 | 2026-08-27 | 2026-08-27 |  |  |  |  | 0 | P06-A20a |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-27 | 2026-08-27 | 2026-12-24 | 2026-12-24 | 85
P06-A22 | P06 | Exception Handling & Remediation | 1.06.4.1 | 2026-10-02 | 2026-10-22 |  |  |  |  | 15 | P06-A18b, P06-A19b, P06-A20b, P06-A21b |  | FALSE | TRUE | P06-CA04 | P06-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-02 | 2026-10-22 | 2026-10-02 | 2026-10-22 | 0
P06-MFULL | P06 | MFULL | 1.06.4.1 | 2026-09-17 | 2026-09-17 |  |  |  |  | 0 | P06-A21a |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-09-17 | 2026-09-17 | 2026-12-24 | 2026-12-24 | 70
P06-A23 | P06 | Final Deployment Verification | 1.06.5.1 | 2026-10-23 | 2026-11-05 |  |  |  |  | 10 | P06-A22 |  | FALSE | TRUE | P06-CA05 | P06-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | 0
P06-A24 | P06 | Operational Handoff / Training | 1.06.5.1 | 2026-11-06 | 2026-11-19 |  |  |  |  | 10 | P06-A23 |  | FALSE | TRUE | P06-CA05 | P06-WP051 | Task | Project-type realism | Semantic WBS mapping corrected: operational handoff/training is acceptance/commissioning scope ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-06 | 2026-11-19 | 2026-11-06 | 2026-11-19 | 0
P06-A25 | P06 | Documentation & Turnover | 1.06.6.1 | 2026-11-20 | 2026-12-03 |  |  |  |  | 10 | P06-A24 |  | FALSE | TRUE | P06-CA06 | P06-WP061 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-20 | 2026-12-03 | 2026-11-20 | 2026-12-03 | 0
P06-M3 | P06 | Substantial Completion | 1.06.4.1 | 2026-11-19 | 2026-11-19 |  |  |  |  | 0 | P06-A24 |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-19 | 2026-11-19 | 2026-12-24 | 2026-12-24 | 25
P06-MOPACC | P06 | MOPACC | 1.06.4.1 | 2026-11-19 | 2026-11-19 |  |  |  |  | 0 | P06-A24 |  | TRUE | FALSE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-11-19 | 2026-11-19 | 2026-12-24 | 2026-12-24 | 25
P06-A26 | P06 | Financial Closeout | 1.06.6.2 | 2026-12-04 | 2026-12-24 |  |  |  |  | 15 | P06-A25 |  | FALSE | TRUE | P06-CA06 | P06-WP062 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-04 | 2026-12-24 | 2026-12-04 | 2026-12-24 | 0
P06-M4 | P06 | Final Completion | 1.06.4.1 | 2026-12-24 | 2026-12-24 |  |  |  |  | 0 | P06-A26 |  | TRUE | TRUE | P06-CA04 | P06-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-24 | 2026-12-24 | 2026-12-24 | 2026-12-24 | 0
P07-A1 | P07 | Hydraulic & Operational Assessment | 1.07.1.1 | 2025-10-01 | 2025-10-21 |  |  |  |  | 15 |  |  | FALSE | TRUE | P07-CA01 | P07-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-01 | 2025-10-21 | 2025-10-01 | 2025-10-21 | 0
P07-A2 | P07 | Project Definition & Pressure-Zone Strategy | 1.07.1.2 | 2025-10-22 | 2025-11-04 |  |  |  |  | 10 | P07-A1 |  | FALSE | TRUE | P07-CA01 | P07-WP012 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-22 | 2025-11-04 | 2025-10-22 | 2025-11-04 | 0
P07-A3 | P07 | Preliminary Design — PRV/Valve Siting & Instrumentation Plan | 1.07.2.1 | 2025-11-05 | 2025-12-02 |  |  |  |  | 20 | P07-A2 |  | FALSE | TRUE | P07-CA02 | P07-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2025-11-05 | 2025-12-02 | 2025-11-05 | 2025-12-02 | 0
P07-A4 | P07 | Final Design (100%) | 1.07.2.2 | 2025-12-10 | 2026-01-06 |  |  |  |  | 20 | P07-A3 |  | FALSE | TRUE | P07-CA02 | P07-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network | 2025-12-10 | 2026-01-06 | 2025-12-10 | 2026-01-06 | 0
P07-A5 | P07 | Bid Advertisement | 1.07.3.1 | 2025-12-24 | 2026-01-13 |  |  |  |  | 15 | P07-A4 |  | FALSE | TRUE | P07-CA03 | P07-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-24 | 2026-01-13 | 2025-12-24 | 2026-01-13 | 0
P07-M1 | P07 | Design Complete | 1.07.4.1 | 2026-01-06 | 2026-01-06 |  |  |  |  | 0 | P07-A4 |  | TRUE | FALSE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-01-06 | 2026-01-06 | 2026-09-01 | 2026-09-01 | 170
P07-A4b | P07 | Regulatory Plan Review & Approval | 1.07.2.2 | 2026-01-07 | 2026-01-27 |  |  |  |  | 15 | P07-A4 |  | FALSE | FALSE | P07-CA02 | P07-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-07 | 2026-01-27 | 2026-02-04 | 2026-02-24 | 20
P07-A5b | P07 | Evaluation & Award | 1.07.3.1 | 2026-01-14 | 2026-01-27 |  |  |  |  | 10 | P07-A5 |  | FALSE | TRUE | P07-CA03 | P07-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-14 | 2026-01-27 | 2026-01-14 | 2026-01-27 | 0
P07-A5c | P07 | Governing Body Approval | 1.07.3.2 | 2026-01-28 | 2026-02-10 |  |  |  |  | 10 | P07-A5b |  | FALSE | TRUE | P07-CA03 | P07-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-28 | 2026-02-10 | 2026-01-28 | 2026-02-10 | 0
P07-M2 | P07 | Contract Award / NTP | 1.07.4.1 | 2026-02-24 | 2026-02-24 |  |  |  |  | 0 | P07-A5c, P07-A4b |  | TRUE | TRUE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 0
P07-A6 | P07 | Contractor Mobilization | 1.07.3.2 | 2026-02-25 | 2026-03-10 |  |  |  |  | 10 | P07-M2 |  | FALSE | FALSE | P07-CA03 | P07-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2026-02-25 | 2026-03-10 | 2026-03-25 | 2026-04-07 | 20
P07-A7 | P07 | Utility Coordination & Locate Requests | 1.07.4.1 | 2026-02-25 | 2026-03-10 |  |  |  |  | 10 | P07-M2 |  | FALSE | FALSE | P07-CA04 | P07-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-02-25 | 2026-03-10 | 2026-03-25 | 2026-04-07 | 20
P07-A8 | P07 | PRV/Valve/Instrumentation Submittal Review | 1.07.3.1 | 2026-02-25 | 2026-03-17 |  |  |  |  | 15 | P07-M2 |  | FALSE | TRUE | P07-CA03 | P07-WP031 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-02-25 | 2026-03-17 | 2026-02-25 | 2026-03-17 | 0
P07-A10 | P07 | PRV Station Vault/Enclosure Construction | 1.07.4.1 | 2026-03-11 | 2026-03-31 |  |  |  |  | 15 | P07-A6, P07-A7 |  | FALSE | FALSE | P07-CA04 | P07-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-11 | 2026-03-31 | 2026-04-08 | 2026-04-28 | 20
P07-A9 | P07 | PRV/Valve/Instrumentation Procurement | 1.07.4.3 | 2026-03-18 | 2026-04-28 |  |  |  |  | 30 | P07-A8 |  | FALSE | TRUE | P07-CA04 | P07-WP043 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-03-18 | 2026-04-28 | 2026-03-18 | 2026-04-28 | 0
P07-A11 | P07 | PRV & Isolation Valve Installation | 1.07.4.2 | 2026-04-29 | 2026-05-19 |  |  |  |  | 15 | P07-A10, P07-A9 |  | FALSE | TRUE | P07-CA04 | P07-WP042 | Task | Project-type realism | Source-derived / reconstructed network | 2026-04-29 | 2026-05-19 | 2026-04-29 | 2026-05-19 | 0
P07-A12 | P07 | Instrumentation & Monitoring Installation | 1.07.4.3 | 2026-05-20 | 2026-06-02 |  |  |  |  | 10 | P07-A11 |  | FALSE | TRUE | P07-CA04 | P07-WP043 | Task | Project-type realism | Source-derived / reconstructed network | 2026-05-20 | 2026-06-02 | 2026-05-20 | 2026-06-02 | 0
P07-A13 | P07 | Electrical/Controls Integration | 1.07.4.3 | 2026-06-03 | 2026-06-16 |  |  |  |  | 10 | P07-A12 |  | FALSE | TRUE | P07-CA04 | P07-WP043 | Task | Project-type realism | Source-derived / reconstructed network | 2026-06-03 | 2026-06-16 | 2026-06-03 | 2026-06-16 | 0
P07-A14 | P07 | Pressure Testing & Commissioning | 1.07.5.1 | 2026-06-17 | 2026-06-30 |  |  |  |  | 10 | P07-A13 |  | FALSE | TRUE | P07-CA05 | P07-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2026-06-17 | 2026-06-30 | 2026-06-17 | 2026-06-30 | 0
P07-MCOMM | P07 | MCOMM | 1.07.4.1 | 2026-06-30 | 2026-06-30 |  |  |  |  | 0 | P07-A14 |  | TRUE | FALSE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-06-30 | 2026-06-30 | 2026-09-01 | 2026-09-01 | 45
P07-A15 | P07 | System Balancing & Optimization | 1.07.5.1 | 2026-07-01 | 2026-07-21 |  |  |  |  | 15 | P07-A14 |  | FALSE | TRUE | P07-CA05 | P07-WP051 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-07-01 | 2026-07-21 | 2026-07-01 | 2026-07-21 | 0
P07-MBAL | P07 | MBAL | 1.07.4.1 | 2026-07-21 | 2026-07-21 |  |  |  |  | 0 | P07-A15 |  | TRUE | FALSE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-07-21 | 2026-07-21 | 2026-09-01 | 2026-09-01 | 30
P07-A16 | P07 | Final Inspection & Punch List | 1.07.4.1 | 2026-07-22 | 2026-08-04 |  |  |  |  | 10 | P07-A15 |  | FALSE | TRUE | P07-CA04 | P07-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-07-22 | 2026-08-04 | 2026-07-22 | 2026-08-04 | 0
P07-M3 | P07 | Substantial Completion | 1.07.4.1 | 2026-08-04 | 2026-08-04 |  |  |  |  | 0 | P07-A16 |  | TRUE | FALSE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-08-04 | 2026-08-04 | 2026-09-01 | 2026-09-01 | 20
P07-A17 | P07 | Documentation & Turnover | 1.07.6.1 | 2026-08-05 | 2026-08-18 |  |  |  |  | 10 | P07-A16 |  | FALSE | TRUE | P07-CA06 | P07-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-18 | 0
P07-A18 | P07 | Financial Closeout | 1.07.6.2 | 2026-08-12 | 2026-09-01 |  |  |  |  | 15 | P07-A17, P07-A16 |  | FALSE | TRUE | P07-CA06 | P07-WP062 | Task | Project-type realism | Recovered from approved P07 M3/M4 dates + SS+5 closeout overlap | 2026-08-12 | 2026-09-01 | 2026-08-12 | 2026-09-01 | 0
P07-M4 | P07 | Final Completion | 1.07.4.1 | 2026-09-01 | 2026-09-01 |  |  |  |  | 0 | P07-A18 |  | TRUE | TRUE | P07-CA04 | P07-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-01 | 0
P08-A1 | P08 | Electrical Load / Resiliency Assessment | 1.08.1.1 | 2025-12-01 | 2025-12-19 |  |  |  |  | 15 |  |  | FALSE | TRUE | P08-CA01 | P08-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-01 | 2025-12-19 | 2025-12-01 | 2025-12-19 | 0
P08-A2 | P08 | Project Definition & Generator Sizing Basis | 1.08.1.2 | 2025-12-22 | 2026-01-02 |  |  |  |  | 10 | P08-A1 |  | FALSE | TRUE | P08-CA01 | P08-WP012 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-22 | 2026-01-02 | 2025-12-22 | 2026-01-02 | 0
P08-A3 | P08 | Preliminary Design — Switchgear/ATS & Site Layout | 1.08.2.1 | 2026-01-05 | 2026-01-30 |  |  |  |  | 20 | P08-A2 |  | FALSE | TRUE | P08-CA02 | P08-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-05 | 2026-01-30 | 2026-01-05 | 2026-01-30 | 0
P08-A7 | P08 | Electric Utility Coordination | 1.08.4.1 | 2026-01-19 | 2026-02-06 |  |  |  |  | 15 | P08-A3 |  | FALSE | FALSE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-19 | 2026-02-06 | 2026-12-21 | 2027-01-08 | 240
P08-A4 | P08 | Final Design — Switchgear/ATS & Site Layout | 1.08.2.2 | 2026-02-09 | 2026-03-06 |  |  |  |  | 20 | P08-A3 |  | FALSE | TRUE | P08-CA02 | P08-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network | 2026-02-09 | 2026-03-06 | 2026-02-09 | 2026-03-06 | 0
P08-A5 | P08 | Bid Advertisement | 1.08.3.1 | 2026-02-23 | 2026-03-13 |  |  |  |  | 15 | P08-A4 |  | FALSE | TRUE | P08-CA03 | P08-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-02-23 | 2026-03-13 | 2026-02-23 | 2026-03-13 | 0
P08-I-P08-01 | P08 | Generator/ATS Controls Design Freeze | 1.08.4.2 | 2026-03-06 | 2026-03-06 |  |  |  |  | 0 | P08-M1 |  | TRUE | FALSE | P08-CA04 | P08-WP042 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-03-06 | 2026-03-06 | 2027-01-08 | 2027-01-08 | 220
P08-M1 | P08 | Design Complete | 1.08.4.1 | 2026-03-06 | 2026-03-06 |  |  |  |  | 0 | P08-A4 |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-03-06 | 2026-03-06 | 2027-01-08 | 2027-01-08 | 220
P08-A4b | P08 | Regulatory Plan Review & Approval | 1.08.2.2 | 2026-03-09 | 2026-03-27 |  |  |  |  | 15 | P08-A4 |  | FALSE | FALSE | P08-CA02 | P08-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-09 | 2026-03-27 | 2026-04-06 | 2026-04-24 | 20
P08-A5b | P08 | Evaluation & Award | 1.08.3.1 | 2026-03-16 | 2026-03-27 |  |  |  |  | 10 | P08-A5 |  | FALSE | TRUE | P08-CA03 | P08-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-16 | 2026-03-27 | 2026-03-16 | 2026-03-27 | 0
P08-A5c | P08 | Governing Body Approval | 1.08.3.2 | 2026-03-30 | 2026-04-10 |  |  |  |  | 10 | P08-A5b |  | FALSE | TRUE | P08-CA03 | P08-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-30 | 2026-04-10 | 2026-03-30 | 2026-04-10 | 0
P08-M2 | P08 | Contract Award / NTP | 1.08.4.1 | 2026-04-24 | 2026-04-24 |  |  |  |  | 0 | P08-A5c, P08-A4b |  | TRUE | TRUE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 0
P08-A13 | P08 | Site/Civil Preparation & Concrete Pad/Enclosure Work | 1.08.4.1 | 2026-04-27 | 2026-05-15 |  |  |  |  | 15 | P08-M2 |  | FALSE | FALSE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-04-27 | 2026-05-15 | 2026-08-31 | 2026-09-18 | 90
P08-A14 | P08 | Outage/Shutdown Planning & Operations Coordination | 1.08.4.1 | 2026-04-27 | 2026-05-08 |  |  |  |  | 10 | P08-M2 |  | FALSE | FALSE | P08-CA04 | P08-WP041 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-04-27 | 2026-05-08 | 2026-05-11 | 2026-05-22 | 10
P08-A6 | P08 | Contractor Mobilization | 1.08.3.2 | 2026-04-27 | 2026-05-08 |  |  |  |  | 10 | P08-M2 |  | FALSE | FALSE | P08-CA03 | P08-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2026-04-27 | 2026-05-08 | 2026-12-28 | 2027-01-08 | 175
P08-A8 | P08 | Generator/Switchgear Submittal Review | 1.08.3.1 | 2026-04-27 | 2026-05-15 |  |  |  |  | 15 | P08-M2 |  | FALSE | TRUE | P08-CA03 | P08-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-04-27 | 2026-05-15 | 2026-04-27 | 2026-05-15 | 0
P08-I-P08-02 | P08 | Approved Point List Available | 1.08.4.1 | 2026-05-15 | 2026-05-15 |  |  |  |  | 0 | P08-A8 |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-05-15 | 2026-05-15 | 2026-11-17 | 2026-11-17 | 132
P08-A10 | P08 | Switchgear/ATS Fabrication | 1.08.4.2 | 2026-05-18 | 2026-08-07 |  |  |  |  | 60 | P08-A8 |  | FALSE | FALSE | P08-CA04 | P08-WP042 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-05-18 | 2026-08-07 | 2026-06-05 | 2026-08-27 | 14
P08-A9 | P08 | Generator Fabrication | 1.08.4.1 | 2026-05-18 | 2026-08-28 |  |  |  |  | 75 | P08-A8 |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-05-18 | 2026-08-28 | 2026-05-18 | 2026-08-28 | 0
P08-MOUTAGE | P08 | MOUTAGE | 1.08.4.1 | 2026-05-22 | 2026-05-22 |  |  |  |  | 0 | P08-A14 |  | TRUE | TRUE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 0
P08-A10fat | P08 | FAT — Switchgear/ATS | 1.08.4.2 | 2026-08-10 | 2026-08-19 |  |  |  |  | 8 | P08-A10 |  | FALSE | FALSE | P08-CA04 | P08-WP042 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-08-10 | 2026-08-19 | 2026-08-28 | 2026-09-08 | 14
P08-A12 | P08 | Delivery & Receiving — Switchgear/ATS | 1.08.4.2 | 2026-08-20 | 2026-08-31 |  |  |  |  | 8 | P08-A10fat |  | FALSE | FALSE | P08-CA04 | P08-WP042 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-20 | 2026-08-31 | 2026-09-09 | 2026-09-18 | 14
P08-A9fat | P08 | FAT — Generator | 1.08.4.1 | 2026-08-31 | 2026-09-11 |  |  |  |  | 10 | P08-A9 |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | 0
P08-A16 | P08 | ATS-Switchgear Installation | 1.08.4.2 | 2026-09-01 | 2026-09-21 |  |  |  |  | 15 | P08-A13, P08-A12, P08-A14 |  | FALSE | FALSE | P08-CA04 | P08-WP042 | Task | Project-type realism | Source-derived / reconstructed network | 2026-09-01 | 2026-09-21 | 2026-09-21 | 2026-10-09 | 14
P08-A11 | P08 | Delivery & Rigging — Generator | 1.08.4.1 | 2026-09-14 | 2026-09-25 |  |  |  |  | 10 | P08-A9fat |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-09-14 | 2026-09-25 | 2026-09-14 | 2026-09-25 | 0
P08-A15 | P08 | Generator Installation & Rigging Set | 1.08.4.1 | 2026-09-28 | 2026-10-09 |  |  |  |  | 10 | P08-A13, P08-A11, P08-A14 |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-09-28 | 2026-10-09 | 2026-09-28 | 2026-10-09 | 0
P08-A17 | P08 | Electrical/Controls Integration | 1.08.4.1 | 2026-10-12 | 2026-10-23 |  |  |  |  | 10 | P08-A15, P08-A16 |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-10-12 | 2026-10-23 | 2026-10-12 | 2026-10-23 | 0
P08-A18 | P08 | Startup | 1.08.5.1 | 2026-10-26 | 2026-11-06 |  |  |  |  | 10 | P08-A17 |  | FALSE | TRUE | P08-CA05 | P08-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2026-10-26 | 2026-11-06 | 2026-10-26 | 2026-11-06 | 0
P08-I-P08-03 | P08 | Controls Available for Integration | 1.08.4.1 | 2026-11-06 | 2026-11-06 |  |  |  |  | 0 | P08-MSTART |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-11-06 | 2026-11-06 | 2027-01-08 | 2027-01-08 | 45
P08-MSTART | P08 | MSTART | 1.08.4.1 | 2026-11-06 | 2026-11-06 |  |  |  |  | 0 | P08-A18 |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-11-06 | 2026-11-06 | 2027-01-08 | 2027-01-08 | 45
P08-A19 | P08 | Load-Bank Testing | 1.08.5.1 | 2026-11-09 | 2026-11-20 |  |  |  |  | 10 | P08-A18 |  | FALSE | TRUE | P08-CA05 | P08-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2026-11-09 | 2026-11-20 | 2026-11-09 | 2026-11-20 | 0
P08-A20 | P08 | Emergency-Transfer (ATS) Testing | 1.08.5.1 | 2026-11-23 | 2026-11-27 |  |  |  |  | 5 | P08-A19 |  | FALSE | TRUE | P08-CA05 | P08-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2026-11-23 | 2026-11-27 | 2026-11-23 | 2026-11-27 | 0
P08-MOPACC | P08 | MOPACC | 1.08.4.1 | 2026-11-27 | 2026-11-27 |  |  |  |  | 0 | P08-A20 |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-11-27 | 2026-11-27 | 2027-01-08 | 2027-01-08 | 30
P08-A21 | P08 | Final Inspection & Punch List | 1.08.4.1 | 2026-11-30 | 2026-12-11 |  |  |  |  | 10 | P08-A20 |  | FALSE | TRUE | P08-CA04 | P08-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-11-30 | 2026-12-11 | 2026-11-30 | 2026-12-11 | 0
P08-M3 | P08 | Substantial Completion | 1.08.4.1 | 2026-12-11 | 2026-12-11 |  |  |  |  | 0 | P08-A21 |  | TRUE | FALSE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-12-11 | 2026-12-11 | 2027-01-08 | 2027-01-08 | 20
P08-A22 | P08 | Documentation & Turnover | 1.08.6.1 | 2026-12-14 | 2026-12-25 |  |  |  |  | 10 | P08-A21 |  | FALSE | TRUE | P08-CA06 | P08-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2026-12-14 | 2026-12-25 | 2026-12-14 | 2026-12-25 | 0
P08-A23 | P08 | Financial Closeout | 1.08.6.2 | 2026-12-21 | 2027-01-08 |  |  |  |  | 15 | P08-A22, P08-A21 |  | FALSE | TRUE | P08-CA06 | P08-WP062 | Task | Project-type realism | Recovered from approved P08 M3/M4 dates + SS+5 closeout overlap | 2026-12-21 | 2027-01-08 | 2026-12-21 | 2027-01-08 | 0
P08-M4 | P08 | Final Completion | 1.08.4.1 | 2027-01-08 | 2027-01-08 |  |  |  |  | 0 | P08-A23 |  | TRUE | TRUE | P08-CA04 | P08-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2027-01-08 | 2027-01-08 | 2027-01-08 | 2027-01-08 | 0
P09-A1 | P09 | Route & Condition Assessment | 1.09.1.1 | 2026-02-02 | 2026-02-20 |  |  |  |  | 15 |  |  | FALSE | TRUE | P09-CA01 | P09-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2026-02-02 | 2026-02-20 | 2026-02-02 | 2026-02-20 | 0
P09-A2 | P09 | Project Definition & Construction Method Selection (HDD) | 1.09.1.2 | 2026-02-23 | 2026-03-06 |  |  |  |  | 10 | P09-A1 |  | FALSE | TRUE | P09-CA01 | P09-WP012 | Task | Synthetic project assumption | Source-derived / reconstructed network | 2026-02-23 | 2026-03-06 | 2026-02-23 | 2026-03-06 | 0
P09-A3a | P09 | Survey / Geotechnical & Subsurface Investigation | 1.09.2.1 | 2026-03-09 | 2026-04-03 |  |  |  |  | 20 | P09-A2 |  | FALSE | TRUE | P09-CA02 | P09-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2026-03-09 | 2026-04-03 | 2026-03-09 | 2026-04-03 | 0
P09-A3 | P09 | Preliminary Design | 1.09.2.1 | 2026-04-06 | 2026-05-01 |  |  |  |  | 20 | P09-A3a |  | FALSE | TRUE | P09-CA02 | P09-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | 0
P09-A4 | P09 | Final Design | 1.09.2.2 | 2026-05-11 | 2026-06-05 |  |  |  |  | 20 | P09-A3 |  | FALSE | TRUE | P09-CA02 | P09-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network | 2026-05-11 | 2026-06-05 | 2026-05-11 | 2026-06-05 | 0
P09-A5 | P09 | Bid Advertisement | 1.09.3.1 | 2026-05-25 | 2026-06-12 |  |  |  |  | 15 | P09-A4 |  | FALSE | FALSE | P09-CA03 | P09-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-05-25 | 2026-06-12 | 2026-06-08 | 2026-06-26 | 10
P09-M1 | P09 | Design Complete | 1.09.4.1 | 2026-06-05 | 2026-06-05 |  |  |  |  | 0 | P09-A4 |  | TRUE | FALSE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-06-05 | 2026-06-05 | 2027-03-03 | 2027-03-03 | 193
P09-A4b | P09 | Environmental/Regulatory Review | 1.09.2.2 | 2026-06-08 | 2026-07-17 |  |  |  |  | 30 | P09-A4 |  | FALSE | FALSE | P09-CA02 | P09-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2026-06-08 | 2026-07-17 | 2026-06-22 | 2026-07-31 | 10
P09-A4c | P09 | Waterway / Environmental Crossing Permit | 1.09.2.2 | 2026-06-08 | 2026-07-31 |  |  |  |  | 40 | P09-A4 |  | FALSE | TRUE | P09-CA02 | P09-WP022 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-06-08 | 2026-07-31 | 2026-06-08 | 2026-07-31 | 0
P09-A5b | P09 | Evaluation & Selection — specialty contractor pool | 1.09.3.1 | 2026-06-15 | 2026-07-03 |  |  |  |  | 15 | P09-A5 |  | FALSE | FALSE | P09-CA03 | P09-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2026-06-15 | 2026-07-03 | 2026-06-29 | 2026-07-17 | 10
P09-A5c | P09 | Governing Body Approval | 1.09.3.2 | 2026-07-06 | 2026-07-17 |  |  |  |  | 10 | P09-A5b |  | FALSE | FALSE | P09-CA03 | P09-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2026-07-06 | 2026-07-17 | 2026-07-20 | 2026-07-31 | 10
P09-M2 | P09 | Contract Award / NTP | 1.09.4.1 | 2026-07-31 | 2026-07-31 |  |  |  |  | 0 | P09-A5c, P09-A4b, P09-A4c |  | TRUE | TRUE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 0
P09-MPERMIT | P09 | MPERMIT | 1.09.2.2 | 2026-07-31 | 2026-07-31 |  |  |  |  | 0 | P09-A4c |  | TRUE | FALSE | P09-CA02 | P09-WP022 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-07-31 | 2026-07-31 | 2027-03-03 | 2027-03-03 | 153
P09-A10 | P09 | HDPE Pipe Submittal Review | 1.09.3.1 | 2026-08-03 | 2026-08-21 |  |  |  |  | 15 | P09-M2 |  | FALSE | TRUE | P09-CA03 | P09-WP031 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-08-03 | 2026-08-21 | 2026-08-03 | 2026-08-21 | 0
P09-A6 | P09 | Specialty (HDD) Contractor Mobilization | 1.09.3.2 | 2026-08-03 | 2026-08-28 |  |  |  |  | 20 | P09-M2 |  | FALSE | FALSE | P09-CA03 | P09-WP032 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-08-03 | 2026-08-28 | 2026-08-27 | 2026-09-23 | 18
P09-A7 | P09 | Utility Coordination & Locate Requests | 1.09.4.1 | 2026-08-03 | 2026-08-21 |  |  |  |  | 15 | P09-M2 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-03 | 2026-08-21 | 2026-09-03 | 2026-09-23 | 23
P09-A8 | P09 | Temporary Bypass/Interconnection Planning | 1.09.4.1 | 2026-08-03 | 2026-08-21 |  |  |  |  | 15 | P09-M2 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-08-03 | 2026-08-21 | 2026-11-12 | 2026-12-02 | 73
P09-A11 | P09 | HDPE Fabrication / Fusion Prep | 1.09.4.2 | 2026-08-24 | 2026-10-23 |  |  |  |  | 45 | P09-A10 |  | FALSE | TRUE | P09-CA04 | P09-WP042 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-08-24 | 2026-10-23 | 2026-08-24 | 2026-10-23 | 0
P09-A9 | P09 | Install Temporary Interconnection/Bypass | 1.09.4.1 | 2026-08-24 | 2026-09-04 |  |  |  |  | 10 | P09-A8 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Synthetic project-specific planning assumption | Source-derived / reconstructed network | 2026-08-24 | 2026-09-04 | 2026-12-03 | 2026-12-16 | 73
P09-MSPECMOB | P09 | MSPECMOB | 1.09.4.1 | 2026-08-28 | 2026-08-28 |  |  |  |  | 0 | P09-A6 |  | TRUE | FALSE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-08-28 | 2026-08-28 | 2027-03-03 | 2027-03-03 | 133
P09-A13 | P09 | Entry/Exit Pit Excavation & Site Setup | 1.09.4.1 | 2026-08-31 | 2026-09-11 |  |  |  |  | 10 | P09-A6, P09-A7 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-31 | 2026-09-11 | 2026-09-24 | 2026-10-07 | 18
P09-A14 | P09 | HDD Pilot Bore | 1.09.4.1 | 2026-09-14 | 2026-10-09 |  |  |  |  | 20 | P09-A13 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Synthetic, industry-informed planning assumption | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-09-14 | 2026-10-09 | 2026-10-08 | 2026-11-04 | 18
P09-A12 | P09 | Delivery & Receiving | 1.09.4.1 | 2026-10-26 | 2026-11-04 |  |  |  |  | 8 | P09-A11 |  | FALSE | TRUE | P09-CA04 | P09-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-10-26 | 2026-11-04 | 2026-10-26 | 2026-11-04 | 0
P09-A15 | P09 | Reaming & Pullback | 1.09.4.1 | 2026-11-05 | 2026-11-25 |  |  |  |  | 15 | P09-A12, P09-A14 |  | FALSE | TRUE | P09-CA04 | P09-WP041 | Task | Synthetic, industry-informed planning assumption | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-11-05 | 2026-11-25 | 2026-11-05 | 2026-11-25 | 0
P09-MCROSSDONE | P09 | MCROSSDONE | 1.09.4.1 | 2026-11-25 | 2026-11-25 |  |  |  |  | 0 | P09-A15 |  | TRUE | FALSE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-11-25 | 2026-11-25 | 2027-03-03 | 2027-03-03 | 70
P09-A16 | P09 | Tie-In — Entry Side | 1.09.4.1 | 2026-11-26 | 2026-12-09 |  |  |  |  | 10 | P09-A15 |  | FALSE | TRUE | P09-CA04 | P09-WP041 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-11-26 | 2026-12-09 | 2026-11-26 | 2026-12-09 | 0
P09-A17 | P09 | Tie-In — Exit Side | 1.09.4.1 | 2026-11-26 | 2026-12-09 |  |  |  |  | 10 | P09-A15 |  | FALSE | FALSE | P09-CA04 | P09-WP041 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-11-26 | 2026-12-09 | 2026-12-03 | 2026-12-16 | 5
P09-A18 | P09 | Pressure Testing & Disinfection | 1.09.5.1 | 2026-12-17 | 2026-12-23 |  |  |  |  | 5 | P09-A16, P09-A17, P09-A9 |  | FALSE | TRUE | P09-CA05 | P09-WP051 | Task | Project-type realism; +5bd settling lag in logic | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-12-17 | 2026-12-23 | 2026-12-17 | 2026-12-23 | 0
P09-A19 | P09 | Bacteriological Sampling & Regulatory Clearance | 1.09.2.2 | 2026-12-24 | 2026-12-30 |  |  |  |  | 5 | P09-A18 |  | FALSE | TRUE | P09-CA02 | P09-WP022 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-12-24 | 2026-12-30 | 2026-12-24 | 2026-12-30 | 0
P09-MINSERVICE | P09 | MINSERVICE | 1.09.4.1 | 2026-12-30 | 2026-12-30 |  |  |  |  | 0 | P09-A19 |  | TRUE | FALSE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-12-30 | 2026-12-30 | 2027-03-03 | 2027-03-03 | 45
P09-A20 | P09 | Riverbank & Pit Restoration | 1.09.4.3 | 2026-12-31 | 2027-01-20 |  |  |  |  | 15 | P09-A19 |  | FALSE | TRUE | P09-CA04 | P09-WP043 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2026-12-31 | 2027-01-20 | 2026-12-31 | 2027-01-20 | 0
P09-A21 | P09 | Final Inspection & Punch List | 1.09.4.1 | 2027-01-21 | 2027-02-03 |  |  |  |  | 10 | P09-A20 |  | FALSE | TRUE | P09-CA04 | P09-WP041 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2027-01-21 | 2027-02-03 | 2027-01-21 | 2027-02-03 | 0
P09-M3 | P09 | Substantial Completion | 1.09.4.1 | 2027-02-03 | 2027-02-03 |  |  |  |  | 0 | P09-A21 |  | TRUE | FALSE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2027-02-03 | 2027-02-03 | 2027-03-03 | 2027-03-03 | 20
P09-A22 | P09 | Documentation & Turnover | 1.09.6.1 | 2027-02-04 | 2027-02-17 |  |  |  |  | 10 | P09-A21 |  | FALSE | TRUE | P09-CA06 | P09-WP061 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2027-02-04 | 2027-02-17 | 2027-02-04 | 2027-02-17 | 0
P09-A23 | P09 | Financial Closeout | 1.09.6.2 | 2027-02-11 | 2027-03-03 |  |  |  |  | 15 | P09-A22, P09-A21 |  | FALSE | TRUE | P09-CA06 | P09-WP062 | Task | Project-type realism | Recovered from approved P09 milestones, durations, and published relationship highlights | 2027-02-11 | 2027-03-03 | 2027-02-11 | 2027-03-03 | 0
P09-M4 | P09 | Final Completion | 1.09.4.1 | 2027-03-03 | 2027-03-03 |  |  |  |  | 0 | P09-A23 |  | TRUE | TRUE | P09-CA04 | P09-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2027-03-03 | 2027-03-03 | 2027-03-03 | 2027-03-03 | 0
P10-A1 | P10 | Existing-System / Controls Inventory Assessment | 1.10.1.1 | 2026-04-01 | 2026-04-21 |  |  |  |  | 15 |  |  | FALSE | TRUE | P10-CA01 | P10-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-01 | 2026-04-21 | 2026-04-01 | 2026-04-21 | 0
P10-A2 | P10 | Project Definition & Network/Architecture Assessment | 1.10.1.1 | 2026-04-22 | 2026-05-05 |  |  |  |  | 10 | P10-A1 |  | FALSE | TRUE | P10-CA01 | P10-WP011 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-04-22 | 2026-05-05 | 2026-04-22 | 2026-05-05 | 0
P10-A3 | P10 | Control Narrative / Functional Requirements | 1.10.2.2 | 2026-05-06 | 2026-05-26 |  |  |  |  | 15 | P10-A2 |  | FALSE | TRUE | P10-CA02 | P10-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-06 | 2026-05-26 | 2026-05-06 | 2026-05-26 | 0
P10-A4 | P10 | PLC/HMI/SCADA Preliminary Design (30%) | 1.10.2.1 | 2026-05-27 | 2026-06-23 |  |  |  |  | 20 | P10-A3 |  | FALSE | TRUE | P10-CA02 | P10-WP021 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-05-27 | 2026-06-23 | 2026-05-27 | 2026-06-23 | 0
P10-A5 | P10 | Communications/Network Design | 1.10.2.2 | 2026-06-10 | 2026-06-30 |  |  |  |  | 15 | P10-A4 |  | FALSE | TRUE | P10-CA02 | P10-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-06-10 | 2026-06-30 | 2026-06-10 | 2026-06-30 | 0
P10-A6b | P10 | Cybersecurity & IT Coordination | 1.10.2.2 | 2026-06-10 | 2026-06-30 |  |  |  |  | 15 | P10-A4 |  | FALSE | TRUE | P10-CA02 | P10-WP022 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-06-10 | 2026-06-30 | 2026-06-10 | 2026-06-30 | 0
P10-A6 | P10 | Final Design (100%) | 1.10.2.2 | 2026-06-24 | 2026-07-21 |  |  |  |  | 20 | P10-A5, P10-A6b |  | FALSE | TRUE | P10-CA02 | P10-WP022 | Task | Project-type realism | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-06-24 | 2026-07-21 | 2026-06-24 | 2026-07-21 | 0
P10-A7 | P10 | Bid Advertisement | 1.10.3.1 | 2026-07-08 | 2026-07-28 |  |  |  |  | 15 | P10-A6 |  | FALSE | TRUE | P10-CA03 | P10-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-08 | 2026-07-28 | 2026-07-08 | 2026-07-28 | 0
P10-M1 | P10 | Controls Design Approved | 1.10.4.1 | 2026-07-21 | 2026-07-21 |  |  |  |  | 0 | P10-A6 |  | TRUE | FALSE | P10-CA04 | P10-WP041 | Milestone | Approved milestone / interface milestone | BLOCKED: source-versus-reconstructed milestone/sequence inconsistency; see focused reconciliation QA report ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-21 | 2026-07-21 | 2026-11-17 | 2026-11-17 | 85
P10-IF-01 | P10 | Final I/O Mapping & Tag Reconciliation | 1.10.4.1 | 2026-07-22 | 2026-08-04 |  |  |  |  | 10 | P03-I-P03-02, P08-I-P08-02, P10-M1 |  | FALSE | FALSE | P10-CA04 | P10-WP041 | Task | Approved synthetic project-specific planning assumption | ID normalized to approved interface naming convention ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-22 | 2026-08-04 | 2026-11-18 | 2026-12-01 | 85
P10-MIF01 | P10 | Final I/O Mapping Complete | 1.10.4.1 | 2026-08-04 | 2026-08-04 |  |  |  |  | 0 | P10-IF-01 |  | TRUE | FALSE | P10-CA04 | P10-WP041 | Milestone | Approved milestone / interface milestone | ID normalized to approved interface naming convention ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-04 | 2026-08-04 | 2026-12-01 | 2026-12-01 | 85
P10-A7b | P10 | Evaluation & Award | 1.10.3.1 | 2026-07-29 | 2026-08-11 |  |  |  |  | 10 | P10-A7 |  | FALSE | TRUE | P10-CA03 | P10-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-07-29 | 2026-08-11 | 2026-07-29 | 2026-08-11 | 0
P10-A7c | P10 | Governing Body Approval | 1.10.3.2 | 2026-08-12 | 2026-08-25 |  |  |  |  | 10 | P10-A7b |  | FALSE | TRUE | P10-CA03 | P10-WP032 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-12 | 2026-08-25 | 2026-08-12 | 2026-08-25 | 0
P10-M2 | P10 | Contract Award / NTP | 1.10.4.1 | 2026-08-25 | 2026-08-25 |  |  |  |  | 0 | P10-A7c |  | TRUE | TRUE | P10-CA04 | P10-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 0
P10-A11 | P10 | SCADA Software Licensing & Base System Procurement | 1.10.4.2 | 2026-08-26 | 2026-09-15 |  |  |  |  | 15 | P10-M2 |  | FALSE | FALSE | P10-CA04 | P10-WP042 | Task | Synthetic project assumption | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-09-15 | 2027-07-19 | 2027-08-06 | 233
P10-A14 | P10 | PLC Programming / Configuration | 1.10.4.1 | 2026-08-26 | 2026-10-06 |  |  |  |  | 30 | P10-M2 |  | FALSE | FALSE | P10-CA04 | P10-WP041 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-10-06 | 2026-10-21 | 2026-12-01 | 40
P10-A15 | P10 | HMI Screen Development & SCADA Software Configuration | 1.10.4.2 | 2026-08-26 | 2026-09-29 |  |  |  |  | 25 | P10-M2 |  | FALSE | FALSE | P10-CA04 | P10-WP042 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-09-29 | 2026-10-28 | 2026-12-01 | 45
P10-A8 | P10 | Contractor/Integrator Mobilization | 1.10.3.2 | 2026-08-26 | 2026-09-08 |  |  |  |  | 10 | P10-M2 |  | FALSE | FALSE | P10-CA03 | P10-WP032 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-09-08 | 2026-12-21 | 2027-01-01 | 83
P10-A9 | P10 | PLC/HMI/Network Hardware Submittal Review | 1.10.3.1 | 2026-08-26 | 2026-09-15 |  |  |  |  | 15 | P10-M2 |  | FALSE | TRUE | P10-CA03 | P10-WP031 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-08-26 | 2026-09-15 | 2026-08-26 | 2026-09-15 | 0
P10-A10 | P10 | Hardware Procurement & Delivery | 1.10.4.3 | 2026-09-16 | 2026-10-27 |  |  |  |  | 30 | P10-A9 |  | FALSE | TRUE | P10-CA04 | P10-WP043 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-09-16 | 2026-10-27 | 2026-09-16 | 2026-10-27 | 0
P10-MIF02 | P10 | Integration Configuration Complete | 1.10.4.1 | 2026-10-06 | 2026-10-06 |  |  |  |  | 0 | P10-MIF01, P10-A14, P10-A15 |  | TRUE | FALSE | P10-CA04 | P10-WP041 | Milestone | Approved milestone / interface milestone | ID normalized to approved interface naming convention ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-06 | 2026-10-06 | 2026-12-01 | 2026-12-01 | 40
P10-A12 | P10 | Control Panel Fabrication & Shop Assembly | 1.10.4.3 | 2026-10-28 | 2026-12-01 |  |  |  |  | 25 | P10-A10 |  | FALSE | TRUE | P10-CA04 | P10-WP043 | Task | Synthetic project assumption | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-10-28 | 2026-12-01 | 2026-10-28 | 2026-12-01 | 0
P10-A13 | P10 | FAT / Bench Test | 1.10.5.1 | 2026-12-02 | 2026-12-22 |  |  |  |  | 15 | P10-A12, P10-A14, P10-A15, P10-MIF02 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Synthetic project-specific planning assumption | Semantic WBS mapping corrected: FAT/bench test is testing & commissioning ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-02 | 2026-12-22 | 2026-12-02 | 2026-12-22 | 0
P10-MFAT | P10 | MFAT | 1.10.5.1 | 2026-12-22 | 2026-12-22 |  |  |  |  | 0 | P10-A13 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: FAT completion milestone ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-22 | 2026-12-22 | 2027-08-06 | 2027-08-06 | 163
P10-A16 | P10 | Delivery & Receiving — Panels/Network Equipment | 1.10.4.3 | 2026-12-23 | 2027-01-01 |  |  |  |  | 8 | P10-A13 |  | FALSE | TRUE | P10-CA04 | P10-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2026-12-23 | 2027-01-01 | 2026-12-23 | 2027-01-01 | 0
P10-A17 | P10 | Site Installation — Panels & Network Infrastructure | 1.10.4.3 | 2027-01-04 | 2027-02-05 |  |  |  |  | 25 | P10-A8, P10-A16 |  | FALSE | TRUE | P10-CA04 | P10-WP043 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-01-04 | 2027-02-05 | 2027-01-04 | 2027-02-05 | 0
P10-MSITEINSTALL | P10 | MSITEINSTALL | 1.10.4.3 | 2027-02-05 | 2027-02-05 |  |  |  |  | 0 | P10-A17 |  | TRUE | FALSE | P10-CA04 | P10-WP043 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: site installation milestone maps to Network & Communications Infrastructure ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-02-05 | 2027-02-05 | 2027-03-12 | 2027-03-12 | 25
P10-A18 | P10 | I/O Checkout & Point-to-Point Verification | 1.10.5.1 | 2027-02-08 | 2027-02-26 |  |  |  |  | 15 | P10-A17 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-02-08 | 2027-02-26 | 2027-02-08 | 2027-02-26 | 0
P10-MIOCHECK | P10 | MIOCHECK | 1.10.5.1 | 2027-02-26 | 2027-02-26 |  |  |  |  | 0 | P10-A18 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: I/O checkout milestone ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-02-26 | 2027-02-26 | 2027-03-12 | 2027-03-12 | 10
P10-A19 | P10 | Communications/Network Testing | 1.10.5.1 | 2027-03-01 | 2027-03-12 |  |  |  |  | 10 | P10-A18 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Source-derived / reconstructed network ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-03-01 | 2027-03-12 | 2027-03-01 | 2027-03-12 | 0
P10-MIF03 | P10 | Site Integration Ready | 1.10.5.1 | 2027-03-12 | 2027-03-12 |  |  |  |  | 0 | P03-I-P03-03, P08-I-P08-03, P10-MSITEINSTALL, P10-MIOCHECK, P10-A19 |  | TRUE | TRUE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: site integration readiness is a testing/integration gate ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-03-12 | 2027-03-12 | 2027-03-12 | 2027-03-12 | 0
P10-A20 | P10 | System Integration — head-end / PLCs / historian | 1.10.5.1 | 2027-03-15 | 2027-04-02 |  |  |  |  | 15 | P10-MIF03 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-03-15 | 2027-04-02 | 2027-03-15 | 2027-04-02 | 0
P10-A21 | P10 | Site Acceptance Testing (SAT) | 1.10.5.1 | 2027-04-05 | 2027-04-23 |  |  |  |  | 15 | P10-A20 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-04-05 | 2027-04-23 | 2027-04-05 | 2027-04-23 | 0
P10-MSAT | P10 | MSAT | 1.10.5.1 | 2027-04-23 | 2027-04-23 |  |  |  |  | 0 | P10-A21 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-04-23 | 2027-04-23 | 2027-08-06 | 2027-08-06 | 75
P10-A22 | P10 | Operator Training | 1.10.5.1 | 2027-04-26 | 2027-05-07 |  |  |  |  | 10 | P10-A21 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Semantic WBS mapping corrected: operator training is acceptance/commissioning scope ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-04-26 | 2027-05-07 | 2027-04-26 | 2027-05-07 | 0
P10-A23 | P10 | Cutover Planning | 1.10.5.1 | 2027-04-26 | 2027-05-07 |  |  |  |  | 10 | P10-A21 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-04-26 | 2027-05-07 | 2027-04-26 | 2027-05-07 | 0
P10-A24 | P10 | Phased Cutover / Migration from Legacy System | 1.10.5.1 | 2027-05-10 | 2027-05-28 |  |  |  |  | 15 | P10-A22, P10-A23 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-05-10 | 2027-05-28 | 2027-05-10 | 2027-05-28 | 0
P10-MCUTOVER | P10 | MCUTOVER | 1.10.5.1 | 2027-05-28 | 2027-05-28 |  |  |  |  | 0 | P10-A24 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-05-28 | 2027-05-28 | 2027-08-06 | 2027-08-06 | 50
P10-A25 | P10 | Post-Cutover Monitoring & Stabilization | 1.10.5.1 | 2027-05-31 | 2027-06-18 |  |  |  |  | 15 | P10-A24 |  | FALSE | TRUE | P10-CA05 | P10-WP051 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-05-31 | 2027-06-18 | 2027-05-31 | 2027-06-18 | 0
P10-MOPACC | P10 | MOPACC | 1.10.5.1 | 2027-06-18 | 2027-06-18 |  |  |  |  | 0 | P10-A25 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: operational acceptance milestone ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-06-18 | 2027-06-18 | 2027-08-06 | 2027-08-06 | 35
P10-A26 | P10 | Documentation, Backup & Turnover | 1.10.6.1 | 2027-06-21 | 2027-07-09 |  |  |  |  | 15 | P10-A25 |  | FALSE | TRUE | P10-CA06 | P10-WP061 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-06-21 | 2027-07-09 | 2027-06-21 | 2027-07-09 | 0
P10-A27 | P10 | Final Inspection & Punch List | 1.10.5.1 | 2027-06-21 | 2027-07-02 |  |  |  |  | 10 | P10-A25 |  | FALSE | FALSE | P10-CA05 | P10-WP051 | Task | Project-type realism | Semantic WBS mapping corrected: final inspection/punch list is acceptance/commissioning scope ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-06-21 | 2027-07-02 | 2027-07-26 | 2027-08-06 | 25
P10-M3 | P10 | Substantial Completion | 1.10.5.1 | 2027-07-02 | 2027-07-02 |  |  |  |  | 0 | P10-A27 |  | TRUE | FALSE | P10-CA05 | P10-WP051 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: substantial completion follows acceptance/testing ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-07-02 | 2027-07-02 | 2027-08-06 | 2027-08-06 | 25
P10-A28 | P10 | Financial Closeout | 1.10.6.2 | 2027-07-19 | 2027-08-06 |  |  |  |  | 15 | P10-A26, P10-A27 |  | FALSE | TRUE | P10-CA06 | P10-WP062 | Task | Project-type realism | Recovered after restoring approved P10 interface chain and published milestone dates ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-07-19 | 2027-08-06 | 2027-07-19 | 2027-08-06 | 0
P10-M4 | P10 | Final Completion | 1.10.6.2 | 2027-08-06 | 2027-08-06 |  |  |  |  | 0 | P10-A28 |  | TRUE | TRUE | P10-CA06 | P10-WP062 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: final completion aligns with financial closeout ¦ Scenario dates calculated from reconstructed logic, not source recovered | 2027-08-06 | 2027-08-06 | 2027-08-06 | 2027-08-06 | 0
P11-A1 | P11 | Valve Inventory / Condition Prioritization | 1.11.1.1 | 2025-04-01 | 2025-04-21 |  |  |  |  | 15 |  |  | FALSE | TRUE | P11-CA01 | P11-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-04-01 | 2025-04-21 | 2025-04-01 | 2025-04-21 | 0
P11-A2 | P11 | Project Definition & Isolation-Zone Planning | 1.11.1.2 | 2025-04-22 | 2025-05-05 |  |  |  |  | 10 | P11-A1 |  | FALSE | TRUE | P11-CA01 | P11-WP012 | Task | Project-type realism | Source-derived / reconstructed network | 2025-04-22 | 2025-05-05 | 2025-04-22 | 2025-05-05 | 0
P11-A3 | P11 | Preliminary Design | 1.11.2.1 | 2025-05-06 | 2025-05-26 |  |  |  |  | 15 | P11-A2 |  | FALSE | TRUE | P11-CA02 | P11-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2025-05-06 | 2025-05-26 | 2025-05-06 | 2025-05-26 | 0
P11-A4 | P11 | Final Design | 1.11.2.2 | 2025-06-03 | 2025-06-23 |  |  |  |  | 15 | P11-A3 |  | FALSE | TRUE | P11-CA02 | P11-WP022 | Task | Project-type realism; +5bd review lag in logic | Source-derived / reconstructed network | 2025-06-03 | 2025-06-23 | 2025-06-03 | 2025-06-23 | 0
P11-A5 | P11 | Bid Advertisement | 1.11.3.1 | 2025-06-17 | 2025-07-07 |  |  |  |  | 15 | P11-A4 |  | FALSE | TRUE | P11-CA03 | P11-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-06-17 | 2025-07-07 | 2025-06-17 | 2025-07-07 | 0
P11-M1 | P11 | Design Complete | 1.11.4.1 | 2025-06-23 | 2025-06-23 |  |  |  |  | 0 | P11-A4 |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-06-23 | 2025-06-23 | 2026-03-09 | 2026-03-09 | 185
P11-A5b | P11 | Evaluation & Award | 1.11.3.1 | 2025-07-08 | 2025-07-21 |  |  |  |  | 10 | P11-A5 |  | FALSE | TRUE | P11-CA03 | P11-WP031 | Task | Project-type realism | Source-derived / reconstructed network | 2025-07-08 | 2025-07-21 | 2025-07-08 | 2025-07-21 | 0
P11-A5c | P11 | Governing Body Approval | 1.11.3.2 | 2025-07-22 | 2025-08-04 |  |  |  |  | 10 | P11-A5b |  | FALSE | TRUE | P11-CA03 | P11-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-07-22 | 2025-08-04 | 2025-07-22 | 2025-08-04 | 0
P11-M2 | P11 | Contract Award / NTP | 1.11.4.1 | 2025-08-11 | 2025-08-11 |  |  |  |  | 0 | P11-A5c |  | TRUE | TRUE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | 0
P11-A10 | P11 | Shutdown & Customer/Service Coordination Planning | 1.11.4.1 | 2025-08-12 | 2025-09-01 |  |  |  |  | 15 | P11-M2 |  | FALSE | FALSE | P11-CA04 | P11-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2025-08-12 | 2025-09-01 | 2025-08-26 | 2025-09-15 | 10
P11-A6 | P11 | Mobilization | 1.11.3.2 | 2025-08-12 | 2025-08-25 |  |  |  |  | 10 | P11-M2 |  | FALSE | FALSE | P11-CA03 | P11-WP032 | Task | Project-type realism | Source-derived / reconstructed network | 2025-08-12 | 2025-08-25 | 2025-09-02 | 2025-09-15 | 15
P11-A7 | P11 | Field Verification / Utility Locating | 1.11.5.1 | 2025-08-12 | 2025-09-01 |  |  |  |  | 15 | P11-M2 |  | FALSE | FALSE | P11-CA05 | P11-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2025-08-12 | 2025-09-01 | 2025-08-26 | 2025-09-15 | 10
P11-A8 | P11 | Traffic / Street-Opening Coordination & Permitting | 1.11.2.2 | 2025-08-12 | 2025-08-25 |  |  |  |  | 10 | P11-M2 |  | FALSE | FALSE | P11-CA02 | P11-WP022 | Task | Project-type realism | Source-derived / reconstructed network | 2025-08-12 | 2025-08-25 | 2025-09-02 | 2025-09-15 | 15
P11-A9 | P11 | Material Procurement — Valves & Fittings | 1.11.4.1 | 2025-08-12 | 2025-09-15 |  |  |  |  | 25 | P11-M2 |  | FALSE | TRUE | P11-CA04 | P11-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2025-08-12 | 2025-09-15 | 2025-08-12 | 2025-09-15 | 0
P11-AFIRST | P11 | Complete First Valve Replacement | 1.11.4.1 | 2025-09-16 | 2025-09-17 |  |  |  |  | 2 | P11-B1inst |  | FALSE | FALSE | P11-CA04 | P11-WP041 | Task | Project-type realism | Source-derived / reconstructed network | 2025-09-16 | 2025-09-17 | 2026-03-06 | 2026-03-09 | 123
P11-B1inst | P11 | Batch 1 Valve Installation | 1.11.4.1 | 2025-09-16 | 2025-11-10 |  |  |  |  | 40 | P11-A6, P11-A7, P11-A8, P11-A9, P11-A10 |  | FALSE | TRUE | P11-CA04 | P11-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2025-09-16 | 2025-11-10 | 2025-09-16 | 2025-11-10 | 0
P11-MFIRST | P11 | MFIRST | 1.11.4.1 | 2025-09-17 | 2025-09-17 |  |  |  |  | 0 | P11-AFIRST |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-09-17 | 2025-09-17 | 2026-03-09 | 2026-03-09 | 123
P11-B1rest | P11 | Batch 1 Restoration | 1.11.4.3 | 2025-10-14 | 2025-12-08 |  |  |  |  | 40 | P11-B1inst |  | FALSE | FALSE | P11-CA04 | P11-WP043 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2025-10-14 | 2025-12-08 | 2025-11-18 | 2026-01-12 | 25
P11-B2inst | P11 | Batch 2 Valve Installation | 1.11.4.1 | 2025-10-21 | 2025-12-15 |  |  |  |  | 40 | P11-B1inst |  | FALSE | TRUE | P11-CA04 | P11-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2025-10-21 | 2025-12-15 | 2025-10-21 | 2025-12-15 | 0
P11-MBATCH1 | P11 | MBATCH1 | 1.11.4.1 | 2025-11-10 | 2025-11-10 |  |  |  |  | 0 | P11-B1inst |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-11-10 | 2025-11-10 | 2026-03-09 | 2026-03-09 | 85
P11-B1test | P11 | Batch 1 Testing / Return to Service | 1.11.5.1 | 2025-11-11 | 2025-11-24 |  |  |  |  | 10 | P11-B1inst |  | FALSE | FALSE | P11-CA05 | P11-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2025-11-11 | 2025-11-24 | 2026-02-24 | 2026-03-09 | 75
P11-B2rest | P11 | Batch 2 Restoration | 1.11.4.3 | 2025-11-18 | 2026-01-12 |  |  |  |  | 40 | P11-B2inst |  | FALSE | TRUE | P11-CA04 | P11-WP043 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2025-11-18 | 2026-01-12 | 2025-11-18 | 2026-01-12 | 0
P11-B1gis | P11 | Batch 1 Records/GIS Update | 1.11.6.1 | 2025-12-09 | 2025-12-22 |  |  |  |  | 10 | P11-B1rest |  | FALSE | FALSE | P11-CA06 | P11-WP061 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2025-12-09 | 2025-12-22 | 2026-01-13 | 2026-01-26 | 25
P11-MTARGET | P11 | MTARGET | 1.11.4.1 | 2025-12-15 | 2025-12-15 |  |  |  |  | 0 | P11-B2inst |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-12-15 | 2025-12-15 | 2026-03-09 | 2026-03-09 | 60
P11-B2test | P11 | Batch 2 Testing / Return to Service | 1.11.5.1 | 2025-12-16 | 2025-12-29 |  |  |  |  | 10 | P11-B2inst |  | FALSE | FALSE | P11-CA05 | P11-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2025-12-16 | 2025-12-29 | 2026-02-24 | 2026-03-09 | 50
P11-B2gis | P11 | Batch 2 Records/GIS Update | 1.11.6.1 | 2026-01-13 | 2026-01-26 |  |  |  |  | 10 | P11-B2rest |  | FALSE | TRUE | P11-CA06 | P11-WP061 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2026-01-13 | 2026-01-26 | 2026-01-13 | 2026-01-26 | 0
P11-A11 | P11 | Final Inspection & Punch List / Isolation Function Verification | 1.11.5.1 | 2026-01-27 | 2026-02-09 |  |  |  |  | 10 | P11-B1gis, P11-B2gis |  | FALSE | TRUE | P11-CA05 | P11-WP051 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2026-01-27 | 2026-02-09 | 2026-01-27 | 2026-02-09 | 0
P11-M3 | P11 | Substantial Completion | 1.11.4.1 | 2026-02-09 | 2026-02-09 |  |  |  |  | 0 | P11-A11 |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-02-09 | 2026-02-09 | 2026-03-09 | 2026-03-09 | 20
P11-MISOVERIFY | P11 | MISOVERIFY | 1.11.4.1 | 2026-02-09 | 2026-02-09 |  |  |  |  | 0 | P11-A11 |  | TRUE | FALSE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-02-09 | 2026-02-09 | 2026-03-09 | 2026-03-09 | 20
P11-A12 | P11 | Documentation & Turnover | 1.11.6.1 | 2026-02-10 | 2026-02-23 |  |  |  |  | 10 | P11-A11 |  | FALSE | TRUE | P11-CA06 | P11-WP061 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2026-02-10 | 2026-02-23 | 2026-02-10 | 2026-02-23 | 0
P11-A13 | P11 | Financial Closeout | 1.11.6.2 | 2026-02-17 | 2026-03-09 |  |  |  |  | 15 | P11-A12 |  | FALSE | TRUE | P11-CA06 | P11-WP062 | Task | Project-type realism | Recovered by reconciliation to approved P11 milestone dates and published durations | 2026-02-17 | 2026-03-09 | 2026-02-17 | 2026-03-09 | 0
P11-M4 | P11 | Final Completion | 1.11.4.1 | 2026-03-09 | 2026-03-09 |  |  |  |  | 0 | P11-A13 |  | TRUE | TRUE | P11-CA04 | P11-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 0
P12-Y1A1 | P12 | Year 1 Annual Planning & Prioritization Window | 1.12.1.1 | 2025-01-02 | 2025-01-22 |  |  |  |  | 15 |  |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-01-02 | 2025-01-22 | 2025-01-02 | 2025-01-22 | 0
P12-MPLANY1 | P12 | MPLANY1 | 1.12.1.1 | 2025-01-22 | 2025-01-22 |  |  |  |  | 0 | P12-Y1A1 |  | TRUE | FALSE | P12-CA01 | P12-WP011 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: annual planning milestone belongs in Planning & Prioritization | 2025-01-22 | 2025-01-22 | 2027-06-23 | 2027-06-23 | 630
P12-Y1A2 | P12 | Year 1 Intake & Triage of Small-Capital/Emergency Needs | 1.12.1.1 | 2025-01-23 | 2025-02-19 |  |  |  |  | 20 | P12-Y1A1 |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-01-23 | 2025-02-19 | 2025-01-23 | 2025-02-19 | 0
P12-Y1A3 | P12 | Year 1 Scope Development | 1.12.2.1 | 2025-02-20 | 2025-03-19 |  |  |  |  | 20 | P12-Y1A2 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Semantic WBS mapping corrected: scope development belongs in Design / Scope Development | 2025-02-20 | 2025-03-19 | 2025-02-20 | 2025-03-19 | 0
P12-Y1A4 | P12 | Year 1 Rapid Design / Standard-Detail Development | 1.12.2.1 | 2025-03-20 | 2025-04-09 |  |  |  |  | 15 | P12-Y1A3 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2025-03-20 | 2025-04-09 | 2025-03-20 | 2025-04-09 | 0
P12-Y1A5 | P12 | Year 1 Procurement / Task-Order Assignment | 1.12.3.1 | 2025-04-10 | 2025-05-14 |  |  |  |  | 25 | P12-Y1A4 |  | FALSE | TRUE | P12-CA03 | P12-WP031 | Task | Synthetic project assumption — standing on-call/task-order contract | Semantic WBS mapping corrected: procurement/task-order assignment belongs in Procurement | 2025-04-10 | 2025-05-14 | 2025-04-10 | 2025-05-14 | 0
P12-Y1A6 | P12 | Year 1 Field Execution | 1.12.4.1 | 2025-05-15 | 2025-09-17 |  |  |  |  | 90 | P12-Y1A5 |  | FALSE | TRUE | P12-CA04 | P12-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2025-05-15 | 2025-09-17 | 2025-05-15 | 2025-09-17 | 0
P12-MY1DONE | P12 | MY1DONE | 1.12.4.1 | 2025-09-17 | 2025-09-17 |  |  |  |  | 0 | P12-Y1A6 |  | TRUE | FALSE | P12-CA04 | P12-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2025-09-17 | 2025-09-17 | 2027-06-23 | 2027-06-23 | 460
P12-Y1A7 | P12 | Year 1 Verification / Acceptance | 1.12.5.1 | 2025-09-18 | 2025-10-08 |  |  |  |  | 15 | P12-Y1A6 |  | FALSE | TRUE | P12-CA05 | P12-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2025-09-18 | 2025-10-08 | 2025-09-18 | 2025-10-08 | 0
P12-Y1A8 | P12 | Year 1 Closeout | 1.12.6.1 | 2025-10-09 | 2025-10-29 |  |  |  |  | 15 | P12-Y1A7 |  | FALSE | TRUE | P12-CA06 | P12-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-09 | 2025-10-29 | 2025-10-09 | 2025-10-29 | 0
P12-Y2A1 | P12 | Year 2 Annual Planning & Prioritization Window | 1.12.1.1 | 2025-10-30 | 2025-11-19 |  |  |  |  | 15 | P12-Y1A8 |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-10-30 | 2025-11-19 | 2025-10-30 | 2025-11-19 | 0
P12-MPLANY2 | P12 | MPLANY2 | 1.12.1.1 | 2025-11-19 | 2025-11-19 |  |  |  |  | 0 | P12-Y2A1 |  | TRUE | FALSE | P12-CA01 | P12-WP011 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: annual planning milestone belongs in Planning & Prioritization | 2025-11-19 | 2025-11-19 | 2027-06-23 | 2027-06-23 | 415
P12-Y2A2 | P12 | Year 2 Intake & Triage of Small-Capital/Emergency Needs | 1.12.1.1 | 2025-11-20 | 2025-12-17 |  |  |  |  | 20 | P12-Y2A1 |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2025-11-20 | 2025-12-17 | 2025-11-20 | 2025-12-17 | 0
P12-Y2A3 | P12 | Year 2 Scope Development | 1.12.2.1 | 2025-12-18 | 2026-01-14 |  |  |  |  | 20 | P12-Y2A2 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Semantic WBS mapping corrected: scope development belongs in Design / Scope Development | 2025-12-18 | 2026-01-14 | 2025-12-18 | 2026-01-14 | 0
P12-Y2A4 | P12 | Year 2 Rapid Design / Standard-Detail Development | 1.12.2.1 | 2026-01-15 | 2026-02-04 |  |  |  |  | 15 | P12-Y2A3 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2026-01-15 | 2026-02-04 | 2026-01-15 | 2026-02-04 | 0
P12-Y2A5 | P12 | Year 2 Procurement / Task-Order Assignment | 1.12.3.1 | 2026-02-05 | 2026-03-11 |  |  |  |  | 25 | P12-Y2A4 |  | FALSE | TRUE | P12-CA03 | P12-WP031 | Task | Synthetic project assumption — standing on-call/task-order contract | Semantic WBS mapping corrected: procurement/task-order assignment belongs in Procurement | 2026-02-05 | 2026-03-11 | 2026-02-05 | 2026-03-11 | 0
P12-Y2A6 | P12 | Year 2 Field Execution | 1.12.4.1 | 2026-03-12 | 2026-07-15 |  |  |  |  | 90 | P12-Y2A5 |  | FALSE | TRUE | P12-CA04 | P12-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2026-03-12 | 2026-07-15 | 2026-03-12 | 2026-07-15 | 0
P12-MY2DONE | P12 | MY2DONE | 1.12.4.1 | 2026-07-15 | 2026-07-15 |  |  |  |  | 0 | P12-Y2A6 |  | TRUE | FALSE | P12-CA04 | P12-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2026-07-15 | 2026-07-15 | 2027-06-23 | 2027-06-23 | 245
P12-Y2A7 | P12 | Year 2 Verification / Acceptance | 1.12.5.1 | 2026-07-16 | 2026-08-05 |  |  |  |  | 15 | P12-Y2A6 |  | FALSE | TRUE | P12-CA05 | P12-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2026-07-16 | 2026-08-05 | 2026-07-16 | 2026-08-05 | 0
P12-Y2A8 | P12 | Year 2 Closeout | 1.12.6.1 | 2026-08-06 | 2026-08-26 |  |  |  |  | 15 | P12-Y2A7 |  | FALSE | TRUE | P12-CA06 | P12-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-06 | 2026-08-26 | 2026-08-06 | 2026-08-26 | 0
P12-Y3A1 | P12 | Year 3 Annual Planning & Prioritization Window | 1.12.1.1 | 2026-08-27 | 2026-09-16 |  |  |  |  | 15 | P12-Y2A8 |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2026-08-27 | 2026-09-16 | 2026-08-27 | 2026-09-16 | 0
P12-MPLANY3 | P12 | MPLANY3 | 1.12.1.1 | 2026-09-16 | 2026-09-16 |  |  |  |  | 0 | P12-Y3A1 |  | TRUE | FALSE | P12-CA01 | P12-WP011 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: annual planning milestone belongs in Planning & Prioritization | 2026-09-16 | 2026-09-16 | 2027-06-23 | 2027-06-23 | 200
P12-Y3A2 | P12 | Year 3 Intake & Triage of Small-Capital/Emergency Needs | 1.12.1.1 | 2026-09-17 | 2026-10-14 |  |  |  |  | 20 | P12-Y3A1 |  | FALSE | TRUE | P12-CA01 | P12-WP011 | Task | Project-type realism | Source-derived / reconstructed network | 2026-09-17 | 2026-10-14 | 2026-09-17 | 2026-10-14 | 0
P12-Y3A3 | P12 | Year 3 Scope Development | 1.12.2.1 | 2026-10-15 | 2026-11-11 |  |  |  |  | 20 | P12-Y3A2 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Semantic WBS mapping corrected: scope development belongs in Design / Scope Development | 2026-10-15 | 2026-11-11 | 2026-10-15 | 2026-11-11 | 0
P12-Y3A4 | P12 | Year 3 Rapid Design / Standard-Detail Development | 1.12.2.1 | 2026-11-12 | 2026-12-02 |  |  |  |  | 15 | P12-Y3A3 |  | FALSE | TRUE | P12-CA02 | P12-WP021 | Task | Project-type realism | Source-derived / reconstructed network | 2026-11-12 | 2026-12-02 | 2026-11-12 | 2026-12-02 | 0
P12-Y3A5 | P12 | Year 3 Procurement / Task-Order Assignment | 1.12.3.1 | 2026-12-03 | 2027-01-06 |  |  |  |  | 25 | P12-Y3A4 |  | FALSE | TRUE | P12-CA03 | P12-WP031 | Task | Synthetic project assumption — standing on-call/task-order contract | Semantic WBS mapping corrected: procurement/task-order assignment belongs in Procurement | 2026-12-03 | 2027-01-06 | 2026-12-03 | 2027-01-06 | 0
P12-Y3A6 | P12 | Year 3 Field Execution | 1.12.4.1 | 2027-01-07 | 2027-05-12 |  |  |  |  | 90 | P12-Y3A5 |  | FALSE | TRUE | P12-CA04 | P12-WP041 | Task | Synthetic, industry-informed planning assumption | Source-derived / reconstructed network | 2027-01-07 | 2027-05-12 | 2027-01-07 | 2027-05-12 | 0
P12-MY3DONE | P12 | MY3DONE | 1.12.4.1 | 2027-05-12 | 2027-05-12 |  |  |  |  | 0 | P12-Y3A6 |  | TRUE | FALSE | P12-CA04 | P12-WP041 | Milestone | Approved milestone / interface milestone | Source-explicit milestone date | 2027-05-12 | 2027-05-12 | 2027-06-23 | 2027-06-23 | 30
P12-Y3A7 | P12 | Year 3 Verification / Acceptance | 1.12.5.1 | 2027-05-13 | 2027-06-02 |  |  |  |  | 15 | P12-Y3A6 |  | FALSE | TRUE | P12-CA05 | P12-WP051 | Task | Project-type realism | Source-derived / reconstructed network | 2027-05-13 | 2027-06-02 | 2027-05-13 | 2027-06-02 | 0
P12-Y3A8 | P12 | Year 3 Closeout | 1.12.6.1 | 2027-06-03 | 2027-06-23 |  |  |  |  | 15 | P12-Y3A7 |  | FALSE | TRUE | P12-CA06 | P12-WP061 | Task | Project-type realism | Source-derived / reconstructed network | 2027-06-03 | 2027-06-23 | 2027-06-03 | 2027-06-23 | 0
P12-MPROGCLOSE | P12 | MPROGCLOSE | 1.12.6.1 | 2027-06-23 | 2027-06-23 |  |  |  |  | 0 | P12-Y3A8 |  | TRUE | TRUE | P12-CA06 | P12-WP061 | Milestone | Approved milestone / interface milestone | Semantic WBS mapping corrected: program close milestone belongs in Closeout | 2027-06-23 | 2027-06-23 | 2027-06-23 | 2027-06-23 | 0

## 04_MONTHLY_COSTS
Monthly Costs
Not yet populated - built in Phase 3 (Monthly Cost Model). Baseline monthly spend per project must sum to that project's BAC.
month | project_id | baseline_monthly | baseline_cumulative | actual_monthly | actual_cumulative | committed_cost | forecast_remaining | forecast_at_completion

## 05_EVM
Evm
Not yet populated - built in Phase 4 (Earned Value Management), calculated as of the status date (Mar 31, 2026).
project_id | bac | pv | ev | ac | cv | sv | cpi | spi | eac | etc | vac | rag_status

## 06_RISKS
Risks
Not yet populated - built in Phase 5 (Risk Register). 25-40 risks planned across the program.
risk_id | project_id | risk_category | risk_statement | probability_score | impact_score | inherent_score | owner | response_strategy | mitigation | residual_probability | residual_impact | residual_score | status

## 07_CHANGES
Changes
Not yet populated - built in Phase 6 (Change Control), including the featured $600K / six-week contractor change scenario.
change_id | project_id | change_description | cause | requested_date | approval_status | cost_impact | schedule_impact_days | contingency_drawdown | approved_by

## 08_RESOURCES
Resources
Not yet populated - built in Phase 7 (Staffing / Resource Plan).
month | project_id | role | planned_fte | notes

## 09_VENDORS
Vendors
Not yet populated - built in Phase 7 (Contractor / Vendor Tracker).
vendor_id | vendor_name | role | project_id | contract_value | status | performance_notes

## 10_MILESTONES
Milestones
Not yet populated - built in Phase 8 (Milestone Tracker). 35-50 milestones planned across the program.
milestone_id | project_id | milestone_name | baseline_date | forecast_date | actual_date | variance_days | status

## 11_KPI_THRESHOLDS
Kpi Thresholds
Not yet populated - built in Phase 4, alongside EVM. Defines RAG (Red/Amber/Green) status logic. These are project assumptions, not industry-mandated values.
kpi | green_threshold | amber_threshold | red_threshold

## 12_DASHBOARD_DATA
Dashboard Data
Not yet populated - built in Phase 9 (Power BI Prep). Flattened export tables consumed by the Power BI dashboard.
table_name | description | refreshed_from

## 03_SCHEDULE_RELATIONSHIPS
HWSD — Approved Baseline Dependency Network
498 relationships, including four P03/P08→P10 cross-project interfaces. FS/SS/FF business-day lags; schedule CPM not yet certified.
Relationship_ID | Project_ID | Predecessor_Activity_ID | Successor_Activity_ID | Relationship_Type | Lag_Days | Relationship_Scope | Recovery_Status
R0001 | P01 | P01-A1 | P01-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0002 | P01 | P01-A2 | P01-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0003 | P01 | P01-A3 | P01-A4 | FS | 10 | Within Project | Reconstructed from approved narrative/logic
R0004 | P01 | P01-A3 | P01-A4u | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0005 | P01 | P01-A4 | P01-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0007 | P01 | P01-A4 | P01-A5 | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0008 | P01 | P01-A5 | P01-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0013 | P01 | P01-A7a | P01-A7b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0014 | P01 | P01-A7b | P01-A7c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0015 | P01 | P01-A6 | P01-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0016 | P01 | P01-A7c | P01-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0017 | P01 | P01-A4u | P01-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0018 | P01 | P01-A8 | P01-A9 | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0019 | P01 | P01-A8 | P01-A9b | SS | 20 | Within Project | Reconstructed from approved narrative/logic
R0020 | P01 | P01-A8 | P01-A11 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0021 | P01 | P01-A9 | P01-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0022 | P01 | P01-A9b | P01-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0023 | P01 | P01-A11 | P01-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0024 | P01 | P01-A12 | P01-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0025 | P01 | P01-A10 | P01-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0026 | P01 | P01-M3 | P01-A13 | FS | 0 | Within Project | PROPOSED: completion-gated turnover after accepted substantial completion; replaces early documentation overlap; synthetic recovery, pending approval
R0028 | P01 | P01-A13 | P01-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0029 | P01 | P01-A15 | P01-A14 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0030 | P01 | P01-A14 | P01-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0031 | P02 | P02-A1 | P02-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0032 | P02 | P02-A2 | P02-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0033 | P02 | P02-A3 | P02-A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0035 | P02 | P02-A4 | P02-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0036 | P02 | P02-A4 | P02-A5 | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0037 | P02 | P02-A5 | P02-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0045 | P02 | P02-A7a | P02-A7b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0046 | P02 | P02-A7b | P02-A7c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0047 | P02 | P02-A7c | P02-A7d | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0048 | P02 | P02-A11a | P02-A11b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0049 | P02 | P02-A11b | P02-A11c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0050 | P02 | P02-A11c | P02-A11d | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0051 | P02 | P02-A6 | P02-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0052 | P02 | P02-A6b | P02-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0053 | P02 | P02-A8 | P02-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0054 | P02 | P02-A9 | P02-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0055 | P02 | P02-A7d | P02-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0056 | P02 | P02-A9 | P02-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0057 | P02 | P02-A11d | P02-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0058 | P02 | P02-A6c | P02-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0059 | P02 | P02-A9 | P02-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0060 | P02 | P02-A10 | P02-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0061 | P02 | P02-A12 | P02-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0062 | P02 | P02-A13 | P02-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0063 | P02 | P02-A14 | P02-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0064 | P02 | P02-A15 | P02-A15b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0066 | P02 | P02-A15 | P02-A16 | SS | 5 | Within Project | Reconstructed from approved narrative/logic
R0067 | P02 | P02-A16 | P02-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0068 | P02 | P02-A15b | P02-A17 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0069 | P02 | P02-A17 | P02-M5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0070 | P03 | P03-A1 | P03-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0071 | P03 | P03-A2 | P03-A2b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0072 | P03 | P03-A2b | P03-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0073 | P03 | P03-A3 | P03-A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0074 | P03 | P03-A4 | P03-A5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0075 | P03 | P03-A5 | P03-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0076 | P03 | P03-A6 | P03-A7 | SS | 5 | Within Project | PROPOSED synthetic recovery: Final design overlaps 90%-design review; reconciles 20bd design to published M1 if upstream dates hold.
R0077 | P03 | P03-A7 | P03-M1 | FS | 0 | Within Project | BLOCKED: documented relationship incompatible with existing reconstructed date(s); see QA report
R0078 | P03 | P03-A7 | P03-A7b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0079 | P03 | P03-A7 | P03-A8 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0080 | P03 | P03-A8 | P03-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0081 | P03 | P03-A9 | P03-A9b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0082 | P03 | P03-A9b | P03-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0083 | P03 | P03-A7b | P03-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0084 | P03 | P03-M2 | P03-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0085 | P03 | P03-M2 | P03-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0086 | P03 | P03-M2 | P03-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0087 | P03 | P03-M2 | P03-A21 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0088 | P03 | P03-A11 | P03-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0089 | P03 | P03-A12 | P03-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0090 | P03 | P03-A13 | P03-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0091 | P03 | P03-A14 | P03-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0092 | P03 | P03-A16 | P03-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0093 | P03 | P03-A17 | P03-A18 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0094 | P03 | P03-A18 | P03-A19 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0095 | P03 | P03-A21 | P03-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0096 | P03 | P03-A22 | P03-A23 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0097 | P03 | P03-A15 | P03-A20 | SS | 20 | Within Project | Reconstructed from approved narrative/logic
R0098 | P03 | P03-A19 | P03-A20 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0099 | P03 | P03-A15 | P03-A24 | SS | 30 | Within Project | Reconstructed from approved narrative/logic
R0100 | P03 | P03-A23 | P03-A24 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0101 | P03 | P03-A15 | P03-A25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0102 | P03 | P03-A20 | P03-A25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0103 | P03 | P03-A15 | P03-A26 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0104 | P03 | P03-A25 | P03-A26 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0105 | P03 | P03-A24 | P03-A26 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0106 | P03 | P03-A26 | P03-A27 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0107 | P03 | P03-A27 | P03-A28 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0108 | P03 | P03-A27 | P03-A29 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0109 | P03 | P03-A28 | P03-A30 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0110 | P03 | P03-A29 | P03-A30 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0111 | P03 | P03-A30 | P03-A31 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0112 | P03 | P03-A30 | P03-A32 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0113 | P03 | P03-A32 | P03-A33 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0114 | P03 | P03-A31 | P03-A33 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0115 | P03 | P03-A14 | P03-M5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0116 | P03 | P03-A26 | P03-M6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0117 | P03 | P03-A27 | P03-M7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0118 | P03 | P03-A28 | P03-M8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0119 | P03 | P03-A30 | P03-M9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0120 | P03 | P03-A30 | P03-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0121 | P03 | P03-A33 | P03-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0122 | P03 | P03-M1 | P03-I-P03-01 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0123 | P03 | P03-A16 | P03-I-P03-02 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0124 | P03 | P03-M6 | P03-I-P03-03 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0125 | P04 | P04-A1 | P04-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0126 | P04 | P04-A2 | P04-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0127 | P04 | P04-A3 | P04-A4 | FS | 10 | Within Project | Reconstructed from approved narrative/logic
R0128 | P04 | P04-A4 | P04-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0129 | P04 | P04-A4 | P04-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0130 | P04 | P04-A4 | P04-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0131 | P04 | P04-A5 | P04-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0132 | P04 | P04-A5b | P04-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0133 | P04 | P04-A5c | P04-M2 | FS | 15 | Within Project | Reconstructed from approved narrative/logic ¦ USER-APPROVED SYNTHETIC POST-GOVERNING-APPROVAL NTP RELEASE HOLD: 15 business days (not recovered original)
R0134 | P04 | P04-A4b | P04-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0135 | P04 | P04-M2 | P04-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0136 | P04 | P04-M2 | P04-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0137 | P04 | P04-A6 | P04-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0138 | P04 | P04-A7 | P04-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0139 | P04 | P04-A8 | P04-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0140 | P04 | P04-A9 | P04-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0141 | P04 | P04-A10 | P04-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0142 | P04 | P04-A11 | P04-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0143 | P04 | P04-A12 | P04-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0144 | P04 | P04-A13 | P04-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0145 | P04 | P04-A14 | P04-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0146 | P04 | P04-A15 | P04-M5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0147 | P04 | P04-A15 | P04-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0148 | P04 | P04-A16 | P04-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0149 | P04 | P04-A16 | P04-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0150 | P04 | P04-A17 | P04-A18 | SS | 5 | Within Project | Recovered by reconciliation to approved M3/M4 dates and published closeout durations
R0151 | P04 | P04-A16 | P04-A18 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0152 | P04 | P04-A18 | P04-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0153 | P05 | P05-A1 | P05-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0154 | P05 | P05-A2 | P05-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0155 | P05 | P05-A3 | P05-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0156 | P05 | P05-A4 | P05-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0157 | P05 | P05-A4 | P05-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0158 | P05 | P05-A4 | P05-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0159 | P05 | P05-A5 | P05-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0160 | P05 | P05-A5b | P05-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0161 | P05 | P05-A5c | P05-M2 | FS | 5 | Within Project | Reconstructed from approved narrative/logic ¦ USER-APPROVED SYNTHETIC POST-GOVERNING-APPROVAL NTP RELEASE HOLD: 5 business days (not recovered original)
R0162 | P05 | P05-A4b | P05-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0163 | P05 | P05-M2 | P05-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0164 | P05 | P05-M2 | P05-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0165 | P05 | P05-A7 | P05-A8 | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0166 | P05 | P05-A7 | P05-A9 | SS | 10 | Within Project | Recovered by reconciliation to approved P05 field milestone dates
R0167 | P05 | P05-M2 | P05-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0168 | P05 | P05-M2 | P05-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0169 | P05 | P05-A6 | P05-A12a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0170 | P05 | P05-A9 | P05-A12a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0171 | P05 | P05-A10 | P05-A12a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0172 | P05 | P05-A11 | P05-A12a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0173 | P05 | P05-A12a | P05-A13a | SS | 20 | Within Project | Reconstructed from approved narrative/logic
R0174 | P05 | P05-A13a | P05-A14a | SS | 20 | Within Project | Reconstructed from approved narrative/logic
R0175 | P05 | P05-A14a | P05-A15a | SS | 20 | Within Project | Reconstructed from approved narrative/logic
R0176 | P05 | P05-A12a | P05-AFIRST | SS | 0 | Within Project | Reconstructed from approved narrative/logic
R0177 | P05 | P05-AFIRST | P05-MFIRST | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0178 | P05 | P05-A12a | P05-A12b | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0179 | P05 | P05-A12b | P05-A12c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0180 | P05 | P05-A13a | P05-A13b | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0181 | P05 | P05-A13b | P05-A13c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0182 | P05 | P05-A14a | P05-A14b | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0183 | P05 | P05-A14b | P05-A14c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0184 | P05 | P05-A15a | P05-A15b | SS | 15 | Within Project | Reconstructed from approved narrative/logic
R0185 | P05 | P05-A15b | P05-A15c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0186 | P05 | P05-A12a | P05-M25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0187 | P05 | P05-A13a | P05-M50 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0188 | P05 | P05-A14a | P05-M75 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0189 | P05 | P05-A15a | P05-MTARGET | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0190 | P05 | P05-A12c | P05-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0191 | P05 | P05-A13c | P05-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0192 | P05 | P05-A14c | P05-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0193 | P05 | P05-A15c | P05-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0194 | P05 | P05-A16 | P05-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0195 | P05 | P05-A16 | P05-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0196 | P05 | P05-A17 | P05-A18 | SS | 10 | Within Project | Recovered by reconciliation to approved P05 M4 date and published closeout durations
R0197 | P05 | P05-A18 | P05-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0198 | P06 | P06-A1 | P06-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0199 | P06 | P06-A2 | P06-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0200 | P06 | P06-A3 | P06-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0201 | P06 | P06-A4 | P06-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0202 | P06 | P06-A4 | P06-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0203 | P06 | P06-A4 | P06-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0204 | P06 | P06-A5 | P06-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0205 | P06 | P06-A5b | P06-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0206 | P06 | P06-A5c | P06-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0207 | P06 | P06-A4b | P06-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0208 | P06 | P06-M2 | P06-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0209 | P06 | P06-M2 | P06-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0210 | P06 | P06-M2 | P06-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0211 | P06 | P06-M2 | P06-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0212 | P06 | P06-M2 | P06-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0213 | P06 | P06-A11 | P06-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0214 | P06 | P06-A12 | P06-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0215 | P06 | P06-A7 | P06-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0216 | P06 | P06-A9 | P06-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0217 | P06 | P06-A8 | P06-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0218 | P06 | P06-M2 | P06-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0219 | P06 | P06-A13 | P06-APILOTSTAGE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0220 | P06 | P06-A14 | P06-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0221 | P06 | P06-A15 | P06-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0222 | P06 | P06-APILOTSTAGE | P06-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0223 | P06 | P06-A8 | P06-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0224 | P06 | P06-A6 | P06-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0225 | P06 | P06-A16 | P06-AFIRSTPILOT | SS | 0 | Within Project | Reconstructed from approved narrative/logic
R0226 | P06 | P06-A16 | P06-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0227 | P06 | P06-A17 | P06-MPILOTDONE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0228 | P06 | P06-A14 | P06-MSYSINT | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0229 | P06 | P06-A17 | P06-A18a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0230 | P06 | P06-A17 | P06-A19a | FS | 15 | Within Project | Reconstructed from approved narrative/logic
R0231 | P06 | P06-A17 | P06-A20a | FS | 30 | Within Project | Reconstructed from approved narrative/logic
R0232 | P06 | P06-A17 | P06-A21a | FS | 45 | Within Project | Reconstructed from approved narrative/logic
R0233 | P06 | P06-A18a | P06-A18b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0234 | P06 | P06-A19a | P06-A19b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0235 | P06 | P06-A20a | P06-A20b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0236 | P06 | P06-A21a | P06-A21b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0237 | P06 | P06-A18a | P06-M25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0238 | P06 | P06-A19a | P06-M50 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0239 | P06 | P06-A20a | P06-M75 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0240 | P06 | P06-A21a | P06-MFULL | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0241 | P06 | P06-A18b | P06-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0242 | P06 | P06-A19b | P06-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0243 | P06 | P06-A20b | P06-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0244 | P06 | P06-A21b | P06-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0245 | P06 | P06-A22 | P06-A23 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0246 | P06 | P06-A23 | P06-A24 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0247 | P06 | P06-A24 | P06-A25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0248 | P06 | P06-A25 | P06-A26 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0249 | P06 | P06-A24 | P06-MOPACC | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0250 | P06 | P06-A24 | P06-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0251 | P06 | P06-A26 | P06-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0252 | P07 | P07-A1 | P07-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0253 | P07 | P07-A2 | P07-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0254 | P07 | P07-A3 | P07-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0255 | P07 | P07-A4 | P07-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0256 | P07 | P07-A4 | P07-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0257 | P07 | P07-A4 | P07-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0258 | P07 | P07-A5 | P07-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0259 | P07 | P07-A5b | P07-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0260 | P07 | P07-A5c | P07-M2 | FS | 10 | Within Project | Reconstructed from approved narrative/logic ¦ USER-APPROVED SYNTHETIC POST-GOVERNING-APPROVAL NTP RELEASE HOLD: 10 business days (not recovered original)
R0261 | P07 | P07-A4b | P07-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0262 | P07 | P07-M2 | P07-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0263 | P07 | P07-M2 | P07-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0264 | P07 | P07-M2 | P07-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0265 | P07 | P07-A8 | P07-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0266 | P07 | P07-A6 | P07-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0267 | P07 | P07-A7 | P07-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0268 | P07 | P07-A10 | P07-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0269 | P07 | P07-A9 | P07-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0270 | P07 | P07-A11 | P07-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0271 | P07 | P07-A12 | P07-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0272 | P07 | P07-A13 | P07-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0273 | P07 | P07-A14 | P07-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0274 | P07 | P07-A15 | P07-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0275 | P07 | P07-A14 | P07-MCOMM | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0276 | P07 | P07-A15 | P07-MBAL | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0277 | P07 | P07-A16 | P07-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0278 | P07 | P07-A16 | P07-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0279 | P07 | P07-A17 | P07-A18 | SS | 5 | Within Project | Recovered by reconciliation to approved M3/M4 dates and published closeout durations
R0280 | P07 | P07-A16 | P07-A18 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0281 | P07 | P07-A18 | P07-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0282 | P08 | P08-A1 | P08-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0283 | P08 | P08-A2 | P08-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0284 | P08 | P08-A3 | P08-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0285 | P08 | P08-A4 | P08-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0286 | P08 | P08-A4 | P08-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0287 | P08 | P08-A3 | P08-A7 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0288 | P08 | P08-A4 | P08-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0289 | P08 | P08-A5 | P08-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0290 | P08 | P08-A5b | P08-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0291 | P08 | P08-A5c | P08-M2 | FS | 10 | Within Project | Reconstructed from approved narrative/logic ¦ USER-APPROVED SYNTHETIC POST-GOVERNING-APPROVAL NTP RELEASE HOLD: 10 business days (not recovered original)
R0292 | P08 | P08-A4b | P08-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0293 | P08 | P08-M2 | P08-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0294 | P08 | P08-M2 | P08-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0295 | P08 | P08-M2 | P08-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0296 | P08 | P08-M2 | P08-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0297 | P08 | P08-A8 | P08-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0298 | P08 | P08-A9 | P08-A9fat | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0299 | P08 | P08-A9fat | P08-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0300 | P08 | P08-A8 | P08-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0301 | P08 | P08-A10 | P08-A10fat | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0302 | P08 | P08-A10fat | P08-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0303 | P08 | P08-A14 | P08-MOUTAGE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0304 | P08 | P08-A13 | P08-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0305 | P08 | P08-A11 | P08-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0306 | P08 | P08-A14 | P08-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0307 | P08 | P08-A13 | P08-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0308 | P08 | P08-A12 | P08-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0309 | P08 | P08-A14 | P08-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0310 | P08 | P08-A15 | P08-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0311 | P08 | P08-A16 | P08-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0312 | P08 | P08-A17 | P08-A18 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0313 | P08 | P08-A18 | P08-A19 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0314 | P08 | P08-A19 | P08-A20 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0315 | P08 | P08-A20 | P08-A21 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0316 | P08 | P08-A18 | P08-MSTART | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0317 | P08 | P08-A20 | P08-MOPACC | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0318 | P08 | P08-A21 | P08-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0319 | P08 | P08-A21 | P08-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0320 | P08 | P08-A22 | P08-A23 | SS | 5 | Within Project | Recovered by reconciliation to approved M3/M4 dates and published closeout durations
R0321 | P08 | P08-A21 | P08-A23 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0322 | P08 | P08-A23 | P08-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0323 | P08 | P08-M1 | P08-I-P08-01 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0324 | P08 | P08-A8 | P08-I-P08-02 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0325 | P08 | P08-MSTART | P08-I-P08-03 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0326 | P09 | P09-A1 | P09-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0327 | P09 | P09-A2 | P09-A3a | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0328 | P09 | P09-A3a | P09-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0329 | P09 | P09-A3 | P09-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0330 | P09 | P09-A4 | P09-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0331 | P09 | P09-A4 | P09-A4b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0332 | P09 | P09-A4 | P09-A4c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0333 | P09 | P09-A4 | P09-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0334 | P09 | P09-A5 | P09-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0335 | P09 | P09-A5b | P09-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0336 | P09 | P09-A4c | P09-MPERMIT | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0337 | P09 | P09-A5c | P09-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0338 | P09 | P09-A4b | P09-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0339 | P09 | P09-A4c | P09-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0340 | P09 | P09-M2 | P09-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0341 | P09 | P09-M2 | P09-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0342 | P09 | P09-M2 | P09-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0343 | P09 | P09-M2 | P09-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0344 | P09 | P09-A6 | P09-MSPECMOB | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0345 | P09 | P09-A10 | P09-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0346 | P09 | P09-A11 | P09-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0347 | P09 | P09-A6 | P09-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0348 | P09 | P09-A7 | P09-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0349 | P09 | P09-A13 | P09-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0350 | P09 | P09-A12 | P09-A15 | FS | 0 | Within Project | Restored from approved P09 relationship highlight (A14 + A12 -> A15)
R0351 | P09 | P09-A14 | P09-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0352 | P09 | P09-A15 | P09-MCROSSDONE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0353 | P09 | P09-A15 | P09-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0354 | P09 | P09-A15 | P09-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0355 | P09 | P09-A8 | P09-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0356 | P09 | P09-A16 | P09-A18 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0357 | P09 | P09-A17 | P09-A18 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0358 | P09 | P09-A9 | P09-A18 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0359 | P09 | P09-A18 | P09-A19 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0360 | P09 | P09-A19 | P09-MINSERVICE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0361 | P09 | P09-A19 | P09-A20 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0362 | P09 | P09-A20 | P09-A21 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0363 | P09 | P09-A21 | P09-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0364 | P09 | P09-A21 | P09-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0365 | P09 | P09-A22 | P09-A23 | SS | 5 | Within Project | Recovered by reconciliation to approved P09 M3/M4 dates and published closeout durations
R0366 | P09 | P09-A21 | P09-A23 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0367 | P09 | P09-A23 | P09-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0368 | P10 | P10-A1 | P10-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0369 | P10 | P10-A2 | P10-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0370 | P10 | P10-A3 | P10-A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0371 | P10 | P10-A4 | P10-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0372 | P10 | P10-A4 | P10-A6b | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0373 | P10 | P10-A5 | P10-A6 | SS | 10 | Within Project | PROPOSED synthetic recovery: Final controls design overlaps network/cybersecurity coordination; allows approval at reported July 21 if upstream dates hold.
R0374 | P10 | P10-A6b | P10-A6 | SS | 10 | Within Project | PROPOSED synthetic recovery: Final controls design overlaps network/cybersecurity coordination; allows approval at reported July 21 if upstream dates hold.
R0375 | P10 | P10-A6 | P10-M1 | FS | 0 | Within Project | BLOCKED: documented relationship incompatible with existing reconstructed date(s); see QA report
R0376 | P10 | P10-A6 | P10-A7 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0377 | P10 | P10-A7 | P10-A7b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0378 | P10 | P10-A7b | P10-A7c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0379 | P10 | P10-A7c | P10-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0380 | P10 | P10-M2 | P10-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0381 | P10 | P10-M2 | P10-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0382 | P10 | P10-M2 | P10-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0383 | P10 | P10-M2 | P10-A14 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0384 | P10 | P10-M2 | P10-A15 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0385 | P10 | P10-A9 | P10-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0386 | P10 | P10-A10 | P10-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0387 | P10 | P10-A12 | P10-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0388 | P10 | P10-A14 | P10-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0389 | P10 | P10-A15 | P10-A13 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0390 | P10 | P10-A13 | P10-MFAT | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0391 | P10 | P10-A13 | P10-A16 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0392 | P10 | P10-A8 | P10-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0393 | P10 | P10-A16 | P10-A17 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0394 | P10 | P10-A17 | P10-MSITEINSTALL | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0395 | P10 | P10-A17 | P10-A18 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0396 | P10 | P10-A18 | P10-A19 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0397 | P10 | P10-A18 | P10-MIOCHECK | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0398 | P03→P10 | P03-I-P03-02 | P10-IF-01 | FS | 0 | Inter-Project | Reconstructed from approved narrative/logic
R0399 | P08→P10 | P08-I-P08-02 | P10-IF-01 | FS | 0 | Inter-Project | Reconstructed from approved narrative/logic
R0400 | P10 | P10-M1 | P10-IF-01 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0401 | P10 | P10-IF-01 | P10-MIF01 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0402 | P10 | P10-MIF01 | P10-MIF02 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0403 | P10 | P10-A14 | P10-MIF02 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0404 | P10 | P10-A15 | P10-MIF02 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0405 | P10 | P10-MIF02 | P10-A13 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0406 | P03→P10 | P03-I-P03-03 | P10-MIF03 | FS | 0 | Inter-Project | Reconstructed from approved narrative/logic
R0407 | P08→P10 | P08-I-P08-03 | P10-MIF03 | FS | 0 | Inter-Project | Reconstructed from approved narrative/logic
R0408 | P10 | P10-MSITEINSTALL | P10-MIF03 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0409 | P10 | P10-MIOCHECK | P10-MIF03 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0410 | P10 | P10-A19 | P10-MIF03 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0411 | P10 | P10-MIF03 | P10-A20 | FS | 0 | Within Project | Restored from approved P03/P08/P10 interface package
R0412 | P10 | P10-A20 | P10-A21 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0413 | P10 | P10-A21 | P10-MSAT | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0414 | P10 | P10-A21 | P10-A22 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0415 | P10 | P10-A21 | P10-A23 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0416 | P10 | P10-A22 | P10-A24 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0417 | P10 | P10-A23 | P10-A24 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0418 | P10 | P10-A24 | P10-A25 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0419 | P10 | P10-A24 | P10-MCUTOVER | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0420 | P10 | P10-A25 | P10-MOPACC | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0421 | P10 | P10-A25 | P10-A27 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0422 | P10 | P10-A25 | P10-A26 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0423 | P10 | P10-A27 | P10-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0424 | P10 | P10-A26 | P10-A28 | FS | 5 | Within Project | Recovered by reconciliation to approved P10 M4 date; original executable script unavailable
R0425 | P10 | P10-A27 | P10-A28 | FF | 0 | Within Project | Reconstructed from approved narrative/logic
R0426 | P10 | P10-A28 | P10-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0427 | P11 | P11-A1 | P11-A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0428 | P11 | P11-A2 | P11-A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0429 | P11 | P11-A3 | P11-A4 | FS | 5 | Within Project | Reconstructed from approved narrative/logic
R0430 | P11 | P11-A4 | P11-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0431 | P11 | P11-A4 | P11-A5 | SS | 10 | Within Project | Reconstructed from approved narrative/logic
R0432 | P11 | P11-A5 | P11-A5b | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0433 | P11 | P11-A5b | P11-A5c | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0434 | P11 | P11-A5c | P11-M2 | FS | 5 | Within Project | Reconstructed from approved narrative/logic ¦ USER-APPROVED SYNTHETIC POST-GOVERNING-APPROVAL NTP RELEASE HOLD: 5 business days (not recovered original)
R0435 | P11 | P11-M2 | P11-A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0436 | P11 | P11-M2 | P11-A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0437 | P11 | P11-M2 | P11-A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0438 | P11 | P11-M2 | P11-A9 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0439 | P11 | P11-M2 | P11-A10 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0440 | P11 | P11-A6 | P11-B1inst | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0441 | P11 | P11-A7 | P11-B1inst | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0442 | P11 | P11-A8 | P11-B1inst | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0443 | P11 | P11-A9 | P11-B1inst | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0444 | P11 | P11-A10 | P11-B1inst | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0445 | P11 | P11-B1inst | P11-B2inst | SS | 25 | Within Project | Reconstructed from approved narrative/logic
R0446 | P11 | P11-B1inst | P11-AFIRST | SS | 0 | Within Project | Reconstructed from approved narrative/logic
R0447 | P11 | P11-AFIRST | P11-MFIRST | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0448 | P11 | P11-B1inst | P11-MBATCH1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0449 | P11 | P11-B2inst | P11-MTARGET | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0450 | P11 | P11-B1inst | P11-B1test | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0451 | P11 | P11-B1inst | P11-B1rest | SS | 20 | Within Project | Recovered by milestone/duration reconciliation; original executable script unavailable
R0452 | P11 | P11-B1rest | P11-B1gis | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0453 | P11 | P11-B2inst | P11-B2test | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0454 | P11 | P11-B2inst | P11-B2rest | SS | 20 | Within Project | Recovered by milestone/duration reconciliation; original executable script unavailable
R0455 | P11 | P11-B2rest | P11-B2gis | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0456 | P11 | P11-B1gis | P11-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0457 | P11 | P11-B2gis | P11-A11 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0458 | P11 | P11-A11 | P11-MISOVERIFY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0459 | P11 | P11-A11 | P11-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0460 | P11 | P11-A11 | P11-A12 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0461 | P11 | P11-A12 | P11-A13 | SS | 5 | Within Project | Recovered by reconciliation to approved P11 M4 date and published closeout durations
R0462 | P11 | P11-A13 | P11-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0463 | P12 | P12-Y1A1 | P12-Y1A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0464 | P12 | P12-Y1A2 | P12-Y1A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0465 | P12 | P12-Y1A3 | P12-Y1A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0466 | P12 | P12-Y1A4 | P12-Y1A5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0467 | P12 | P12-Y1A5 | P12-Y1A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0468 | P12 | P12-Y1A6 | P12-Y1A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0469 | P12 | P12-Y1A7 | P12-Y1A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0470 | P12 | P12-Y1A1 | P12-MPLANY1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0471 | P12 | P12-Y1A6 | P12-MY1DONE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0472 | P12 | P12-Y1A8 | P12-Y2A1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0473 | P12 | P12-Y2A1 | P12-Y2A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0474 | P12 | P12-Y2A2 | P12-Y2A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0475 | P12 | P12-Y2A3 | P12-Y2A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0476 | P12 | P12-Y2A4 | P12-Y2A5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0477 | P12 | P12-Y2A5 | P12-Y2A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0478 | P12 | P12-Y2A6 | P12-Y2A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0479 | P12 | P12-Y2A7 | P12-Y2A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0480 | P12 | P12-Y2A1 | P12-MPLANY2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0481 | P12 | P12-Y2A6 | P12-MY2DONE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0482 | P12 | P12-Y2A8 | P12-Y3A1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0483 | P12 | P12-Y3A1 | P12-Y3A2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0484 | P12 | P12-Y3A2 | P12-Y3A3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0485 | P12 | P12-Y3A3 | P12-Y3A4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0486 | P12 | P12-Y3A4 | P12-Y3A5 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0487 | P12 | P12-Y3A5 | P12-Y3A6 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0488 | P12 | P12-Y3A6 | P12-Y3A7 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0489 | P12 | P12-Y3A7 | P12-Y3A8 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0490 | P12 | P12-Y3A1 | P12-MPLANY3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0491 | P12 | P12-Y3A6 | P12-MY3DONE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0492 | P12 | P12-Y3A8 | P12-MPROGCLOSE | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0493 | P01 | P01-A4 | P01-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0494 | P01 | P01-A5b | P01-M2 | FS | 10 | Within Project | Reconstructed from approved narrative/logic
R0495 | P01 | P01-A4b | P01-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0496 | P01 | P01-A15 | P01-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0497 | P02 | P02-A4 | P02-M1 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0498 | P02 | P02-A5b | P02-M2 | FS | 10 | Within Project | Reconstructed from approved narrative/logic
R0499 | P02 | P02-A4b | P02-M2 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0500 | P02 | P02-A8 | P02-M3 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0501 | P02 | P02-A15b | P02-M4 | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0502 | P06 | P06-MSYSINT | P06-MPILOTREADY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0503 | P06 | P06-A15 | P06-MPILOTREADY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0504 | P06 | P06-APILOTSTAGE | P06-MPILOTREADY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0505 | P06 | P06-A8 | P06-MPILOTREADY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0506 | P06 | P06-A6 | P06-MPILOTREADY | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0507 | P06 | P06-MPILOTREADY | P06-A16 | FS | 0 | Within Project | BLOCKED: documented relationship incompatible with existing reconstructed date(s); see QA report
R0508 | P06 | P06-AFIRSTPILOT | P06-MFIRSTPILOT | FS | 0 | Within Project | Reconstructed from approved narrative/logic
R0509 | P01 | P01-M2 | P01-A6 | FS | 0 | Within Project | PROPOSED synthetic recovery: Contractor mobilization/submittals cannot begin before award/NTP; procurement and mobilization run in parallel.
R0510 | P01 | P01-M2 | P01-A7a | FS | 0 | Within Project | PROPOSED synthetic recovery: Contractor mobilization/submittals cannot begin before award/NTP; procurement and mobilization run in parallel.
R0511 | P02 | P02-M2 | P02-A6 | FS | 0 | Within Project | PROPOSED synthetic recovery: Contractor mobilization/submittals cannot begin before award/NTP; procurement and mobilization run in parallel.
R0512 | P02 | P02-M2 | P02-A7a | FS | 0 | Within Project | PROPOSED synthetic recovery: Contractor mobilization/submittals cannot begin before award/NTP; procurement and mobilization run in parallel.
R0513 | P02 | P02-M2 | P02-A11a | FS | 0 | Within Project | PROPOSED synthetic recovery: Contractor mobilization/submittals cannot begin before award/NTP; procurement and mobilization run in parallel.

## SCHEDULE_VERSION_LOG
HWSD — Schedule Version & Approval History
Previous approved coordination dates are retained; synthetic recovery authorized by user. P12 standing-work scope is excluded from ordinary substantial-completion comparisons.
Project_ID | Version | Status | Version_Basis | Start | Finish | Change_Calendar_Days | Approval_Note
P01 | Prior coordinated baseline | SUPERSEDED | Original approved coordinated scheduling version | 2025-01-02 | 2026-01-05 | 0 | Historical date comparator; no baseline overwrite
P01 | Synthetic recovery baseline | APPROVED | Reconstructed network with accepted documented assumptions | 2025-01-02 | 2025-12-29 | -7 | User-approved synthetic baseline + release holds; CPM/float calculated, all approved finish dates retained
P02 | Prior coordinated baseline | SUPERSEDED | Original approved coordinated scheduling version | 2025-02-03 | 2026-04-01 | 0 | Historical date comparator; no baseline overwrite
P02 | Synthetic recovery baseline | APPROVED | Reconstructed network with accepted documented assumptions | 2025-02-03 | 2026-02-25 | -35 | User-approved synthetic baseline + release holds; CPM/float calculated, all approved finish dates retained
P03 | Prior coordinated baseline | SUPERSEDED | Original approved coordinated scheduling version | 2025-01-02 | 2027-02-17 | 0 | Historical date comparator; no baseline overwrite
P03 | Synthetic recovery baseline | APPROVED | Reconstructed network with accepted documented assumptions | 2025-01-02 | 2027-01-27 | -21 | User-approved synthetic baseline + release holds; CPM/float calculated, all approved finish dates retained
P04 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-06-02 | 2026-04-24 | 0 | Historical date comparator; no baseline overwrite
P04 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-06-02 | 2026-04-24 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P05 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-03-03 | 2026-05-15 | 0 | Historical date comparator; no baseline overwrite
P05 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-03-03 | 2026-05-15 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P06 | Prior coordinated baseline | SUPERSEDED | Original approved coordinated scheduling version | 2025-08-01 | 2027-01-07 | 0 | Historical date comparator; no baseline overwrite
P06 | Synthetic recovery baseline | APPROVED | Reconstructed network with accepted documented assumptions | 2025-08-01 | 2026-12-24 | -14 | User-approved synthetic baseline + release holds; CPM/float calculated, all approved finish dates retained
P07 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-10-01 | 2026-09-01 | 0 | Historical date comparator; no baseline overwrite
P07 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-10-01 | 2026-09-01 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P08 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-12-01 | 2027-01-08 | 0 | Historical date comparator; no baseline overwrite
P08 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-12-01 | 2027-01-08 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P09 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2026-02-02 | 2027-03-03 | 0 | Historical date comparator; no baseline overwrite
P09 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2026-02-02 | 2027-03-03 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P10 | Prior coordinated baseline | SUPERSEDED | Original approved coordinated scheduling version | 2026-04-01 | 2027-08-20 | 0 | Historical date comparator; no baseline overwrite
P10 | Synthetic recovery baseline | APPROVED | Reconstructed network with accepted documented assumptions | 2026-04-01 | 2027-08-06 | -14 | User-approved synthetic baseline + release holds; CPM/float calculated, all approved finish dates retained
P11 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-04-01 | 2026-03-09 | 0 | Historical date comparator; no baseline overwrite
P11 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-04-01 | 2026-03-09 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.
P12 | Prior coordinated baseline | RETAINED | Original approved coordinated scheduling version | 2025-01-02 | 2027-06-23 | 0 | Historical date comparator; no baseline overwrite
P12 | Synthetic recovery baseline | APPROVED | Unchanged reference network, carried forward | 2025-01-02 | 2027-06-23 | 0 | Reference project dates unchanged; CPM/float calculated. P12 is standing work.

## RESOURCE_ASSUMPTIONS
HWSD — Resource Capacity Assumptions
Planning assumptions are synthetic. Six concurrent distribution crews at peak vs seven-unit baseline; commissioning demand three vs two internal + one temporary specialist.
Assumption_ID | Resource_or_Issue | Approved_Assumption | Sensitivity_or_Note
RA-01 | Distribution/excavation contractors | 7 concurrent crew groups available | Approved baseline capacity
RA-02 | Distribution constrained sensitivity | 4 concurrent crews | Sensitivity only; not baseline
RA-03 | P05 field delivery | Maximum 3 concurrent field crew groups | Existing approved schedule assumption
RA-04 | P11 field delivery | Maximum 2 concurrent field crew groups | Existing approved schedule assumption
RA-05 | P12 recurring work | 1 standing field crew/group per active annual cycle | Synthetic portfolio assumption
RA-06 | Owner commissioning | 2 internal commissioning/acceptance teams | Approved baseline capacity
RA-07 | Late-2026 commissioning peak | +1 temporary specialist/vendor commissioning resource | Preserves P03/P06/P08 dates
RA-08 | Electrical resources | Multiple contractor packages may support approved overlap | Monitor P08/P10 overlap; capacity not hard-leveled
RA-09 | Controls/I&C resources | Multiple specialist resources may operate concurrently | Interface logic manages dependency rather than delaying all P10
RA-10 | Owner inspection | Capacity not hard-leveled yet | Track detailed demand before treating as a hard constraint
RA-11 | PM / project-controls staff | Management workload KPI, not hard schedule constraint | Revisit if staffing model is added
RA-12 | Baseline feasibility | Dates feasible conditional on approved capacity assumptions | Portfolio baseline disclaimer

## SCHEDULE_RECONCILIATION
HWSD — Baseline Date Reconciliation
Phase 1 placeholders → previously approved coordinated dates → user-approved synthetic recovery dates. P12 is recurring standing work.
Project_ID | Phase_1_Planned_Start | Phase_1_Planned_Finish | Prior_Approved_Baseline_Start | Prior_Approved_Baseline_Finish | Approved_Recovery_Baseline_Start | Approved_Recovery_Baseline_Finish | Finish_Variance_Calendar_Days | Status | Notes
P01 | 2025-01-01 | 2026-02-01 | 2025-01-02 | 2026-01-05 | 2025-01-02 | 2025-12-29 | -7 | APPROVED SYNTHETIC RECOVERY | Synthetic recovery of original unavailable executable schedule
P02 | 2025-02-01 | 2026-09-01 | 2025-02-03 | 2026-04-01 | 2025-02-03 | 2026-02-25 | -35 | APPROVED SYNTHETIC RECOVERY | Synthetic recovery of original unavailable executable schedule
P03 | 2025-01-01 | 2027-09-01 | 2025-01-02 | 2027-02-17 | 2025-01-02 | 2027-01-27 | -21 | APPROVED SYNTHETIC RECOVERY | Synthetic recovery of original unavailable executable schedule
P04 | 2025-06-01 | 2026-04-01 | 2025-06-02 | 2026-04-24 | 2025-06-02 | 2026-04-24 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P05 | 2025-03-01 | 2026-12-01 | 2025-03-03 | 2026-05-15 | 2025-03-03 | 2026-05-15 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P06 | 2025-08-01 | 2026-10-01 | 2025-08-01 | 2027-01-07 | 2025-08-01 | 2026-12-24 | -14 | APPROVED SYNTHETIC RECOVERY | Synthetic recovery of original unavailable executable schedule
P07 | 2025-10-01 | 2026-06-01 | 2025-10-01 | 2026-09-01 | 2025-10-01 | 2026-09-01 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P08 | 2025-12-01 | 2027-02-01 | 2025-12-01 | 2027-01-08 | 2025-12-01 | 2027-01-08 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P09 | 2026-02-01 | 2027-04-01 | 2026-02-02 | 2027-03-03 | 2026-02-02 | 2027-03-03 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P10 | 2026-04-01 | 2027-03-01 | 2026-04-01 | 2027-08-20 | 2026-04-01 | 2027-08-06 | -14 | APPROVED SYNTHETIC RECOVERY | Synthetic recovery of original unavailable executable schedule
P11 | 2025-04-01 | 2026-08-01 | 2025-04-01 | 2026-03-09 | 2025-04-01 | 2026-03-09 | 0 | UNCHANGED REFERENCE | Unchanged project baseline, no new full reconstruction
P12 | 2025-01-01 | 2027-12-01 | 2025-01-02 | 2027-06-23 | 2025-01-02 | 2027-06-23 | 0 | UNCHANGED REFERENCE | P12 is standing work, not a discrete program-level substantial-completion gate

## CPM_METHOD
HWSD — CPM, Calendar & Baseline Constraints
Approved synthetic recovery, project-finish anchored CPM snapshot — not resource-leveled or a forecast.
Method / Assumption | Applied Convention / Limitation
Calendar | Monday–Friday business days, no holidays; all task durations inclusive, milestones zero duration.
FS milestone convention | For FS+0, zero-duration successor milestones fire on predecessor finish date; task successors start next business day. Lag is in business days.
SS / FF conventions | SS lag constrains successor start against predecessor start. FF lag constrains successor finish against predecessor finish.
Early dates | Forward pass uses approved per-project start as the lower anchor, all cross-project dependencies, and approved release holds.
Late dates | Backward pass constrains every activity finish no later than its own approved project finish and honors cross-project dependencies.
Total Float | Late Start minus Early Start in business days; float is relative to each approved project finish, not a common program finish.
Critical Flag | TRUE when total float is zero business days. Near-critical is 1–5 business days. Critical paths are based on tight relationships, not just a label.
P08 MOUTAGE fixed event | P08-MOUTAGE (Outage Planning Complete) retains its previously approved 2026-05-22 date as an explicit fixed-date milestone; A14 planning finishes 2026-05-08. No unsourced 10bd causal hold was added; the milestone may have constraint-driven zero float and is not itself evidence of a driving construction path.
Five approved NTP release holds | P04 R0133 +15bd; P05 R0161 +5bd; P07 R0260 +10bd; P08 R0291 +10bd; P11 R0434 +5bd. Synthetic, explicitly user approved; NOT recovered originals.
P12 standing program | P12 uses its own June 23, 2027 finish for float. It is standing work, not an ordinary program Substantial Completion gate.
Capacity screening | Distribution peak 6 vs baseline 7 contractor crew groups (4-crew sensitivity deficit 2). Commissioning peak 3 vs 2 internal +1 temporary specialist; temporary resource not booked.
Data limitations | Seven P01/P02 activity durations remain provisional synthetic planning assumptions. Other reconstructed activity/relationship logic is model-derived, not original-script recovered.
Approval and source | User approved synthetic recovery project finishes and five date-neutral release holds; previously approved project boundaries preserved.

## CPM_SUMMARY
HWSD — Baseline Critical Path Summary
Project-finish anchored float; critical=0bd, near-critical=1–5bd. P08 outage has a separately constrained milestone.
Project_ID | Approved_Baseline_Start | Approved_Baseline_Finish | Schedule_Rows | Critical_Rows | Near_Critical_Rows | Critical_Link_Count | Critical_Start_Activities | Critical_End_Activities
P01 | 2025-01-02 | 2025-12-29 | 25 | 19 | 0 | 18 | P01-A1 | P01-M4
P02 | 2025-02-03 | 2026-02-25 | 33 | 17 | 1 | 16 | P02-A1 | P02-M5
P03 | 2025-01-02 | 2027-01-27 | 48 | 26 | 0 | 25 | P03-A1 | P03-M4
P04 | 2025-06-02 | 2026-04-24 | 26 | 21 | 1 | 20 | P04-A1 | P04-M4
P05 | 2025-03-03 | 2026-05-15 | 39 | 21 | 0 | 21 | P05-A1 | P05-M4
P06 | 2025-08-01 | 2026-12-24 | 48 | 23 | 0 | 23 | P06-A1 | P06-M4
P07 | 2025-10-01 | 2026-09-01 | 27 | 19 | 0 | 18 | P07-A1 | P07-M4
P08 | 2025-12-01 | 2027-01-08 | 38 | 22 | 0 | 20 | P08-A1, P08-MOUTAGE | P08-MOUTAGE, P08-M4
P09 | 2026-02-02 | 2027-03-03 | 36 | 19 | 1 | 18 | P09-A1 | P09-M4
P10 | 2026-04-01 | 2027-08-06 | 45 | 29 | 0 | 30 | P10-A1 | P10-M4
P11 | 2025-04-01 | 2026-03-09 | 32 | 17 | 0 | 16 | P11-A1 | P11-M4
P12 | 2025-01-02 | 2027-06-23 | 31 | 25 | 0 | 24 | P12-Y1A1 | P12-MPROGCLOSE