## Field_Dictionary
HWSD Project Controls Model — Data Dictionary
Defines every field before it is populated. Expanded in each build phase as new sheets are added.
01_PROJECTS — Project Master List (built in Phase 1)
Field | Definition | Example
project_id | Unique project identifier, constant across every file in this repository | P03
project_name | Short, plain-English project title | Central WTP Process Upgrade
category | Infrastructure category used for grouping and dashboard filtering. Note: P12's category is 'Small Capital & Emergency Response' — real, planned, scoped standing capital work with its own BAC, not the program contingency reserve. Truly unplanned scope changes draw from the reserve via change control, not from P12. | Treatment
project_manager | Name of the project manager accountable for this project | Sarah Whitfield
bac | Budget at Completion — total authorized baseline budget for THIS PROJECT only (USD). Sums to the $88,500,000 project BAC total, which excludes the program contingency reserve. | 20300000
pct_of_project_bac_total | This project's BAC as a share of the $88,500,000 project BAC total (P01-P12). Deliberately NOT a share of the $96,000,000 total program authorization, since the reserve isn't a project. | 22.9%
planned_start | Baseline planned start date (month-level precision at this phase) | Jan-2025
planned_finish | Baseline planned finish date (month-level precision at this phase) | Sep-2027
planned_duration_months | planned_finish minus planned_start, in months | 33
status_as_of_status_date | High-level phase status as of the fixed reporting date (Mar 31, 2026) | In Construction
Program-Level Budget Architecture (not per-project fields; live in 01_PROJECTS below the project table)
Field | Definition | Example
project_bac_total | Sum of all 12 project BACs. This is the 'BAC' used in every Phase 4 EVM rollup calculation. | 88500000
program_contingency_reserve | Unallocated funds held at the program level, controlled by the Program Manager, for known-unknown risks within the program's risk profile. Not assigned to any project and not part of any project's BAC. Released only through an approved change request (07_CHANGES), at which point it transfers into the receiving project's BAC. | 7500000
total_program_authorization | project_bac_total + program_contingency_reserve. The total dollar amount authorized/appropriated for the program by the governing body. This is a governance figure, not an EVM figure — do not use it as the denominator for CPI/SPI rollups. | 96000000
Fields defined in the guide, populated starting Phase 4 (Earned Value Management)
Field | Definition | Example
pv | Planned Value — budgeted cost of work scheduled through the status date | 7700000
ev | Earned Value — budgeted cost of work actually performed through the status date | 6600000
ac | Actual Cost — actual cumulative cost incurred through the status date | 7100000
cpi | Cost Performance Index = EV / AC. Above 1.0 is favorable, below 1.0 is unfavorable. | 0.93
spi | Schedule Performance Index = EV / PV. Above 1.0 is favorable, below 1.0 is unfavorable. | 0.86
eac | Estimate at Completion = BAC / CPI (simplified method, assumes current efficiency continues) | 23655914
etc | Estimate to Complete = EAC − AC | 16555914
vac | Variance at Completion = BAC − EAC | -1655914
Fields defined in the guide, populated starting Phase 5 (Risk Register)
Field | Definition | Example
risk_id | Unique risk identifier | R-014
risk_score | Inherent risk score = probability_score (1-5) × impact_score (1-5) | 16
Fields defined in the guide, populated starting Phase 6 (Change Control)
Field | Definition | Example
change_cost | Approved or proposed budget impact of a change order (USD) | 600000

## Phase3G_Cost_PV_Fields
Dataset | Field | Definition | Source
cost_control_accounts.csv | Project_ID | Approved project P01–P12; joins project BAC and approved schedule. | Approved Phase 3D/3F
cost_control_accounts.csv | Control_Account_ID | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_control_accounts.csv | Control_Account_Name | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_control_accounts.csv | Standard_Lifecycle_Phase | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_control_accounts.csv | Project_BAC_USD | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_control_accounts.csv | Proposed_CA_Share_Pct | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_control_accounts.csv | Proposed_CA_BAC_USD | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_control_accounts.csv | Allocation_Basis | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_control_accounts.csv | Approval_Status | APPROVED_SYNTHETIC_PORTFOLIO or APPROVED_SYNTHETIC_PV_RULE, not real municipal approval. | Approved Phase 3D/3F
cost_control_accounts.csv | Candidate_Loaded_BAC_USD | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_control_accounts.csv | Unresolved_BAC_USD | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_control_accounts.csv | Phase3B_Status | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Project_ID | Approved project P01–P12; joins project BAC and approved schedule. | Approved Phase 3D/3F
cost_work_packages.csv | Control_Account_ID | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Work_Package_ID | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | WBS_Code | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Work_Package_Name | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Control_Account_BAC_USD | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Proposed_WP_Share_Pct | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Proposed_WP_BAC_USD | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Mapped_Task_Count | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Coverage_Status | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Allocation_Basis | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Approval_Status | APPROVED_SYNTHETIC_PORTFOLIO or APPROVED_SYNTHETIC_PV_RULE, not real municipal approval. | Approved Phase 3D/3F
cost_work_packages.csv | Candidate_Loaded_BAC_USD | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Unresolved_BAC_USD | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_work_packages.csv | Phase3B_Status | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_activity_ownership.csv | Project_ID | Approved project P01–P12; joins project BAC and approved schedule. | Approved Phase 3D/3F
cost_activity_ownership.csv | Schedule_Activity_ID | Approved nonmilestone activity carrying budgeted work; no schedule dates changed. | Approved Phase 3D/3F
cost_activity_ownership.csv | Schedule_WP_ID | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_activity_ownership.csv | Cost_Control_Account_ID | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_activity_ownership.csv | Cost_WP_ID | Funded WBS work package owner of a component BAC. | Approved Phase 3D/3F
cost_activity_ownership.csv | Cost_Component | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_activity_ownership.csv | Candidate_Component_BAC_USD | Approved synthetic budget of a single funded component, source Phase 3D. | Approved Phase 3D/3F
cost_activity_ownership.csv | PV_Recognition_Method | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_activity_ownership.csv | Evidence_or_Assumption | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_activity_ownership.csv | Mapping_Status | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_activity_ownership.csv | Candidate_Share_of_Cost_WP_Pct | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_activity_ownership.csv | Cost_Ownership_Line_ID | Unique funded component key; monthly PV sums to this component BAC exactly. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Cost_Ownership_Line_ID | Unique funded component key; monthly PV sums to this component BAC exactly. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Project_ID | Approved project P01–P12; joins project BAC and approved schedule. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Schedule_Activity_ID | Approved nonmilestone activity carrying budgeted work; no schedule dates changed. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Schedule_WP_ID | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Funded_Cost_WP_ID | Funded WBS work package; distinct from schedule-assigned WP when scope spans packages. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Cost_Component | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Component_BAC_USD | Approved synthetic budget of one unique cost-ownership line. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Activity_Start | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Activity_Finish | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Calendar | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Proposed_Rule_Code | Approved synthetic PV rule: WORKDAY_SPREAD, WORKDAY_FALLBACK, PROCUREMENT_20_30_30_20, FINAL_GATE. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Weights_Pct | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Synthetic_Planned_Event_Dates | Schedule-relative proxy dates for procurement or final gate; not actual vendor/acceptance events. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Scheduled_Recognition_Definition | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Future_EV_Evidence_Requirement | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Source_Method | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Prior_Readiness_Status | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Provenance | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Approved Phase 3D/3F
cost_component_earning_rules.csv | Approval_Status | APPROVED_SYNTHETIC_PORTFOLIO or APPROVED_SYNTHETIC_PV_RULE, not real municipal approval. | Approved Phase 3D/3F
monthly_planned_value_detail.csv | Cost_Ownership_Line_ID | Unique funded component key; monthly PV sums to this component BAC exactly. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_detail.csv | Project_ID | Approved project P01–P12; joins project BAC and approved schedule. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_detail.csv | Funded_Cost_WP_ID | Funded WBS work package; distinct from schedule-assigned WP when scope spans packages. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_detail.csv | Schedule_Activity_ID | Approved nonmilestone activity carrying budgeted work; no schedule dates changed. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_detail.csv | Reporting_Month | Calendar month YYYY-MM of planned recognition, between 2025-01 and 2027-12. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_detail.csv | Monthly_PV_USD | Component or project baseline planned value for the reporting month; USD with integer-cent rounding. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_detail.csv | PV_Rule | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_detail.csv | Synthetic_Recognition_Proxy | YES indicates schedule-based modeling dates, not verified construction/vendor event records. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_project.csv | Reporting_Month | Calendar month YYYY-MM of planned recognition, between 2025-01 and 2027-12. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_project.csv | Project_ID | Approved project P01–P12; joins project BAC and approved schedule. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_project.csv | Monthly_PV_USD | Component or project baseline planned value for the reporting month; USD with integer-cent rounding. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_project.csv | Cumulative_PV_USD | Sum of project monthly PV through and including reporting month; equals project BAC at its completion. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_project.csv | Planned_Cash_USD | Reserved; blank in Phase 3G; must use separate vendor/payment cash-flow assumptions. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_project.csv | Actual_Cost_USD | Reserved; blank in Phase 3G; no actual invoiced or incurred costs simulated. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_project.csv | Earned_Value_USD | Reserved; blank in Phase 3G; needs independently documented physical progress. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_program.csv | Reporting_Month | Calendar month YYYY-MM of planned recognition, between 2025-01 and 2027-12. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_program.csv | Program_Monthly_PV_USD | Sum of the twelve project monthly PV values for a month; excludes contingency. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_program.csv | Program_Cumulative_PV_USD | Sum of monthly program PV through reporting month; equals $88.5M by December 2027. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_program.csv | Project_BAC_USD | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_program.csv | Program_Contingency_USD | Unallocated $7.5M outside project BAC and baseline PV; changes require approved change control. | Derived Phase 3G integer-cent recognition schedule
monthly_planned_value_program.csv | Authorized_Budget_USD | Approved synthetic cost baseline field; see source Phase 3D/3F register and Phase 3G report for allocation provenance. | Derived Phase 3G integer-cent recognition schedule