## 00_README
HWSD_Project_Controls_Model.xlsx
Source-of-truth project-controls workbook for the HWSD Municipal Water Capital Improvement Program (simulated).
Program BAC: $96,000,000 ¦ 12 projects ¦ 36-month program (Jan 2025 - Dec 2027)
Status date (all PV/EV/AC/schedule status is measured as of this date): March 31, 2026 (Month 15 of 36)
Build status: Phase 1 complete (01_PROJECTS). All other tabs are structural shells only —
column headers are final, but data has not yet been entered. Each phase of the build populates
the next tab(s). See the repository README for the full phase sequence.
Conventions used throughout this workbook:
- Blue font = hardcoded input. Black font = formula. Do not hand-edit formula cells.
- All dollar figures are in whole USD.
- project_id is the join key across every sheet in this workbook and every CSV in /02_data.
- This workbook is the controlled source of truth. Power BI and Python read from exports
of this workbook or from /02_data/processed — they do not maintain independent copies of
baseline data.
All program, project, cost, schedule, risk, and vendor data in this workbook is synthetic
and created for portfolio demonstration purposes only.

## 01_PROJECTS
Project Master List
One row per project. project_id is the join key used across every other sheet and CSV in this repository.
project_id | project_name | category | project_manager | bac | pct_of_program_budget | planned_start | planned_finish | planned_duration_months | status_as_of_status_date
P01 | Downtown 12-inch Water Main Replacement | Distribution | Maria Chen | 8000000 | 8.333% | 2025-01-01 | 2026-02-01 | 13 | Substantially Complete
P02 | Northside Pump Station Rehabilitation | Pumping | David Okafor | 9500000 | 9.896% | 2025-02-01 | 2026-09-01 | 19 | In Construction
P03 | Central Water Treatment Plant Process Upgrade | Treatment | Sarah Whitfield | 22000000 | 22.92% | 2025-01-01 | 2027-09-01 | 32 | In Construction
P04 | Hilltop Storage Tank Rehabilitation | Storage | James Patel | 6000000 | 6.25% | 2025-06-01 | 2026-04-01 | 10 | In Construction
P05 | Lead Service Line Replacement - Phase 1 | Distribution / Public Health | Maria Chen | 12000000 | 12.5% | 2025-03-01 | 2026-12-01 | 21 | In Construction
P06 | AMI / Smart Meter Modernization | Metering / Digital | Angela Torres | 7500000 | 7.812% | 2025-08-01 | 2026-10-01 | 14 | In Construction
P07 | East Zone Pressure Management Improvements | Distribution | Robert Kim | 4500000 | 4.688% | 2025-10-01 | 2026-06-01 | 8 | In Construction
P08 | Emergency Generator & Electrical Resiliency | Resiliency | Robert Kim | 5000000 | 5.208% | 2025-12-01 | 2027-02-01 | 14 | Design / Early Construction
P09 | River Crossing Main Rehabilitation | Distribution | David Okafor | 8500000 | 8.854% | 2026-02-01 | 2027-04-01 | 14 | Mobilization / Early Construction
P10 | SCADA Controls Modernization | Digital / Controls | Angela Torres | 4000000 | 4.167% | 2026-04-01 | 2027-03-01 | 11 | Planning / Not Started
P11 | Valve Replacement & Isolation Program | Distribution | James Patel | 3500000 | 3.646% | 2025-04-01 | 2026-08-01 | 16 | In Construction
P12 | Programwide Emergency / Contingency Work | Contingency | Program Controls Office | 5500000 | 5.729% | 2025-01-01 | 2027-12-01 | 35 | Ongoing / As-Needed
| PROGRAM TOTAL |  |  | 96000000
QA check: | OK - Program BAC = $96.0M
Formulas:
planned_duration_months = DATEDIF([planned_start],[planned_finish],"m")

## 02_WBS
Wbs
Not yet populated - built in Phase 2 (Work Breakdown Structure). 3-level WBS: Program > Project > Control Account/Phase.
wbs_code | level | parent_wbs_code | wbs_name | project_id

## 03_SCHEDULE
Schedule
Not yet populated - built in Phase 2 (Baseline Schedule).
activity_id | project_id | activity_name | wbs_code | baseline_start | baseline_finish | forecast_start | forecast_finish | actual_start | actual_finish | duration_days | predecessor | percent_complete | is_milestone | critical_flag

## 04_MONTHLY_COSTS
Monthly Costs
Not yet populated - built in Phase 3 (Monthly Cost Model). Baseline monthly spend per project must sum to that project's BAC.
month | project_id | baseline_monthly | baseline_cumulative | actual_monthly | actual_cumulative | committed_cost | forecast_remaining | forecast_at_completion

## 05_EVM
Evm
Not yet populated - built in Phase 4 (Earned Value Management), calculated as of the status date (Mar 31, 2026).
project_id | bac | pv | ev | ac | cv | sv | cpi | spi | eac | etc | vac | rag_status

## 06_RISKS
Risks
Not yet populated - built in Phase 5 (Risk Register). 25-40 risks planned across the program.
risk_id | project_id | risk_category | risk_statement | probability_score | impact_score | inherent_score | owner | response_strategy | mitigation | residual_probability | residual_impact | residual_score | status

## 07_CHANGES
Changes
Not yet populated - built in Phase 6 (Change Control), including the featured $600K / six-week contractor change scenario.
change_id | project_id | change_description | cause | requested_date | approval_status | cost_impact | schedule_impact_days | contingency_drawdown | approved_by

## 08_RESOURCES
Resources
Not yet populated - built in Phase 7 (Staffing / Resource Plan).
month | project_id | role | planned_fte | notes

## 09_VENDORS
Vendors
Not yet populated - built in Phase 7 (Contractor / Vendor Tracker).
vendor_id | vendor_name | role | project_id | contract_value | status | performance_notes

## 10_MILESTONES
Milestones
Not yet populated - built in Phase 8 (Milestone Tracker). 35-50 milestones planned across the program.
milestone_id | project_id | milestone_name | baseline_date | forecast_date | actual_date | variance_days | status

## 11_KPI_THRESHOLDS
Kpi Thresholds
Not yet populated - built in Phase 4, alongside EVM. Defines RAG (Red/Amber/Green) status logic. These are project assumptions, not industry-mandated values.
kpi | green_threshold | amber_threshold | red_threshold

## 12_DASHBOARD_DATA
Dashboard Data
Not yet populated - built in Phase 9 (Power BI Prep). Flattened export tables consumed by the Power BI dashboard.
table_name | description | refreshed_from